## Dashboard
TILLMAN PROJECT DASHBOARD
Last Updated: 10/10/2026 1:51 PM
FILTERS
Area Filter: | All | Status Filter: | All | Vendor Filter: | All | Supervisor Filter: | All
KEY PERFORMANCE INDICATORS — ACTIVE PROJECTS
Total Active Projects |  |  | Total Planned Footage (ft) |  |  |  | Footage Completed (ft) |  |  | Footage Remaining (ft)
173 |  |  | 1055483 |  |  |  | 193973 |  |  | 870533
Overall % Complete |  |  | Total SOW Est. Cost |  |  |  | Total HHP |  |  | Projects Pending PW
18.38% |  |  | 9986420.55 |  |  |  | 10586 |  |  | 103
PROJECTS BY AREA |  |  |  |  | CONSTRUCTION STATUS |  |  |  | PERMIT STATUS
Area | Projects | Footage | % Complete |  | Status | Count | Footage | Est. Cost | Permit Status | Count | % of Total
St Petersburg | 1 | 6182 | 95.42% |  | In Process | 30 | 201366 | 1781324.45 | Received | 98 | 56.65%
Lakeland | 2 | 4107 | 95.64% |  | Not Started | 92 | 534834 | 4613883.25 | Pending | 73 | 42.2%
Bradenton | 11 | 52836 | 20.23% |  | Locates Called | 51 | 319283 | 3591212.85 | Not Required | 2 | 1.156%
Fort Myers | 26 | 169836 | 36.34% |  | Completed | 6 | 47138 | 572325 | TOTAL | 173 | 100%
Port Charlotte | 4 | 10662 | 55.95% |  | TOTAL | 179 | 1102621 | 10558745.55
Naples | 0 | 0 | 0%
Kissimmee | 54 | 379857 | 3.861%
Miami | 2 | 16213 | 84.09%
Pinellas | 30 | 177702 | 8.003%
TOTAL | 130 | 817395 | 18.38%
TOP VENDORS |  |  |  |  | SUPERVISOR ASSIGNMENTS | [6 empty] | HELPER – Vendors (auto) | Active | Completed | Total
Vendor | Active | Completed | Total |  | Supervisor | Active | Completed | Total |  |  |  | A1 Broadband | 2 | 1 | 3
Lightspeed In-House | 2 | 15 | 17 |  | Joshua | 26 | 41 | 67 |  |  |  | AG QUALITY | 1 | 0 | 1
GN Systems | 4 | 6 | 10 |  | Cody | 1 | 3 | 4 |  |  |  | AGN | 6 | 5 | 11
North Path | 10 | 8 | 18 |  | Travis | 0 | 0 | 0 |  |  |  | AGN Undergrounds | 2 | 0 | 2
Brothers | 8 | 16 | 24 |  | Johnnie | 6 | 10 | 16 |  |  |  | Alpha Omega | 3 | 2 | 5
Kattle One | 5 | 0 | 5 |  | Miguel | 7 | 2 | 9 |  |  |  | AMB Communications | 3 | 0 | 3
Yosep AER | 2 | 7 | 9 |  | Eric | 1 | 0 | 1 |  |  |  | APT Communications | 4 | 3 | 7
APT Communications | 4 | 3 | 7 |  | Anthony | 4 | 11 | 15 |  |  |  | APT Communications / New Gen Unlimited | 1 | 0 | 1
Lopez Underground | 7 | 16 | 23 |  | James | 0 | 0 | 0 |  |  |  | APT Communications/Kattleone | 0 | 1 | 1
Power Connect | 7 | 5 | 12 |  | Marcelo | 1 | 5 | 6 |  |  |  | APT Communications/North Path | 1 | 0 | 1
HAS Global | 1 | 2 | 3 |  | Matthew Nunes | 2 | 6 | 8 |  |  |  | ASM | 3 | 4 | 7
Legant | 4 | 2 | 6 |  | Treyvon | 8 | 4 | 12 |  |  |  | ASM Utilities | 2 | 4 | 6
Mid Florida Contractors | 0 | 1 | 1 |  | Wilson | 0 | 0 | 0 |  |  |  | BICOM | 5 | 2 | 7
R&F Underground | 0 | 2 | 2 |  | Efrian | 0 | 2 | 2 |  |  |  | Brothers | 8 | 16 | 24
NIA Underground | 0 | 2 | 2 |  | TOTAL | 56 | 84 | 140 |  |  |  | DMC Boring | 2 | 2 | 4
Alpha Omega | 3 | 2 | 5 | [8 empty] | DMG - JOHN | 1 | 0 | 1
J Garcia Underground | 0 | 0 | 0 | [8 empty] | Full Circle In-House/Saul/Felipe | 1 | 0 | 1
Splice Only | 1 | 0 | 1 | [8 empty] | GN Systems | 4 | 6 | 10
TOTAL | 58 | 87 | 145 | [8 empty] | Gulfstream | 1 | 5 | 6
[12 empty] | HAS Global | 1 | 2 | 3
[12 empty] | HD Cable | 3 | 1 | 4
[12 empty] | HDD Underground / R&F Underground Construction Inc | 0 | 1 | 1
[12 empty] | ITG In-House | 3 | 0 | 3
[12 empty] | Kattle One | 5 | 0 | 5
[12 empty] | Kattle One/LSCG | 1 | 0 | 1
[12 empty] | Legant Livings | 4 | 2 | 6
CHARTS | [11 empty] | Lightspeed In-House | 2 | 15 | 17
[12 empty] | Lightspeed In-House / GN Systems | 0 | 1 | 1
[12 empty] | Lightspeed In-House/North Path | 0 | 1 | 1
[12 empty] | Lopez Underground | 7 | 16 | 23
[12 empty] | Mid Florida Contractors | 0 | 1 | 1
[12 empty] | NIA Underground | 0 | 2 | 2
[12 empty] | North Path | 10 | 8 | 18
[12 empty] | Power Connect | 7 | 5 | 12
[12 empty] | Quinteros Cable Installation | 3 | 0 | 3
[12 empty] | R&F Underground Construction Inc | 0 | 2 | 2
[12 empty] | Randy's Utilities | 2 | 0 | 2
[12 empty] | RDA Solutions | 9 | 0 | 9
[12 empty] | Restoring Pro | 2 | 1 | 3
[12 empty] | Sosa Line | 2 | 1 | 3
[12 empty] | Splice Only Project | 1 | 0 | 1
[12 empty] | TBD | 2 | 0 | 2
[12 empty] | Yosep AER | 2 | 7 | 9
[12 empty] | HELPER – Supervisors (auto) | Active | Completed
[12 empty] | Aldo Layedra | 49 | 14 | 63
[12 empty] | Allen Johns | 8 | 0 | 8
[12 empty] | Anthony Adum | 4 | 11 | 15
[12 empty] | Brenton Copelin | 2 | 9 | 11
[12 empty] | Cody | 1 | 3 | 4
[12 empty] | Danny Combs | 7 | 1 | 8
[12 empty] | Efrian | 0 | 2 | 2
[12 empty] | Eric | 1 | 0 | 1
[12 empty] | Johnnie Williams | 6 | 10 | 16
[12 empty] | Jose | 2 | 5 | 7
[12 empty] | Joshua | 26 | 41 | 67
[12 empty] | Joshua Pacheco | 8 | 4 | 12
[12 empty] | Joshua Wheatcroft | 0 | 32 | 32
[12 empty] | Marcelo Zaldivar | 1 | 5 | 6
[12 empty] | Matthew Nunes | 2 | 6 | 8
[12 empty] | Miguel | 7 | 2 | 9
[12 empty] | Miguel Herrero | 1 | 0 | 1
[12 empty] | Randy Emmett | 1 | 0 | 1
[12 empty] | Robert Portee | 0 | 1 | 1
[12 empty] | Scott | 7 | 0 | 7
[12 empty] | Treyvon Tillman | 8 | 4 | 12
COMPLETED PROJECTS PENDING PAPERWORK
NTP Number | Area | Vendor | Supervisor | HHP | Footage UG | Completed Footage | Est. Cost
BHU-FLX-01-E | Bradenton | Lightspeed In-House | Johnnie Williams | 0 | 3109 | 3128 | 49846.95
BHUD-FOE-401-W | Bradenton | North Path | Cody | 0 | 1412 | 1406 | 18856.2
D-HAL113 | Bradenton | North Path | Brenton Copelin | 86 | 3508 | 3492 | 52728
D-HAL114 | Bradenton | North Path | Brenton Copelin | 62 | 3148 | 3199 | 42744
D-HAL116 | Bradenton | North Path | Brenton Copelin | 81 | 4065 | 4167 | 52593.6
D-HLX421 | Bradenton | GN Systems | Cody | 20 | 1322 | 1322 | 23501
D-HLX503 | Bradenton | North Path | Brenton Copelin | 85 | 4380 | 4475 | 60062
D-HLX505 | Bradenton | North Path | Brenton Copelin | 87 | 4888 | 5016 | 64040
FB-HLR201 | Bradenton | Lightspeed In-House / GN Systems | Cody | 0 | 9840 | 9806 | 144972.5
FB-HLX175 | Bradenton | Lightspeed In-House/North Path | Brenton Copelin | 0 | 3036 | 3056 | 36166.65
FB-HOE401-V6 | Bradenton | Lightspeed In-House | Brenton Copelin | 0 | 194 | 200 | 3232.9
D-HPP607 | Clearwater | Lightspeed In-House | Treyvon Tillman | 46 | 5649 | 5893 | 71754.5
D-HPP608 | Clearwater | Lightspeed In-House | Robert Portee | 94 | 7741 | 7673 | 94021.5
D-HPP613 | Clearwater | APT Communications | Johnnie Williams | 79 | 8175 | 8120 | 100208
D-HPP614 | Clearwater | Mid Florida Contractors | Johnnie Williams | 110 | 8444 | 8277 | 101920.5
D-HPP621 | Clearwater | Brothers | Anthony Adum | 91 | 5934 | 6020 | 72668.5
D-HPP625 | Clearwater | Brothers | Treyvon Tillman | 88 | 7623 | 7341 | 96607
D-HPP626 | Clearwater | Brothers | Marcelo Zaldivar | 75 | 7966 | 8323 | 95477
D-HPP627 | Clearwater | Brothers | Marcelo Zaldivar | 97 | 7856 | 7519 | 94688.5
D-HPP628 | Clearwater | Brothers | Marcelo Zaldivar | 65 | 8047 | 7881 | 97700
D-HPP629 | Clearwater | Brothers | Anthony Adum | 51 | 7529 | 7407 | 91700
D-HPP633 | Clearwater | Power Connect | Johnnie Williams | 70 | 8201 | 8350 | 99590
D-HPP634 | Clearwater | NIA Underground | Johnnie Williams | 91 | 8384 | 8386 | 103644.5
D-HPP635 | Clearwater | NIA Underground | Johnnie Williams | 57 | 8751 | 8542 | 106431.5
D-HPP636 | Clearwater | Brothers | Marcelo Zaldivar | 86 | 7996 | 7742 | 97386.5
D-HPP638 | Clearwater | Lightspeed In-House | Treyvon Tillman | 88 | 6647 | 6717 | 81059.5
D-HPP639 | Clearwater | ASM Utilities | Marcelo Zaldivar | 88 | 8787 | 8921 | 106600
FB-HPP612 | Clearwater | Brothers | Anthony Adum | 0 | 5251 | 5190 | 66431.7
FB-HPP631 | Clearwater | Brothers | Anthony Adum | 0 | 6335 | 6762 | 65477.3
BHCD-FPW-03-W | Fort Myers | North Path | Joshua Wheatcroft | 0 | 3461 | 3578 | 146065.95
D-HDF707 | Fort Myers | Lightspeed In-House | Joshua Wheatcroft | 80 | 5052 | 4889 | 65843.5
D-HDF713 | Fort Myers | GN Systems | Joshua Wheatcroft | 77 | 8013 | 7885 | 90786
D-HPW346 | Fort Myers | A1 Broadband | Joshua Wheatcroft | 89 | 7299 | 7212 | 93910.15
D-HPW348 | Fort Myers | Alpha Omega | Joshua Wheatcroft | 83 | 6192 | 6179 | 78322
FB-HPW331 | Fort Myers | Gulfstream | Joshua | 0 | 1797 | 1781 | 25174.45
D-HTG201 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 53 | 4814 | 5133 | 56455
D-HTG206 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 89 | 6549 | 6536 | 70666
D-HTG207 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 76 | 5649 | 5777 | 72914
D-HTG208 | Fort Myers | Lopez Underground | Joshua | 74 | 8145 | 8102 | 92274
D-HTG210 | Fort Myers | Gulfstream | Joshua Wheatcroft | 77 | 5803 | 5753 | 68598
D-HTG215 | Fort Myers | Gulfstream | Joshua | 56 | 4625 | 4596 | 55008
D-HTG216 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 79 | 6786 | 6598 | 80274
D-HTG217 | Fort Myers | Lopez Underground | Joshua | 77 | 6200 | 6081 | 76557.5
D-HTG218 | Fort Myers | Gulfstream | Joshua Wheatcroft | 48 | 3850 | 3834 | 50669
D-HTG225 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 69 | 6189 | 6050 | 72896
D-HTG228 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 60 | 5673 | 5183 | 70151.5
D-HTG229 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 70 | 5460 | 5325 | 65362
D-HTG230 | Fort Myers | Restoring Pro | Joshua | 79 | 7494 | 7415 | 89293.95
D-HTG233 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 71 | 7255 | 7248 | 91537.75
D-HTG235 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 71 | 5624 | 5577 | 68762
D-HTG237 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 56 | 4652 | 4625 | 55504
D-HTG238 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 74 | 5756 | 5626 | 70534.5
D-HTG239 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 85 | 5218 | 5194 | 64590
D-HTG305 | Fort Myers | Lightspeed In-House | Joshua Wheatcroft | 56 | 4159 | 4159 | 50042
D-HTG241 | Fort Myers | Lightspeed In-House | Joshua Wheatcroft | 28 | 2238 | 2269 | 27694
FB-HTG204 | Fort Myers | Alpha Omega | Joshua Wheatcroft | 0 | 2635 | 2631 | 35456.55
FB-HTG238 | Fort Myers | Lopez Underground | Joshua Wheatcroft | 0 | 5666 | 5757 | 72557.35
FB-HTG279 | Fort Myers | Lightspeed In-House | Joshua Wheatcroft | 0 | 949 | 952 | 17689.15
FB-HTG289 | Fort Myers | HAS Global | Joshua Wheatcroft | 0 | 2342 | 2421 | 31327.7
FB-HTG290 | Fort Myers | HAS Global | Joshua Wheatcroft | 0 | 2367 | 2367 | 27837.25
FB-HTG292 | Fort Myers | Gulfstream | Joshua Wheatcroft | 0 | 1618 | 1646 | 21849.3
Colonial Pointe | Fort Myers | APT Communications | Joshua Wheatcroft | 72 | 5950 | 5332 | 60744.4
BHC-FSW-04-E | Kissimmee | BICOM | Miguel | 0 | 4564 | 4419 | 68022.75
FB-HSW419 | Kissimmee | BICOM | Miguel | 0 | 7261 | 7434 | 9232.4
D-HBR252 | Miami | Yosep AER | Efrian | 53 | 4005 | 4047 | 51528.05
D-HBR256 | Miami | Yosep AER | Efrian | 73 | 7660 | 7703 | 99925.7
D-HBR257 | Miami | Yosep AER | Jose | 87 | 8596 | 8403 | 108458.4
D-HBR258 | Miami | Yosep AER | Jose | 70 | 5648 | 5650 | 70105.25
D-HBR259 | Miami | Yosep AER | Jose | 77 | 6238 | 6300 | 78047.35
D-HBR260 | Miami | Yosep AER | Jose | 52 | 5926 | 5982 | 91411.65
FB-HBR252 | Miami | Yosep AER | Jose | 0 | 3682 | 3730 | 50239.7
D-HPP303 | Pinellas | R&F Underground Construction Inc | Joshua Pacheco | 35 | 7699 | 7300 | 98498
D-HPP305 | Pinellas | HDD Underground / R&F Underground Construction Inc | Matthew Nunes | 87 | 6321 | 6271 | 77365.5
D-HPP310 | Pinellas | Legant Livings | Joshua Pacheco | 58 | 6258 | 5944 | 78994.5
D-HPP311 | Pinellas | Legant Livings | Joshua Pacheco | 85 | 5055 | 5140 | 62709
D-HPP314 | Pinellas | Power Connect | Matthew Nunes | 69 | 8137 | 8054 | 99986.2
D-HPP854 | Pinellas | Brothers | Anthony Adum | 90 | 6218 | 5826 | 78625.9
D-HPP858 | Pinellas | Brothers | Anthony Adum | 68 | 5646 | 5626 | 73595.5
FB-HPP314 | Pinellas | Power Connect | Joshua Pacheco | 0 | 72 | 58 | 419
FB-HPP375 | Pinellas | Power Connect | Johnnie Williams | 0 | 2286 | 1957 | 24396.5
FB-HPP879 | Pinellas | Brothers | Anthony Adum | 0 | 5871 | 5903 | 73440.1
D-HLC506 | Pinellas | Brothers | Anthony Adum | 83 | 5259 | 5241 | 63582
D-HLC507 | Pinellas | ASM Utilities | Danny Combs | 63 | 6335 | 6762 | 78078
D-HLC511 | Pinellas | Lightspeed In-House | Treyvon Tillman | 93 | 5861 | 5935 | 72479.5
D-HLC512 | Pinellas | Brothers | Anthony Adum | 67 | 7115 | 7040 | 86106.8
D-HLC513 | Pinellas | Lightspeed In-House | Matthew Nunes | 91 | 6519 | 6118 | 79458
D-HLC517 | Pinellas | ASM Utilities | Matthew Nunes | 83 | 6058 | 6169 | 79947
D-HLC518 | Pinellas | ASM Utilities | Matthew Nunes | 93 | 5775 | 5444 | 74446.5
D-HLC519 | Pinellas | Brothers | Anthony Adum | 44 | 6969 | 6980 | 84001.5
D-HLC539 | Pinellas | Sosa Line | Johnnie Williams | 64 | 6946 | 6979 | 88399.4
FB-HLC512 | Pinellas | Brothers | Anthony Adum | 0 | 5642 | 5699 | 71505.7
FB-HLC519 | Pinellas | Power Connect | Matthew Nunes | 0 | 2013 | 2039 | 25127.05
D-HSF308 | Port Charlotte | HD Cable | Joshua Wheatcroft | 68 | 5495 | 5365 | 62074
D-HSF320 | Port Charlotte | GN Systems | Joshua Wheatcroft | 79 | 5974 | 5911 | 73533
D-HSF322 | Port Charlotte | Lopez Underground | Joshua Wheatcroft | 89 | 6825 | 6741 | 81150
D-HSF402 | Port Charlotte | GN Systems | Brenton Copelin | 78 | 5890 | 5834 | 72242
D-HSF419 | Port Charlotte | GN Systems | Brenton Copelin | 49 | 5185 | 4940 | 62657
FB-HSF304 | Port Charlotte | Lightspeed In-House | Joshua Wheatcroft | 0 | 3693 | 3896 | 33518.7
FB-HNP133 | St Petersburg | Lightspeed In-House | Johnnie Williams | 0 | 1697 | 1815 | 23800.25
Vantage Point Condominiums | St Petersburg | APT Communications/Kattleone | Johnnie Williams | 380 | 9181 | 9179 | 117414
D-HLP610 | Collier | AGN | Aldo Layedra | 78 | 4373 | 4404 | 0
D-HPW304 | Lee | DMG | Aldo Layedra | 39 | 2705 | 2705 | 0
D-HPW306 | Lee | AGN | Aldo Layedra | 90 | 5254 | 5254 | 0
D-HPW309 | Lee | AGN | Aldo Layedra | 83 | 5336 | 5501 | 0
D-HPW310 | Lee | DMC Boring | Aldo Layedra | 0 | 5634 | 5906 | 0
D-HPW311 | Lee | DMC Boring | Aldo Layedra | 68 | 3909 | 3909 | 0
D-HPW325 | Lee | RDA | Aldo Layedra | 80 | 6023 | 6055 | 0
D-HPW340 | Lee | RDA | Aldo Layedra | 79 | 5773 | 5744 | 0
D-HPW343 | Lee | RDA | Aldo Layedra | 82 | 6788 | 6794 | 0
D-HTG402 | Lee | RDA | Aldo Layedra | 78 | 5125 | 3972 | 0
FB-HTG308 | Lee | AGN | Aldo Layedra | 0 | 590 | 590 | 0
TOTAL |  |  |  | 6451 | 606783 | 602710 | 6933979.1

## Raw Data (hidden)
| YTD | JAN | FEB | MARCH | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC
Total Completed | YTD: 23; JAN: 23
Total Goal | YTD: 13721; JAN: 921; FEB: 11888; MARCH: 753; APR: 159
DOY | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% to Year End | 5.976% | 68.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Achieved % to Goal | 0.1676% | 2.497% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total % | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| 251 | 22 | 20 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22

## UG Condensed (hidden)
NTP Number | AREA | SOW TSD Date | Penguin ID |  | HHP | On Track or In Jeopardy | NTP Received | SOW Received | Permit Status | Door Tag Date | Constuction Status | Locate Date | UG Conduit Status | Proofing Conduits-ABF Tested | Pulling Fiber | Stingrays | Fiber Spliced | Restoration | Tillman QC Status | COP Package To Biz-Ops Date | Invoice | #REF!
BHT-FOE-03 | Bradenton | 2025-11-30 | MAN97574 |  | 0 |  | Yes | Yes | Received | 2025-07-14 | In Process | 2025-07-14 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
BHUD-FOE-02-W | Bradenton | 2025-03-26 | MAN92070 |  | 0 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-05 | Completed | Completed | Completed | Not Required | Completed | Completed | Pending |  | Pending | #REF!
BHUD-FOE-06-E | Bradenton | 2025-03-26 | MAN92243 |  | 0 |  | Yes | Yes | Received | 2025-02-28 | In Process | 2025-03-05 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending |  | Pending | #REF!
BHZD-FOE-03-W | Bradenton | 2025-11-30 | PPM89496 |  | 0 |  | Yes | Yes | Received | 2025-05-16 | In Process | 2025-05-16 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending |  | Pending
D-HOE102 | Bradenton | 2025-03-31 | MAN89819 |  | 56 |  | Yes | Yes | Received | 2025-02-13 | Completed | 2025-03-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HOE111 | Bradenton | 2025-03-26 | PPM92353 |  | 60 |  | Yes | Yes | Received | 2025-02-28 | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HOE116 | Bradenton | 2025-03-26 | PPM90592 |  | 84 |  | Yes | Yes | Received | 2025-02-28 | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HOE117 | Bradenton | 2025-03-26 | MAN90788 |  | 79 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HOE120 | Bradenton | 2025-03-26 | MAN90778 |  | 83 |  | Yes | Yes | Received | 2025-02-28 | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HOE206 | Bradenton | 2025-11-30 | PPM92353 | 31 | 31 |  | Yes | Yes | Received | 2025-02-28 | In Process | 2025-02-28 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending
D-HOE215 | Bradenton | 2025-04-25 | PPM92353 |  | 31 |  | Yes | Yes | Received | 2025-02-28 | In Process | 2025-02-28 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending |  | Pending | #REF!
FB-HLR201 | Bradenton | 2025-10-30 | MAN98152 |  | 0 |  | Yes | Yes | Received | 2025-07-29 | In Process | 2025-07-29 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
D-HOE302 | Bradenton | 2025-11-30 | MAN98158 |  | 57 |  | Yes | Yes | Received | 2025-07-25 | In Process | 2025-07-25 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
FB-HOE117 | Bradenton | 2025-02-23 | MAN89824 |  | 0 |  | Yes | Yes | Received | 2025-02-13 | Completed | 2025-03-02 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-07-18 | Submitted | #REF!
FB-HOE201 | Bradenton | 2025-03-26 | MAN91981 |  | 0 |  | Yes | Yes | Received | 2/29/2025 | Completed | 2/29/2025 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending |  | Pending | #REF!
FB-HOE301 | Bradenton | 2025-11-30 | MAN98180 |  | 0 |  | Yes | Yes | Received | 2025-07-25 | Completed | 2025-07-25 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending
FB-HOE375 | Bradenton | 2025-11-30 | MAN99383 |  | 0 |  | Yes | Yes | Received | 2025-08-12 | Completed | 2025-08-12 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending
12 Oaks MHP | Lakeland | 2025-08-30 |  |  | 50 |  | Yes | Yes | Not Required | 2025-08-04 | Completed | 2025-08-04 | Completed | Completed | Completed | Not Required | Completed | Completed | Pending
BHT-FWP-06 | Lakeland | 2025-03-26 | PLK89457 |  | 0 |  | Yes | Yes | Received | 2025-02-20 | Completed | 2025-02-21 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-03 | Submitted | #REF!
BHT-FWP-07 | Lakeland | 2025-04-25 | PLK91807 |  | 0 |  | Yes | Yes | Received | 2025-02-20 | Completed | 2025-03-21 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-05-02 | Submitted | #REF!
BHT-FWP-08 | Lakeland | 2025-07-30 | PLK96231 |  | 0 |  | Yes | Yes | Received | Not Required | Completed | 2025-06-06 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-07-10 | Submitted
BHT-FWP-09 | Lakeland | 2025-06-30 | PLK95075 |  | 0 |  | Yes | Yes | Received | 2025-05-09 | Completed | 2025-05-12 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed
BHT-FWP-10 | Lakeland | 2025-05-30 | PLK94470 |  | 0 |  | Yes | Yes | Received | 2025-05-01 | Completed | 2025-05-05 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-18 | Submitted
BHUD-FWP-08-E | Lakeland | 2025-05-10 | PLK91306 |  | 0 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-02-28 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-05-16 | Submitted | #REF!
BHUD-FWP-13-W | Lakeland | 2025-07-30 | PLK95092 |  | 0 |  | Yes | Yes | Received | Not Required | Completed | 2025-07-02 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed
BHZD-FWP-11-W | Lakeland | 2025-07-30 | PLK97102 |  | 0 |  | Yes | Yes | Received | Not Required | Completed | 2025-07-15 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed
BHZD-FWP-13-E | Lakeland | 2025-07-30 | PLK95389 |  | 0 |  | Yes | Yes | Received | 2025-05-16 | Completed | 2025-05-16 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed
D-HWP102 | Lakeland | 2025-02-23 | MAN91697 |  | 54 |  | Yes | Yes | Received | 2025-01-02 | Completed | 2025-02-04 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP103 | Lakeland | 2025-02-23 | PLK88967 |  | 49 |  | Yes | Yes | Received | 2025-02-25 | Completed | 2025-02-04 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP105 | Lakeland | 2025-02-28 | PLK90239 |  | 56 |  | Yes | Yes | Received | 2025-02-19 | Completed | 2025-02-19 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-02 | Submitted | #REF!
D-HWP1304 | Lakeland | 2025-04-25 | PLK93497 |  | 82 |  | Yes | Yes | Received | 2025-04-09 | Completed | 2025-04-09 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-15 | Submitted
D-HWP1306 | Lakeland | 2025-04-25 | PLK92368 |  | 79 |  | Yes | Yes | Received | 2025-04-02 | Completed | 2025-04-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-04 | Submitted | #REF!
D-HWP1309 | Lakeland | 2025-04-25 | PLK92363 |  | 59 |  | Yes | Yes | Received | 2025-04-03 | Completed | 2025-04-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-20 | Submitted
D-HWP412 | Lakeland | 2025-01-31 | PLK87663 |  | 23 |  | Yes | Yes | Received | 2025-01-02 | Completed | 2025-01-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP415 | Lakeland | 2025-01-31 | PLK88133 |  | 70 |  | Yes | Yes | Received | 2025-01-02 | Completed | 2025-01-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-16 | Submitted | #REF!
D-HWP425 | Lakeland | 2025-01-31 | PLK88584 |  | 75 |  | Yes | Yes | Received | Completed | Completed | 2025-01-15 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP436 | Lakeland | 2025-01-31 | PLK88375 |  | 65 |  | Yes | Yes | Received | 2025-01-16 | Completed | 2025-01-16 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP441 | Lakeland | 2025-01-31 | PLK88853 |  | 81 |  | Yes | Yes | Received | Completed | Completed | 2025-01-15 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP701 | Lakeland | 2025-03-26 | PLK89401 |  | 50 |  | Yes | Yes | Received | 2025-02-17 | Completed | 2025-02-27 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP702 | Lakeland | 2025-03-26 | PLK92108 |  | 52 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-13 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP703 | Lakeland | 2025-04-25 | PLK92329 |  | 86 |  | Yes | Yes | Received | 2025-03-21 | Completed | 2025-03-21 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP705 | Lakeland | 2025-02-28 | PLK91019 |  | 51 |  | Yes | Yes | Received | Completed | Completed | 2025-03-10 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-09 | Submitted | #REF!
D-HWP707 | Lakeland | 2025-04-25 | PLK91963 |  | 35 |  | Yes | Yes | Received | 2025-03-20 | Completed | 2025-03-25 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP713 | Lakeland | 2025-02-23 | PLK89267 |  | 22 |  | Yes | Yes | Received | Completed | Completed | 2025-02-07 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP801 | Lakeland | 2025-07-30 | PLK95087 |  | 90 |  | Yes | Yes | Received | 2025-05-20 | Completed | 2025-06-02 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-07-09 | Submitted
D-HWP803 | Lakeland | 2025-08-30 | PLK97105 |  | 62 |  | Yes | Yes | Received | 2025-08-11 | Completed | 2025-08-11 | Completed | Completed | Completed | Not Required | Completed | Completed | Pending
D-HWP805 | Lakeland | 2025-09-30 | PLK97109 |  | 85 |  | Yes | Yes | Received | 2025-08-13 | Completed | 2025-08-13 | Completed | Completed | Completed | Completed | Completed | Completed | Pending
D-HWP812 | Lakeland | 2025-08-30 | PLK97117 |  | 77 |  | Yes | Yes | Received | 2025-07-02 | Completed | 2025-07-02 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-08 | Submitted
D-HWP814 | Lakeland | 2025-08-30 | PLK97122 |  | 81 |  | Yes | Yes | Received | 2025-07-09 | Completed | 2025-07-09 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-26 | Submitted
D-HWP815 | Lakeland | 2025-08-30 | PLK97093 |  | 86 |  | Yes | Yes | Received | 2025-07-02 | Completed | 2025-07-02 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-08 | Submitted
D-HWP821 | Lakeland | 2025-07-30 | PLK96634 |  | 66 |  | Yes | Yes | Received | 2025-06-25 | Completed | 2025-06-25 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-07-10 | Submitted
D-HWP822 | Lakeland | 2025-07-30 | PLK97098 |  | 43 |  | Yes | Yes | Received | 2025-07-02 | Completed | 2025-07-02 | Completed | Not Required | Completed | Completed | Completed | Completed | Completed | 2025-09-16 | Submitted
D-HWP824 | Lakeland | 2025-08-30 |  |  | 73 |  | Yes | Yes | Received | 2025-08-18 | Completed | 2025-08-18 | Completed | Completed | Completed | Completed | Completed | Completed | Pending
D-HWP825 | Lakeland | 2025-08-30 |  |  | 70 |  | Yes | Yes | Received | 2025-08-18 | Completed | 2025-08-18 | Completed | Completed | Completed | Completed | Completed | Completed | Pending
D-HWP826 | Lakeland | 2025-08-30 |  |  | 84 |  | Yes | Yes | Received | 2025-08-18 | Completed | 2025-08-18 | Completed | Completed | Completed | Completed | Completed | Completed | Pending
D-HWP902 | Lakeland | 2025-07-24 | PLK93385 |  | 62 |  | Yes | Yes | Received | 2025-04-15 | Completed | 2025-05-06 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-05 | Submitted
D-HWP903 | Lakeland | 2025-07-24 | PLK93393 |  | 89 |  | Yes | Yes | Received | 2025-04-15 | Completed | 2025-04-29 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-19 | Submitted
D-HWP904 | Lakeland | 2025-07-24 | PLK93379 |  | 87 |  | Yes | Yes | Received | 2025-04-15 | Completed | 5/52025 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-19 | Submitted
D-HWP905 | Lakeland | 2025-07-30 | PLK94794 |  | 60 |  | Yes | Yes | Received | 2025-05-13 | Completed | 2025-06-04 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-16 | Submitted
FB-HWP101 | Lakeland | 2025-01-31 | PLK88377 |  | 0 |  | Yes | Yes | Received | Completed | Completed | 2025-01-16 | Completed | Completed | In Process | Not Required | Completed | Completed | Completed | 2025-04-11 | Submitted | #REF!
FB-HWP1302 | Lakeland | 2025-07-30 | PLK97344 |  | 0 |  | Yes | Yes | Received | 2025-07-10 | Completed | 2025-07-10 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-07 | Submitted
FB-HWP1310 | Lakeland | 2025-09-30 |  |  | 0 |  | Yes | Yes | Received | 2025-08-15 | Completed | 2025-08-13 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending
FB-HWP1375 | Lakeland | 2025-08-30 | PLK97346 |  | 0 |  | Yes | Yes | Received | 2025-08-15 | Completed | 2025-08-15 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-09-08
FB-HWP1376 | Lakeland | 2025-07-30 | PLK96627 |  | 0 |  | Yes | Yes | Received | 2025-06-16 | Completed | 2025-06-16 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending |  | Pending
FB-HWP175 | Lakeland | 2025-06-30 | PLK96355 |  | 0 |  | Yes | Yes | Received | 2025-06-10 | Completed | 2025-06-09 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-07 | Submitted
FB-HWP375 | Lakeland | 2025-08-30 |  |  | 0 |  | Yes | Yes | Received | 2025-08-07 | Completed | 2025-08-07 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending | 2025-09-05
FB-HWP401 | Lakeland | 2025-02-28 |  |  | 0 |  | No | No | Received | Completed | Completed | Completed | Completed | Completed | Completed | Not Required | Completed | Completed | Completed |  | Pending | #REF!
FB-HWP482 | Lakeland | 2025-08-30 | PLK97720 |  | 0 |  | Yes | Yes | Received | 2025-08-01 | Completed | 2025-08-01 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending
FB-HWP701 | Lakeland | 2025-02-28 | PLK89265 |  | 0 |  | Yes | Yes | Received | 2025-02-17 | Completed | 2025-02-17 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed |  | Submitted | #REF!
FB-HWP775 | Lakeland | 2025-08-30 | PLK98767 |  | 0 |  | Yes | Yes | Received | 2025-08-01 | Completed | 2025-08-01 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending
FB-HWP776 | Lakeland | 2025-08-30 |  |  | 0 |  | Yes | Yes | Received | 2025-08-13 | Completed | 2025-08-13 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-09-08
FB-HWP801 | Lakeland | 2025-06-30 | PLK94839 |  | 0 |  | Yes | Yes | Received | 2025-05-13 | Completed | 2025-05-13 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-13 | Pending
FB-HWP802 | Lakeland | 2025-08-30 | PLK98828 |  | 0 |  | Yes | Yes | Received | 2025-07-30 | Completed | 2025-08-02 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending | 2025-09-09
FB-HWP804 | Lakeland | 2025-07-30 | PLK97717 |  | 0 |  | Yes | Yes | Received | 2025-07-15 | Completed | 2025-07-15 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-09-05 | Submitted
FB-HWP902 | Lakeland | 2025-07-30 | PLK97335 |  | 0 |  | Yes | Yes | Received | 2025-06-30 | Completed | 2025-06-30 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-26 | Submitted
FB-HWP975 | Lakeland | 2025-09-30 |  |  | 0 |  | Yes | Yes | Received | 2025-09-02 | Completed | 2025-09-02 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending | 2025-09-23
FB-HWP1075 | Lakeland | 2025-09-30 |  |  | 0 |  | Yes | Yes | Received | 2025-09-02 | Completed | 2025-09-02 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending | 2025-09-25
FX4-FWP-08 | Lakeland | 2025-05-15 | PLK89273 |  | 0 |  | Yes | Yes | Received | Completed | Completed | Completed | Completed | Not Required | Not Required | Not Required | Completed | Completed | Completed | 2025-06-12 | Submitted | #REF!
FX4-FWP-13 | Lakeland | 2025-05-10 | PLK93160 |  | 0 |  | Yes | Yes | Received | TBD | Completed | TBD | Completed | Not Required | Not Required | Not Required | Completed | Completed | Completed | 2025-07-10 | Pending
Golden Wings MHP | Lakeland | 2025-01-31 | PLK88370 |  | 48 |  | Yes | Yes | Not Required | Completed | Completed | 2025-01-21 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
Skyview Estates MHP | Lakeland | 2025-08-30 |  |  | 208 |  | Yes | Yes | Not Required | 2025-08-05 | Completed | 2025-08-05 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed
BHU-FDH-01-W | St Petersburg | 2025-02-28 | PPM89496 |  | 0 |  | Yes | Yes | Received | 2025-02-17 | Completed | 2025-02-18 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-10 | Pending | #REF!
D-H0220A | St Petersburg | 2025-03-26 | PPM95827 |  | 57 |  | Yes | Yes | Received | 2025-03-12 | Completed | 2025-03-12 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-08-06 | Submitted | #REF!
D-H0220B | St Petersburg | 2025-03-26 | PPM91680 |  | 60 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-08-05 | Submitted | #REF!
D-H0220C | St Petersburg | 2025-03-26 | PPM91630 |  | 80 |  | Yes | Yes | Received | 2025-03-12 | Completed | 2025-03-12 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-16 | Submitted | #REF!
D-H0220D | St Petersburg | 2025-03-26 | PPM90335 |  | 68 |  | Yes | Yes | Received | 2025-02-28 | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-H0221A | St Petersburg | 2025-03-26 | PPM91357 |  | 80 |  | Yes | Yes | Received | 2025-03-12 | Completed | 2025-03-12 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-04-10 | Pending | #REF!
D-H0221B | St Petersburg | 2025-03-26 | PPM91351 |  | 56 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-06 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-06-17 | Pending | #REF!
D-H0221C | St Petersburg | 2025-03-26 | PPM91690 |  | 71 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-11 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-06-20 | Pending | #REF!
D-H0221D | St Petersburg | 2025-03-26 | PPM91321 |  | 81 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-07 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-23 | Submitted | #REF!
D-H0221E | St Petersburg | 2025-03-26 | PPM90342 |  | 38 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-H0221F | St Petersburg | 2025-04-25 | PPM91656 |  | 83 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-11 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-H0222A | St Petersburg | 2025-02-23 | PPM89513 |  | 86 |  | Yes | Yes | Received | 2025-02-26 | Completed | 2025-02-05 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending |  | Pending | #REF!
D-H0222B | St Petersburg | 2025-02-23 | PPM89528 |  | 76 |  | Yes | Yes | Received | 2025-02-04 | Completed | 2025-02-06 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-06 | Submitted | #REF!
D-H0222C | St Petersburg | 2025-02-23 | PPM89539 |  | 89 |  | Yes | Yes | Received | 2025-02-07 | Completed | 2025-02-06 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending |  | Pending | #REF!
D-H0222D | St Petersburg | 2025-02-23 | PPM89539 |  | 86 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-01-31 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-16 | Submitted | #REF!
D-H0223A | St Petersburg | 2025-02-23 | PPM89575 |  | 77 |  | Yes | Yes | Received | 2025-01-29 | Completed | 2025-02-04 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-07-02 | Pending | #REF!
D-H0223C | St Petersburg | 2025-02-23 | PPM89447 |  | 81 |  | Yes | Yes | Received | 2025-02-12 | Completed | 2025-02-04 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-06 | Submitted | #REF!
D-H0223D | St Petersburg | 2025-02-23 | PPM89579 |  | 81 |  | Yes | Yes | Received | 2025-02-11 | Completed | 2025-02-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Pending | #REF!
D-H0223E | St Petersburg | 2025-02-23 | PPM89581 |  | 84 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-07 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-06-02 | Pending | #REF!
D-HDH03 | St Petersburg | 2025-01-31 | PPM89589 |  | 90 |  | Yes | Yes | Received | Completed | Completed | 2025-02-11 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-27 | Submitted | #REF!
D-HDH04 | St Petersburg | 2025-01-31 | PPM88371 |  | 86 |  | Yes | Yes | Received | 2025-01-20 | Completed | 2025-01-18 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed |  | Pending | #REF!
D-HDH31 | St Petersburg | 2025-01-31 | PPM89043 |  | 86 |  | Yes | Yes | Received | Completed | Completed | 2025-01-18 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-12 | Submitted | #REF!
D-HDH32 | St Petersburg | 2025-01-31 | PPM89595 |  | 88 |  | Yes | Yes | Received | 2025-03-26 | Completed | 2025-03-27 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending |  | Pending | #REF!
D-HDH34 | St Petersburg | 2025-01-31 | PPM88372 |  | 88 |  | Yes | Yes | Received | 2025-02-18 | Completed | 2025-01-22 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending | 2025-06-12 | Pending | #REF!
D-HDH41 | St Petersburg | 2025-04-25 | PPM91655 |  | 85 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-04-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending
D-HDH42 | St Petersburg | 2025-04-25 | PPM92270 |  | 88 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-04-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-21 | Submitted
D-HDH43 | St Petersburg | 2025-04-25 | PPM92271 |  | 57 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Not Req | Completed | Completed | Priority | Pending | 2025-05-27 | Pending | #REF!
D-HDH45 | St Petersburg | 2025-02-23 | PPM89601 |  | 73 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-09-02 | Submitted | #REF!
D-HDH46 | St Petersburg | 2025-02-23 | PPM89610 |  | 65 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-20 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-13 | Submitted | #REF!
D-HDH47 | St Petersburg | 2025-04-25 | PPM92273 |  | 70 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-14 | Submitted | #REF!
D-HDH48 | St Petersburg | 2025-04-25 | PPM92278 |  | 84 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-04-08 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-14 | Submitted
D-HDH49 | St Petersburg | 2025-04-25 | PPM92276 |  | 75 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-31 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-21 | Submitted | #REF!
D-HDH50 | St Petersburg | 2025-04-25 | PPM93107 |  | 69 |  | Yes | Yes | Received | 2025-04-10 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-06 | Submitted
D-HDH52 | St Petersburg | 2025-04-25 | PPM93114 |  | 50 |  | Yes | Yes | Received | 2025-04-10 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-30 | Submitted
D-HDH53 | St Petersburg | 2025-04-25 | PPM93118 |  | 76 |  | Yes | Yes | Received | 2025-04-10 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-03 | Submitted
D-HDH54 | St Petersburg | 2025-04-25 | PPM93122 |  | 88 |  | Yes | Yes | Received | 2025-04-10 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-02 | Submitted
D-HDH55 | St Petersburg | 2025-04-25 | PPM93069 |  | 86 |  | Yes | Yes | Received | 2025-04-09 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-05 | Submitted
D-HDH56 | St Petersburg | 2025-04-25 | PPM92087 |  | 84 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-04-01 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-03 | Submitted
D-HDH57 | St Petersburg | 2025-04-25 | PPM92588 |  | 87 |  | Yes | Yes | Received | 2025-04-10 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending | 2025-06-30 | Pending
D-HDH58 | St Petersburg | 2025-04-25 | PPM92280 |  | 81 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-31 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HDH60 | St Petersburg | 2025-04-25 | PPM92088 |  | 80 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-03 | Submitted | #REF!
D-HDH62 | St Petersburg | 2025-04-25 | PPM92283 |  | 63 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Not Req | Completed | Completed | Priority | Pending | 2025-06-24 | Pending | #REF!
D-HDH66 | St Petersburg | 2025-01-31 | PPM88373 |  | 90 |  | Yes | Yes | Received | Completed | Completed | 2025-01-22 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-06 | Submitted | #REF!
D-HDH67 | St Petersburg | 2025-04-25 | PPM91122 |  | 86 |  | Yes | Yes | Received | Completed | Completed | 2025-03-04 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-11 | Submitted | #REF!
D-HDH68 | St Petersburg | 2025-02-23 | PPM89616 |  | 90 |  | Yes | Yes | Received | 2025-02-12 | Completed | 2025-01-22 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-04 | Submitted | #REF!
D-HDH69 | St Petersburg | 2025-03-26 | PPM89618 |  | 82 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-06 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-08-14 | Submitted | #REF!
D-HDH70 | St Petersburg | 2025-04-25 | PPM91121 |  | 82 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-04 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-06 | Submitted | #REF!
D-HDH71 | St Petersburg | 2025-03-31 | PPM89623 |  | 64 |  | Yes | Yes | Received | 2025-02-13 | Completed | 2025-02-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-21 | Submitted | #REF!
D-HDH72 | St Petersburg | 2025-03-26 | PPM89624 |  | 82 |  | Yes | Yes | Received | Completed | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Completed |  | Pending | #REF!
D-HDH73 | St Petersburg | 2025-02-23 | PPM89626 |  | 59 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-12 | Submitted | #REF!
D-HDH73 | St Petersburg | 2025-03-26 | PPM90342 |  | 38 |  | Yes | Yes | Received | Completed | Completed | 2025-02-13 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-13 | Submitted | #REF!
D-HDH74 | St Petersburg | 2025-02-23 | PPM89643 |  | 85 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-21 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-06-17 | Pending | #REF!
D-HDH75 | St Petersburg | 2025-04-25 | PPM91431 |  | 88 |  | Yes | Yes | Received | Completed | Completed | 2025-03-04 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-11 | Submitted | #REF!
D-HDH76 | St Petersburg | 2025-02-23 | PPM89553 |  | 86 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-14 | Submitted | #REF!
D-HDH77 | St Petersburg | 2025-03-26 | PPM92290 |  | 84 |  | Yes | Yes | Received | 2025-02-27 | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HDH78 | St Petersburg | 2025-02-23 | PPM90248 |  | 85 |  | Yes | Yes | Received | 2025-02-19 | Completed | 2025-02-19 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-13 | Submitted | #REF!
D-HDH79 | St Petersburg | 2025-03-26 | PPM90331 |  | 87 |  | Yes | Yes | Received | Completed | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HDH80 | St Petersburg | 2025-04-25 | PPM92262 |  | 91 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-27 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-11 | Submitted | #REF!
D-HDH82 | St Petersburg | 2025-04-25 | PPM92198 |  | 20 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-27 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-03 | Submitted | #REF!
D-HDH83 | St Petersburg | 2025-03-26 | PPM90333 |  | 87 |  | Yes | Yes | Received | Completed | Completed | 2025-02-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HDH84 | St Petersburg | 2025-01-31 | PPM88311 |  | 79 |  | Yes | Yes | Received | Completed | Completed | 2025-01-18 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HNP104 | St Petersburg | 2025-07-24 | PPM93993 |  | 78 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-04-02 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-19 | Submitted
D-HNP106 | St Petersburg | 2025-11-30 | PPM93922 |  | 69 |  | Yes | Yes | Received | 2025-03-25 | In Process | 2025-03-28 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
D-HNP107 | St Petersburg | 2025-11-30 | PPM90859 |  | 85 |  | Yes | Yes | Received | 2025-03-25 | Not Started | 2025-03-28 | Not Started | [7 empty] | Pending | #REF!
D-HNP111 | St Petersburg | 2025-11-30 | PPM92084 |  | 86 |  | Yes | Yes | Received | 2025-03-25 | In Process | 2025-04-02 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
D-HNP113 | St Petersburg | 2025-11-30 | PPM90871 |  | 70 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending |  | Pending | #REF!
D-HNP114_H0103D | St Petersburg | 2025-11-30 | PLK88966 |  | 81 |  | Yes | Yes | Received | 2025-02-14 | In Process | 2025-02-08 | In Process | In Process | Not Req | In Process | In Process | Pending | Pending |  | Pending | #REF!
D-HNP117 | St Petersburg | 2025-11-30 | PPM93990 |  | 60 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending |  | Pending
D-HNP123 | St Petersburg | 2025-11-30 | PPM89671 |  | 90 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-10 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-06-10 | Pending | #REF!
D-HNP135 | St Petersburg | 2025-11-30 | PPM94426 |  | 70 |  | Yes | Yes | Received | 2025-03-25 | In Process | 2025-03-25 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
D-HNP137 | St Petersburg | 2025-11-30 | PPM89749 |  | 78 |  | Yes | Yes | Received | 2025-02-20 | Completed | 2025-02-08 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-30 | Submitted | #REF!
D-HNP138 | St Petersburg | 2025-11-30 | PPM89683 |  | 87 |  | Yes | Yes | Received | 2025-02-20 | Completed | 2025-02-08 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-15 | Submitted | #REF!
D-HNP141 | St Petersburg | 2025-11-30 | PPM89690 |  | 60 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-11 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-13 | Submitted | #REF!
D-HNP143 | St Petersburg | 2025-11-30 | PPM89772 |  | 87 |  | Yes | Yes | Received | 2025-02-11 | Completed | 2025-02-11 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending | 2025-03-31 | Pending | #REF!
D-HNP144 | St Petersburg | 2025-11-30 | PPM90863 |  | 79 |  | Yes | Yes | Received | 2025-03-19 | In Process | 2025-03-21 | In Process | In Process | Not Req | In Process | In Process | Pending |  |  | Pending | #REF!
D-HNP151 | St Petersburg | 2025-11-30 | PPM90865 |  | 50 |  | Yes | Yes | Received | 2025-03-19 | Completed | 2025-03-20 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-09 | Submitted | #REF!
FB-H0205A | St Petersburg | 2025-03-26 | PPM90591 |  | 0 |  | Yes | Yes | Received | 2025-02-28 | Completed | Completed | Completed | Completed | Completed | Not Required | Completed | Completed | Pending |  | Pending | #REF!
FB-H0220A | St Petersburg | 2025-03-26 | PPM89778 |  | 0 |  | Yes | Yes | Received | 2025-02-24 | Completed | 2025-03-07 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-28 | Submitted | #REF!
FB-H0221A | St Petersburg | 2025-03-26 | PPM89791 |  | 0 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-10 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-06 | Submitted | #REF!
FB-H0222A | St Petersburg | 2025-02-23 | PPM88374 |  | 0 |  | Yes | Yes | Received | 2025-02-07 | Completed | 2025-02-05 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-30 | Submitted | #REF!
FB-H0223A | St Petersburg | 2025-02-23 | PPM89789 |  | 0 |  | Yes | Yes | Received | 2025-01-29 | Completed | 2025-02-05 | Completed | Completed | Completed | Not Required | Completed | Completed | Pending |  | Pending | #REF!
FB-HDH01 | St Petersburg | 2025-01-31 |  |  | 0 |  |  |  | Received | Completed | Completed | Completed | Completed | Completed | Completed | Not Required | Completed | Completed | Completed |  | Pending | #REF!
FB-HDH01A-2A | St Petersburg | 2025-06-30 | PPM96333 |  | 0 |  | Yes | Yes | Received | Completed | Completed | 2025-06-10 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-07-16 | Submitted
FB-HDH02A | St Petersburg | 2025-02-28 | PPM87852 |  | 0 |  | Yes | Yes | Received | Completed | Completed | 2025-02-05 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed |  | Pending | #REF!
FB-HDH275 | St Petersburg | 2025-03-26 | PPM89801 |  | 0 |  | Yes | Yes | Received | 2025-02-26 | Completed | 2025-03-04 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-09-02 | Submitted | #REF!
FB-HNP104 | St Petersburg | 2025-03-26 | PPM90880 |  | 0 |  | Yes | Yes | Received | 2025-03-25 | Not Started | 2025-03-27 | Not Started |  |  | Not Required |  |  |  |  | Pending | #REF!
FB-HNP133 | St Petersburg | 2025-11-30 | PPM92370 |  | 0 |  | Yes | Yes | Received | 2025-03-26 | In Process | 2025-03-27 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
FB-HNP138 | St Petersburg | 2025-04-30 | PPM89817 |  | 0 |  | Yes | Yes | Received | 2025-02-12 | In Process | 2025-02-08 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending |  | Pending | #REF!
FB-HNP144 | St Petersburg | 2025-04-25 | PPM90914 |  | 0 |  | Yes | Yes | Received | 2025-03-25 | Not Started | 2025-03-27 | Not Started |  |  | Not Required |  |  |  |  | Pending | #REF!
FX4-FML-05 | St Petersburg | 2025-07-24 | PPM93377 |  | 0 |  | Yes | Yes | Received | TBD | Completed | TBD | Completed | Not Required | Not Required | Not Required | Completed | Pending | Pending
Note on A7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hand Dig Tie In For Tillman.
Note on A87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Splice Only Project.
Note on A133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A139: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A159: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.

## Completed Jobs Summary (hidden)
CURRENT ASSIGNMENTS |  | MONTHLY ASSIGNED FOOTAGE
Sum of Footage UG |  | Vendor Assignment | (Multiple Items) |  |  |  | On Track or In Jeopardy | In Jeopardy
Vendor Assignment | Total |  |  | Tillman forecasted Month | APRIL |  | Tillman forecasted Month | APRIL
Brothers | 53127 | Sum of Footage UG | Total | [7 empty] | Working Day | 22
Lightspeed In-House | 12248 | Total | 107526 | Count of Job No |  |  | Count of Job No |  |  |  | Day to Month | 13
(blank) | 48410 |  |  | On Track or In Jeopardy | Job No | Total | Blockers | Job No | Total
Vendor Assignment | 0 |  |  | In Jeopardy | BHT-FWP-06 | 1 | Manpower |  | 1 |  |  | % Month | % to Goal
North Path | 42234 |  |  |  | BHT-FWP-07 | 1 | NTP Permit |  | 1 | Monthly Forecast Footage | 203521 | 59.09% | 31.45%
GN Systems | 22737 |  |  |  | D-HDH40 | 1 | Tie-ends | D-HDH40 | 1 | Footage Complete | 64000
Splice Only Project | 3 |  |  |  | D-HDH41 | 1 |  | D-HDH42 | 1
Kattle One | 24711 |  |  |  | D-HDH42 | 1 |  | D-HDH43 | 1
Kattle One/LSCG | 6182 |  |  |  | D-HDH43 | 1 |  | D-HDH51 | 1
APT Communications / New Gen Unlimited | 30807 |  |  |  | D-HDH44 | 1 |  | D-HDH62 | 1
Lopez Underground | 58481 |  |  |  | D-HDH50 | 1 | Tie-ends Total |  | 5
Power Connect | 42151 |  |  |  | D-HDH51 | 1 | (blank) |  | 12
Alpha Omega | 18823 |  |  |  | D-HDH52 | 1 | Grand Total |  | 19
HAS Global | 3106 |  |  |  | D-HDH53 | 1
APT Communications | 15600 |  |  |  | D-HDH54 | 1
ASM Utilities | 11043 |  |  |  | D-HDH55 | 1
HD Cable | 16923 |  |  |  | D-HDH57 | 1
Legant Livings | 24336 |  |  |  | D-HDH61 | 1
Gulfstream | 10070 |  |  |  | D-HDH62 | 1
Restoring Pro | 19892 |  |  |  | D-HDH80 | 1
Randy's Utilities | 13494 |  |  |  | FB-HDH02A | 1
A1 Broadband | 13430 |  |  |  | FB-HWP601 | 1
Full Circle In-House/Saul/Felipe | 5350 |  |  | In Jeopardy Total |  | 19
Sosa Line | 7602 |  |  | Complete | D-HDH47 | 1
APT Communications/North Path | 9133 |  |  |  | D-HDH48 | 1
ASM | 9260 |  |  |  | D-HDH49 | 1
ITG In-House | 7068 |  |  |  | D-HDH56 | 1
Grand Total | 526221 |  |  |  | D-HDH58 | 1
[5 empty] | D-HDH59 | 1
[5 empty] | D-HDH60 | 1
[5 empty] | D-HDH82 | 1
[5 empty] | D-HWP702 | 1
[5 empty] | D-HWP703 | 1
[5 empty] | D-HWP706 | 1
[5 empty] | D-HWP707 | 1
|  |  |  | Complete Total |  | 12
|  |  |  | Grand Total |  | 31

## Project Summary (hidden)
[7 empty] | D&E Update | [8 empty] | Constuction Status
[17 empty] | Prism | Local Team | Penguin Task | Penguin Task | Penguin Task | Penguin Task | PLC | Noes
Job No | AREA | TSD | HHP | Tillman forecasted Month | Days | On Track or In Jeopardy | Permit Status | Funding | Required Permits | Drafting | Submitted | Approved | Pending Permits | % Complete | Blockers | Constuction Status | Funding | Materials | Construction Start | UG Percentage Complete | Aerial Percentage Complete | Splicing Percentage Complete | Construction Total Percent Complete | Additional Information | Required Footage
FB-HNP104 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP107 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP106 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP110 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP109 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | NTP Permit | Hold | Missing | [7 empty] | #REF!
D-HNP108 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP104 | St Petersburg | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Not Started | Funded | [7 empty] | #REF!
FB-HNP111 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP114 | St Petersburg | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP111 | St Petersburg | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP113 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP117 | St Petersburg | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP115 | St Petersburg | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
FB-HDH02A | St Petersburg | #N/A |  | APRIL |  | In Jeopardy | [9 empty] | Locates Called | Funded | [7 empty] | #REF!
D-HDH80 | St Petersburg | 2025-05-30 |  | APRIL |  | In Jeopardy | [8 empty] | Manpower |  | Funded | [7 empty] | #REF!
D-HDH82 | St Petersburg | #N/A |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH47 | St Petersburg | #N/A |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH44 | #N/A | 2025-05-30 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [6 empty] | Need to follow-up if we need to place any additional underground conduit for the tie ins | #REF!
D-HDH48 | St Petersburg | #N/A |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH41 | St Petersburg | #N/A |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [6 empty] | blowing sting ray 5.1 | #REF!
D-HDH40 | #N/A | 2025-02-28 |  | APRIL |  | In Jeopardy | [8 empty] | Tie-ends | In Process | Funded | [6 empty] | blowing sting ray 5.1 | #REF!
D-HDH42 | St Petersburg | 2025-04-25 |  | APRIL |  | In Jeopardy | [8 empty] | Tie-ends | In Process | Funded | [7 empty] | #REF!
D-HDH43 | St Petersburg | 2025-04-25 |  | APRIL |  | In Jeopardy | [8 empty] | Tie-ends | In Process | Funded | [7 empty] | #REF!
D-HDH62 | St Petersburg | 2025-04-25 |  | APRIL |  | In Jeopardy | [8 empty] | Tie-ends | In Process | Funded | [7 empty] | #REF!
D-HDH51 |  |  |  | APRIL |  | In Jeopardy | [8 empty] | Tie-ends | In Process | Funded | [6 empty] | Need to follow-up if we need to place any additional underground conduit for the tie ins | #REF!
D-HDH61 | #N/A | #N/A |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [6 empty] | Need to follow-up if we need to place any additional underground conduit for the tie ins | #REF!
D-HDH56 | St Petersburg | 2025-04-25 |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH60 | St Petersburg | 2025-04-25 |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [6 empty] | Pending: confirm rock adder w/ Tillman Inspector to complete measurements | #REF!
D-HDH58 | St Petersburg | 2025-04-25 |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH53 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
D-HDH50 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
D-HDH52 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
D-HDH49 | St Petersburg | 2025-04-25 |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH54 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
D-HDH55 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
D-HDH59 | #N/A | #N/A |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [6 empty] | Need to follow-up if we need to place any additional underground conduit for the tie ins | #REF!
D-HDH57 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
FB-HNP144 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Not Started | Funded | [7 empty] | #REF!
FB-HNP138 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | In Process | Funded | [7 empty] | #REF!
FB-HNP133 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Not Started | Funded | [7 empty] | #REF!
FB-HNP118 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Manpower | In Process | Funded | [7 empty] | #REF!
BHT-FWP-06 | St Petersburg | 2025-05-30 |  | APRIL |  | In Jeopardy | [9 empty] | Not Started | Funded | [7 empty] | #REF!
BHT-FWP-07 | St Petersburg | 2025-05-30 |  | APRIL |  | In Jeopardy | [9 empty] | Not Started | Funded | [7 empty] | #REF!
FB-HWP601 | St Petersburg | 2025-05-30 |  | APRIL |  | In Jeopardy | [8 empty] | NTP Permit | Not Started | Missing | [7 empty] | #REF!
D-HWP707 | St Petersburg | 2025-05-30 |  | APRIL |  | Complete | [8 empty] | QC | Complete | Funded | [7 empty] | #REF!
D-HWP703 | Lakeland | 2025-04-25 |  | APRIL |  | Complete | [8 empty] | QC | Complete | Funded | [7 empty] | #REF!
D-HWP702 | Lakeland | 2025-04-25 |  | APRIL |  | Complete | [8 empty] | QC | Complete | Funded | [7 empty] | #REF!
D-HWP706 | #N/A | #N/A |  | APRIL |  | Complete | [8 empty] | QC | Complete | Funded | [7 empty] | #REF!
D-HWP1306 | Lakeland | 2025-09-25 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | In Process | Funded | [7 empty] | #REF!
D-HWP1309 | Lakeland | 2025-09-25 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | In Process | Funded | [7 empty] | #REF!
D-HWP1304 | Lakeland | 2025-09-25 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | In Process | Funded | [7 empty] | #REF!
D-HWP905 | Lakeland | 2025-07-24 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | NTP Permit | Not Started | Missing | [7 empty] | #REF!
D-HWP603 |  | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | SOW | Not Started | Missing | [7 empty] | #REF!
BHT-FWP-10 | Lakeland | 2025-05-10 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | NTP Permit | Not Started | Missing | [7 empty] | #REF!
D-HWP1304 | St Petersburg | 2025-05-30 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded
D-HWP1306 | Lakeland | 2025-04-25 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded
D-HWP1309 | Lakeland | 2025-04-25 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded
| #N/A | #N/A
| Lakeland | 2025-09-25
| Lakeland | 2025-09-25
| Lakeland | 2025-09-25
| Lakeland | 2025-07-24
#N/A
Drafting | 0 | #DIV/0!
Submitted | 0 | #DIV/0!
Approved | 0 | #DIV/0!
Total | 0
Locates - St Pete
Locates - WOW
Locates
Locates - USIC
Permits

## Tillman UG Footage
Market 1 NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | Restoration Completed | QC Requested Date | QC Sheet Phase 1 Received | QC Sheet Phase 2 Received | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | UG Percentage Complete | Construction Start Date | Construction End Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Fiber Placement and Splice Only Footage | Notes
D-HPP630 | Clearwater | 2026-10-30 | Brothers | 2026-05-29 | Marcelo Zaldivar |  | 67 | On Track | Received |  |  | Yes | 100866 | Yes | Completed | 2026-06-02 |  |  |  |  | 9021 | 8341 | 680 | 92.46% | 2026-06-22 | 2026-07-27 | 0% | 0% | 0 | 5/1 NTP Package Received.
D-HPP631 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Treyvon Tillman |  | 93 | On Track | Received |  |  | Yes | 104934 | Yes | Completed | 2026-06-03 |  |  |  |  | 8701 | 7811 | 890 | 89.77% | 2026-06-18 | 2026-08-27 | 0% | 0% | 0 | 5/1 NTP Package Received.
D-HPP637 | Clearwater | 2026-10-30 | Lightspeed In-House | 2026-05-29 | Treyvon Tillman |  | 40 | On Track | Received |  | 2026-06-09 | Yes | 91774 | Yes | In Process | 2026-05-29 |  |  |  |  | 7530 | 7204 | 326 | 95.67% | 2026-07-14 |  | 0% | 0% | 0 | 5/1 NTP Package Received.
FB-HPP612-2 | Clearwater | 2026-10-10 |  |  | Anthony Adum |  | 0 | On Track | Received |  |  | No | 649 | Yes | Not Started | [5 empty] | 0 |  | 0 | 0% |  |  | 0% | 0% | 0 | 9/23 NTP Package Received--PO In Full Circle's Name Not ITG--Tillman Needs To Upload A New PO. Aerial Work Project.
D-HNP108/D-H0102E | St Petersburg | 2026-02-27 | Kattle One/LSCG | 2025-12-27 | Johnnie Williams | PPM91941 | 89 | On Track | Received |  | 2026-01-06 | Yes | 72131.5 | Yes | In Process | 2025-12-23 |  |  |  |  | 6182 | 5899 | 283 | 95.42% | 2025-08-22 |  | 0% | 0% | 0 | 5/11 - Stop work in place for City of St. Pete till 5/15 - 5/4 Will have to redrill 380' K1 drilled to deep and did not install the 2 tobys, Locates Called in - 4-28 JW // REPAIRED 1 OF 2 DAPs. NEED TO FIND ISSUE WITH THE 2ND DAP LOCATION - 3.16 JW // LSCG QC discovered missing section of Route 2, called in locates and they are pending
Market 1 NTP Number Pinellas | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | Restoration Completed | QC Requested Date | QC Sheet Phase 1 Received | QC Sheet Phase 2 Received | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | UG Percentage Complete | Construction Start Date | Construction End Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Fiber Placement and Splice Only Footage | Notes
D-HLC505 | Pinellas | 2026-10-30 | Brothers | 2026-09-30 | Joshua Pacheco |  | 41 | On Track | Received | Pending Locates | 2026-07-22 | Yes | 78963.5 | Yes | Locates Called | 2026-07-22 |  |  |  |  | 5973 |  | 5973 | 0% |  |  | 0% | 0% | 0 | 7/13 NTP Package Received. 7/17 PO Received And Approved.
D-HLC508 | Pinellas | 2026-09-30 | ASM Utilities | 2026-07-20 | Danny Combs |  | 69 | Completed -Missed TSD | Received |  |  | Yes | 84458.5 | Yes | Completed | 2026-07-27 |  |  |  |  | 6831 | 5274 | 1557 | 77.21% | 2026-09-16 | 2026-10-01 | 100% | 100% | 0 | 7/13 NTP Package Received. 7/17 PO Received And Approved.
D-HLC509 | Pinellas | 2026-10-30 | Brothers | 2026-09-23 | Anthony Adum |  | 72 | On Track | Received | Pending Locates |  | No | 69525.5 | Yes | Locates Called | 2026-09-23 |  |  |  |  | 5407 |  | 5407 | 0% |  |  | 0% | 0% | 0 | 9/18 NTP Package Received. PO Approved 9/24.
D-HLC510 | Pinellas | 2026-10-30 | Lightspeed In-House | 2026-07-20 | Treyvon Tillman |  | 102 | On Track | Received |  | 2026-07-21 | Yes | 59181 | Yes | In Process | 2026-07-27 |  |  |  |  | 4718 | 3520 | 1198 | 74.61% | 2026-09-18 |  | 0% | 0% | 0 | 7/13 NTP Package Received. 7/17 PO Received And Approved.
D-HLC514 | Pinellas | 2026-09-30 | APT Communications | 2026-07-16 | Joshua Pacheco | PPM112724 | 83 | Completed | Received | Pending Locates | 2026-07-20 | Yes | 87651 | Yes | Completed | 2026-07-20 |  |  |  |  | 7199 | 6948 | 251 | 96.51% | 2026-09-22 | 2026-10-01 | 100% | 100% | 0 | 7/13 NTP Package Received. 7/17 PO Received And Approved.
D-HLC515 | Pinellas | 2026-09-30 | Randy's Utilities | 2026-08-07 | Joshua Pacheco |  | 18 | Completed | Received | Pending Locates | 2026-08-12 | Yes | 80560 | Yes | Completed | 2026-08-12 |  |  |  |  | 6416 | 6040 | 376 | 94.14% | 2026-09-10 | 2026-09-24 | 100% | 100% | 0 | 8/5 NTP Package Received--8/6 PO Received.
D-HLC516 | Pinellas | 2026-09-30 | Legant Livings | 2026-08-07 | Joshua Pacheco |  | 90 | Completed | Received | Pending Locates | 2026-08-03 | Yes | 113855.5 | Yes | Completed | 2026-08-26 |  |  |  |  | 8970 | 8050 | 920 | 89.74% | 2026-09-09 | 2026-10-05 | 100% | 100% | 0 | 7/31 NTP Package Received.
D-HLC520 | Pinellas | 2026-11-30 | Power Connect | 2026-10-06 | Johnnie Williams |  | 101 | On Track | Received | Pending Locates | 2026-09-10 | Yes | 72023 | Yes | Not Started | [5 empty] | 5644 |  | 5644 | 0% |  |  | 0% | 0% | 0 | 8/24 NTP Package and PO Received.
D-HLC521 | Pinellas | 2026-10-30 | Legant Livings | 2026-09-02 | Joshua Pacheco |  | 108 | On Track | Received | Pending Locates |  | Yes | 105904.5 | Yes | Locates Called | 2026-09-08 |  |  |  |  | 8808 |  | 8808 | 0% |  |  | 0% | 0% | 0 | 8/24 NTP Package and PO Received.
D-HLC522 | Pinellas | 2026-10-30 | Legant Livings | 2026-09-02 | Joshua Pacheco |  | 71 | On Track | Received | Pending Locates |  | Yes | 79435.5 | Yes | Locates Called | 2026-09-09 |  |  |  |  | 6374 |  | 6374 | 0% |  |  | 0% | 0% | 0 | 8/24 NTP Package and PO Received.
D-HLC523 | Pinellas | 2026-11-30 | Full Circle In-House/Saul/Felipe | 2026-09-04 | Johnnie Williams |  | 92 | On Track | Received | Pending Locates |  | Yes | 66908 | Yes | Locates Called | 2026-09-26 |  |  |  |  | 5350 |  | 5350 | 0% |  |  | 0% | 0% | 0 | 8/24 NTP Package and PO Received.
D-HLC524 | Pinellas | 2026-10-30 | Randy's Utilities | 2026-09-03 | Joshua Pacheco |  | 89 | On Track | Received | Pending Locates |  | Yes | 86487 | Yes | Locates Called | 2026-09-16 |  |  |  |  | 7078 |  | 7078 | 0% | 2026-10-08 |  | 0% | 0% | 0 | 8/24 NTP Package and PO Received.
D-HLC525 | Pinellas | 2026-11-30 |  |  |  |  | 77 | On Track | Received |  |  | Yes | 92514.5 | Yes | Not Started | [5 empty] | 7434 |  | 7434 | 0% |  |  | 0% | 0% | 0 | 9/30 NTP Package Received--Pending SOW/PO To Be Uploaded Into SiteTracker and For The Change Order To Be Approved By Tillman. 10/5 PO Approved--James H No Change Order Due At This Time.
D-HLC527 | Pinellas | 2026-11-30 |  |  |  |  | 69 | On Track | Received |  |  | Yes | 41647.5 | Yes | Not Started | [5 empty] | 3170 |  | 3170 | 0% |  |  | 0% | 0% | 0 | 9/30 NTP Package Received--Pending SOW/PO To Be Uploaded Into SiteTracker and For The Change Order To Be Approved By Tillman. 10/5 PO Approved--James H No Change Order Due At This Time.
D-HLC538 | Pinellas | 2026-11-30 | APT Communications | 2026-09-23 | Johnnie Williams |  | 37 | On Track | Received | Pending Locates |  | Yes | 105048 | Yes | Locates Called | 2026-09-23 |  |  |  |  | 8401 |  | 8401 | 0% |  |  | 0% | 0% | 0 | 8/31 NTP Package and PO Received.
D-HLC540 | Pinellas | 2026-11-30 | Sosa Line | 2026-10-02 | Matthew Nunes |  | 110 | On Track | Received |  |  | Yes | 54275 | Yes | Locates Called | 2026-10-02 |  |  |  |  | 4386 |  | 4386 | 0% |  |  | 0% | 0% | 0 | 8/25 NTP Package and PO Received.
D-HLC541 | Pinellas | 2026-11-30 |  |  |  |  | 50 | On Track | Received |  |  | Yes | 82194.5 | Yes | Not Started | [5 empty] | 6948 |  | 6948 | 0% |  |  | 0% | 0% | 0 | 9/30 NTP Package Received--Pending SOW/PO To Be Uploaded Into SiteTracker and For The Change Order To Be Approved By Tillman. 10/5 PO Approved--James H No Change Order Due At This Time.
D-HLC547 | Pinellas | 2026-11-30 | ASM Utilities | 2026-10-02 | Matthew Nunes |  | 51 | On Track | Received |  |  | Yes | 53744.5 | Yes | Locates Called | 2026-10-02 |  |  |  |  | 4212 |  | 4212 | 0% |  |  | 0% | 0% | 0 | 8/26 NTP Package and PO Received.
D-HPP837 | Pinellas | 2026-10-30 | Kattle One | 2026-09-03 | Danny Combs |  | 23 | On Track | Received |  |  | Yes | 62033 | Yes | Locates Called | 2026-09-08 |  |  |  |  | 4828 |  | 4828 | 0% |  |  | 0% | 0% | 0 | 8/25 NTP Package and PO Received.
D-HPP838 | Pinellas | 2026-10-30 | Kattle One | 2026-09-03 | Danny Combs |  | 77 | On Track | Received | Pending Locates |  | Yes | 64431 | Yes | Locates Called | 2026-09-08 |  |  |  |  | 4931 |  | 4931 | 0% |  |  | 0% | 0% | 0 | 8/25 NTP Package and PO Received.
D-HPP839 | Pinellas | 2026-10-30 | Kattle One | 2026-09-03 | Danny Combs |  | 65 | On Track | Received | Pending Locates |  | Yes | 80031 | Yes | In Process | 2026-09-08 |  |  |  |  | 6185 | 5196 | 6185 | 84.01% | 2026-09-29 |  | 0% | 0% | 0 | 8/25 NTP Package and PO Received.
D-HPP852 | Pinellas | 2026-10-30 | Power Connect | 2026-10-07 | Treyvon Tillman |  | 62 | On Track | Received | Pending Locates |  | Yes | 95912 | Yes | Locates Called | 2026-10-06 |  |  |  |  | 7541 |  | 7541 | 0% |  |  | 0% | 0% | 0 | 8/25 NTP Package and PO Received.
D-HPP853 | Pinellas | 2026-10-30 | Power Connect | 2026-08-27 | Treyvon Tillman |  | 44 | On Track | Received | Pending Locates |  | Yes | 89669 | Yes | Locates Called | 2026-10-09 |  |  |  |  | 7072 |  | 7072 | 0% |  |  | 0% | 0% | 0 | 8/25 NTP Package and PO Received.
D-HPP855 | Pinellas | 2026-10-30 | Power Connect | 2026-08-27 | Treyvon Tillman |  | 110 | On Track | Received | Pending Locates |  | Yes | 96644.5 | Yes | Locates Called | 2026-10-06 |  |  |  |  | 8090 |  | 8090 | 0% |  |  | 0% | 0% | 0 | 8/24 NTP Package and PO Received.
D-HPP856 | Pinellas | 2026-10-30 | Brothers | 2026-09-23 | Treyvon Tillman |  | 45 | On Track | Received | Pending Locates |  | Yes | 99698.5 | Yes | Locates Called | 2026-09-24 |  |  |  |  | 8469 |  | 8469 | 0% |  |  | 0% | 0% | 0 | 8/24 NTP Package and PO Received.
D-HPP857 | Pinellas | 2026-10-30 | ASM | 2026-09-23 | Treyvon Tillman |  | 90 | On Track | Received | Pending Locates |  | Yes | 111605.5 | Yes | Locates Called | 2026-09-29 |  |  |  |  | 9260 |  | 9260 | 0% |  |  | 0% | 0% | 0 | 8/24 NTP Package and PO Received.
D-HPP860 | Pinellas | 2026-10-30 | Brothers | 2026-08-27 | Anthony Adum |  | 95 | On Track | Received | Pending Locates | 2026-09-02 | Yes | 69986 | Yes | Locates Called | 2026-09-19 |  |  |  |  | 5310 |  | 5310 | 0% |  |  | 0% | 0% | 0 | 8/25 NTP Package and PO Received.
D-HPP882 | Pinellas | 2026-10-30 | Power Connect | 2026-08-28 | Danny Combs |  | 64 | On Track | Received | Pending Locates |  | Yes | 69701 | Yes | Locates Called | 2026-10-09 |  |  |  |  | 5357 |  | 5357 | 0% |  |  | 0% | 0% | 0 | 8/26 NTP Package and PO Received.
D-HPP883 | Pinellas | 2026-10-30 | Power Connect | 2026-08-28 | Danny Combs |  | 90 | On Track | Received | Pending Locates |  | Yes | 92174.5 | Yes | Locates Called | 2026-10-09 |  |  |  |  | 7153 | 2088 | 7153 | 29.19% | 2026-09-22 |  | 0% | 0% | 0 | 8/26 NTP Package and PO Received.
D-HPP884 | Pinellas | 2026-10-30 | Kattle One | 2026-09-17 | Danny Combs |  | 72 | On Track | Received | Pending Locates |  | Yes | 105926.5 | Yes | Locates Called | 2026-10-01 |  |  |  |  | 8767 |  | 8767 | 0% |  |  | 0% | 0% | 0 | 8/26 NTP Package and PO Received.
FB-HLC521 | Pinellas | 2026-10-30 | Legant Livings | 2026-09-02 | Joshua Pacheco |  | 0 | On Track | Received |  |  | Yes | 2524 | Yes | Locates Called | 2026-09-08 |  |  |  |  | 184 |  | 184 | 0% |  |  | 0% | 0% | 0 | 8/26 NTP Package and PO Received.
FB-HLC524 | Pinellas | 2026-10-30 | Power Connect | 2026-09-04 | Johnnie Williams |  | 0 | On Track | Received |  |  | Yes | 16946.9 | Yes | Locates Called | 2026-09-05 |  |  |  |  | 1294 |  | 1294 | 0% |  |  | 0% | 0% | 0 | 8/26 NTP Package and PO Received.
FB-HLC538 | Pinellas | 2026-11-27 | Sosa Line | 2026-09-18 | Johnnie Williams |  | 0 | On Track | Received |  |  | Yes | 41225.6 | Yes | In Process | 2026-09-22 |  |  |  |  | 3216 | 1739 | 3216 | 54.07% | 2026-10-06 |  | 0% | 0% | 0 | 8/26 NTP Package and PO Received.
FB-HPP854 | Pinellas | 2026-10-30 | Brothers | 2026-08-27 | Anthony Adum |  | 0 | On Track | Received | Pending Locates | 2026-09-02 | Yes | 77452.2 | Yes | Locates Called | 2026-09-21 |  |  |  |  | 6142 | 1679 | 4463 | 27.34% | 2026-09-29 |  | 0% | 0% | 0 | 8/26 NTP Package and PO Received.
Market 2 NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | Restoration Completed | QC Requested Date | QC Sheet Phase 1 Received | QC Sheet Phase 2 Received | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | UG Percentage Complete | Construction Start Date | Construction End Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Fiber Placement and Splice Only Footage | Notes
FB-HWP376 | Lakeland | 2025-12-15 | Brothers | 2025-10-06 | Miguel Herrero | PLK102584 | 0 | On Track | Received | On Hold Per Tillman | N/A | Yes | 54857.5 | Yes | In Process | 2025-10-03 |  |  |  |  | 4104 | 3928 | 176 | 95.71% | 2025-10-08 |  | 0% | 0% | 0 | 9/29 FDOT Permit Received.Assigned to brothers 9-30/CX Began 10/8. 10/21 FDOT is complete, wtg on city permit 12-15, 10/8/26 - Tillman is working on plan to get Fiber Pulled and Spliced (Jesse)
FB-HWP881 | Lakeland | 2026-04-30 | Splice Only Project |  | Eric | PLK105476 | 0 | On Track | Received | On Hold Per Tillman |  | Yes | 255.05 | Yes | Locates Called | [5 empty] | 3 |  | 3 | 0% |  |  | 0% | 0% | 0 | 11/17 Pending Permit.-Splice Only Project.
Market 3 NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | Restoration Completed | QC Requested Date | QC Sheet Phase 1 Received | QC Sheet Phase 2 Received | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | UG Percentage Complete | Construction Start Date | Construction End Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Fiber Placement and Splice Only Footage | Notes
D-HLX101 | Bradenton | 2026-11-18 | North Path | 2026-09-27 | Allen Johns |  | 75 | On Track | Received |  | 2026-09-27 | Yes | 73339.6 | Yes | In Process | 2026-09-27 |  |  |  |  | 5791 | 1706 | 4085 | 29.46% | 2026-10-05 |  | 0% | 0% | 0 | 9/29 NTP Package Received--Pending SOW/PO To Be Uploaded Into SiteTracker and For The Change Order To Be Approved By Tillman. 10/5 PO and Change Order Approved.
D-HLX102 | Bradenton | 2026-11-18 | North Path |  | Allen Johns |  | 75 | On Track | Received |  |  | No |  | Yes | Not Started | [5 empty] | 5465 |  | 5465 | 0% |  |  | 0% | 0% | 0 | 9/29 NTP Package Received--Pending SOW/PO To Be Uploaded Into SiteTracker and For The Change Order To Be Approved By Tillman.
D-HLX103 | Bradenton | 2026-11-18 | North Path |  | Allen Johns |  | 86 | On Track | Received |  |  | No |  | Yes | Not Started | [5 empty] | 5520 |  | 5520 | 0% |  |  | 0% | 0% | 0 | 9/29 NTP Package Received--Pending SOW/PO To Be Uploaded Into SiteTracker and For The Change Order To Be Approved By Tillman.
D-HLX104 | Bradenton | 2026-11-18 | North Path |  | Allen Johns |  | 83 | On Track | Received |  |  | No |  | Yes | Not Started | [5 empty] | 6204 |  | 6204 | 0% |  |  | 0% | 0% | 0 | 9/29 NTP Package Received--Pending SOW/PO To Be Uploaded Into SiteTracker and For The Change Order To Be Approved By Tillman.
D-HLX105 | Bradenton | 2026-11-18 | North Path |  | Allen Johns |  | 36 | On Track | Received |  |  | No |  | Yes | Not Started | [5 empty] | 3700 |  | 3700 | 0% |  |  | 0% | 0% | 0 | 9/29 NTP Package Received--Pending SOW/PO To Be Uploaded Into SiteTracker and For The Change Order To Be Approved By Tillman.
D-HLX106 | Bradenton | 2026-11-18 | North Path |  | Allen Johns |  | 67 | On Track | Received |  |  | No |  | Yes | Not Started | [5 empty] | 5013 |  | 5013 | 0% |  |  | 0% | 0% | 0 | 9/29 NTP Package Received--Pending SOW/PO To Be Uploaded Into SiteTracker and For The Change Order To Be Approved By Tillman.
D-HLX107 | Bradenton | 2026-11-18 | North Path |  | Allen Johns |  | 47 | On Track | Received |  |  | No |  | Yes | Not Started | [5 empty] | 4414 |  | 4414 | 0% |  |  | 0% | 0% | 0 | 9/29 NTP Package Received--Pending SOW/PO To Be Uploaded Into SiteTracker and For The Change Order To Be Approved By Tillman.
D-HLX108 | Bradenton | 2026-11-18 | North Path |  | Allen Johns |  | 69 | On Track | Received |  |  | Yes | 65485.9 | Yes | Locates Called | 2026-09-22 |  |  |  |  | 4613 |  | 4613 | 0% |  |  | 0% | 0% | 0 | 9/29 NTP Package Received--Pending SOW/PO To Be Uploaded Into SiteTracker and For The Change Order To Be Approved By Tillman. 10/9 PO and Change Order Approved.
FB-HOE179 | Bradenton | 2026-01-18 | North Path | 2026-04-13 | Cody | MAN104758 | 0 | On Track | Received |  |  | Yes | 18171.6 | Yes | Locates Called | 2026-04-14 |  |  |  |  | 1514 |  | 1514 | 0% |  |  | 0% | 0% | 0 | 10/27 FDOT Permit Received--NTP Package Missing The Fiber Details Splicing Document. 4-24-25 On hold per Tillman
FB-HLX101 | Bradenton | 2026-11-18 |  |  |  |  | 0 | On Track | Received |  |  | Yes | 21152.35 | Yes | Not Started | [5 empty] | 1469 |  | 1469 | 0% |  |  | 0% | 0% | 0 | 10/6 NTP Package Received--Pending Change Order To Be Approved By Tillman, Once Received I Can Approve The PO.
Plantation Bay - 4 | Bradenton | 2026-07-30 | APT Communications/North Path | 2026-08-17 | Brenton Copelin | FM112414 | 88 | On Track | Not Required |  | 2026-08-17 | Yes | 101036.5 | Yes | In Process | 2026-07-21 |  |  |  |  | 9133 | 8984 | 149 | 98.37% | 2026-09-10 |  | 100% | 100% | 0 | 6/11 NTP Package Received.
BHCD-FPW-03-E | Fort Myers | 2026-07-30 | Lopez Underground | 2026-06-23 | Joshua |  | 0 | On Track | Received |  |  | Yes | 43061.3 | Yes | In Process | 2026-04-14 |  |  |  |  | 11789 | 10232 | 1557 | 86.79% | 2026-07-07 |  | 0% | 0% | 0
D-HDF708 | Fort Myers | 2026-02-28 | GN Systems | 2026-01-16 | Joshua | MAN104766 | 88 | On Track | Pending | Permits | 2025-12-30 | Yes | 79638 | Yes | In Process | 2026-01-06 |  |  |  |  | 6613 | 6302 | 311 | 95.3% | 2026-01-20 |  | 0% | 0% | 0 | 10/31 Permit Received With NTP Package./ 2/4 CX Construction Continues--Progress At 75% Complete./ 2/5 CX Construction Continues--Progress At 85% Complete./ 2/6 CX Construction Continues--Progress At 85% Complete./ 2/25 CX Construction Continues--Progress at 95% Complete.
D-HDF709 | Fort Myers | 2026-11-18 |  |  |  |  | 80 | On Track | Received |  |  | Yes | 71500 | Yes | Not Started | [5 empty] | 5625 |  | 5625 | 0% | [5 empty] | 10/7 NTP Package Received--PO Approved No Change Order Is Required.
D-HDF712 | Fort Myers | 2026-02-28 | GN Systems | 2026-02-02 | Joshua | MAN108516 | 86 | On Track | Pending | Permits | 2026-02-03 | Yes | 97494 | Yes | In Process | 2026-02-09 |  |  |  |  | 8265 | 8140 | 125 | 98.49% | 2026-02-11 |  | 0% | 0% | 0 | 2/12 CX Construction Continues--Progress At 58% Complete./ 2/13 CX Construction Continues--Progress At 77% Complete./ 2/23 CX Construction Continues--Progress At 90% Complete./ 2/25 CX Construction Continues--Progress At 98% Complete.
D-HDF717 | Fort Myers | 2026-10-30 | ITG In-House | 2026-10-09 | Scott |  | 86 | On Track | Received |  | 2026-09-29 | Yes | 83702 | Yes | Locates Called | 2026-10-06 |  |  |  |  | 6907 |  | 6907 | 0% |  |  | 0% | 0% | 0 | 8/12 NTP Package and PO Received--PO In Full Circles Name Not ITG.
D-HDF740 | Fort Myers | 2026-05-29 | GN Systems | 2026-01-21 | Joshua | MAN104770 | 26 | On Track | Pending | Permits |  | Yes | 35576 | Yes | In Process | 2026-01-06 |  |  |  |  | 3150 | 2970 | 180 | 94.29% | 2026-01-21 |  | 0% | 0% | 0 | 10/29 Permit Received With NTP Package./ Requires FDOT Permit.
D-HPW326 | Fort Myers | 2026-09-30 | Lopez Underground | 2026-08-21 | Joshua | FM113100 | 81 | On Track | Received |  |  | Yes | 77302 | Yes | Locates Called | 2026-09-11 |  |  |  |  | 6384 |  | 6384 | 0% |  |  | 0% | 0% | 0 | 7/29 NTP Package Recived
D-HPW327 | Fort Myers | 2026-09-30 | Lopez Underground | 2026-08-21 | Joshua | FM113101 | 85 | On Track | Received |  |  | Yes | 78787 | Yes | Locates Called | 2026-09-03 |  |  |  |  | 6242 |  | 6242 | 0% |  |  | 0% | 0% | 0 | 7/29 NTP Package Recived
D-HPW328 | Fort Myers | 2026-09-30 | Lopez Underground | 2026-08-21 | Joshua | FM113102 | 84 | On Track | Received |  |  | Yes | 45941.5 | Yes | Locates Called | 2026-09-10 |  |  |  |  | 3794 |  | 3794 | 0% |  |  | 0% | 0% | 0 | 7/29 NTP Package Recived
D-HPW329 | Fort Myers | 2026-09-30 | Lopez Underground | 2026-08-21 | Joshua | FM113103 | 71 | On Track | Received |  |  | Yes | 71012.5 | Yes | Locates Called | 2026-09-03 |  |  |  |  | 5739 |  | 5739 | 0% |  |  | 0% | 0% | 0 | 7/24 NTP Package Recived
D-HPW330 | Fort Myers | 2026-09-30 | Lopez Underground | 2026-08-21 | Joshua | FM113104 | 80 | On Track | Received |  |  | Yes | 78742 | Yes | In Process | 2026-08-12 |  |  |  |  | 6179 | 2958 | 3221 | 47.87% | 2026-08-27 |  | 0% | 0% | 0 | 7/29 NTP Package Recived
D-HPW349 | Fort Myers | 2026-08-26 | Alpha Omega | 2026-09-09 | Scott | FM112767 | 80 | On Track | Received |  |  | Yes | 77657.7 | Yes | Locates Called | 2026-09-29 |  |  |  |  | 6243 |  | 6243 | 0% |  |  | 0% | 0% | 0 | 6/11 NTP Package Received.
D-HPW350 | Fort Myers | 2026-09-30 | A1 Broadband | 2026-09-23 | Scott | FM113097 | 76 | On Track | Received |  |  | Yes | 88272 | Yes | Locates Called | 2026-09-26 |  |  |  |  | 7206 | 2730 | 4476 | 37.89% | 2026-10-05 |  | 0% | 0% | 0 | 7/29 NTP Package Recived
D-HPW351 | Fort Myers | 2026-09-30 | Restoring Pro | 2026-09-23 | Joshua | FM113098 | 83 | On Track | Received |  |  | Yes | 57368 | Yes | Locates Called | 2026-09-29 |  |  |  |  | 4517 |  | 4517 | 0% |  |  | 0% | 0% | 0 | 7/24 NTP Package Recived
D-HPW361 | Fort Myers | 2026-07-26 | Alpha Omega | 2026-08-20 | Scott | FM113099 | 82 | On Track | Received |  |  | Yes | 85513 | Yes | In Process | 2026-09-21 |  |  |  |  | 6678 | 3060 | 3618 | 45.82% | 2026-09-09 |  | 0% | 0% | 0 | 6/11 NTP Package Received.
D-HTG211 | Fort Myers | 2026-11-18 | A1 Broadband | 2026-10-09 | Scott |  | 68 | On Track | Received |  |  | No | 76637.05 | Yes | Not Started | [5 empty] | 6224 |  | 6224 | 0% |  |  | 0% | 0% | 0 | 10/6 NTP Package Received--Pending PO To Be Approved and Verification Of BOM To See If A Change Order Is Required.
D-HTG212 | Fort Myers | 2026-08-30 | Gulfstream | 2026-07-28 | Joshua | FM112875 | 85 | On Track | Received |  |  | Yes | 64416.5 | Yes | In Process | 2026-07-29 |  |  |  |  | 5445 | 4690 | 755 | 86.13% | 2026-08-11 |  | 0% | 0% | 0 | 7/24 NTP Package Recived
D-HTG213 | Fort Myers | 2026-09-30 | HD Cable | 2026-07-28 | Joshua | FM112877 | 46 | On Track | Received |  |  | Yes | 54627.5 | Yes | In Process | 2026-07-29 |  |  |  |  | 4834 | 4752 | 82 | 98.3% | 2026-08-13 |  | 0% | 0% | 0 | 7/24 NTP Package Recived
D-HTG214 | Fort Myers | 2026-09-30 | HD Cable | 2026-07-28 | Joshua | FM112878 | 82 | On Track | Received |  |  | Yes | 77688.5 | Yes | Locates Called | 2026-07-29 |  |  |  |  | 6136 |  | 6136 | 0% |  |  | 0% | 0% | 0 | 7/24 NTP Package Recived
D-HTG231 | Fort Myers | 2026-08-30 | Restoring Pro | 2026-07-28 | Joshua | FM112883 | 90 | On Track | Received |  |  | Yes | 90888 | Yes | In Process | 2026-07-29 |  |  |  |  | 7881 | 6923 | 958 | 87.84% | 2026-08-12 |  | 0% | 0% | 0 | 5/29 NTP Received
D-HTG242 | Fort Myers | 2026-12-30 | HAS Global | 2026-10-09 | Joshua |  | 66 | On Track | Received |  |  | Yes | 38841 | Yes | Not Started | [5 empty] | 3106 |  | 3106 | 0% |  |  | 0% | 0% | 0 | 8/17 NTP Package Received
D-HTG307 | Fort Myers | 2026-06-30 | Lopez Underground | 2026-06-11 | Joshua |  | 62 | On Track | Received |  |  | Yes | 48766 | Yes | In Process | 2026-06-12 |  |  |  |  | 4009 | 3230 | 779 | 80.57% | 2026-09-16 |  | 0% | 0% | 0 | 4/30 NTP Received.
FB-HTG285 | Fort Myers | 2026-10-30 | ITG In-House | 2026-10-08 | Scott |  | 0 | On Track | Received |  | na | Yes | 1721.7 | Yes | Not Started | 2026-10-08 |  |  |  |  | 79 |  | 79 | 0% |  |  | 0% | 0% | 0 | 10/7 NTP Package Received--PO Approved No Change Order Is Required.
FB-HTG288 | Fort Myers | 2026-06-30 | Alpha Omega | 2026-06-11 | Joshua |  | 0 | On Track | Received |  |  | Yes | 75219.2 | Yes | In Process | 2026-06-16 |  |  |  |  | 5902 | 5737 | 165 | 97.2% | 2026-07-07 |  | 0% | 0% | 0 | 5/8 NTP Package Received
FB-HTG302 | Fort Myers | 2026-10-30 | ITG In-House | 2026-10-08 | Scott |  | 0 | On Track | Received |  | na | Yes | 1549.65 | Yes | Not Started | 2026-10-08 |  |  |  |  | 82 |  | 82 | 0% |  |  | 0% | 0% | 0 | 10/7 NTP Package Received--PO Approved No Change Order Is Required.
Promenades At The Forum | Fort Myers | 2026-05-30 | APT Communications / New Gen Unlimited |  |  |  | 402 | On Track | Not Required |  | 2026-03-11 | Yes | 438978.5 | Yes | Locates Called | 2026-03-10 |  |  |  |  | 30807 |  | 30807 | 0% |  |  | 0% | 0% | 0 | 3/16/2026 on hold needs permit per tillman. 4/2 Pending Utility Permit From Tillman.
D-HSF401 | Port Charlotte | 2026-09-30 | HD Cable | 2026-08-20 | Joshua | FM113091 | 79 | On Track | Received |  |  | Yes | 75443.75 | Yes | In Process | 2026-08-25 |  |  |  |  | 5953 | 1603 | 4350 | 26.93% | 2026-09-25 |  | 0% | 0% | 0 | 7/24 PO Received.
D-HSF420 | Port Charlotte | 2026-09-30 | GN Systems | 2026-08-20 | Brenton Copelin | FM113095 | 49 | On Track | Received |  |  | Yes | 58273.5 | No | In Process | 2026-09-09 |  |  |  |  | 4709 | 4362 | 347 | 92.63% | 2026-09-23 |  | 0% | 0% | 0 | 8/3 PO Uploaded Into SiteTracker.
FB-HSF606 | Port Charlotte | 2026-03-30 |  |  |  |  | 0 | On Track | Pending | SOW Pending |  | No |  | No | Not Started | [7 empty] | 0 | 0% |  |  | 0% | 0% | 0 | 2/19 Pending NTP Package and SOW.
FB-HSF675 | Port Charlotte | 2026-03-30 |  |  |  |  | 0 | On Track | Pending | SOW Pending |  | No |  | No | Not Started | [7 empty] | 0 | 0% |  |  | 0% | 0% | 0 | 2/19 Pending NTP Package and SOW.
Market 4 NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | Restoration Completed | QC Requested Date | QC Sheet Phase 1 Received | QC Sheet Phase 2 Received | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | UG Percentage Complete | Construction Start Date | Construction End Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Fiber Placement and Splice Only Footage | Notes
D-HEF115 | Lee | 2026-11-18 |  |  |  |  | 74 | On Track | Received |  |  | No | 42924 | Yes | Not Started | [5 empty] | 3159 |  | 3159 | 0% |  |  | 0% | 0% | 0 | 10/7 NTP Package Received--Pending PO To Be Approved and Verification Of BOM To See If A Change Order Is Required.
D-HEF116 | Lee | 2026-11-18 |  |  |  |  | 87 | On Track | Received |  |  | No | 73538 | Yes | Not Started | [5 empty] | 5678 |  | 5678 | 0% |  |  | 0% | 0% | 0 | 10/7 NTP Package Received--Pending PO To Be Approved and Verification Of BOM To See If A Change Order Is Required.
D-HLP401 | Collier |  |  |  | Aldo Layedra |  | 85 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 14927 | 0 | 14927 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HLP403 | Collier |  |  |  | Aldo Layedra |  | 87 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 15088 | 0 | 15088 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HLP404 | Collier | 2026-09-18 | DMC Boring |  | Aldo Layedra |  | 87 | On Track | Received |  |  | Yes |  | Yes | In Process | 2026-08-04 |  |  |  |  | 17114 | 12706 | 4408 | 74.24% |  |  | 0% | 0% | 0
D-HLP405 | Collier |  |  |  | Aldo Layedra |  | 76 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 0 | 0 | 0 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HLP406 | Collier |  |  |  | Aldo Layedra |  | 86 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 14639 | 0 | 14639 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HLP601 | Collier |  |  |  | Aldo Layedra |  | 83 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 5731 | 0 | 5731 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HLP603 | Collier |  |  |  | Aldo Layedra |  | 84 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 6590 | 0 | 6590 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HLP604 | Collier |  |  |  | Aldo Layedra |  | 87 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 6765 | 0 | 6765 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HLP605 | Collier |  |  |  | Aldo Layedra |  | 79 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 5974 | 0 | 5974 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HLP606 | Collier |  |  |  | Aldo Layedra |  | 82 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 5120 | 0 | 5120 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HLP607 | Collier | 2026-10-15 | AGN Undergrounds |  | Aldo Layedra |  | 73 | On Track | Pending | Pending Locates |  | Yes |  | Yes | Locates Called | [5 empty] | 4585 | 0 | 4585 | 0% |  |  | 0% | 0% | 0
D-HLP608 | Collier | 2026-10-15 | AGN Undergrounds | 2026-09-11 | Randy Emmett |  | 66 | On Track | Received |  |  | Yes | 66448 | Yes | Not Started | [5 empty] | 5404 | 0 | 5404 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending Walkout Per Aldo
D-HLP609 | Collier |  |  |  | Aldo Layedra |  | 80 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 5133 | 0 | 5133 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HPW301 | Lee | 2026-09-20 | DMC Boring |  | Aldo Layedra |  | 80 | On Track | Pending | Pending Locates |  | Yes |  | Yes | Locates Called | [5 empty] | 6429 | 6015 | 414 | 93.56% |  |  | 0% | 0% | 0
D-HPW302 | Lee | 2026-10-27 | DMG - JOHN |  | Aldo Layedra |  | 77 | On Track | Pending | Pending Re-Design |  | Yes |  | Yes | [6 empty] | 6460 | 655 | 5805 | 10.14% |  |  | 0% | 0% | 0 | 9/7 Pending Re-Design Per Aldo
D-HPW324 | Lee | 2026-09-21 | AG QUALITY |  | Aldo Layedra |  | 80 | On Track | Received |  |  | Yes |  | Yes | In Process | [5 empty] | 6850 | 6849 | 1 | 99.99% |  |  | 0% | 0% | 0
D-HPW339 | Lee | 2026-08-21 | RDA Solutions |  | Aldo Layedra |  | 83 | On Track | Received |  |  | Yes |  | Yes | In Process | 2026-08-25 |  |  |  |  | 6528 | 5795 | 733 | 88.77% |  |  | 0% | 0% | 0
D-HPW341 | Lee | 2026-10-09 | RDA Solutions |  | Aldo Layedra |  | 78 | On Track | Received |  |  | Yes |  | Yes | In Process | 2026-09-01 |  |  |  |  | 6620 | 2876 | 3744 | 43.44% |  |  | 0% | 0% | 0
D-HPW342 | Lee |  |  |  | Aldo Layedra |  |  | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 7133 | 0 | 7133 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HPW344 | Lee | 2026-10-27 | RDA Solutions |  | Aldo Layedra |  | 66 | On Track | Pending | On Hold |  | Yes |  | Yes | [6 empty] | 5191 | 0 | 5191 | 0% |  |  | 0% | 0% | 0 | 9/7 On Hold Per Aldo
D-HPW347 | Lee | 2026-10-27 | RDA Solutions |  | Aldo Layedra |  | 70 | On Track | Received |  |  | Yes | 64762 | Yes | Locates Called | 2026-09-28 |  |  |  |  | 5148 | 2662 | 2486 | 51.71% |  |  | 0% | 0% | 0 | 9/25 NTP Package Recived
D-HTG220 | Lee | 2026-10-27 | RDA Solutions |  | Aldo Layedra |  | 70 | On Track | Pending | Reassigned |  | Yes |  | Yes | [6 empty] | 6468 | 0 | 6468 | 0% |  |  | 0% | 0% | 0
D-HTG222 | Lee | 2026-10-09 | RDA Solutions |  | Aldo Layedra |  | 78 | On Track | Pending | Pending Locates |  | Yes |  | Yes | Locates Called | 2026-08-20 |  |  |  |  | 6730 | 6374 | 356 | 94.71% | 2026-09-16 |  | 0% | 0% | 0
D-HTG223 | Lee | 2026-10-09 | RDA Solutions |  | Aldo Layedra |  | 52 | On Track | Pending | Pending Locates |  | Yes |  | Yes | Locates Called | 2026-08-17 |  |  |  |  | 4785 | 773 | 4012 | 16.15% | 2026-09-16 |  | 0% | 0% | 0
D-HTG301 | Lee | 2026-10-15 | AMB Communications |  | Aldo Layedra |  | 81 | On Track | Received |  |  | Yes |  | Yes | [6 empty] | 5811 | 1495 | 4316 | 25.73% | 2026-10-02 |  | 0% | 0% | 0 | 9/7 Pending Re-Design Per Aldo
D-HTG302 | Lee | 2026-10-27 | AGN |  | Aldo Layedra |  | 72 | On Track | Pending | Pending Re-Design |  | Yes |  | Yes | [6 empty] | 5222 | 2357 | 2865 | 45.14% |  |  | 0% | 0% | 0 | 9/7 Pending Re-Design Per Aldo
D-HTG303 | Lee |  |  |  | Aldo Layedra |  |  | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 6038 | 0 | 6038 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HTG304 | Lee | 2026-11-18 | RDA Solutions | 2026-09-28 | Aldo Layedra |  | 71 | On Track | Received |  |  | Yes | 83654 | Yes | Locates Called | 2026-09-28 |  |  |  |  | 7094 | 2429 | 4665 | 34.24% |  |  | 0% | 0% | 0 | 9/28 NTP Package Received
D-HTG306 | Lee | 2026-10-15 | Quinteros Cable Installation |  | Aldo Layedra |  | 29 | On Track | Received |  |  | Yes |  | Yes | In Process | [5 empty] | 3727 | 3196 | 531 | 85.75% |  |  | 0% | 0% | 0
D-HTG311 | Lee |  |  |  | Aldo Layedra |  |  | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 1750 | 0 | 1750 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HTG312 | Lee |  |  |  | Aldo Layedra |  |  | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 2069 | 0 | 2069 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HTG401 | Lee | 2026-09-21 | RDA Solutions |  | Aldo Layedra |  | 72 | On Track | Received |  |  | Yes |  | Yes | In Process | 2026-06-30 |  |  |  |  | 5521 | 2823 | 2698 | 51.13% |  |  | 0% | 0% | 0
D-HTG404 | Lee |  |  |  | Aldo Layedra |  |  | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 5990 |  | 5990 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HTG405 | Lee | 2026-10-27 | Quinteros Cable Installation |  | Aldo Layedra |  | 25 | On Track | Pending | Pending Re-Design |  | Yes |  | Yes | [6 empty] | 3802 |  | 3802 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending Re-Design Per Aldo
D-HTG406 | Lee | 2026-11-11 | AGN |  | Aldo Layedra |  | 75 | On Track | Pending | Pending Re-Design |  | Yes |  | Yes | [6 empty] | 3452 |  | 3452 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending Re-Design Per Aldo
D-HTG407 | Lee | 2026-10-27 | AGN |  | Aldo Layedra |  | 77 | On Track | Pending | Pending Re-Design |  | Yes |  | Yes | Locates Called | 2026-10-05 |  |  |  |  | 6848 |  | 6848 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending Re-Design Per Aldo
D-HTG408 | Lee |  |  |  | Aldo Layedra |  |  | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 1875 |  | 1875 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HTG409 | Lee |  |  |  | Aldo Layedra |  |  | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 2961 |  | 2961 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HTG410 | Lee |  |  |  | Aldo Layedra |  |  | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 1205 |  | 1205 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
D-HTG411 | Lee |  |  |  | Aldo Layedra |  |  | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 3714 |  | 3714 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
FB-HLP410 | Collier | 2026-10-15 | TBD |  | Aldo Layedra |  | 0 | On Track | Pending | On Hold |  | Yes |  | Yes | [6 empty] | 15253 |  | 15253 | 0% |  |  | 0% | 0% | 0 | 9/7 On Hold Per Aldo
FB-HLP602 | Collier | 2026-09-25 | AGN |  | Aldo Layedra |  | 0 | On Track | Pending | Pending Locates |  | Yes |  | Yes | Locates Called | [5 empty] | 3064 | 1284 | 1780 | 41.91% | 2026-09-08 |  | 0% | 0% | 0
FB-HLP607 | Collier |  |  |  | Aldo Layedra |  | 0 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 927 |  | 927 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
FB-HLP610 | Collier |  |  |  | Aldo Layedra |  | 0 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 3803 |  | 3803 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
FB-HPW303 | Lee |  |  |  | Aldo Layedra |  | 0 | On Track | Pending | NTP Pending |  | No |  | No | Not Started | [5 empty] | 5111 |  | 5111 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending NTP Package
FB-HTG301 | Lee | 2026-10-27 | AMB Communications |  | Aldo Layedra |  | 0 | On Track | Pending | Pending Re-Design |  | Yes |  | Yes | [6 empty] | 773 |  | 773 | 0% |  |  | 0% | 0% | 0 | 9/7 Pending Re-Design Per Aldo
FB-HTG309 | Lee | 2026-11-11 | TBD |  | Aldo Layedra |  | 0 | On Track | Pending | On Hold |  | Yes |  | Yes | [6 empty] | 708 |  | 708 | 0% |  |  | 0% | 0% | 0 | 9/7 On Hold Per Aldo
FB-HTG316 | Lee |  |  |  | Aldo Layedra |  | 0 | On Track | Pending | On Hold |  | Yes |  | Yes | [6 empty] | 610 |  | 610 | 0% |  |  | 0% | 0% | 0 | 9/7 On Hold Per Aldo
FB-HTG318 | Lee | 2026-10-20 | Quinteros Cable Installation |  | Aldo Layedra |  | 0 | On Track | Pending | Pending Locates |  | Yes |  | Yes | Locates Called | [5 empty] | 1352 | 935 | 417 | 69.16% | 2026-09-16 |  | 0% | 0% | 0
FB-HTG413 | Lee | 2026-10-15 | AMB Communications |  | Aldo Layedra |  | 0 | On Track | Pending | Pending Re-Design |  | Yes |  | Yes | Locates Called | 2026-09-13 |  |  |  |  | 1379 | 1324 | 55 | 96.01% |  |  | 0% | 0% | 0 | 9/7 Pending Re-Design Per Aldo
Market 7 NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | Restoration Completed | QC Requested Date | QC Sheet Phase 1 Received | QC Sheet Phase 2 Received | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | UG Percentage Complete | Construction Start Date | Construction End Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Fiber Placement and Splice Only Footage | Notes
BHT-FSE-01 | Kissimmee | 2026-10-31 | BICOM | 2026-08-03 | Miguel | WP113018 | 0 | On Track | Received |  | 2026-08-03 | Yes | 75444.55 | Yes | Locates Called | 2026-08-03 |  |  |  |  | 5936 | 3401 | 2535 | 57.29% | 2026-09-10 |  | 0% | 0% | 0 | 7/30 NTP Package Recived/Locates called 8/3/construction was paused due to need of a revised Runnining line 8-21/ Cx continues 9-11/
D-HSW401 | Kissimmee | 2026-10-23 |  |  |  |  | 60 | On Track | Received |  |  | Yes | 82732 | Yes | Not Started | [5 empty] | 7117 |  | 7117 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW402 | Kissimmee | 2026-10-23 | BICOM | 2026-09-29 | Miguel |  | 83 | On Track | Received |  |  | Yes | 110980 | Yes | Locates Called | 2026-09-28 |  |  |  |  | 9590 | 2940 | 6650 | 30.66% | 2026-09-24 |  | 0% | 0% | 0 | 2/11 Pending Permit/PART OF THIS ON FB419/
D-HSW403 | Kissimmee | 2026-10-23 |  |  |  |  | 84 | On Track | Received |  |  | Yes | 108948 | Yes | In Process | 2026-09-03 |  |  |  |  | 9329 | 1850 | 7479 | 19.83% | 2026-09-22 |  | 0% | 0% | 0 | 5/18 Cannot Approve PO In SiteTracker. 8/31 PO Uploaded and Received.
D-HSW404 | Kissimmee | 2026-10-23 |  |  |  |  | 89 | On Track | Received |  |  | Yes | 116114 | Yes | Not Started | [5 empty] | 9709 | 505 | 9204 | 5.201% | 2026-09-22 |  | 0% | 0% | 0 | 5/18 Cannot Approve PO In SiteTracker. 8/31 PO Uploaded and Received.
D-HSW405 | Kissimmee | 2026-10-23 | BICOM | 2026-09-04 | Miguel |  | 79 | On Track | Received |  |  | Yes | 108665 | Yes | In Process | 2026-08-17 |  |  |  |  | 9263 | 2040 | 7223 | 22.02% | 2026-08-27 |  | 0% | 0% | 0 | 8/18 Permit Received/partial build with fb419 start 9-2
D-HSW406 | Kissimmee | 2026-10-23 |  |  |  |  | 87 | On Track | Received |  |  | Yes | 120731 | Yes | Not Started | [5 empty] | 10385 |  | 10385 | 0% |  |  | 0% | 0% | 0 | 5/19 Pending Notice To Proceed From Tillman
D-HSW407 | Kissimmee | 2026-11-25 |  |  |  |  | 86 | On Track | Received |  |  | Yes | 111864 | Yes | Not Started | [5 empty] | 9398 |  | 9398 | 0% |  |  | 0% | 0% | 0 | 8/18 Permit Received
D-HSW408 | Kissimmee | 2026-11-25 |  |  |  |  | 63 | On Track | Pending | Permits |  | Yes | 88533.5 | Yes | Not Started | [5 empty] | 7517 |  | 7517 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW409 | Kissimmee | 2026-12-23 |  |  |  |  | 78 | On Track | Received |  |  | Yes | 75143.5 | Yes | Not Started | [5 empty] | 5920 |  | 5920 | 0% |  |  | 0% | 0% | 0 | 5/18 Pending Notice To Proceed From Tillman
D-HSW410 | Kissimmee | 2027-04-10 |  |  |  |  | 60 | On Track | Pending | Permits |  | Yes | 66890 | Yes | Not Started | [5 empty] | 5589 |  | 5589 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW411 | Kissimmee | 2026-10-15 |  |  |  |  | 60 | On Track | Pending | Permits |  | Yes | 65974 | Yes | Not Started | [5 empty] | 5515 |  | 5515 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW412 | Kissimmee | 2027-04-15 |  |  |  |  | 62 | On Track | Pending | Permits |  | Yes | 63989.5 | Yes | Not Started | [5 empty] | 5191 |  | 5191 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW413 | Kissimmee | 2027-04-10 |  |  |  |  | 60 | On Track | Pending | Permits |  | Yes | 67355.5 | Yes | Not Started | [5 empty] | 5620 |  | 5620 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW414 | Kissimmee | 2026-12-23 |  |  |  |  | 86 | On Track | Pending | Permits |  | Yes | 86438.5 | Yes | Not Started | [5 empty] | 6864 |  | 6864 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW415 | Kissimmee | 2027-04-10 |  |  |  |  | 89 | On Track | Pending | Permits |  | Yes | 88748.5 | Yes | Not Started | [5 empty] | 6461 |  | 6461 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW416 | Kissimmee | 2026-11-25 |  |  |  |  | 25 | On Track | Pending | Permits |  | Yes | 33288 | Yes | Not Started | [5 empty] | 2790 |  | 2790 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW417 | Kissimmee | 2026-11-25 |  |  |  |  | 79 | On Track | Pending | Permits |  | Yes | 89875.5 | Yes | Not Started | [5 empty] | 7368 |  | 7368 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW418 | Kissimmee | 2026-10-23 |  |  |  |  | 84 | On Track | Pending | Permits |  | Yes | 95052.5 | Yes | Not Started | [5 empty] | 7844 |  | 7844 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW419 | Kissimmee | 2026-10-23 | BICOM | 2026-09-03 | Miguel |  | 88 | On Track | Received |  | 2026-09-03 | Yes | 102476 | Yes | In Process | [5 empty] | 8148 | 3931 | 4217 | 48.24% | 2026-09-09 |  | 0% | 0% | 0 | 5/18 Pending Notice To Proceed From Tillman/precon sch on 9-3 for 9-9/dis to sub 9-3/cx continues 9-11/
D-HSW420 | Kissimmee | 2026-10-23 |  |  |  |  | 60 | On Track | Received |  |  | Yes | 80344 | Yes | Not Started | [5 empty] | 6829 |  | 6829 | 0% |  |  | 0% | 0% | 0 | 5/18 Pending Notice To Proceed From Tillman
D-HSW421 | Kissimmee | 2026-10-23 |  |  |  |  | 61 | On Track | Pending | Permits |  | Yes | 73166 | Yes | Not Started | [5 empty] | 6157 |  | 6157 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW422 | Kissimmee | 2026-10-23 |  |  |  |  | 89 | On Track | Pending | Permits |  | Yes | 114642 | Yes | Not Started | [5 empty] | 9537 |  | 9537 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW423 | Kissimmee | 2027-01-28 |  |  |  |  | 87 | On Track | Pending | Permits |  | Yes | 85589.5 | Yes | Not Started | [5 empty] | 6796 |  | 6796 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW424 | Kissimmee | 2027-01-28 |  |  |  |  | 76 | On Track | Pending | Permits |  | Yes | 76640 | Yes | Not Started | [5 empty] | 6149 |  | 6149 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW425 | Kissimmee | 2026-12-11 |  |  |  |  | 89 | On Track | Pending | Permits |  | Yes | 80780 | Yes | Not Started | [5 empty] | 6284 |  | 6284 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit for city
D-HSW426 | Kissimmee | 2026-12-11 |  |  |  |  | 85 | On Track | Pending | Permits |  | Yes | 95244 | Yes | Not Started | [5 empty] | 7743 |  | 7743 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW427 | Kissimmee | 2027-01-28 |  |  |  |  | 87 | On Track | Pending | Permits |  | Yes | 86888 | Yes | Not Started | [5 empty] | 6932 |  | 6932 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW428 | Kissimmee | 2027-04-10 |  |  |  |  | 87 | On Track | Pending | Permits |  | Yes | 75700 | Yes | Not Started | [5 empty] | 6213 |  | 6213 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW429 | Kissimmee | 2027-04-10 |  |  |  |  | 52 | On Track | Pending | Permits |  | Yes | 53698 | Yes | Not Started | [5 empty] | 4339 |  | 4339 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW430 | Kissimmee | 2027-04-10 |  |  |  |  | 48 | On Track | Pending | Permits |  | Yes | 48883 | Yes | Not Started | [5 empty] | 3940 |  | 3940 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW431 | Kissimmee | 2026-12-23 |  |  |  |  | 88 | On Track | Pending | Permits |  | Yes | 83382 | Yes | Not Started | [5 empty] | 6855 |  | 6855 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW432 | Kissimmee | 2027-01-28 |  |  |  |  | 90 | On Track | Pending | Permits |  | Yes | 88834 | Yes | Not Started | [5 empty] | 7147 |  | 7147 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW433 | Kissimmee | 2027-04-10 |  |  |  |  | 83 | On Track | Pending | Permits |  | Yes | 81027.5 | Yes | Not Started | [5 empty] | 6376 |  | 6376 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW434 | Kissimmee | 2027-01-28 |  |  |  |  | 63 | On Track | Pending | Permits |  | Yes | 60264 | Yes | Not Started | [5 empty] | 4784 |  | 4784 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW435 | Kissimmee | 2026-12-11 |  |  |  |  | 86 | On Track | Pending | Permits |  | Yes | 81096 | Yes | Not Started | [5 empty] | 6387 |  | 6387 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW436 | Kissimmee | 2026-12-11 |  |  |  |  | 81 | On Track | Pending | Permits |  | Yes | 79796 | Yes | Not Started | [5 empty] | 6372 |  | 6372 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW437 | Kissimmee | 2026-12-23 |  |  |  |  | 77 | On Track | Pending | Permits |  | Yes | 69082 | Yes | Not Started | [5 empty] | 5363 |  | 5363 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW438 | Kissimmee | 2026-12-23 |  |  |  |  | 67 | On Track | Pending | Permits |  | Yes | 65448 | Yes | Not Started | [5 empty] | 5199 |  | 5199 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW439 | Kissimmee | 2026-12-23 |  |  |  |  | 90 | On Track | Pending | Permits |  | Yes | 116020.5 | Yes | Not Started | [5 empty] | 9771 |  | 9771 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW440 | Kissimmee | 2026-12-23 |  |  |  |  | 90 | On Track | Pending | Permits |  | Yes | 114306 | Yes | Not Started | [5 empty] | 9562 |  | 9562 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW441 | Kissimmee | 2026-11-25 |  |  |  |  | 87 | On Track | Pending | Permits |  | Yes | 80784 | Yes | Not Started | [5 empty] | 6309 |  | 6309 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW442 | Kissimmee | 2026-12-23 |  |  |  |  | 90 | On Track | Pending | Permits |  | Yes | 125540.85 | Yes | Not Started | [5 empty] | 10260 |  | 10260 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW443 | Kissimmee | 2027-04-10 |  |  |  |  | 89 | On Track | Pending | Permits |  | Yes | 119327 | Yes | Not Started | [5 empty] | 10080 |  | 10080 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW444 | Kissimmee | 2026-11-14 |  |  |  |  | 76 | On Track | Pending | Permits |  | Yes | 85720 | Yes | Not Started | [5 empty] | 6859 |  | 6859 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW445 | Kissimmee | 2026-11-14 |  |  |  |  | 84 | On Track | Pending | Permits |  | Yes | 75682 | Yes | Not Started | [5 empty] | 5873 |  | 5873 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW446 | Kissimmee | 2026-11-14 |  |  |  |  | 55 | On Track | Pending | Permits |  | Yes | 60784 | Yes | Not Started | [5 empty] | 4945 |  | 4945 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW447 | Kissimmee | 2026-12-11 |  |  |  |  | 54 | On Track | Pending | Permits |  | Yes | 52670 | Yes | Not Started | [5 empty] | 4275 |  | 4275 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending Permit
D-HSW448 | Kissimmee | 2026-12-23 |  |  |  |  | 88 | On Track | Received |  |  | Yes | 86455.5 | No | Not Started | [5 empty] | 6378 |  | 6378 | 0% |  |  | 0% | 0% | 0 | 7/30 NTP Package Recived
FB-HSW406 | Kissimmee | 2026-10-23 |  |  |  |  | 0 | On Track | Received |  |  | Yes | 94474.5 | No | Not Started | [5 empty] | 7373 |  | 7373 | 0% |  |  | 0% | 0% | 0 | 7/30 NTP Package Recived
FB-HSW416 | Kissimmee | 2026-10-23 |  |  | Miguel |  | 0 | On Track | Pending | Permits |  | Yes | 74145.85 | Yes | Not Started | [5 empty] | 5781 |  | 5781 | 0% |  |  | 0% | 0% | 0 | 7/24 NTP Package Recived
FB-HSW417 | Kissimmee | 2026-10-23 |  |  |  |  | 0 | On Track | Received |  |  | No |  | No | Not Started | [5 empty] | 9051 |  | 9051 | 0% |  |  | 0% | 0% | 0 | 2/11 Pending SOW and Permit
FB-HSW425 | Kissimmee | 2026-12-11 | BICOM | 2026-08-04 | Miguel | WP113019 | 0 | On Track | Received |  | 2026-08-05 | Yes | 126441.9 | Yes | Locates Called | 2026-08-06 |  |  |  |  | 9638 |  | 9638 | 0% |  |  | 0% | 0% | 0 | 8/4 PO Received--FDOT Permit Received.Locates called 8-6/
FB-HSW443 | Kissimmee | 2026-10-23 |  |  |  |  | 0 | On Track | Received |  |  | Yes | 111398.8 | Yes | Not Started | [5 empty] | 8746 |  | 8746 | 0% |  |  | 0% | 0% | 0 | 7/30 PO Received
0%
0%
Market 10 NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | Restoration Completed | QC Requested Date | QC Sheet Phase 1 Received | QC Sheet Phase 2 Received | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | UG Percentage Complete | Construction Start Date | Construction End Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Fiber Placement and Splice Only Footage | Notes
D-HBR261 | Miami | 2026-12-31 | Yosep AER | 2026-01-07 | Jose |  | 81 | On Track | Received |  | 2026-09-10 | Yes | 105892.05 | Yes | Locates Called | 2026-09-12 |  |  |  |  | 8711 | 8894 | -183 | 102.1% | 2026-09-11 |  | 100% | 100% | 100% | 12/24 NTP Package Received.
D-HBR262 | Miami | 2026-12-31 | Yosep AER | 2026-01-07 | Jose |  | 79 | On Track | Received |  | 2026-09-25 | Yes | 88420 | Yes | Locates Called | 2026-09-12 |  |  |  |  | 7502 | 4739 | 2763 | 63.17% | 2026-10-01 |  | 0% | 0% | 0 | 12/24 NTP Package Received.
Note on J47: Tom McGuire: need city 10-23
Note on AE151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Locates called 8/3 (216607470, 216607340, 216607274, 216607219, 216605143, 216605023, 216605095, 216605237, 216605254, 216605270, 216605280, 216605302)
Note on AE203: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8/4 PO Received--FDOT Permit Received.Locates called 8-6/ (Locates Tickets 218607727, 218608250, 218608816, 218608482, 218608640, 218608572, 218608785, 218608857, 218608873, 218608881, 218608889, 218608905, 218608911, 218608918, 218608924, 218608935

## Pending Resto-COP Packages
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | Restoration Completed | QC Requested Date | QC Sheet Phase 1 Received | QC Sheet Phase 2 Received | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | UG Percentage Complete | Construction Start Date | Construction End Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Fiber Placement and Splice Only Footage | Notes | Friday 09/25 updates
BHU-FLX-01-E | Bradenton | 2026-05-30 | Lightspeed In-House | 2026-02-24 | Johnnie Williams | MAN109507 | 0 | Completed on Track | Received |  | N/A | Yes | 49846.95 | Yes | Completed | 2026-03-12 | Yes | 2026-06-09 | 6/22 Failed QC | 2026-06-09 | 3109 | 3128 | -19 | 100.6% | 2026-04-20 | 2026-05-08 | 100% | 100% | 100% | 3/9 NTP and SOW Received.3/12 LC/4-17 Locates cleared/Cx starts 4-20 | Passed QC. Pending email
BHUD-FOE-401-W | Bradenton | 2026-09-30 | North Path | 2026-07-28 | Cody | MAN112893 | 0 | Completed on Track | Received |  | N/A | Yes | 18856.2 | Yes | Completed | 2026-07-31 | Yes | 2026-09-14 | 2026-09-18 | 2026-09-18 | 1412 | 1406 | 6 | 99.58% | 2026-08-18 | 2026-08-19 | 100% | 0% | 0 | 7/24 NTP Package Recived--Pending Fiber Details Splcing Document | Needs to be scheduled for QC
D-HAL113 | Bradenton | 2026-09-30 | North Path | 2026-08-24 | Brenton Copelin | MAN113114 | 86 | Completed on Track | Received |  | 2026-08-31 | Yes | 52728 | Yes | Completed | 2026-08-27 | Yes | 2026-09-29 | 2026-10-01 | 2026-10-01 | 3508 | 3492 | 16 | 99.54% | 2026-09-15 | 2026-09-24 | 100% | 100% | 100% | 8/24 NTP Package Received | Needs change order.
D-HAL114 | Bradenton | 2026-09-30 | North Path | 2026-08-17 | Brenton Copelin | MAN113033 | 62 | Completed on Track | Received |  | N/A | Yes | 42744 | Yes | Completed | 2026-08-21 | Yes | 2026-09-29 | 2026-10-01 | 2026-10-01 | 3148 | 3199 | -51 | 101.6% | 2026-08-25 | 2026-08-27 | 100% | 100% | 100% | 8/17 NTP Package Received | QC turned in and start COP & Change order needed
D-HAL116 | Bradenton | 2026-09-30 | North Path | 2026-08-17 | Brenton Copelin | MAN113039 | 81 | Completed on Track | Received |  | N/A | Yes | 52593.6 | Yes | Completed | 2026-08-21 | Yes | 2026-09-28 | 2026-09-28 | 2026-09-28 | 4065 | 4167 | -102 | 102.5% | 2026-09-03 | 2026-09-16 | 100% | 100% | 0 | 8/17 NTP Package Received | Needs change order.
D-HLX421 | Bradenton | 2026-03-26 | GN Systems | 2026-04-06 | Cody | MAN108652 | 20 | Completed on Track | Received |  | 2026-04-08 | Yes | 23501 | Yes | Completed | 2026-04-06 | Yes | 2026-05-29 | 6/5 Failed QC | 2026-06-05 | 1322 | 1322 | 0 | 100% | 2026-05-06 | 2026-05-07 | 100% | 100% | 100% | 10/22 Permit Received. 5-29-26 sent in site tracker for QC 509' was built with BHZD-FLX-04-W. Cody to verify. 6/5 Failed Gig List Received From Tillman. | GN Systems. Need bore logs. John has been in touch
D-HLX503 | Bradenton | 2026-06-08 | North Path | 2026-05-29 | Brenton Copelin |  | 85 | Completed on Track | Received |  | N/A | Yes | 60062 | Yes | Completed | 2026-06-01 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 4380 | 4475 | -95 | 102.2% | 2026-07-24 | 2026-08-06 | 100% | 100% | 100% | 4/29 NTP Package Received. On hold due to community shutdown. CX start 7-13-26 again | Change order needed. Holding up billing
D-HLX505 | Bradenton | 2026-06-18 | North Path | 2026-05-29 | Brenton Copelin |  | 87 | Completed on Track | Received |  | N/A | Yes | 64040 | Yes | Completed | 2026-06-01 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 4888 | 5016 | -128 | 102.6% | 2026-08-03 | 2026-08-07 | 100% | 100% | 100% | 4/29 NTP Package Received. On hold due to community shutdown. CX start 7-13-26 again | Change order needed. Holding up billing
FB-HLR201 | Bradenton | 2026-01-18 | Lightspeed In-House / GN Systems | 2025-07-29 | Cody | MAN99683 | 0 | Completed on Track | Received |  | N/A | Yes | 144972.5 | Yes | Completed | 2025-07-29 | Yes | 2026-06-17 | 2026-06-19 | 2026-06-19 | 9840 | 9806 | 34 | 99.65% | 2025-08-15 | 2026-02-09 | 100% | 100% | 0 | 1/5 CX Construction Started. 2/5 CX Construction Complete--144F Placed Pending Splicing, 13 Ground Rods and Switches./ 2/9 695' Tracer Wire and Mule Tape. Failed Gig List Received From Tillman On 4/24. | Still needed an in house inspector to complete bore logs
FB-HLX175 | Bradenton | 2026-09-30 | Lightspeed In-House/North Path | 2026-07-22 | Brenton Copelin | MAN112869 | 0 | Completed on Track | Received |  | N/A | Yes | 36166.65 | Yes | Completed | 2026-07-23 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 3036 | 3056 | -20 | 100.7% | 2026-08-05 | 2026-08-20 | 100% | 100% | 100% | 7/21 NTP Package Received | Change order needed, fiber splicing complete. needs that added to SOW
FB-HOE401-V6 | Bradenton | 2026-09-30 | Lightspeed In-House | 2026-07-29 | Brenton Copelin | MAN112894 | 0 | Completed on Track | Received |  | N/A | Yes | 3232.9 | Yes | Completed | 2026-07-30 | Yes | 2026-09-18 | 2026-09-18 | 2026-09-18 | 194 | 200 | -6 | 103.1% | 2026-08-17 | 2026-08-17 | 100% | 100% | 0 | 7/24 NTP Package Recived--Pending Fiber Details Splcing Document, 7/29/26 Assigned to In House | QC complete phase 1 & Phase 2. Need change order
D-HPP607 | Clearwater | 2026-10-30 | Lightspeed In-House | 2026-05-01 | Treyvon Tillman | PPM111646 | 46 | Completed on Track | Received |  | 2026-05-05 | Yes | 71754.5 | Yes | Completed | 2026-05-05 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5649 | 5893 | -244 | 104.3% | 2026-05-27 | 2026-07-08 | 0% | 0% | 0 | 5/5 Door Tag Complete : Locates Called - 5/4 Whitelined, will call locates 5/5/ - 5/1 NTP Package Received. | Passed QC. COP next week
D-HPP608 | Clearwater | 2026-10-30 | Lightspeed In-House | 2026-05-19 | Robert Portee | PPM111675 | 94 | Completed on Track | Received |  | N/A | Yes | 94021.5 | Yes | Completed | 2026-05-20 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 7741 | 7673 | 68 | 99.12% | 2026-08-07 | 2026-09-18 | 0% | 0% | 0 | 5/1 NTP Package Received./Whitelined 5-19/ locates called 5-20/Will be dortagged 5-21/Pending Locates cleared, Construction Completed 9/18/2026, Path Completed, SOW incorrect
D-HPP613 | Clearwater | 2026-10-30 | APT Communications | 2026-05-15 | Johnnie Williams |  | 79 | Completed on Track | Received |  | 2026-05-10 | Yes | 100208 | Yes | Completed | 2026-05-07 | No | 2026-09-01 | Pending Tillman QC Form | Pending Tillman QC Form | 8175 | 8120 | 55 | 99.33% | 2026-05-26 | 2026-07-08 | 0% | 0% | 0 | 5/1 NTP Package Received. | Not started
D-HPP614 | Clearwater | 2026-10-30 | Mid Florida Contractors | 2026-05-19 | Johnnie Williams |  | 110 | Completed on Track | Received |  | N/A | Yes | 101920.5 | Yes | Completed | 2026-05-20 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 8444 | 8277 | 167 | 98.02% | 2026-06-01 | 2026-07-28 | 0% | 0% | 0 | 5/1 NTP Package Received. | Re walk has not been set
D-HPP621 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Anthony Adum |  | 91 | Completed on Track | Received |  | 2026-06-02 | Yes | 72668.5 | Yes | Completed | 2026-06-03 | Yes | 2026-09-10 | 2026-09-22 | Pending Tillman QC Form | 5934 | 6020 | -86 | 101.4% | 2026-06-18 | 2026-07-01 | 0% | 0% | 0 | 5/1 NTP Package Received. | QC Passed. working on this one
D-HPP625 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Treyvon Tillman |  | 88 | Completed on Track | Received |  | 2026-06-15 | Yes | 96607 | Yes | Completed | 2026-06-03 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 7623 | 7341 | 282 | 96.3% | 2026-06-22 | 2026-07-01 | 0% | 0% | 0 | 5/1 NTP Package Received. | Passed QC. COP next week
D-HPP626 | Clearwater | 2026-10-30 | Brothers | 2026-05-29 | Marcelo Zaldivar |  | 75 | Completed on Track | Received |  | N/A | Yes | 95477 | Yes | Completed | 2026-06-25 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 7966 | 8323 | -357 | 104.5% | 2026-07-10 | 2026-09-25 | 0% | 0% | 0 | 5/1 NTP Package Received.
D-HPP627 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Marcelo Zaldivar |  | 97 | Completed on Track | Received |  | N/A | Yes | 94688.5 | Yes | Completed | 2026-06-03 | Yes | 2026-08-19 | 2026-08-24 | Pending Tillman QC Form | 7856 | 7519 | 337 | 95.71% | 2026-06-17 | 2026-08-17 | 0% | 0% | 0 | 5/1 NTP Package Received. | Waiting on inspector to give final walk out footages
D-HPP628 | Clearwater | 2026-10-30 | Brothers | 2026-05-29 | Marcelo Zaldivar |  | 65 | Completed on Track | Received |  | N/A | Yes | 97700 | Yes | Completed | 2026-06-25 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 8047 | 7881 | 166 | 97.94% | 2026-07-09 | 2026-07-15 | 0% | 0% | 0 | 5/1 NTP Package Received. | 0
D-HPP629 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Anthony Adum |  | 51 | Completed on Track | Received |  | N/A | Yes | 91700 | Yes | Completed | 2026-06-03 | Yes | Not Submitted | 2026-09-08 | Pending Tillman QC Form | 7529 | 7407 | 122 | 98.38% | 2026-06-18 | 2026-08-17 | 0% | 0% | 0 | 5/1 NTP Package Received. | Bore logs sent. needs review.
D-HPP633 | Clearwater | 2026-10-30 | Power Connect | 2026-06-04 | Johnnie Williams |  | 70 | Completed on Track | Received |  | N/A | Yes | 99590 | Yes | Completed | 2026-06-04 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 8201 | 8350 | -149 | 101.8% | 2026-06-22 | 2026-07-31 | 0% | 0% | 0 | 5/1 NTP Package Received. | Internal QC 9/28
D-HPP634 | Clearwater | 2026-10-30 | NIA Underground | 2026-06-09 | Johnnie Williams |  | 91 | Completed on Track | Received |  | N/A | Yes | 103644.5 | Yes | Completed | 2026-06-10 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 8384 | 8386 | -2 | 100% | 2026-07-21 | 2026-08-05 | 0% | 0% | 0 | 5/11 NTP Package Received. | Internal QC 9/29
D-HPP635 | Clearwater | 2026-10-30 | NIA Underground | 2026-06-09 | Johnnie Williams |  | 57 | Completed on Track | Received |  | N/A | Yes | 106431.5 | Yes | Completed | 2026-06-10 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 8751 | 8542 | 209 | 97.61% | 2026-07-13 | 2026-08-12 | 0% | 0% | 0 | 5/12 NTP Package Received. | Internal QC 9/30
D-HPP636 | Clearwater | 2026-10-30 | Brothers | 2026-06-09 | Marcelo Zaldivar |  | 86 | Completed on Track | Received |  | N/A | Yes | 97386.5 | Yes | Completed | 2026-06-15 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 7996 | 7742 | 254 | 96.82% | 2026-07-16 | 2026-08-14 | 0% | 0% | 0 | 5/1 NTP Package Received. | 0
D-HPP638 | Clearwater | 2026-10-30 | Lightspeed In-House | 2029-05-29 | Treyvon Tillman |  | 88 | Completed on Track | Received |  | 2026-06-08 | Yes | 81059.5 | Yes | Completed | 2026-06-01 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6647 | 6717 | -70 | 101.1% | 2026-06-15 | 2026-08-20 | 0% | 0% | 0 | 5/1 NTP Package Received. | Pending QC
D-HPP639 | Clearwater | 2026-10-30 | ASM Utilities | 2026-06-29 | Marcelo Zaldivar |  | 88 | Completed on Track | Received |  | N/A | Yes | 106600 | Yes | Completed | 2026-06-07 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 8787 | 8921 | -134 | 101.5% | 2026-07-06 | 2026-07-30 | 0% | 0% | 0 | 5/1 NTP Package Received. | Starting on the COP
FB-HPP612 | Clearwater | 2026-10-27 | Brothers | 2026-08-19 | Anthony Adum |  | 0 | Completed on Track | Received |  | N/A | Yes | 66431.7 | Yes | Completed | 2026-08-21 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5251 | 5190 | 61 | 98.84% | 2026-09-15 | 2026-09-18 | 100% | 0% | 0 | 8/19 NTP Package Received--8/20 PO Received. | Phase 1 vaults are being set
FB-HPP631 | Clearwater | 2026-10-30 | Brothers | 2026-05-13 | Anthony Adum | PPM111690 | 0 | Completed on Track | Received |  | 2026-05-12 | Yes | 65477.3 | Yes | Completed | 2026-05-15 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6335 | 6762 | -427 | 106.7% | 2026-09-11 | 2026-10-02 | 100% | 100% | 100% | 7/13 NTP Package Received. 7/17 PO Received And Approved.
BHCD-FPW-03-W | Fort Myers | 2026-05-30 | North Path | 2026-04-16 | Joshua Wheatcroft | MAN109687 | 0 | Completed on Track | Received |  | N/A | Yes | 146065.95 | Yes | Completed | 2026-03-06 | Yes | 2026-06-17 | 6/24 Failed QC | 6/24 Failed QC | 3461 | 3578 | -117 | 103.4% | 2026-03-25 | 2026-04-24 | 100% | 0% | 0 | 3/5 Fiber Splicing Document Received. | Not started
D-HDF707 | Fort Myers | 2026-02-28 | Lightspeed In-House | 2025-12-10 | Joshua Wheatcroft | MAN104765 | 80 | Completed on Track | Received |  | 2025-12-30 | Yes | 65843.5 | Yes | Completed | 2025-12-04 | Yes | 2026-06-17 | Pending Tillman QC Form | Pending Tillman QC Form | 5052 | 4889 | 163 | 96.77% | 2025-12-10 | 2025-12-31 | 0% | 0% | 0 | 10/31 Permit Received With NTP Package./ | Asbuilt done, needs BOM
D-HDF713 | Fort Myers | 2026-01-31 | GN Systems | 2025-11-13 | Joshua Wheatcroft | MAN104149 | 77 | Completed on Track | Received |  | 2025-11-04 | Yes | 90786 | Yes | Completed | 2025-11-04 | Yes | 2026-06-17 | Pending Tillman QC Form | Pending Tillman QC Form | 8013 | 7885 | 128 | 98.4% | 2025-11-18 | 2025-11-21 | 0% | 0% | 0 | 10/29 Permit Received With NTP Package. | Pictures of DAPS needed
D-HPW346 | Fort Myers | 2026-09-30 | A1 Broadband | 2026-08-11 | Joshua Wheatcroft | FM113017 | 89 | Completed on Track | Received |  | N/A | Yes | 93910.15 | Yes | Completed | 2026-08-17 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 7299 | 7212 | 87 | 98.81% | 2026-09-10 | 2026-10-02 | 0% | 0% | 0 | 7/29 NTP Package Recived
D-HPW348 | Fort Myers | 2026-09-30 | Alpha Omega | 2026-08-06 | Joshua Wheatcroft | FM112925 | 83 | Completed on Track | Received |  | N/A | Yes | 78322 | Yes | Completed | 2026-08-17 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6192 | 6179 | 13 | 99.79% | 2026-08-17 | 2026-09-21 | 0% | 0% | 0 | 7/29 NTP Package Recived 9-8-26 refreshed locates | Just completed
FB-HPW331 | Fort Myers | 2026-07-24 | Gulfstream | 2026-07-10 | Joshua | FM112418 | 0 | Completed on Track | Received |  | N/A | Yes | 25174.45 | Yes | Completed | 2026-08-04 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 1797 | 1781 | 16 | 99.11% | 2026-08-18 | 2026-10-09 | 0% | 0% | 0 | 6/9 NTP Package Received. 10-9-26 path complete missing 4 HH
D-HTG201 | Fort Myers | 2026-06-30 | Lopez Underground | 2026-05-29 | Joshua Wheatcroft |  | 53 | Completed on Track | Received |  | N/A | Yes | 56455 | Yes | Completed | 2026-06-01 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 4814 | 5133 | -319 | 106.6% | 2026-06-11 | 2026-07-01 | 100% | 100% | 100% | 4/30 NTP Received 7-17-26 tillman approved bury the route that is on private property and close the job. | Working On asbuilt
D-HTG206 | Fort Myers | 2026-05-29 | Lopez Underground | 2026-04-29 | Joshua Wheatcroft |  | 89 | Completed on Track | Received |  | N/A | Yes | 70666 | Yes | Completed | 2026-05-08 | Yes | 2026-06-17 | 6/24 Failed QC | 2026-06-24 | 6549 | 6536 | 13 | 99.8% | 2026-05-12 | 2026-05-21 | 100% | 100% | 100% | 4/14 NTP Received | Asbuilt complete. Pending phase 1 email
D-HTG207 | Fort Myers | 2026-06-14 | Lopez Underground | 2026-05-29 | Joshua Wheatcroft |  | 76 | Completed on Track | Received |  | N/A | Yes | 72914 | Yes | Completed | 2026-06-01 | Yes | 2026-06-17 | 2026-07-10 | 2026-07-10 | 5649 | 5777 | -128 | 102.3% | 2026-06-04 | 2026-06-12 | 100% | 100% | 100% | 4/30 NTP Received | Started Asbuilt
D-HTG208 | Fort Myers | 2026-06-30 | Lopez Underground | 2026-04-29 | Joshua |  | 74 | Completed on Track | Received |  | N/A | Yes | 92274 | Yes | Completed | 2026-04-30 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 8145 | 8102 | 43 | 99.47% | 2026-05-07 | 2026-10-09 | 100% | 100% | 100% | 4/24 NTP Received 7-13-26 permit waiting on new permit
D-HTG210 | Fort Myers | 2026-08-31 | Gulfstream | 2026-07-28 | Joshua Wheatcroft | FM112876 | 77 | Completed on Track | Received |  | N/A | Yes | 68598 | Yes | Completed | 2026-07-29 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5803 | 5753 | 50 | 99.14% | 2026-08-19 | 2026-10-07 | 100% | 100% | 100% | 7/17 NTP Received. 10-6-26 Path walked out and complete.
D-HTG215 | Fort Myers | 2026-08-30 | Gulfstream | 2026-07-16 | Joshua | FM112727 | 56 | Completed on Track | Received |  | N/A | Yes | 55008 | Yes | Completed | 2026-07-17 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 4625 | 4596 | 29 | 99.37% | 2026-07-28 | 2026-10-09 | 100% | 100% | 100% | 7/7 NTP Package Received.
D-HTG216 | Fort Myers | 2026-09-30 | Lopez Underground | 2026-07-28 | Joshua Wheatcroft | FM112879 | 79 | Completed on Track | Received |  | N/A | Yes | 80274 | Yes | Completed | 2026-07-29 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6786 | 6598 | 188 | 97.23% | 2026-08-07 | 2026-08-12 | 0% | 0% | 0 | 7/24 NTP Package Recived | Missing Bore logs Lopez
D-HTG217 | Fort Myers | 2026-09-30 | Lopez Underground | 2026-07-28 | Joshua | FM112881 | 77 | Completed on Track | Received |  | N/A | Yes | 76557.5 | Yes | Completed | 2026-07-29 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6200 | 6081 | 119 | 98.08% | 2026-08-11 | 2026-10-09 | 0% | 0% | 0 | 7/24 NTP Package Recived
D-HTG218 | Fort Myers | 2026-07-30 | Gulfstream | 2026-07-16 | Joshua Wheatcroft | FM112751 | 48 | Completed on Track | Received |  | N/A | Yes | 50669 | Yes | Completed | 2026-07-17 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 3850 | 3834 | 16 | 99.58% | 2026-07-23 | 2026-08-28 | 0% | 0% | 0 | 5/29 NTP Received | Waiting on Bore logs from Lopez
D-HTG225 | Fort Myers | 2026-06-30 | Lopez Underground | 2026-05-14 | Joshua Wheatcroft |  | 69 | Completed on Track | Received |  | N/A | Yes | 72896 | Yes | Completed | 2026-05-15 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6189 | 6050 | 139 | 97.75% | 2026-05-27 | 2026-07-16 | 100% | 100% | 100% | 5/8 NTP Package Received | Not Started
D-HTG228 | Fort Myers | 2026-06-30 | Lopez Underground | 2026-05-27 | Joshua Wheatcroft |  | 60 | Completed on Track | Received |  | N/A | Yes | 70151.5 | Yes | Completed | 2026-05-28 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5673 | 5183 | 490 | 91.36% | 2026-06-24 | 2026-07-16 | 100% | 100% | 100% | 5/8 NTP Package Received | Missing Bore logs Lopez
D-HTG229 | Fort Myers | 2026-06-30 | Lopez Underground | 2026-05-27 | Joshua Wheatcroft |  | 70 | Completed on Track | Received |  | N/A | Yes | 65362 | Yes | Completed | 2026-05-28 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5460 | 5325 | 135 | 97.53% | 2026-06-16 | 2026-08-28 | 100% | 100% | 100% | 5/8 NTP Package Received | Pending Bore logs from Lopez & asbuilt
D-HTG230 | Fort Myers | 2026-07-30 | Restoring Pro | 2026-07-16 | Joshua | FM112752 | 79 | Completed on Track | Received |  | N/A | Yes | 89293.95 | Yes | Completed | 2026-07-17 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 7494 | 7415 | 79 | 98.95% | 2026-07-28 | 2026-10-09 | 100% | 100% | 100% | 4/14 NTP Received
D-HTG233 | Fort Myers | 2026-06-30 | Lopez Underground | 2026-05-14 | Joshua Wheatcroft |  | 71 | Completed on Track | Received |  | N/A | Yes | 91537.75 | Yes | Completed | 2026-05-15 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 7255 | 7248 | 7 | 99.9% | 2026-06-01 | 2026-08-28 | 100% | 100% | 100% | 4/14 NTP Received | Walked out. Need to update asbuilt
D-HTG235 | Fort Myers | 2026-06-30 | Lopez Underground | 2026-05-29 | Joshua Wheatcroft |  | 71 | Completed on Track | Received |  | N/A | Yes | 68762 | Yes | Completed | 2026-06-01 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5624 | 5577 | 47 | 99.16% | 2026-06-17 | 2026-07-10 | 100% | 100% | 100% | 4/14 NTP Received | Missing Bore logs Lopez
D-HTG237 | Fort Myers | 2026-06-22 | Lopez Underground | 2026-05-29 | Joshua Wheatcroft |  | 56 | Completed on Track | Received |  | N/A | Yes | 55504 | Yes | Completed | 2026-06-01 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 4652 | 4625 | 27 | 99.42% | 2026-06-16 | 2026-06-23 | 100% | 100% | 100% | 5/8 NTP Package Received | Not Started
D-HTG238 | Fort Myers | 2026-06-30 | Lopez Underground | 2026-05-29 | Joshua Wheatcroft |  | 74 | Completed on Track | Received |  | N/A | Yes | 70534.5 | Yes | Completed | 2026-06-01 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5756 | 5626 | 130 | 97.74% | 2026-06-18 | 2026-08-28 | 100% | 100% | 100% | 5/8 NTP Package Received | Pending asbuilt
D-HTG239 | Fort Myers | 2026-06-14 | Lopez Underground | 2026-05-29 | Joshua Wheatcroft |  | 85 | Completed on Track | Received |  | N/A | Yes | 64590 | Yes | Completed | 2026-06-01 | Yes | 2026-06-17 | Pending Tillman QC Form | Pending Tillman QC Form | 5218 | 5194 | 24 | 99.54% | 2026-06-04 | 2026-06-12 | 100% | 100% | 100% | 4/30 NTP Received | Missing Bore logs Lopez
D-HTG305 | Fort Myers | 2026-06-30 | Lightspeed In-House | 2026-08-17 | Joshua Wheatcroft | FM113030 | 56 | Completed on Track | Received |  | N/A | Yes | 50042 | Yes | Completed | 2026-08-21 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 4159 | 4159 | 0 | 100% | 2026-08-28 | 2026-09-17 | 100% | 100% | 100% | 4/30 NTP Received. | just completed
D-HTG241 | Fort Myers | 2026-06-22 | Lightspeed In-House | 2026-05-19 | Joshua Wheatcroft |  | 28 | Completed on Track | Received |  | N/A | Yes | 27694 | Yes | Completed | 2026-05-20 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 2238 | 2269 | -31 | 101.4% | 2026-06-08 | 2026-06-22 | 100% | 100% | 100% | 5/8 NTP Package Received | Not Started
FB-HTG204 | Fort Myers | 2026-07-06 | Alpha Omega | 2026-06-10 | Joshua Wheatcroft |  | 0 | Completed on Track | Received |  | N/A | Yes | 35456.55 | Yes | Completed | 2026-06-12 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 2635 | 2631 | 4 | 99.85% | 2026-06-25 | 2026-07-21 | 0% | 0% | 0 | 5/22 NTP Package Received--Pending Fiber Details Splicing Document | Not Started
FB-HTG238 | Fort Myers | 2026-07-30 | Lopez Underground | 2026-07-10 | Joshua Wheatcroft | FM112420 | 0 | Completed on Track | Received |  | N/A | Yes | 72557.35 | Yes | Completed | 2026-07-10 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5666 | 5757 | -91 | 101.6% | 2026-07-27 | 2026-09-16 | 0% | 0% | 0 | 6/15 NTP Package Received | Just completed. Need to pull fiber
FB-HTG279 | Fort Myers | 2026-09-30 | Lightspeed In-House | 2026-07-28 | Joshua Wheatcroft | FM112884 | 0 | Completed on Track | Received |  | N/A | Yes | 17689.15 | Yes | Completed | 2026-07-29 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 949 | 952 | -3 | 100.3% | 2026-08-19 | 2026-09-08 | 0% | 0% | 0 | 7/24 NTP Package Recived | Pending Phase 2. pulling fiber today
FB-HTG289 | Fort Myers | 2026-07-26 | HAS Global | 2026-06-11 | Joshua Wheatcroft |  | 0 | Completed on Track | Received |  | N/A | Yes | 31327.7 | Yes | Completed | 2026-06-16 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 2342 | 2421 | -79 | 103.4% | 2026-07-09 | 2026-07-22 | 0% | 0% | 0 | 6/11 NTP Package Received. | Not Started
FB-HTG290 | Fort Myers | 2026-07-18 | HAS Global | 2026-06-11 | Joshua Wheatcroft |  | 0 | Completed on Track | Received |  | N/A | Yes | 27837.25 | Yes | Completed | 2026-06-16 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 2367 | 2367 | 0 | 100% | 2026-06-25 | 2026-07-08 | 0% | 0% | 0 | 6/1 NTP Package Received. 8-6-26 tillman okd bill for tchr47 x 6 for the trip charge becuase they already had someone splicing it. | Not Started
FB-HTG292 | Fort Myers | 2026-07-31 | Gulfstream | 2026-07-09 | Joshua Wheatcroft | FM112413 | 0 | Completed on Track | Received |  | N/A | Yes | 21849.3 | Yes | Completed | 2026-07-15 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 1618 | 1646 | -28 | 101.7% | 2026-07-21 | 2026-08-05 | 0% | 0% | 0 | 7/6 NTP Packafe Received | Not Started
Colonial Pointe | Fort Myers | 2026-07-18 | APT Communications | 2026-06-23 | Joshua Wheatcroft | FM112152 | 72 | Completed on Track | Not Required |  | N/A | Yes | 60744.4 | Yes | Completed | 2026-06-24 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5950 | 5332 | 618 | 89.61% | 2026-07-13 | 2026-07-24 | 0% | 0% | 0 | 6/5 NTP Package Received. | Not started
BHC-FSW-04-E | Kissimmee | 2026-10-31 | BICOM | 2026-08-13 | Miguel |  | 0 | Completed on Track | Received |  | 2026-08-17 | Yes | 68022.75 | Yes | Completed | 2026-08-17 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 4564 | 4419 | 145 | 96.82% | 2026-08-26 | 2026-10-06 | 0% | 0% | 0 | 8/4 PO Received/.Locates called 8/17/Locates not clear (Sewer, Water) 8-24/CX started 8/25 Drill broke down/ Cx continuing 8-26/crossing US1 ON HOLD, DOT doing work.
FB-HSW419 | Kissimmee | 2026-10-23 | BICOM | 2026-09-01 | Miguel |  | 0 | Completed on Track | Received |  | N/A | Yes | 9232.4 | Yes | Completed | 2026-09-03 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 7261 | 7434 | -173 | 102.4% | 2026-09-01 | 2026-10-06 | 0% | 0% | 0 | 6/10 NTP Package Received With Permit. Partial Build with BHC-FSW-04-E
D-HBR252 | Miami | 2026-05-29 | Yosep AER | 2026-01-07 | Efrian |  | 53 | Completed on Track | Received |  | 2026-01-07 | Yes | 51528.05 | Yes | Completed | 2026-01-02 | Yes | 2026-06-19 | 2026-06-26 | 2026-07-17 | 4005 | 4047 | -42 | 101% | 2026-03-31 | 2026-06-02 | 100% | 100% | 100% | 12/24 NTP Package Received. Assigned to Yosep 1/7/26 | COP is ready
D-HBR256 | Miami | 2026-10-31 | Yosep AER | 2026-01-07 | Efrian |  | 73 | Completed on Track | Received |  | 2026-03-11 | Yes | 99925.7 | Yes | Completed | 2026-06-09 | Yes | 2026-07-09 | Pending Tillman QC Form | Pending Tillman QC Form | 7660 | 7703 | -43 | 100.6% | 2026-06-11 | 2026-07-06 | 100% | 100% | 100% | 12/24 NTP Package Received. Assigned to Yosep 1/7/26 | COP is ready
D-HBR257 | Miami | 2026-12-31 | Yosep AER | 2026-01-07 | Jose |  | 87 | Completed on Track | Received |  | 2026-06-25 | Yes | 108458.4 | Yes | Completed | 2026-06-17 | Yes | 2026-08-27 | Pending Tillman QC Form | Pending Tillman QC Form | 8596 | 8403 | 193 | 97.75% | 2026-06-30 | 2026-07-29 | 100% | 100% | 100% | 12/24 NTP Package Received. Assigned to Yosep 1/7/26 | Not Started
D-HBR258 | Miami | 2026-10-31 | Yosep AER | 2026-01-07 | Jose |  | 70 | Completed on Track | Received |  | N/A | Yes | 70105.25 | Yes | Completed | 2026-07-10 | Yes | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5648 | 5650 | -2 | 100% | 2026-07-23 | 2026-08-28 | 100% | 100% | 100% | 12/24 NTP Package Received. Assigned to Yosep 1/7/26 | Not Started
D-HBR259 | Miami | 2026-12-31 | Yosep AER | 2026-01-07 | Jose |  | 77 | Completed on Track | Received |  | N/A | Yes | 78047.35 | Yes | Completed | 2026-08-07 | Yes | 2026-10-01 | Failed QC 10/5/2026 | Pending Tillman QC Form | 6238 | 6300 | -62 | 101% | 2026-08-14 | 2026-09-30 | 100% | 100% | 100% | 12/24 NTP Package Received. Assigned to Yosep 1/7/26
D-HBR260 | Miami | 2026-12-31 | Yosep AER | 2026-01-07 | Jose |  | 52 | Completed on Track | Received |  | N/A | Yes | 91411.65 | Yes | Completed | 2026-08-26 | Yes | 2026-10-01 | Failed QC 10/5/2026 | Pending Tillman QC Form | 5926 | 5982 | -56 | 100.9% | 2026-08-28 | 2026-09-10 | 0% | 0% | 0 | 12/24 NTP Package Received. | Not started
FB-HBR252 | Miami | 2026-05-31 | Yosep AER | 2026-01-07 | Jose |  | 0 | Completed on Track | Received |  | N/A | Yes | 50239.7 | Yes | Completed | 2026-01-02 | Yes | 2026-09-18 | Failed QC 9/25/2026 | 2026-09-23 | 3682 | 3730 | -48 | 101.3% | 2026-05-13 | 2026-08-13 | 50% | 50% | 0 | 12/24 NTP Package Received. 5/5 PO Received. Phase 1 Failed QC Report Uploaded Into SiteTracker. | QC failed
D-HPP303 | Pinellas | 2026-08-28 | R&F Underground Construction Inc | 2026-05-29 | Joshua Pacheco |  | 35 | Completed on Track | Received |  | 2026-06-10 | Yes | 98498 | Yes | Completed | 2026-06-10 | Yes | 2026-09-25 | 2026-10-07 | 2026-10-07 | 7699 | 7300 | 399 | 94.82% | 2026-06-22 | 2026-08-28 | 100% | 100% | 100% | 5/29 NTP Package Received--PO Received 6/1 | Actualized. Will submit 10/2
D-HPP305 | Pinellas | 2026-08-28 | HDD Underground / R&F Underground Construction Inc | 2026-06-05 | Matthew Nunes |  | 87 | Completed on Track | Received |  | 2026-06-05 | Yes | 77365.5 | Yes | Completed | 2026-06-05 | Yes | 2026-09-25 | 2026-10-07 | 2026-10-07 | 6321 | 6271 | 50 | 99.21% | 2026-06-18 | 2026-08-04 | 100% | 100% | 100% | 6/24 Job reassgned to R&F after HDD was removed from the project -- 6/4 NTP Package Received | Actualized. Will submit 10/2
D-HPP310 | Pinellas | 2026-08-28 | Legant Livings | 2026-06-08 | Joshua Pacheco |  | 58 | Completed on Track | Received |  | 2026-06-08 | Yes | 78994.5 | Yes | Completed | 2026-06-05 | Yes | 2026-09-25 | 2026-10-07 | Pending Tillman QC Form | 6258 | 5944 | 314 | 94.98% | 2026-06-22 | 2026-07-23 | 100% | 0% | 0 | 5/29 NTP Package Received--PO Received 6/1 | Actualized. Will submit 10/2
D-HPP311 | Pinellas | 2026-08-28 | Legant Livings | 2026-06-08 | Joshua Pacheco |  | 85 | Completed on Track | Received |  | 2026-06-08 | Yes | 62709 | Yes | Completed | 2026-06-05 | Yes | 2026-09-25 | Failed QC 10/6/2026 | Pending Tillman QC Form | 5055 | 5140 | -85 | 101.7% | 2026-06-15 | 2026-08-20 | 100% | 0% | 0 | 5/29 NTP Package Received--PO Received 6/1 | Actualized. Will submit 10/2
D-HPP314 | Pinellas | 2026-08-28 | Power Connect | 2026-06-24 | Matthew Nunes | MAN112114 | 69 | Completed on Track | Received |  | 2026-06-25 | Yes | 99986.2 | Yes | Completed | 2026-06-25 | Yes | 2026-09-25 | Failed QC 10/5/2026 | Pending Tillman QC Form | 8137 | 8054 | 83 | 98.98% | 2026-08-03 | 2026-08-12 | 0% | 0% | 0 | 6/18 NTP Package Received...6-29-26 permit called in | Actualized. Will submit 10/2
D-HPP854 | Pinellas | 2026-10-27 | Brothers | 2026-08-27 | Anthony Adum |  | 90 | Completed on Track | Received |  | 2026-09-02 | Yes | 78625.9 | Yes | Completed | 2026-09-21 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6218 | 5826 | 392 | 93.7% | 2026-09-17 | 2026-10-09 | 0% | 0% | 0 | 8/24 NTP Package and PO Received.
D-HPP858 | Pinellas | 2026-10-27 | Brothers | 2026-08-27 | Anthony Adum |  | 68 | Completed on Track | Received |  | 2026-09-02 | Yes | 73595.5 | Yes | Completed | 2026-09-02 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5646 | 5626 | 20 | 99.65% | 2026-09-21 | 2026-09-28 | 0% | 0% | 0 | 8/24 NTP Package and PO Received.
FB-HPP314 | Pinellas | 2026-08-28 | Power Connect | 2026-06-08 | Joshua Pacheco |  | 0 | Completed on Track | Received |  | 2026-06-08 | Yes | 419 | Yes | Completed | 2026-06-05 | Yes | 2026-09-25 | 2026-10-06 | 2026-10-06 | 72 | 58 | 14 | 80.56% | 2026-08-05 | 2026-08-05 | 100% | 0% | 0 | 5/29 NTP Package Received--PO Received 6/1 | Actualized. Will submit 10/2
FB-HPP375 | Pinellas | 2026-09-30 | Power Connect | 2026-09-21 | Johnnie Williams |  | 0 | Completed on Track | Received |  | N/A | Yes | 24396.5 | Yes | Completed | 2026-09-21 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 2286 | 1957 | 329 | 85.61% | 2026-09-24 | 2026-09-28 | 0% | 0% | 0 | 9/18 NTP Package and PO Received.
FB-HPP879 | Pinellas | 2026-10-27 | Brothers | 2026-08-27 | Anthony Adum |  | 0 | Completed on Track | Received |  | N/A | Yes | 73440.1 | Yes | Completed | 2026-09-07 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5871 | 5903 | -32 | 100.5% | 2026-09-28 | 2026-10-01 | 0% | 0% | 0 | 8/26 NTP Package and PO Received.
D-HLC506 | Pinellas | 2026-09-25 | Brothers | 2026-07-20 | Anthony Adum |  | 83 | Completed on Track | Received |  | 2026-07-29 | Yes | 63582 | Yes | Completed | 2026-07-29 | No | Not Submitted | Pending Tillman QC Form | 2026-10-07 | 5259 | 5241 | 18 | 99.66% | 2026-08-24 | 2026-09-02 | 100% | 100% | 100% | 7/20 NTP and PO Received. | QC passed today. Working on this one
D-HLC507 | Pinellas | 2026-09-25 | ASM Utilities | 2026-07-20 | Danny Combs |  | 63 | Completed -Missed TSD | Received |  | 2026-07-21 | Yes | 78078 | Yes | Completed | 2026-07-27 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6335 | 6762 | -427 | 106.7% | 2026-09-11 | 2026-10-02 | 100% | 100% | 0 | 7/13 NTP Package Received. 7/17 PO Received And Approved.
D-HLC511 | Pinellas | 2026-09-25 | Lightspeed In-House | 2026-07-20 | Treyvon Tillman |  | 93 | Completed on Track | Received |  | 2026-07-21 | Yes | 72479.5 | Yes | Completed | 2026-07-24 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5861 | 5935 | -74 | 101.3% | 2026-08-24 | 2026-09-28 | 100% | 100% | 100% | 7/13 NTP Package Received. 7/17 PO Received And Approved.
D-HLC512 | Pinellas | 2026-09-25 | Brothers | 2026-07-20 | Anthony Adum | PPM113028 | 67 | Completed on Track | Received |  | 2026-07-23 | Yes | 86106.8 | Yes | Completed | 2026-07-23 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 7115 | 7040 | 75 | 98.95% | 2026-08-13 | 2026-09-25 | 100% | 100% | 100% | 7/14 NTP Package Received
D-HLC513 | Pinellas | 2026-09-25 | Lightspeed In-House | 2026-07-16 | Matthew Nunes | PPM112719 | 91 | Completed on Track | Received |  | N/A | Yes | 79458 | Yes | Completed | 2026-07-17 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6519 | 6118 | 401 | 93.85% | 2026-08-13 | 2026-09-08 | 0% | 0% | 0 | 7/13 NTP Package Received. 7/17 PO Received And Approved., Actual VERIFED FOOTAGE wheeled out 6118, SOW incorrect
D-HLC517 | Pinellas | 2026-09-25 | ASM Utilities | 2026-07-16 | Matthew Nunes | PPM112721 | 83 | Completed on Track | Received |  | 2026-09-07 | Yes | 79947 | Yes | Completed | 2026-07-27 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6058 | 6169 | -111 | 101.8% | 2026-08-17 | 2026-09-25 | 100% | 100% | 100% | 7/14 NTP Package Received
D-HLC518 | Pinellas | 2026-09-25 | ASM Utilities | 2026-07-16 | Matthew Nunes | PPM112722 | 93 | Completed on Track | Received |  | N/A | Yes | 74446.5 | Yes | Completed | 2026-07-27 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5775 | 5444 | 331 | 94.27% | 2026-08-11 | 2026-10-01 | 100% | 100% | 100% | 7/14 NTP Package Received
D-HLC519 | Pinellas | 2026-09-25 | Brothers | 2026-08-11 | Anthony Adum | PPM113024 | 44 | Completed on Track | Received |  | 2026-08-17 | Yes | 84001.5 | Yes | Completed | 2026-08-17 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6969 | 6980 | -11 | 100.2% | 2026-08-31 | 2026-09-10 | 100% | 100% | 100% | 7/31 NTP Package Received. | Gig list sent to contractor.
D-HLC539 | Pinellas | 2026-10-27 | Sosa Line | 2026-09-18 | Johnnie Williams |  | 64 | Completed on Track | Received |  | N/A | Yes | 88399.4 | Yes | Completed | 2026-09-22 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6946 | 6979 | -33 | 100.5% | 2026-09-29 | 2026-10-05 | 0% | 0% | 0 | 8/25 NTP Package and PO Received.
FB-HLC512 | Pinellas | 2026-09-25 | Brothers | 2026-07-20 | Anthony Adum | PPM112758 | 0 | Completed on Track | Received |  | 2026-07-22 | Yes | 71505.7 | Yes | Completed | 2026-07-22 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5642 | 5699 | -57 | 101% | 2026-08-07 | 2026-09-09 | 0% | 0% | 0 | 7/13 NTP Package Received | Passed QC. Working on COP
FB-HLC519 | Pinellas | 2026-09-25 | Power Connect | 2026-07-16 | Matthew Nunes | PPM112720 | 0 | Completed on Track | Received |  | N/A | Yes | 25127.05 | Yes | Completed | 2026-07-17 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 2013 | 2039 | -26 | 101.3% | 2026-09-08 | 2026-09-09 | 0% | 0% | 0 | 7/14 NTP Package Received | Actualized. Will submit 10/2
D-HSF308 | Port Charlotte | 2026-07-31 | HD Cable | 2026-07-07 | Joshua Wheatcroft |  | 68 | Completed on Track | Received |  | N/A | Yes | 62074 | Yes | Completed | 2026-07-08 | No | Not Submitted | 8/28 Failed QC | 8/28 Failed QC | 5495 | 5365 | 130 | 97.63% | 2026-07-20 | 2026-07-31 | 0% | 0% | 0 | 6/17 NTP Package Received. | working on change orders
D-HSF320 | Port Charlotte | 2026-05-30 | GN Systems | 2026-04-30 | Joshua Wheatcroft |  | 79 | Completed on Track | Received |  | N/A | Yes | 73533 | Yes | Completed | 2026-05-05 | Yes | 2026-06-17 | 2026-08-10 | 2026-08-10 | 5974 | 5911 | 63 | 98.95% | 2026-06-01 | 2026-06-03 | 0% | 0% | 0 | 4/29 NTP Package Received. | Pending bore logs from lopez
D-HSF322 | Port Charlotte | 2026-05-30 | Lopez Underground | 2026-07-07 | Joshua Wheatcroft |  | 89 | Completed on Track | Received |  | N/A | Yes | 81150 | Yes | Completed | 2026-05-06 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 6825 | 6741 | 84 | 98.77% | 2026-08-13 | 2026-08-24 | 0% | 0% | 0 | 4/21 NTP Received. | Pending bore logs from lopez
D-HSF402 | Port Charlotte | 2026-09-30 | GN Systems | 2026-08-20 | Brenton Copelin | FM113092 | 78 | Completed on Track | Received |  | N/A | Yes | 72242 | Yes | Completed | 2026-09-09 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5890 | 5834 | 56 | 99.05% | 2026-09-24 | 2026-10-07 | 0% | 0% | 0 | 7/24 PO Received.
D-HSF419 | Port Charlotte | 2026-09-30 | GN Systems | 2026-08-20 | Brenton Copelin | FM113094 | 49 | Completed on Track | Received |  | N/A | Yes | 62657 | Yes | Completed | 2026-09-09 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 5185 | 4940 | 245 | 95.27% | 2026-09-21 | 2026-09-22 | 0% | 0% | 0 | 7/31 NTP Package Received. | Just started. Not ready for QC
FB-HSF304 | Port Charlotte | 2026-05-30 | Lightspeed In-House | 2026-04-28 | Joshua Wheatcroft |  | 0 | Completed on Track | Received |  | N/A | Yes | 33518.7 | Yes | Completed | 2026-04-28 | No | Not Submitted | Pending Tillman QC Form | Pending Tillman QC Form | 3693 | 3896 | -203 | 105.5% | 2026-05-04 | 2026-08-28 | 0% | 0% | 0 | 4/21 NTP Received. Failed Gig List Received From Tillman on 8/28. | change orders needed
FB-HNP133 | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-05-02 | Johnnie Williams | PPM92370 | 0 | Completed on Track | Received |  | 2025-03-26 | Yes | 23800.25 | Yes | Completed | 2025-03-27 | Yes | 2026-04-22 | 2026-06-23 | Pending Tillman QC Form | 1697 | 1815 | -118 | 107% | 2025-05-14 | 2025-11-07 | 100% | 0% | 0 | 4.22 JW // Requested PH1 QC | Missing Photos
Vantage Point Condominiums | St Petersburg | 2026-07-15 | APT Communications/Kattleone | TBD | Johnnie Williams | PPM105151 | 380 | Completed on Track | Not Required |  | 2025-11-03 | Yes | 117414 | Yes | Completed | 2025-11-03 | Yes | 2026-05-01 | Pending Tillman QC Form | Pending Tillman QC Form | 9181 | 9179 | 2 | 99.98% | 2025-12-01 | 11/22/2026--MDU work still pending | 100% | 0% | 0 | 3.16 JW // Unable to closeout job // Pending MDU installation and removeable of FPs | In progress
D-HLP610 | Collier | 2026-10-15 | AGN | TBD | Aldo Layedra |  | 78 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 4373 | 4404 | -31 | 100.7% |  |  | 0% | 0% | 0
D-HPW304 | Lee | 2026-08-04 | DMG | TBD | Aldo Layedra |  | 39 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 2705 | 2705 | 0 | 100% |  |  | 0% | 0% | 0
D-HPW306 | Lee | 2026-08-26 | AGN | TBD | Aldo Layedra |  | 90 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 5254 | 5254 | 0 | 100% |  |  | 0% | 0% | 0
D-HPW309 | Lee | 2026-09-25 | AGN | TBD | Aldo Layedra |  | 83 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 5336 | 5501 | -165 | 103.1% |  |  | 0% | 0% | 0
D-HPW310 | Lee | 2026-08-26 | DMC Boring | TBD | Aldo Layedra |  |  | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 5634 | 5906 | -272 | 104.8% |  |  | 0% | 0% | 0
D-HPW311 | Lee | 2026-08-21 | DMC Boring | TBD | Aldo Layedra |  | 68 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 3909 | 3909 | 0 | 100% |  |  | 0% | 0% | 0
D-HPW325 | Lee | 2026-08-10 | RDA | TBD | Aldo Layedra |  | 80 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 6023 | 6055 | -32 | 100.5% |  |  | 0% | 0% | 0
D-HPW340 | Lee | 2026-08-21 | RDA |  | Aldo Layedra |  | 79 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | 2026-08-25 |  |  |  |  | 5773 | 5744 | 29 | 99.5% |  | 2026-10-01 | 0% | 0% | 0
D-HPW343 | Lee | 2026-09-03 | RDA | TBD | Aldo Layedra |  | 82 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 6788 | 6794 | -6 | 100.1% |  |  | 0% | 0% | 0
D-HTG402 | Lee | 2026-08-28 | RDA | TBD | Aldo Layedra |  | 78 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 5125 | 3972 | 1153 | 77.5% |  |  | 0% | 0% | 0
FB-HTG308 | Lee | 2026-08-31 | AGN | TBD | Aldo Layedra |  | 0 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 590 | 590 | 0 | 100% |  |  | 0% | 0% | 0
FB-HTG422 | Lee | 2026-08-18 | RDA | TBD | Aldo Layedra |  | 0 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 9602 | 10097 | -495 | 105.2% |  |  | 0% | 0% | 0
FB-HTG475 | Lee | 2026-07-29 | AGN | TBD | Aldo Layedra |  | 0 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 12 | 12 | 0 | 100% |  |  | 0% | 0% | 0
FB-HTG476 | Lee | 2026-08-14 | RDA | TBD | Aldo Layedra |  | 0 | Completed on Track | Received |  | N/A | Yes |  | Yes | Completed | [5 empty] | 96 | 78 | 18 | 81.25% |  |  | 0% | 0% | 0
Note on W4: Caten Murphy: added 126' hand dig 9/28
Note on W16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-28-2026 Final Footage Completed 8,277'--SiteTracker number is wrong.
Note on W17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-6-2026 Final Footage Completed 6,020'--SiteTracker number is wrong.
Note on W18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-1-2026 Final Footage Completed 7,341'--SiteTracker number is wrong.
Note on W21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-15-2026 Final Footage Completed 7,881'--SiteTracker number is wrong.
Note on W25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-13-2026 Final Footage Completed 8,542'--SiteTracker number is wrong.
Note on W26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-11-2026 Pending EOS and Redline For 1,797' Per James Heatherman
Note on W37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2026 Additional Footage Added For Stingray Path.
Note on V39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-11-2026 Additional Footage Was Built On The Backhaul.
Note on W45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2026 SiteTracker number 3,600' is wrong--Correct Footage Should Be 3,850'
Note on W47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-16-2026 Final Footage Completed 5,183'--SiteTracker number is wrong.
Note on W61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2026 Additional Footage Added To Feeder By Tillman.
Note on W63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-24-2026 Final Footage Completed 5,332'--SiteTracker number is wrong.
Note on AE64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Locates 228600459 228600513 229602546 230602485 230602946 230603575 230603625 230603667 230603700 230603782 230603859 230603930
Note on W75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-27-2026 Final Footage Completed 5,944'--SiteTracker number is wrong.
Note on W78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-9-2026 Final Footage Completed 5,826' SiteTracker Number Is Wrong.
Note on W81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-28-2026 Final Footage Completed 1,957' SiteTracker Number Is Wrong.
Note on W87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-29-2026 Final Footage Completed 6,118 SiteTracker Number Is Wrong.
Note on W89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-1-2026 Final Footage Completed 5,444 SiteTracker Number Is Wrong.
Note on W99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2026 Additional Footage Added To Due Re-Design.

## Invoiced-Paid Out-Pending
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Door Tag Date | SOW Received | SOW Estimated Cost | Invoice Amount Paid | Phase 2 Invoice | Total Invoice | NTP Received | Constuction Status | Locate Date | Footage UG | Actual Redline Completed Footage UG | UG Percentage Complete | Construction Start Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Construction Total Percent Complete | QC Received From Tillman | Phase 2 QC Received From Tillman | Comments
BHT-FLX-01 | Bradenton | 2026-05-30 | Baseline | 2025-08-28 | Cody |  | 0 | Completed on Track | Received | 2025-08-22 | Yes | 184994.5 | 159271.5 | 39954.2 | 199225.7 | Yes | Completed | 2025-08-22 | 14790 | 14871 | 101% | 2025-09-10 | 100% | 100% | 100% | 2026-02-11 | 2026-02-11 | 8/20 Project Received.
BHT-FLX-02 | Bradenton | 2026-05-30 | GN Systems | 2026-02-24 | Cody | MAN108635 | 0 | Completed on Track | Received | N/A | Yes | 12404.9 | 11793.85 | 8457.75 | 20251.6 | Yes | Completed | 2026-02-24 | 1111 | 1163 | 105% | 2026-03-16 | 100% | 100% | 100% | 2026-03-23 | 2026-03-23 | 2/12 Print Attached To Permit, Pending Fiber Splicing Documention.
BHT-FOE-03 | Bradenton | 2025-10-30 | North Path | 2025-07-14 | Joshua | MAN97574 | 0 | Completed on Track | Received | 2025-07-14 | Yes | 42837.2 | 36701.2 |  | 36701.2 | Yes | Completed | 2025-07-14 | 3432 | 3519 | 103% | 2025-07-28 | 100% | 100% | 100% | 2026-05-06 | Pending Tillman QC Form | 5/7 Phase 2 Failed Gig List Received From Tillman.
BHU-FAL-01-E | Bradenton | 2025-10-30 | HAS Global / Lightspeed | 2025-09-09 | Betsy | MAN101752 | 0 | Completed on Track | Received | 2025-09-05 | Yes | 98170.1 | 98170.1 |  | 98170.1 | Yes | Completed | 2025-09-08 | 9086 | 8945 | 98% | 2025-09-22 | 100% | 100% | 100% | 2026-06-22 | 2026-07-23 | 8/28 Permit Received With NTP Package. Assigned to HAS Global. 9.24 new design recieved and whitelined. Pending locates/ 1/13 CX Construction Complete...144F Placed. Phase 1 and 2 Failed Gig List Uploaded On 2/12/2026.
BHU-FAL-01-W | Bradenton | 2026-05-30 | Lightspeed In-House | 2025-09-05 | Betsy |  | 0 | Completed on Track | Received | 2025-10-13 | Yes | 2167.3 | 7455 | 64855.05 | 72310.05 | Yes | Completed | 2025-09-08 | 158 | 395 | 250% | 10/1/3/2025 | 100% | 100% | 100% | 2026-04-24 | 2026-04-24 | 8/22 Project Received With Permit. 9-18-25 on hold per tillman needs redesign. 9/22 Package 10 Permit Received. 9.24 new design recieved and whitelined. Pending locates.
BHU-FAL-01-W-2 | Bradenton | 2026-05-30 | Lightspeed In-House | 2025-09-05 | Betsy |  | 0 | Completed on Track | Received | 2025-10-13 | Yes | 2167.3 | 1930.3 | 1737.5 | 3667.8 | Yes | Completed | 2025-09-08 | 279 | 279 | 100% | 10/1/3/2025 | 100% | 100% | 100% | 2026-04-21 | 2026-04-21 | 8/22 Project Received With Permit. 9-18-25 on hold per tillman needs redesign. 9/22 Package 10 Permit Received. 9.24 new design recieved and whitelined. Pending locates.
BHUD-FLX-04-E | Bradenton | 2026-05-30 | GN Systems | 2026-04-02 | Cody | MAN104351 | 0 | Completed on Track | Received | N/A | Yes | 82825 | 73316 |  | 73316 | Yes | Completed | 2025-11-04 | 6210 | 6217 | 100% | 2026-04-16 | 100% | 100% | 100% | 2026-06-25 | 2026-07-21 | 9/29 Package 10 Permit.
BHUD-FOE-02-W | Bradenton | 2025-07-30 | Power Connect | 2025-02-28 | Joshua | MAN92070 | 0 | Completed on Track | Received | 2025-02-28 | Yes | 64932.55 | 69110.8 |  | 69110.8 | Yes | Completed | 2025-03-05 | 5151 | 5207 | 101% | 2025-04-01 | 100% | 100% | 100% | Legacy Project | Legacy Project
BHZD-FLX-04-W | Bradenton | 2026-05-30 | GN Systems | 2026-04-02 | Cody | MAN104071 | 0 | Completed on Track | Received | N/A | Yes | 34736.85 | 30641.35 |  | 30641.35 | Yes | Completed | 2025-11-04 | 2601 | 2890 | 111.1% | 2025-11-12 | 100% | 100% | 100% | 2026-06-22 | 2026-06-04 | 10/1 ntp received
BHZD-FOE-03-W | Bradenton | 2025-11-30 | Raven | 2025-02-19 | Joshua | PPM89496 | 0 | Completed on Track | Received | 2025-02-20 | Yes | 87944.4 | 99159.12 |  | 99159.12 | Yes | Completed | 2025-02-21 | 7008 | 7258 | 104% | 2025-03-31 | 100% | 100% | 100% | 2026-02-19 | 2026-02-19 | Needs soft dig to finish. Locates expired and re-called
D-HLR203 | Bradenton | 2025-11-30 | North Path | 2025-10-20 | Joshua |  | 82 | Completed on Track | Received | 2025-09-02 | Yes | 87830 | 72935 | 12266.1 | 85201.1 | Yes | Completed | 2025-08-29 | 7022 | 7002 | 100% | 2025-10-28 | 100% | 100% | 100% | 2026-04-22 | 2026-04-22 | 8/27 Permit Received With NTP Package.
D-HLR204 | Bradenton | 2026-03-18 | Lightspeed In-House | 2025-10-29 | Betsy | MAN103593 | 69 | Completed on Track | Received | 2025-09-25 | Yes | 51632 | 39035 |  | 39035 | Yes | Completed | 2025-10-02 | 3997 | 3937 | 98.5% | 2025-10-30 | 100% | 100% | 100% | 2026-04-27 | 2026-04-27 | 4-28 JW // COP Submitted - 9/15 Pending Permit. 9/22 Package 10 Permit Received. was gold gate but due to damages we dismissed them./ 2/3 CX Construction Continues--FDH Placed.
D-HLR205 | Bradenton | 2025-11-28 | North Path | 2025-11-03 | Joshua | MAN104002 | 74 | Completed on Track | Received | 2025-10-02 | Yes | 47064 | 43955 |  | 43955 | Yes | Completed | 2025-10-02 | 4716 | 4731 | 100.3% | 2025-11-10 | 100% | 100% | 100% | 2026-04-28 | 2026-04-28 | 9/15 Pending Permit. 9/22 Package 10 Permit Received.
D-HLR207 | Bradenton | 2025-10-30 | North Path | 2025-09-30 | Joshua |  | 80 | Completed on Track | Received | 2025-09-02 | Yes | 90173 | 73132 |  | 73132 | Yes | Completed | 2025-08-29 | 7009 | 6948 | 99% | 2025-10-14 | 100% | 100% | 100% | 2026-04-22 | 2026-04-22 | 8/27 Permit Received With NTP Package.
D-HLR208 | Bradenton | 2025-12-08 | GN Systems | 2025-11-03 | Cody | MAN104067 | 81 | Completed on Track | Received | N/A | Yes | 68962 | 53757 | 11950.2 | 65707.2 | Yes | Completed | 2025-10-02 | 5333 | 5339 | 100% | 2026-01-22 | 100% | 100% | 100% | 2026-04-16 | 2026-04-16 | 9/15 Pending Permit. 9/22 Package 10 Permit Received./ 1/22 CX Construction Started/
D-HLR210 | Bradenton | 2025-10-30 | GN Systems | 2025-10-20 | Cody |  | 80 | Completed on Track | Received | 2025-09-05 | Yes | 66674.3 | 50364.3 | 19125.8 | 69490.1 | Yes | Completed | 2025-09-22 | 5285 | 5305 | 100% | 2025-10-24 | 100% | 100% | 100% | 2025-11-21 | 2025-11-21 | 8/28 Permit Received With NTP Package.
D-HLR211 | Bradenton | 2025-10-30 | GN Systems | 2025-10-07 | Cody |  | 82 | Completed on Track | Received | 2025-09-03 | Yes | 93666.75 | 78401.25 | 15459.55 | 93860.8 | Yes | Completed | 2025-08-28 | 7883 | 7909 | 100% | 2025-10-15 | 100% | 100% | 100% | 2026-02-26 | 2026-02-26 | 8/27 Permit Received With NTP Package.
D-HLR212 | Bradenton | 2026-03-18 | North Path | 2025-11-14 | Joshua | MAN104535 | 48 | Completed on Track | Received | N/A | Yes | 39064 | 30327 |  | 30327 | Yes | Completed | 2025-10-02 | 2982 | 3061 | 102% | 2026-03-23 | 100% | 100% | 100% | 2026-04-28 | 2026-04-28 | 4-28 JW // HAS BOTH PASSING QAQC FORMS - COP WIP 9/15 Pending Permit. 10/2 permit added to site tracker on 9/25 downloaded and put in sharepoint folder
D-HOE102 | Bradenton | 2025-05-30 | MTX | 2025-02-18 | Joshua | MAN89819 | 56 | Completed on Track | Received | 2025-02-13 | Yes | 55089 | 57509 |  | 57509 | Yes | Completed | 2025-02-21 | 4836 | 5095 | 105.4% | 2025-03-25 | 100% | 100% | 100% | 2025-09-26 | 2025-09-26 | 4-29-25 Was MTX need to reassign.
D-HOE206 | Bradenton | 2025-11-30 | Power Connect - In-House | 2025-02-28 | Betsy | PPM92353 | 31 | Completed on Track | Received | 2025-02-28 | Yes | 28777 | 28496.8 |  | 28496.8 | Yes | Completed | 2025-02-28 | 2315 | 2279 | 98% | 2025-07-24 | 100% | 100% | 100% | 2025-12-02 | 2025-12-02
D-HOE302 | Bradenton | 2025-11-30 | North Path | 2025-08-11 | Joshua | MAN98158 | 57 | Completed on Track | Received | 2025-07-25 | Yes | 49223.7 | 37040.5 | 10534.7 | 47575.2 | Yes | Completed | 2025-07-25 | 3649 | 3557 | 97% | 2025-09-16 | 100% | 100% | 100% | 2026-02-02 | Pending Tillman QC Form | 10.10.25 changed total drill footage to 3394 as per walked out footages
D-HOE306 | Bradenton | 2025-11-30 | North Path | 2025-08-11 | Joshua | MAN99374 | 75 | Completed on Track | Received | 2025-08-10 | Yes | 68151.75 | 54018.75 |  | 54018.75 | Yes | Completed | 2025-08-12 | 5362 | 5236 | 98% | 2025-09-26 | 100% | 100% | 100% | 2026-05-05 | 2026-05-05 | 5/5 QC Forms Received From Tillman For Phase 1 and 2.
D-HOE501 | Bradenton | 2026-03-26 | North Path | 2025-11-19 | Cody | MAN104528 | 82 | Completed on Track | Received | N/A | Yes | 56294 | 41907 | 19111.55 | 61018.55 | Yes | Completed | 2025-11-20 | 4146 | 4184 | 101% | 2026-03-03 | 100% | 100% | 100% | 2026-04-13 | 2026-04-13 | 12/18 CX Construction.
D-HOE502 | Bradenton | 2026-03-26 | North Path | 2025-12-18 | Cody | MAN104531 | 54 | Completed on Track | Received | 2026-02-24 | Yes | 58240 | 47101 |  | 47101 | Yes | Completed | 2026-02-24 | 3599 | 3613 | 100% | 2026-03-04 | 100% | 100% | 100% | 2026-04-13 | 2026-04-13 | 10/17 Permit Received With NTP Package./ 3/4 CX Construction Started
FB-HAL101 | Bradenton | 2026-05-30 | North Path | 2026-04-30 | Cody | MAN108654 | 0 | Completed on Track | Received | N/A | Yes | 36998.55 | 31640.05 |  | 31640.05 | Yes | Completed | 2026-05-01 | 2944 | 2988 | 101.5% | 2026-05-13 | 100% | 100% | 100% | 2026-06-03 | 2026-06-03
FB-HAL113 | Bradenton | 2026-05-30 | North Path | 2026-03-20 | Cody | MAN108657 | 0 | Completed on Track | Received | N/A | Yes | 49932.8 | 43666.8 | 11479.55 | 55146.35 | Yes | Completed | 2026-02-24 | 4048 | 4028 | 99.51% | 2026-03-30 | 100% | 100% | 100% | 2026-05-08 | 2026-05-08
FB-HAL177 | Bradenton | 2026-05-30 | North Path | 2026-03-20 | Cody | MAN108659 | 0 | Completed on Track | Received | N/A | Yes | 18270.8 | 15994.8 |  | 15994.8 | Yes | Completed | 2026-02-24 | 1388 | 1360 | 97.98% | 2026-04-06 | 100% | 100% | 100% | 2026-05-08 | 2026-05-08 | 11/28 FDOT Permit Received.
FB-HAL175 | Bradenton | 2026-05-30 | GN Systems | 2026-02-02 | Cody | MAN104100 | 0 | Completed on Track | Received | N/A | Yes | 11518.95 | 10003.35 |  | 10003.35 | Yes | Completed | 2026-02-03 | 881 | 817 | 93% | 2026-02-10 | 100% | 100% | 100% | 2026-02-19 | 2026-02-19 | 9/16 Pending Permit. 1/30 Permit Received./ 2/10 CX Construction Started/ 2/12 CX Complete--96F Placed, Pending Splicing.
FB-HAL176 | Bradenton | 2026-03-31 | North Path | 2026-04-13 | Cody | MAN104756 | 20 | Completed on Track | Received | N/A | Yes | 1733.25 | 1381.75 |  | 1381.75 | Yes | Completed | 2026-04-16 | 145 | 145 | 100% | 2026-05-14 | 100% | 100% | 100% | 6/3 Failed QC | 2026-06-03 | 11/5 Permit Package 11 Received./
FB-HLR201 | Bradenton | 2026-01-18 | Lightspeed In-House / GN Systems | 2025-07-29 | Cody | MAN99683 | 0 | Completed on Track | Received | N/A | Yes | 144972.5 | 130196 |  | 130196 | Yes | Completed | 2025-07-29 | 9840 | 9806 | 99.65% | 2025-08-15 | 100% | 100% | 100% | 2026-06-19 | 2026-06-19 | 1/5 CX Construction Started. 2/5 CX Construction Complete--144F Placed Pending Splicing, 13 Ground Rods and Switches./ 2/9 695' Tracer Wire and Mule Tape.
FB-HLR202 | Bradenton | 2025-12-20 | GN Systems | 2025-09-23 | Cody | MAN104099 | 0 | Completed on Track | Received | N/A | Yes | 139581.6 | 120387.6 |  | 120387.6 | Yes | Completed | 2025-09-18 | 11150 | 10923 | 98% | 2026-01-05 | 100% | 100% | 100% | 2026-02-25 | 2026-02-25 | 9/15 FDOT Permit Received With NTP Package. FDOT Crossing 01-06-26/ 1/5 CX Construction Started/ 2/10 CX Complete
D-HLX401 | Bradenton | 2026-08-15 | North Path | 2026-04-27 | Cody | MAN108640 | 52 | Completed on Track | Received | N/A | Yes | 61830 | 51785 |  | 51785 | Yes | Completed | 2026-04-24 | 5149 | 5226 | 101% | 2026-05-06 | 100% | 100% | 100% | 2026-05-27 | 2026-05-27 | 10/27 Permit Package 11 Received. Hold Removed
D-HLX402 | Bradenton | 2026-05-29 | North Path | 2026-04-15 | Cody | MAN108642 | 56 | Completed on Track | Received | 2026-04-08 | Yes | 75665 | 64224 |  | 64224 | Yes | Completed | 2026-04-20 | 6249 | 6333 | 101.3% | 2026-04-29 | 100% | 100% | 100% | 2026-05-27 | 2026-05-27 | 10/22 Permit Received.
D-HLX403 | Bradenton | 2026-05-29 | North Path | 2026-05-14 | Cody | MAN104103 | 70 | Completed on Track | Received | N/A | Yes | 80624 | 65915 |  | 65915 | Yes | Completed | 2026-05-16 | 6856 | 6979 | 101.8% | 2026-05-20 | 100% | 100% | 100% | 2026-07-09 | 2026-07-09 | 9/26 Permit Received.
D-HLX404 | Bradenton | 2026-05-29 | North Path | 2026-04-15 | Cody | MAN108644 | 30 | Completed on Track | Received | N/A | Yes | 45160 | 37295 |  | 37295 | Yes | Completed | 2026-04-20 | 3700 | 3815 | 103.1% | 2026-04-23 | 100% | 100% | 100% | 2026-05-11 | 2026-06-04 | 10/21 Package 11 Permit Received With NTP.
D-HLX405 | Bradenton | 2026-04-19 | North Path | 2026-05-14 | Cody | MAN109508 | 2 | Completed on Track | Received | N/A | Yes | 21370 | 21200 |  | 21200 | Yes | Completed | 2026-05-17 | 1782 | 1731 | 97% | 2026-05-27 | 100% | 100% | 100% | 2026-07-14 | 2026-07-14
D-HLX406 | Bradenton | 2026-05-29 | North Path | 2026-05-06 | Cody | MAN108646 | 48 | Completed on Track | Received | N/A | Yes | 54814 | 71430 |  | 71430 | Yes | Completed | 2026-05-07 | 7140 | 7084 | 99% | 2026-05-13 | 100% | 100% | 100% | 2026-06-03 | 2026-07-23 | 9/24 Package 10 Permit Received With NTP.
D-HLX407 | Bradenton | 2026-05-29 | North Path | 2026-05-14 | Cody | MAN104101 | 60 | Completed on Track | Received | N/A | Yes | 76865.5 | 45050 |  | 45050 | Yes | Completed | 2026-05-17 | 4514 | 4605 | 102% | 2026-05-26 | 100% | 100% | 100% | 2026-07-14 | 2026-07-14 | 9/24 Package 10 Permit Received With NTP.
D-HLX416 | Bradenton | 2026-05-30 | GN Systems | 2026-04-06 | Cody | MAN104102 | 72 | Completed on Track | Received | 2026-04-08 | Yes | 85035 | 65950.6 |  | 65950.6 | Yes | Completed | 2026-04-06 | 5830 | 5830 | 100% | 2026-04-23 | 100% | 100% | 100% | 2026-07-14 | 2026-06-25 | 9/24 Package 10 Permit Received With NTP.
D-HLX516 | Bradenton | 2026-06-18 | North Path | 2026-05-27 | Cody | MAN111883 | 85 | Completed on Track | Received | N/A | Yes | 56492 | 56322 |  | 56322 | Yes | Completed | 2026-05-28 | 4054 | 4212 | 104% | 2026-06-11 | 100% | 100% | 100% | 2026-07-28 | 2026-07-28 | 4/29 NTP Package Received.
D-HLX518 | Bradenton | 2026-06-18 | North Path | 2026-05-21 | Cody | MAN111853 | 83 | Completed on Track | Received | N/A | Yes | 58914 | 58744 |  | 58744 | Yes | Completed | 2026-05-22 | 4343 | 4460 | 102.7% | 2026-06-01 | 100% | 100% | 100% | 2026-06-22 | 2026-06-25 | 4/29 NTP Package Received.
D-HLX519 | Bradenton | 2026-06-18 | North Path | 2026-05-27 | Cody | MAN111885 | 56 | Completed on Track | Received | N/A | Yes | 42220 | 42050 |  | 42050 | Yes | Completed | 2026-05-28 | 3090 | 2998 | 97.02% | 2026-06-10 | 100% | 100% | 100% | 2026-07-09 | 2026-07-09 | 4/29 NTP Package Received.
FB-HLX401 | Bradenton | 2026-03-15 | GN Systems | 2026-02-24 | Cody | MAN108663 | 0 | Completed on Track | Received | N/A | Yes | 73653.9 | 64828.9 | 56982.6 | 121811.5 | Yes | Completed | 2026-02-24 | 6668 | 6668 | 100% | 2026-03-09 | 100% | 100% | 100% | 2026-04-08 | 2026-04-08
FB-HLX409 | Bradenton | 2026-03-22 | Lightspeed In-House | 2026-02-24 | Cody | MAN108666 | 0 | Completed on Track | Received | N/A | Yes | 15002.75 | 13046.25 |  | 13046.25 | Yes | Completed | 2026-05-05 | 1175 | 1238 | 105.4% | 2026-03-09 | 100% | 100% | 100% | 2026-06-25 | 2026-07-09
FB-HLX417 | Bradenton | 2026-03-22 | GN Systems | 2026-02-24 | Cody | MAN108669 | 0 | Completed on Track | Received | N/A | Yes | 12977.65 | 11240.15 |  | 11240.15 | Yes | Completed | 2026-04-03 | 1029 | 1036 | 100.7% | 2026-04-08 | 100% | 100% | 100% | 2026-05-08 | 2026-05-08
FB-HLX501 | Bradenton | 2026-06-01 | North Path | 2026-04-06 | Joshua | MAN105619 | 0 | Completed on Track | Received | N/A | Yes | 170309.8 | 146163.8 | 57984.4 | 204148.2 | Yes | Completed | 2026-04-07 | 14858 | 14858 | 100% | 2026-04-10 | 100% | 100% | 100% | 2026-05-13 | 2026-05-13 | 10/21 Package 11 Permit Received With NTP.
FB-HOE175 | Bradenton | 2025-10-30 | GN Systems | 2025-11-05 | Cody |  | 0 | Completed on Track | Received | N/A | Yes | 29960 | 25458 |  | 25458 | Yes | Completed | 2025-09-22 | 2372 | 2326 | 98% | 2025-11-07 | 100% | 100% | 100% | 2026-02-12 | 2026-02-12 | 9/15 FDOT Permit Received With NTP Package/ 1/8 CX Complete...2,706' of 48F Placed. Splicing to Follow
FB-HOE178 | Bradenton | 2025-10-30 | GN Systems | 2025-10-14 | Cody |  | 0 | Completed on Track | Received | N/A | Yes | 50539.6 | 44321.6 |  | 44321.6 | Yes | Completed | 2025-10-02 | 4084 | 4064 | 100% | 2025-10-22 | 100% | 100% | 100% | 2025-12-17 | 2025-12-17 | Pending Splice Detail File.
FB-HOE180 | Bradenton | 2026-01-18 | Lightspeed In-House | 2026-02-24 |  | MAN104760 | 0 | Completed on Track | Received | N/A | Yes | 1675.2 | 1273.05 |  | 1273.05 | Yes | Completed | 2026-02-24 | 123 | 130 | 106% | 2026-03-17 | 100% | 100% | 100% | 2026-03-23 | 2026-03-23 | 10/27 FDOT Permit Received.
FB-HOE201 | Bradenton | 2025-11-30 | Brothers / Power Connect | 2025-03-19 | Joshua | MAN91981 | 0 | Completed on Track | Received | 2025-03-02 | Yes | 200394.1 | 209003.94 |  | 209003.94 | Yes | Completed | 2025-02-28 | 15386 | 15339 | 100% | 2025-03-31 | 100% | 100% | 100% | 2025-09-26 | 2025-09-26
FB-HOE301 | Bradenton | 2025-11-30 | Raven | 2025-07-28 | Joshua | MAN98180 | 0 | Completed on Track | Received | 2025-07-25 | Yes | 143407.25 | 172716.95 |  | 172716.95 | Yes | Completed | 2025-07-25 | 11987 | 12324 | 102.8% | 2025-07-31 | 100% | 100% | 100% | 2026-07-24 | 2026-07-24
FB-HOE401-V2 | Bradenton | 2026-01-18 | North Path | 2026-01-20 | Cody |  | 0 | Completed on Track | Received | N/A | Yes | 45312.55 | 39954.05 | 14829.75 | 54783.8 | Yes | Completed | 2026-01-22 | 3683 | 3713 | 101% | 2026-01-28 | 100% | 100% | 100% | 2026-02-20 | 2026-02-20 | 12/3 Permit Received. / 2/11 CX Complete--6 HH and Ground Rods, 144F--Pending Splicing.
FB-HOE501 | Bradenton | 2026-02-20 | GN Systems | 2026-02-02 | Cody | MAN104761 | 0 | Completed on Track | Received | N/A | Yes | 105558.2 | 86338.55 |  | 86338.55 | Yes | Completed | 2025-11-17 | 7753 | 7663 | 99% | 2026-02-17 | 100% | 100% | 100% | 2026-03-09 | 2026-07-24 | 11/5 FDOT Received. NTP Package Missing The Pending Fiber Details Documents. 2/3 MOT Required As Per John K/ 2/17 CX Construction Started--2/25 CX Construction Complete--Progress At 100% Complete. Pending Fiber and Splicing. Fail Gig List Uploaded On 3/9/2026.
FB-HOE675 | Bradenton | 2/30/2026 | Lightspeed In-House | 2025-11-03 | Betsy |  | 0 | Completed on Track | Received | N/A | Yes | 2670.65 | 2163.15 | 1684.45 | 3845.6 | Yes | Completed | 2025-10-07 | 209 | 207 | 99% | 2025-11-03 | 100% | 100% | 100% | 2026-03-16 | 2026-03-16 | 9/29 Package 10 Permit./ 1/12 CX Complete...FDH and 48F Complete, Splicing to Follow.
FX4-FAL-01 | Bradenton | 2025-10-25 | Brothers | 2025-09-19 | Cody | MAN93941 | 0 | Completed on Track | Received | N/A | Yes | 4646.75 | 9453.74 |  | 9453.74 | Yes | Completed | Not Required | 117 | 117 | 100% | 2025-10-16 | 0% | 0% | 0% | 2026-07-27 | 2026-07-27
RELO-BHZD-FOE-06-W | Bradenton | 2026-01-31 | Vault Relocation | 2026-01-08 | Cody |  | 0 | Completed on Track | Received | N/A | Yes | 1035 | 875 |  | 875 | Yes | Completed | Not Required | 0 | 0 | 100% | 2026-01-08 | 0% | 0% | 0% | 2026-02-26 | 2026-02-26
D-HPP609 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Miguel |  | 65 | Completed on Track | Received | 2026-06-02 | Yes | 97544 | 97180 |  | 97180 | Yes | Completed | 2026-05-29 | 7771 | 7623 | 98% | 2026-06-05 | 0% | 0% | 0 | 2026-07-15 | 2026-07-15 | 6-5 Work Started - 5/1 NTP Package Received./Restoration completed 6-15/ QC request 6-17/
D-HPP611 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Miguel |  | 93 | Completed on Track | Received | 2026-06-02 | Yes | 111096 | 110732 |  | 110732 | Yes | Completed | 2026-05-29 | 9483 | 9171 | 97% | 2026-06-15 | 0% | 0% | 0 | 2026-07-10 | 2026-07-10 | 5/1 NTP Package Received./Restoration Complete/Schedule QC 7-1/
D-HPP615 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Miguel |  | 91 | Completed on Track | Received | 2026-06-02 | Yes | 111633.5 | 111299.5 |  | 111299.5 | Yes | Completed | 2026-06-05 | 9431 | 9211 | 98% | 2026-06-24 | 0% | 0% | 0 | 2026-08-03 | 2026-08-03 | 5/1 NTP Package Received. CX started 6-24/Cx and Restoration completed 7/2/ Pending QC Sheet from Tillman to submit COP 7/29
D-HPP619 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Miguel |  | 42 | Completed on Track | Received | 2026-06-05 | Yes | 101724.5 | 101360.5 |  | 101360.5 | Yes | Completed | 2026-05-29 | 7993 | 7505 | 94% | 2026-06-17 | 0% | 0% | 0 | 2026-08-03 | 2026-08-03 | 5/1 NTP Package Received./Restoration Complete/Schedule QC 7-1/Pending QC Sheet from Tillman to submit COP 7/29
FB-HPP617 | Clearwater | 2026-10-30 | Brothers | 2026-05-13 | Anthony | PPM111730 | 0 | Completed on Track | Received | 2026-06-03 | Yes | 10128.05 | 8414.55 |  | 8414.55 | Yes | Completed | 2026-06-03 | 813 | 800 | 98% | 2026-06-11 | 0% | 0% | 0 | 2026-08-03 | Pending Tillman QC Form | 6/3 LOCATES CALLED - 5/15 - Door Tagging / Whiteling this afternoon - 5/12 NTP Package Received.
BHT-FWP-06 | Lakeland | 2025-04-25 | Lightspeed In-House | 2025-02-03 | Travis | PLK89457 | 0 | Completed on Track | Received | 2025-02-20 | Yes | 62460.45 | 61491.05 |  | 61491.05 | Yes | Completed | 2025-02-21 | 4949 | 5089 | 102.8% | 2025-03-04 | 100% | 100% | 100% | 2025-06-13 | 2025-06-13
BHT-FWP-07 | Lakeland | 2025-04-25 | LSCG | 2025-03-19 | Travis | PLK91807 | 0 | Completed on Track | Received | 2025-03-19 | Yes | 15690.1 | 16153.75 |  | 16153.75 | Yes | Completed | 2025-03-19 | 1242 | 1243 | 100.1% | 2025-03-27 | 100% | 100% | 100% | 2025-06-27 | 2025-06-27 | locates updated 3-21/SOW REC 3-21/ about 600' left 3-31,ecd 4-4/need to confirm 144 cut at carol vault- / Job Complete. Need Walkout/ Closeout sent/ Walkout cleared by paul, turn over to tanner 4-23
BHT-FWP-08 | Lakeland | 2025-07-30 | Brothers | 2025-06-05 | Anthony | PLK96231 | 0 | Completed on Track | Received | 2025-05-16 | Yes | 104070.8 | 106593.55 |  | 106593.55 | Yes | Completed | 2025-05-16 | 7848 | 7859 | 100% | 2025-06-17 | 100% | 100% | 100% | 2025-08-28 | 2025-08-28 | 1465 drilled 6-17/ 6/23 Drilling 1269'/ 6/24 - DOT Xing scheduled for 6/26. 6/30- All path complete, Dave Simmon is getting a date to place fiber. Cozmin to work on restoration 7/1. 7/7- placing and restoration complete, only thing pending is splicing. Construction CO sent to Garrison
BHT-FWP-09 | Lakeland | 2025-07-30 | Brothers | 2025-05-09 | Travis | PLK95075 | 0 | Completed on Track | Received | 2025-05-09 | Yes | 133172.15 | 167474.19 |  | 167474.19 | Yes | Completed | 2025-05-12 | 13306 | 12936 | 97% | 2025-06-02 | 100% | 100% | 100% | 2025-09-18 | 2025-09-18 | Piping complete 6-17/do we need a change order for greyed out area? Brothers sch 7-21/need cop needs uploaded
BHT-FWP-10 | Lakeland | 2025-05-30 | Brothers | 2025-05-01 | Travis | PLK94470 | 0 | Completed on Track | Received | 2025-05-05 | Yes | 119135.3 | 121256.65 |  | 121256.65 | Yes | Completed | 2025-05-05 | 9356 | 9202 | 98.35% | 2025-05-15 | 100% | 100% | 100% | 2025-08-28 | 2025-08-28 | Dispatched 5-1/ Locates expedited 5/8. / 5/14 Brothers to start 5.15 w 1 drill. LS Jeff to GPR 5.15/ 1580' 5-15/270' 5-19/5-20 waiting on city locates/ 948' 5-22/ 954' 5-27/ 2,973' 5-28/ DOT crossing sch 6-5/ 2,248' 5-29. Fiber Pulled 6-17/COP Sent 6-18/needs jobs next to it completed for fs to take place
BHU-FWP-08-E | Lakeland | 2025-09-30 | Lightspeed In-House | 2025-09-18 | Travis |  | 0 | Completed on Track | Received | 2025-09-18 | Yes | 10840.25 | 11474.35 |  | 11474.35 | Yes | Completed | 2025-09-12 | 865 | 851 | 98% | 2025-09-24 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | CL 9-12/CX START 9-24/cx complete,pulling tracer wire 9-30
BHUD-FWP-08-E | Lakeland | 2025-05-10 | Brothers | 2025-02-27 | Travis | PLK91306 | 0 | Completed on Track | Received | Completed | Yes | 12601.45 | 13008.1 |  | 13008.1 | Yes | Completed | 2025-02-28 | 939 | 928 | 98.83% | 2025-03-17 | 100% | 100% | 100% | 2025-06-16 | 2025-06-16
BHZD-FWP-08-W | Lakeland | 2025-10-30 | Lightspeed In-House | 2025-09-18 | Travis | PLK102593 | 0 | Completed on Track | Received | 2025-09-18 | Yes | 9611.95 | 11484.1 |  | 11484.1 | Yes | Completed | 2025-09-18 | 807 | 896 | 111% | 2025-10-08 | 100% | 100% | 100% | 2025-12-18 | 2025-12-18 | 9/15 FDOT Permit Received With NTP Package. / 9/19- CL9.18 WL 9.19/water locates issue still 9-30 / 10/2- CX started 10/6 City Of Lakeland Permit Received./Sidewalk closed signs will be ready to pick up the 21st/picked up 10-21/had to renew locate s1-21/
BHUD-FWP-13-W | Lakeland | 2025-07-30 | Brothers | 2025-06-20 | Anthony | PLK95092 | 0 | Completed on Track | Received | 2025-06-18 | Yes | 144886 | 138688 |  | 138688 | Yes | Completed | 2025-07-02 | 11054 | 11092 | 100% | 2025-07-07 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | Needs City Permit, Just Email. 6/18 COL permit rec'd, WL/DT 7.1. Still need County permit/greyed out on city portion ,need other jobs to build (1312+1310+1307bh-13w002) 7/3- need county permit
BHZD-FWP-11-W | Lakeland | 2025-08-30 | Brothers | 2025-07-15 | Travis | PLK97102 | 0 | Completed on Track | Received | 2025-07-15 | Yes | 60849.9 | 69149.45 |  | 69149.45 | Yes | Completed | 2025-07-15 | 5276 | 5289 | 100% | 2025-08-05 | 100% | 100% | 100% | 2025-09-16 | 2025-09-16 | Sch 8-7 DOT Bore Brothers/need bore logs ,splicing docs + change order for cop 8-20
BHZD-FWP-13-E | Lakeland | 2025-07-30 | Lightspeed In-House | 2025-05-16 | Travis | PLK95389 | 0 | Completed on Track | Received | 2025-05-16 | Yes | 53589.8 | 36600 |  | 36600 | Yes | Completed | 2025-05-16 | 8305 | 8810 | 106% | 2025-06-02 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | Locates called in 5/16, doortags 5/16 and 5/19. Only have city of Lakeland Permit, still need APPROVED FDOT and County permits. 5/22 Jeff in market doing GPR. / 5/27- IH drill broke down, failed to pull back. / 6/2- IH drilling for 275', becket broke during 2nd pullback. / 6/4 - IH Drilling, 310' bad weather. / 6/5-IH drilling lost pullback, crew got dispatched to a different Tillman escalation. / 6/12- IH had flat tired on vac, had to move job sites after starting because FTR needed to work damaged fiber, ground was hard and drill head could not come up, incliment weather set it and was not able to complete any shots. / 7/3- Change order request sent to Tillman for more bore footage needed to continue. 7/3- need fdot permit/ 12-16 COP sent
D-H0306A-1 | Lakeland | 2026-02-20 | Lightspeed In-House | 2026-01-20 | Miguel | PLK105465 | 11 | Completed on Track | Received | 2026-01-07 | Yes | 10772 | 7890 | 2882 | 10610 | Yes | Completed | 2026-01-07 | 789 | 888 | 113% | 2026-02-03 | 0% | 0% | 0% | 2026-02-20 | 2026-02-20 | 10/29 Pending Permit/permit received1-13/Locates called 1/7/2026/Locates cleared 2/3/2026/ Cx starts 2-3-2026/ 2/3 CX Construction Started 2/11 CX Construction Path 100% Completed--Pending Splicing.
D-HWP102 | Lakeland | 2025-02-23 | Power Connect /SB | 2025-02-05 | Anthony | PLK88966 | 54 | Completed -Missed TSD | Received | Completed | Yes | 47461.5 | 45340 |  | 45340 | Yes | Completed | 2025-02-04 | 3775 | 3734 | 98.91% | 2025-02-20 | 100% | 100% | 100% | 2025-03-27 | 2025-03-27
D-HWP103 | Lakeland | 2025-02-23 | Brothers | 2025-02-24 | Travis | PLK88967 | 49 | Completed -Missed TSD | Received | 2025-02-25 | Yes | 43064 | 44346 |  | 44346 | Yes | Completed | 2025-02-04 | 3422 | 3519 | 102.8% | 2025-03-11 | 100% | 100% | 100% | 2025-03-27 | 2025-03-27
D-HWP105 | Lakeland | 2025-02-28 | Brothers | 2025-02-18 | Anthony | PLK90239 | 56 | Completed -Missed TSD | Received | 2025-02-19 | Yes | 62522.54 | 56001 |  | 56001 | Yes | Completed | 2025-02-19 | 4063 | 4097 | 100.8% | 2025-03-03 | 100% | 100% | 100% | 2025-06-27 | 2025-06-27
D-HWP106 | Lakeland | 2026-02-20 | Brothers | 2026-01-19 | Travis | PLK105199 | 67 | Completed on Track | Received | 2026-01-16 | Yes | 66854 | 65121.4 | 170 | 65291.4 | Yes | Completed | 2026-01-07 | 5534 | 5407 | 98% | 2026-02-16 | 100% | 100% | 100% | 2026-02-26 | 2026-03-20 | 10/17 Pending Permit./White lined door tag 1-6/Cx starts 2-16-2026/ 2/16 CX Construction Started/ CX COmplete, need D110 built for SR 2-23
D-HWP107 | Lakeland | 2026-03-20 | Brothers | 2026-01-20 | Travis | PLK105200 | 65 | Completed on Track | Received | 2026-01-06 | Yes | 60922 | 59221.8 | 170 | 59391.8 | Yes | Completed | 2026-01-07 | 4907 | 4808 | 98% | 2026-02-19 | 100% | 100% | 100% | 2026-03-10 | 2026-03-31 | 11/20 Pending Permit./White lined and door tagged 1-6-2026/LC called 1-7-2026/ 2/19 CX Construction Started--Pending Fiber and Splicing./ 3-4 Sch SR and Splicing/Lighrt Levels Received 3-5-2026.
D-HWP108 | Lakeland | 2026-03-20 | Brothers | 2026-01-20 | Miguel | PLK105202 | 79 | Completed on Track | Received | N/A | Yes | 59768 | 59370.8 | 170 | 59540.8 | Yes | Completed | 2026-01-07 | 4862 | 4880 | 100% | 2026-03-10 | 100% | 100% | 100% | 2026-03-20 | 2026-03-24 | 11/11 Pending Permit./pemit rec 2-4/Cx begins 3-10-2026/Path complete 3-16/FDH proofing 3-19/Stingray scheduled for 3-20/
D-HWP109 | Lakeland | 2026-02-20 | J.Garcia | 2026-01-23 | Miguel | PLK105203 | 87 | Completed on Track | Received | 2026-01-16 | Yes | 82790 | 82620 | 6131.83 | 88751.83 | Yes | Completed | 2026-01-07 | 7108 | 7301 | 103% | 2026-02-04 | 100% | 100% | 100% | 2026-02-26 | 2026-03-24 | 11/7 Pending Permit./received permit/cl 1-7/2-4 CX Started/ 2/4 CX Construction Started/ 2/23 CX Construction Complete Pending Fiber and Splicing./ 3/4 CX Construction Complete--Pending Splicing./Lighrt Levels Received 3-5-2026
D-HWP110 | Lakeland | 2026-03-20 | Brothers | 2026-01-20 | Miguel | PLK105391 | 55 | Completed on Track | Received | 2026-01-16 | Yes | 44782 | 44759 | 170 | 44929 | Yes | Completed | 2026-01-07 | 3690 | 3784 | 103% | 2026-03-02 | 100% | 100% | 100% | 2026-03-20 | 2026-03-24 | 10/21 Pending Permit./permit rec 2-4CX starts 3-2-2026/Proofing 3-19/Stigray scheduled for 3-20/
D-HWP412 | Lakeland | 2025-01-31 | SB Martinez | 2025-01-09 | Travis | PLK87663 | 23 | Completed on Track | Received | Completed | Yes | 26617 | 25405 |  | 25405 | Yes | Completed | 2025-01-02 | 2121 | 2106 | 99.29% | 2025-01-13 | 100% | 100% | 100% | 2025-02-14 | 2025-02-14
D-HWP415 | Lakeland | 2025-01-31 | Lightspeed In-House | 2025-01-22 | Travis | PLK88133 | 70 | Completed -Missed TSD | Received | Completed | Yes | 72118 | 70778 |  | 70778 | Yes | Completed | 2025-01-02 | 5987 | 5879 | 98.2% | 2025-01-22 | 100% | 100% | 100% | 2025-06-13 | 2025-06-13
D-HWP425 | Lakeland | 2025-01-31 | Brothers | 2025-01-28 | Travis | PLK88584 | 75 | Completed -Missed TSD | Received | Completed | Yes | 69288 | 70664 |  | 70664 | Yes | Completed | 2025-01-15 | 5690 | 5759 | 101.2% | 2025-01-28 | 100% | 100% | 100% | 2025-03-28 | 2025-03-28
D-HWP436 | Lakeland | 2025-01-31 | HH/LS | 2025-02-05 | Anthony | PLK88375 | 65 | Completed -Missed TSD | Received | 2025-01-16 | Yes | 69555 | 70432 |  | 70432 | Yes | Completed | 2025-01-16 | 5661 | 5633 | 99.51% | 2025-02-05 | 100% | 100% | 100% | 2025-06-13 | 2025-06-13
D-HWP441 | Lakeland | 2025-01-31 | Brothers | 2025-01-28 | Travis | PLK88853 | 81 | Completed -Missed TSD | Received | Completed | Yes | 83754 | 80572.5 |  | 80572.5 | Yes | Completed | 2025-01-15 | 7140 | 6854 | 95.99% | 2025-01-28 | 100% | 100% | 100% | 2025-02-14 | 2025-02-14
D-HWP701 | Lakeland | 2025-03-26 | Brothers | 2025-02-20 | Anthony | PLK89401 | 50 | Completed -Missed TSD | Received | 2025-02-17 | Yes | 43895.5 | 44479.5 |  | 44479.5 | Yes | Completed | 2025-02-18 | 3581 | 3634 | 101.5% | 2025-03-12 | 100% | 100% | 100% | 2025-03-27 | 2025-03-27
D-HWP702 | Lakeland | 2025-03-26 | Brothers | 2025-03-13 | Anthony | PLK92108 | 52 | Completed on Track | Received | 2025-03-17 | Yes | 50824.5 | 50928.5 |  | 50928.5 | Yes | Completed | 2025-03-13 | 4030 | 4064 | 100.8% | 2025-04-02 | 100% | 100% | 100% | 2025-05-12 | 2025-05-12
D-HWP703 | Lakeland | 2025-04-25 | Brothers | 2025-03-19 | Travis | PLK92329 | 86 | Completed on Track | Received | 2025-03-21 | Yes | 83462 | 83033 |  | 83033 | Yes | Completed | 2025-03-19 | 6723 | 6757 | 100.5% | 2025-04-07 | 100% | 100% | 100% | 2025-05-12 | 2025-05-12
D-HWP705 | Lakeland | 2025-02-28 | Brothers | 2025-02-24 | Anthony | PLK91019 | 51 | Completed -Missed TSD | Received | Completed | Yes | 47414 | 45744 |  | 45744 | Yes | Completed | 2025-02-28 | 3597 | 3636 | 101.1% | 2025-03-11 | 100% | 100% | 100% | 2025-03-27 | 2025-03-27
D-HWP706 | Lakeland | 2025-04-25 | Brothers | 2025-03-19 | Anthony | PLK91963 | 59 | Completed on Track | Received | 2025-03-20 | Yes | 59562.5 | 52525.5 |  | 52525.5 | Yes | Completed | 2025-03-19 | 4123 | 4094 | 99.3% | 2025-03-31 | 100% | 100% | 100% | 2025-05-12 | 2025-05-12
D-HWP707 | Lakeland | 2025-04-25 | Brothers | 2025-03-19 | Travis | PLK92185 | 35 | Completed on Track | Received | 2025-03-19 | Yes | 41187 | 39597.5 |  | 39597.5 | Yes | Completed | 2025-03-19 | 3235 | 3240 | 100.2% | 2025-04-03 | 100% | 100% | 100% | 2025-05-12 | 2025-05-12
D-HWP713 | Lakeland | 2025-02-23 | Brothers | 2025-02-07 | Anthony | PLK89267 | 22 | Completed on Track | Received | Completed | Yes | 14497.5 | 14042 |  | 14042 | Yes | Completed | 2025-02-07 | 1073 | 1091 | 101.7% | 2025-02-18 | 100% | 100% | 100% | 2025-03-05 | 2025-03-05
D-HWP801 | Lakeland | 2025-07-30 | Brothers | 2025-05-19 | Anthony | PLK95087 | 58 | Completed on Track | Received | 2025-05-20 | Yes | 43097.65 | 40400 |  | 40400 | Yes | Completed | 2025-06-02 | 3309 | 3194 | 97% | 2025-06-24 | 100% | 100% | 100% | 2025-08-29 | 2025-08-29 | NEED NTP per James. City of Lakeland Permit Received/dis for doortag and locates 5-19. 5/27-I asked Brothers to call in locates/doortags b/c they have not done so yet. / 6/9 doortagged 6/6 and loc called in 6/2 / 6/24- Brothers drilling 1044' / 1100' 6-25/ 1050' Path complete 6-26/pending qc form 7-1/needs change order
D-HWP808-1 | Lakeland | 2025-12-30 | Brothers | 2025-12-10 | Miguel |  | 49 | Completed on Track | Received | 2025-12-03 | Yes | 42150 | 49107 |  | 49107 | Yes | Completed | 2025-12-03 | 3885 | 3910 | 100.6% | 2025-12-15 | 100% | 100% | 100% | 2025-12-22 | 2026-03-31 | 12/12 NTP Package Received./NTP received 12/12/2025/Cx starts 12/15/2025/ 12-17/ FDH/Proofing Sch 12/19/
D-HWP802 | Lakeland | 2025-08-30 | Longo Underground | 2025-08-20 | Anthony |  | 76 | Completed on Track | Received | 2025-08-19 | Yes | 53902 | 42685 | 1597.8 | 44282.8 | Yes | Completed | 2025-08-18 | 3566 | 3704 | 103.9% | 2025-09-04 | 100% | 100% | 100% | 2025-10-02 | 2025-10-02 | waiting on locates 9-3/In Progress 45% complete 9-8/90% 9-16/ug cx com 9-17/sr placed 9-18/wo 9-23 *passed inspection/permiit closed 9-25
D-HWP803 | Lakeland | 2025-09-30 | Brothers | 2025-08-11 | Anthony | PLK97105 | 62 | Completed on Track | Received | 2025-08-11 | Yes | 56807.95 | 56716 |  | 56716 | Yes | Completed | 2025-08-11 | 3787 | 4670 | 123% | 2025-08-19 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | Needs City Permit, Just Email/start 8-21/8-25 complete/walkout scheduled for 9-9. 10/21 D-HWP803 COP complete
D-HWP805 | Lakeland | 2025-09-30 | Brothers | 2025-08-13 | Anthony | PLK97109 | 85 | Completed on Track | Received | 2025-08-13 | Yes | 59869.5 | 67514 |  | 67514 | Yes | Completed | 2025-08-13 | 4537 | 4604 | 101% | 2025-08-25 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | permit receved 8-13/dispatched 8-13/cx started 8-25/moved to 826 for priorities/cx in progress 9-3(stingray spl 9-3)/ walk out schedule 9-9/permit closed 9-25. 10/21 COP IP
D-HWP809 | Lakeland | 2025-09-30 | Brothers | 2025-08-27 | Anthony | PLK97122 | 72 | Completed on Track | Received | 2025-08-28 | Yes | 50874.95 | 40948 |  | 40948 | Yes | Completed | 2025-08-28 | 3012 | 3012 | 100% | 2025-09-16 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | Needs City Permit, Just Email. 8/29 Permit Received./cx start 9-16/cx sch completion 9-18 / 9/19-resto/proofing/fdh scheduled to comp 9.23/permit closed 9-25
D-HWP811 | Lakeland | 2025-09-30 | Brothers | 2025-08-27 | Anthony | PLK97116 | 66 | Completed on Track | Received | 2025-08-28 | Yes | 44896.1 | 33021 |  | 33021 | Yes | Completed | 2025-08-28 | 2385 | 2385 | 100% | 2025-09-18 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | Needs City Permit, Just Email. 8/29 Permit Received./cx start sch 9-18 / 9/19-cx IP ECD 9.23/permit closed 9-25. 10/21 COP IP/ COP submitted 11-4-2025
D-HWP812 | Lakeland | 2025-07-30 | Brothers | 2025-07-01 | Travis | PLK97117 | 77 | Completed on Track | Received | 2025-07-02 | Yes | 10430.55 | 37639.8 |  | 37639.8 | Yes | Completed | 2025-07-02 | 2773 | 2659 | 96% | 2025-07-21 | 100% | 100% | 100% | 2025-08-06 | 2025-08-06 | Needs City Permit, Just Email
D-HWP813 | Lakeland | 2025-09-30 | Brothers | 2025-09-10 | Anthony | PLK97686 | 87 | Completed on Track | Received | 2025-09-12 | Yes | 60115.95 | 58210 |  | 58210 | Yes | Completed | 2025-09-08 | 4774 | 4605 | 96% | 2025-09-30 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | Have NTP, No permit. Permit Received 9/11/cx start 9-30/SR Blown 9-30/fs complete. / 10/1- CX comp, working on resto / 10/6- tillman walkout complete and passed
D-HWP814 | Lakeland | 2025-07-30 | Brothers | 2025-07-02 | Travis | PLK97122 | 81 | Completed on Track | Received | 2025-07-09 | Yes | 71310.9 | 62984.35 |  | 62984.35 | Yes | Completed | 2025-07-09 | 4940 | 4818 | 98% | 2025-07-16 | 100% | 100% | 100% | 2025-08-06 | 2025-08-06 | need bore logs to finish cop
D-HWP815 | Lakeland | 2025-07-30 | Brothers | 2025-07-01 | Travis | PLK97093 | 86 | Completed on Track | Received | 2025-07-02 | Yes | 53605.2 | 52185.2 |  | 52185.2 | Yes | Completed | 2025-07-02 | 4009 | 4039 | 101% | 2025-07-24 | 100% | 100% | 100% | 2025-08-06 | 2025-08-06 | Tickets expedited 7-14
D-HWP816 | Lakeland | 2025-09-30 | Brothers | 2025-09-10 | Travis | PLK98762 | 80 | Completed on Track | Received | 2025-09-03 | Yes | 59116.7 | 48615 | 7901 | 56516 | Yes | Completed | 2025-09-03 | 4833 | 4646 | 96.13% | 2025-09-23 | 100% | 100% | 100% | 2026-03-16 | 2026-03-16 | Have NTP, No permit. Permit Received 9/11/cx start 9-25/cx complete 9-09/stingray blow 9-30
D-HWP817 | Lakeland | 2025-12-19 | Longo Underground | 2025-11-13 | Travis | PLK100611 | 67 | Completed on Track | Received | 2025-10-06 | Yes | 38192 | 37810.4 |  | 37810.4 | Yes | Completed | 2025-10-06 | 2845 | 2825 | 99.3% | 2025-12-11 | 100% | 100% | 100% | 2025-12-22 | 2026-02-11 | 8/28 Pending Permit./ Locates called 10-6. 11/13 City Of Lakeland Permit Received./ /ECD CX 12-17 SR SCH 12-19/ FDH/Proofing 12/18/2025/ Light levels Received 12-19
D-HWP818 | Lakeland | 2025-09-30 | Brothers | 2025-09-10 | Anthony | PLK99387 | 67 | Completed on Track | Received | 2025-09-03 | Yes | 40406 | 32259 | 17384.6 | 49643.6 | Yes | Completed | 2025-09-03 | 3895 | 3809 | 97.79% | 2025-09-24 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | Have NTP, No permit. Permit Received 9/11 / start cx 9.24 / 9/29- CX expected to be done today and blow SR on 9.30/fs complete / 10/2- last portion on mckay pending good locates, rest of job is complete/spliced.
D-HWP819 | Lakeland | 2025-12-19 | Longo Underground | 2025-11-13 | Travis | PLK100616 | 68 | Completed on Track | Received | 2025-10-06 | Yes | 37755.6 | 29346.6 | 4292.2 | 33638.8 | Yes | Completed | 2025-10-06 | 2584 | 2584 | 100% | 2025-12-09 | 100% | 100% | 100% | 2025-12-22 | 2026-02-11 | 8/28 Pending Permit./ Locates called 10-6. 11/13 City Of Lakeland Permit Received./CX Complete SR SCH 12-19/ Light levels Received 12-19
D-HWP820 | Lakeland | 2025-12-19 | Longo Underground | 2025-11-13 | Travis | PLK105377 | 28 | Completed on Track | Received | 2025-11-11 | Yes | 27615.5 | 21572 | 6990.4 | 28562.4 | Yes | Completed | 2025-11-18 | 2027 | 2146 | 105.9% | 2025-12-03 | 100% | 100% | 100% | 2025-12-22 | 2026-02-11 | 9/4 Pending Permit. 11/13 City Of Lakeland Permit Received.12/2 Locates cleared./ Crossing SCH 12-15 to complete CX SR SCH 12-19/ Path completed, FDH/Proofing 12/18/2025/ Light Levels received 12-19
D-HWP821 | Lakeland | 2025-07-30 | Brothers | 2025-06-25 | Anthony | PLK96634 | 66 | Completed on Track | Received | 2025-06-25 | Yes | 32940.45 | 43258.2 |  | 43258.2 | Yes | Completed | 2025-06-25 | 2067 | 2937 | 142% | 2025-07-02 | 100% | 100% | 100% | 2025-08-28 | 2025-08-28 | dispatched 6-25,start eta 7.3 / 7/2 Brothers drilled 355' and drill broke down, will resume next week.
D-HWP822 | Lakeland | 2025-07-30 | Brothers | 2025-07-01 | Travis | PLK97098 | 43 | Completed on Track | Received | 2025-07-02 | Yes | 23404.75 | 18702.4 |  | 18702.4 | Yes | Completed | 2025-07-02 | 1667 | 1661 | 100% | 2025-07-15 | 100% | 100% | 100% | 2025-09-16 | 2025-09-16 | Needs City Permit, Just Email/ Assigned to Brothers 7-1/ 7/3- need city permit / 7/9- Pending clear locates, ESD 7/14-15/need light levels to complete cop/
D-HWP823 | Lakeland | 2025-09-30 | Brothers | 2025-09-10 | Travis |  | 54 | Completed on Track | Received | 2025-09-03 | Yes | 27186 | 21155 | 5696 | 26851 | Yes | Completed | 2025-09-03 | 2084 | 2039 | 98% | 2025-09-18 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | 8/20 Pending Permit. Permit Received 9/11/cx sch start 9-18/cx complete/stingray blow 9-30
D-HWP824 | Lakeland | 2025-08-30 | Brothers | 2025-08-18 | Anthony | PLK100224 | 73 | Completed on Track | Received | 2025-08-18 | Yes | 37930 | 38208 |  | 38208 | Yes | Completed | 2025-08-18 | 2649 | 2678 | 101% | 2025-08-26 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | construction start 8-26/cx complete/walkout with tillman complete 9-2
D-HWP825 | Lakeland | 2025-08-30 | Longo Underground | 2025-08-18 | Anthony | PLK100282 | 70 | Completed on Track | Received | 2025-08-18 | Yes | 69889 | 49412 | 0 | 49412 | Yes | Completed | 2025-08-18 | 3836 | 3836 | 100% | 2025-08-27 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | 8/20 Project Received./waiting on locates 8-26/cx in progress 9-2/cx complete 9-4/ Walkout schedule 9-9/permit closed 9-25
D-HWP826 | Lakeland | 2025-08-30 | Brothers | 2025-08-18 | Travis | PLK100281 | 84 | Completed on Track | Received | 2025-08-18 | Yes | 52110 | 44802.8 |  | 44802.8 | Yes | Completed | 2025-08-18 | 4071 | 4043 | 99% | 2025-08-26 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | construction start 8-26/ Construction Complete 9-2
D-HWP827 | Lakeland | 2025-09-30 | Brothers | 2025-08-27 | Anthony |  | 87 | Completed on Track | Received | 2025-08-28 | Yes | 52204 | 41495 |  | 41495 | Yes | Completed | 2025-08-27 | 4048 | 5120 | 126% | 2025-09-10 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | 8/20 Pending Permit. 8/29 Permit Received. 9-10 CX started/ cx sch completion 9-18 / 9/24- cx comp, tillman walk comp, SR rts/permit closed 9-25
D-HWP901 | Lakeland | 2025-12-15 | Brothers | 2025-12-08 | Travis | PLK100635 | 87 | Completed on Track | Received | 2025-12-08 | Yes | 74384 | 70635.4 |  | 70635.4 | Yes | Completed | 2025-12-08 | 6130 | 5915 | 96.49% | 2025-12-15 | 100% | 100% | 100% | 2026-06-03 | 2026-06-03 | 8/26 Pending Permit./ 12/11 Pending City Permit/ 12-15 CX Start./
D-HWP902 | Lakeland | 2025-07-24 | Brothers | 2025-04-11 | Travis | PLK93385 | 62 | Completed on Track | Received | 2025-04-15 | Yes | 62502 | 59129.5 |  | 59129.5 | Yes | Completed | 2025-04-15 | 5008 | 4791 | 95.67% | 2025-05-06 | 100% | 100% | 100% | 2025-06-23 | 2025-06-23
D-HWP903 | Lakeland | 2025-07-24 | Brothers | 2025-04-11 | Travis | PLK93393 | 89 | Completed on Track | Received | 2025-04-15 | Yes | 70705.5 | 67666 |  | 67666 | Yes | Completed | 2025-04-15 | 5203 | 5333 | 102.5% | 2025-04-29 | 100% | 100% | 100% | 2025-06-10 | 2025-06-10
D-HWP904 | Lakeland | 2025-07-24 | Brothers | 2025-04-11 | Travis | PLK93379 | 87 | Completed on Track | Received | 2025-04-15 | Yes | 66004.5 | 64943.5 |  | 64943.5 | Yes | Completed | 2025-04-15 | 5120 | 5340 | 104.3% | 2025-05-05 | 100% | 100% | 100% | 2025-06-10 | 2025-06-10
D-HWP905 | Lakeland | 2025-07-30 | Brothers | 2025-05-09 | Travis | PLK94794 | 60 | Completed on Track | Received | 2025-05-13 | Yes | 57237 | 55777 |  | 55777 | Yes | Completed | 2025-05-13 | 4508 | 4426 | 98.18% | 2025-06-04 | 100% | 100% | 100% | 2025-06-26 | 2025-06-26 | DISPATCHED 5-9/ Locates called 5-12/Tillman Walkout completed 6-13/need other jobs done to pull fiber and splice in
D-HWP906 | Lakeland | 2025-12-15 | Brothers | 2025-11-18 | Anthony | PLK105397 | 28 | Completed on Track | Received | 2025-11-18 | Yes | 29683 | 31275.4 |  | 31275.4 | Yes | Completed | 2025-11-18 | 2416 | 2533 | 104.8% | 2025-12-03 | 100% | 100% | 100% | 2025-12-09 | 2025-12-18 | 9/22 Pending Permit./ Permit released 11/10/2025/Cx started 12-3-2025/ 12/4 CX Construction Started--Progress At 57% Complete./ 12-8 CX complete, Blowing stingray./ 12/9 12 Ct Fiber Placed with Trace Wire, and 1 Stingray./12/10 Stingray Spliced
D-HWP907 | Lakeland | 2025-12-15 | Brothers | 2025-12-15 | Travis | PLK100638 | 21 | Completed on Track | Received | 2025-12-15 | Yes | 20891 | 21223.4 |  | 21223.4 | Yes | Completed | 2025-12-15 | 1820 | 1714 | 94% | 2026-01-06 | 100% | 100% | 100% | 2026-01-12 | 2026-03-31 | 8/20 Pending Permit. LC called 12-22/ CX started 1-6/ 1/6 CX Construction Started--Progress At 63% Complete./ 1/7 CX Construction Continues--Progress At 73% Complete./ 1/13 CX Construction Continues--12F Stingray Installed./ 1/14 CX Construction Continues--FDH Installed.
D-HWP908 | Lakeland | 2025-09-30 | Brothers | 2025-09-15 | Anthony |  | 53 | Completed on Track | Received | 2025-09-12 | Yes | 47676 | 39345 | 8362.4 | 47707.4 | Yes | Completed | 2025-09-12 | 4022 | 3933 | 98% | 2025-10-01 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | 8/20/Pending Permit.Permit Received 9/11. 9/12 - cl wl dt complete. / 9/18- still pending water / 9/29- still pending water. / 10/2- CX to start today / 10/6- cx ip. 10/13 cx comp/sr rts.
D-HWP909 | Lakeland | 2025-10-15 | Brothers | 2025-10-15 | Miguel |  | 59 | Completed on Track | Received | 2025-10-03 | Yes | 44697.6 | 35278.6 | 9125.4 | 44404 | Yes | Completed | 2025-10-03 | 3495 | 3448 | 99% | 2025-10-15 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | 9/8 Pending Permit./ Locates called 10-3. 10/7 Permit Received./ Cx started 10-15-2025/ 10/21 path comp, wtg on D911 for sting/ Stingray done 10-31-2025/COP submitted 11-4-2025/Tillman walkout completew , Passed
D-HWP910 | Lakeland | 2025-10-30 | Brothers | 2025-09-15 | Anthony |  | 82 | Completed on Track | Received | 2025-09-12 | Yes | 82621.15 | 71681.4 |  | 71681.4 | Yes | Completed | 2025-09-12 | 5653 | 5653 | 100% | 2025-10-02 | 100% | 100% | 100% | 2026-03-24 | 2026-03-24 | 8/25 Pending Permit.Permit Received 9/11. 9/12 - cl wl dt complete. / 9/18- still pending water / 9/29- still pending water/construction start 10-1 / 10-1 CX started / 10/6- cx ip
D-HWP911 | Lakeland | 2025-10-30 | Brothers | 2025-10-06 | Miguel |  | 35 | Completed on Track | Received | 2025-10-03 | Yes | 26026 | 26295.6 |  | 26295.6 | Yes | Completed | 2025-10-03 | 2071 | 2072 | 100% | 2025-10-28 | 100% | 100% | 100% | 2025-11-10 | 2025-11-10 | 8/26 Pending Permit. / 10/6- loc called 10/3. 10/7 Permit Received./ Pending Locates 10-20-2025/ 10/21 starting next week, SR fed from D-HWP914 pending completion of D-HWP914/Cx starts 10-28-2025/ Cx completed. Stingray ISSUES 10-31/SCH REPAIR 11-3/COP submitted 11/5/2025/ Tillman walkout competed and Passed
D-HWP912 | Lakeland | 2025-10-30 | Brothers | 2025-10-20 | Miguel |  | 82 | Completed on Track | Received | 2025-10-03 | Yes | 58864 | 61054 |  | 61054 | Yes | Completed | 2025-10-03 | 4747 | 4925 | 104% | 2025-10-21 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | 9/3 Pending Permit./ Locates called 10-3. 10/7 Permit Received.Pending Locates 10-16/ Locates clear 10/20/Assigned to Brothers 10-20-2025/ 10/21 CX START. SR fed from D-HWP913/Cx completed 10-28-2025
D-HWP913 | Lakeland | 2025-10-15 | Brothers | 2025-10-02 | Anthony |  | 34 | Completed on Track | Received | 2025-10-03 | Yes | 29646 | 30169.8 |  | 30169.8 | Yes | Completed | 2025-10-03 | 2188 | 2278 | 104.1% | 2025-10-01 | 100% | 100% | 100% | 2026-03-24 | 2026-03-24 | 9/26Pending Permit./Loacets Called 10-3. 10/7 Permit Received. 10/13 cx started./ 10/21 city permit complete, will return to complete tobies/SR upon completion of FB-HWP901. / 10/30 - cx complete, stingray to be blown on 10/31./COP submitted 11-6-20258/ Tillman Walkout completred and passed
D-HWP914 | Lakeland | 2025-10-30 | Brothers | 2025-10-02 | Travis |  | 79 | Completed on Track | Received | 2025-10-03 | Yes | 45014 | 44739.6 |  | 44739.6 | Yes | Completed | 2025-10-03 | 3378 | 3372 | 99.82% | 2025-10-28 | 100% | 100% | 100% | 2025-11-06 | 2026-02-11 | 10/21 starting next week. Reassigned to Brothers. Fed from 913.Cx started 10-28-2025
D-HWP915 | Lakeland | 2025-10-30 | Brothers | 2025-10-06 | Travis |  | 75 | Completed on Track | Received | 2025-10-06 | Yes | 38796 | 37566 |  | 37566 | Yes | Completed | 2025-10-06 | 2874 | 2875 | 100% | 2025-10-14 | 100% | 100% | 100% | 2025-11-06 | 2026-04-01 | 8/28 Pending Permit. Locates and whitelined 10-6. 10/7 Permit Received. 10/14 CX Started. 10/21 path complete, will return for SR after D914 completion.11/7 COP Sent
D-HWP916 | Lakeland | 2025-11-15 | Brothers | 2025-10-29 | Miguel |  | 61 | Completed on Track | Received | 2025-11-01 | Yes | 35050 | 34279.8 |  | 34279.8 | Yes | Completed | 2025-10-31 | 2527 | 2647 | 104.7% | 2025-11-12 | 100% | 100% | 100% | 2025-12-07 | 2026-03-24 | 9/3 Peding Permit/ Permit received,/Locates called White lined, door tagged 11-1-2025/Cx started 11-12-2025/FDH and ABF proofing scheduled for friday 11-21-2025
D-HWP917 | Lakeland | 2025-11-15 | Brothers | 2025-10-29 | Treyvon |  | 69 | Completed on Track | Received | 2025-11-01 | Yes | 37418 | 28949 | 11240.4 | 40189.4 | Yes | Completed | 2025-10-31 | 2851 | 2925 | 103% | 2025-11-12 | 100% | 100% | 100% | 2026-12-07 | 2026-04-01 | 9/3 Pending Permit./Permit received,/ Locates called, white lined and door tagged 11-1-2025/Cx starts 11-12-2025/
D-HWP918 | Lakeland | 2025-11-15 | Brothers | 2025-10-28 | Miguel |  | 48 | Completed on Track | Received | 2025-10-24 | Yes | 54228.7 | 54969 |  | 54969 | Yes | Completed | 2025-10-23 | 4141 | 4316 | 104.2% | 2025-11-03 | 100% | 100% | 100% | 2025-12-07 | 2026-02-12 | 9/10 Pending Permit.Locates called 10-23/Whitelined 10-24, Cx started 11-3-2025/Cx done/ Light Levels Received 11-14-2025/Locates called for stingray path to D-HWP904 cleared 11-29-2025
D-HWP919 | Lakeland | 2025-06-30 | J Garcia Underground | 2026-03-03 | Travis | PLK105401 | 26 | Completed on Track | Received | N/A | Yes | 12781.6 | 9788.85 |  | 9788.85 | Yes | Completed | 2026-03-03 | 937 | 923 | 99% | 2026-03-17 | 100% | 100% | 100% | 2026-03-31 | 2026-03-31 | 11/7 Pending Permit./Locates caleed 3-3-2026/Permit Recieved 3-4-2026/Locates clear 3-16/Cx starts 3-17/Cx Completed 3-18/ Spliced scheduled
D-HWP1003 | Lakeland | 2025-12-15 | Brothers | 2025-12-30 | Travis | PLK105403 | 85 | Completed on Track | Received | 2026-01-05 | Yes | 38323.55 | 38080 |  | 38080 | Yes | Completed | 2025-12-30 | 2691 | 2740 | 102% | 2026-01-07 | 100% | 100% | 100% | 2026-01-12 | 2026-02-09 | 9/3 Pending Permit. LC 12/30/ CX Complete--12F Stingray Placed
D-HWP1004 | Lakeland | 2025-12-15 | Brothers | 2025-12-30 | Travis | PLK105404 | 87 | Completed on Track | Received | 2026-01-05 | Yes | 63322.45 | 52829.45 | 14838.85 | 67668.3 | Yes | Completed | 2025-12-30 | 5030 | 5102 | 101% | 2026-01-07 | 100% | 100% | 100% | 2026-01-21 | 2026-02-09 | 8/26 Pending Permit. LC 12/30/ path complete 1-15/ FDH set and proofed 1-20/ 1-20 FDH Ground Rod Swing Arm Installed.
D-HWP1005 | Lakeland | 2026-01-30 | Brothers | 2025-12-30 | Miguel | PLK105405 | 88 | Completed on Track | Received | 2025-12-30 | Yes | 77109.5 | 75843.2 |  | 75843.2 | Yes | Completed | 2025-12-30 | 6325 | 6251 | 99% | 2026-01-21 | 100% | 100% | 100% | 2026-02-09 | 2026-02-09 | LC 12/30/ 1-21 CX started/ 1/21 CX Construction Started/ 2/2 FDH Installed./Splicng scheduled for 2-3-2026
D-HWP1006 | Lakeland | 2026-01-30 | Longo Underground | 2025-12-30 | Miguel | PLK104098 | 58 | Completed on Track | Received | 2025-12-30 | Yes | 58952.88 | 55647.74 |  | 55647.74 | Yes | Completed | 2025-12-30 | 4731 | 4579 | 97% | 2026-01-21 | 100% | 100% | 100% | 2026-02-09 | 2026-02-09 | 9/3 Pending Permit. LC 12/30/ 1-21 CX started./ 1/21 CX Construction Started/ Splicng scheduled for 2-3-2026
D-HWP1007 | Lakeland | 2026-01-30 | Brothers | 2026-01-23 | Miguel | PLK105406 | 69 | Completed on Track | Received | 2026-01-05 | Yes | 41834.75 | 42897.7 |  | 42897.7 | Yes | Completed | 2026-01-05 | 3183 | 3121 | 98% | 2026-01-26 | 100% | 100% | 100% | 2026-02-09 | 2026-02-09 | 9/3 Pending Permit. LC 1-5 / 1/23 Permit Received./ 1-26 CX Started/ 1/27 CX Construction Started/ 2/2 FDH and 12F Stingray Installed. Splicing 2/3
D-HWP1303 | Lakeland | 2026-02-20 | Brothers | 2026-01-23 | Travis |  | 81 | On Track | Received | 2026-01-05 | Yes | 53152.33 | 52394.05 | 170 | 52564.05 | Yes | Completed | 2026-01-05 | 3323 | 3445 | 104% | 2026-02-03 | 100% | 100% | 100% | 2026-03-20 | 2026-03-20 | 12/8 Pending Permit. LC 1-5/cx start 2-3/ 2/3 CX Construction Started--96F Placed./ 2/12 CX Construction Complete...12F Stingray Installed.
D-HWP1304 | Lakeland | 2025-09-25 | Brothers | 2025-04-08 | Anthony | PLK93497 | 82 | Completed on Track | Received | 2025-04-09 | Yes | 67171.5 | 64739 |  | 64739 | Yes | Completed | 2025-04-09 | 5373 | 5300 | 98.64% | 2025-04-28 | 100% | 100% | 100% | 2025-06-10 | 2025-06-10
D-HWP1306 | Lakeland | 2025-09-25 | LSCG | 2025-04-02 | Anthony | PLK92368 | 79 | Completed on Track | Received | 2025-04-02 | Yes | 72492 | 73087.5 |  | 73087.5 | Yes | Completed | 2025-04-02 | 5941 | 5972 | 100.5% | 2025-04-14 | 0% | 0% | 0% | 2025-06-26 | 2025-06-26
D-HWP1307 | Lakeland | 2025-11-30 | Brothers | 2025-10-06 | Miguel |  | 83 | Completed on Track | Received | 2025-10-06 | Yes | 96748 | 83497.4 |  | 83497.4 | Yes | Completed | 2025-10-06 | 6240 | 6197 | 99.31% | 2025-10-21 | 100% | 100% | 100% | 2025-12-07 | 2025-12-07 | 8/18 Pending Permit. Locates and whitelined 10-6. 10/7 Permit Received. Pending Locates 10-16/ Locates clear. Cx started, needs path/48f and will be fed from existing 13w./not completed 10-28/needs 2 crossings for county 11-10-25/Cx completed 11-10-2025./Stingray placed to D-HWP1302, Pendimg Fiber pulled. Pending Sr placed to D-HWP1309/
D-HWP1309 | Lakeland | 2025-09-25 | Brothers | 2025-04-02 | Travis | PLK92363 | 59 | Completed on Track | Received | 2025-04-03 | Yes | 51295 | 51485.5 |  | 51485.5 | Yes | Completed | 2025-04-03 | 4122 | 4138 | 100.4% | 2025-04-17 | 100% | 100% | 100% | 2025-06-10 | 2025-06-10
D-HWP1310 | Lakeland | 2025-09-30 | Brothers | 2025-08-15 | Anthony |  | 69 | Completed on Track | Received | 2025-08-15 | Yes | 67441 | 55265.7 | 0 | 55265.7 | Yes | Completed | 2025-08-15 | 4348 | 4122 | 95% | 2025-08-26 | 100% | 100% | 100% | 2025-10-02 | 2025-10-02 | Disp. 8/15- Locates called 8-15/pass through completed, spl sch 8-29/cx in progress 9-3/ cx complete 9-8/ Stingray Blown 9-10/permit closed 9-25
D-HWP1311 | Lakeland | 2025-11-30 | Brothers | 2025-11-05 | Travis | PLK104494 | 69 | Completed on Track | Received | 2025-11-08 | Yes | 75672.1 | 70222.4 |  | 70222.4 | Yes | Completed | 2025-11-08 | 5654 | 5654 | 100% | 2025-11-17 | 100% | 100% | 100% | 2025-12-07 | 2025-12-09 | 10/15 Pending Permit./LC 11/8/2025/LC cleared 11-13-2025. 11/13 City Of Lakeland Permit Received/Cx starts 11-17-2025 /Path completed 11-24-2025/48ct Fiber pulled 11-28-2025. Pending splice//Stingray scheduled for 12-5-2025/Light levels received
D-HWP1312 | Lakeland | 2025-12-10 | Brothers | 2025-11-05 | Travis | PLK104413 | 88 | Completed on Track | Received | 2025-11-06 | Yes | 76565.85 | 74825.6 |  | 74825.6 | Yes | Completed | 2025-11-06 | 6025 | 6130 | 101.7% | 2025-11-24 | 100% | 100% | 100% | 2025-12-07 | 2025-12-09 | 9/15 Pending Permit.LC 11-6. 11/14 County Permit Received./Cx starts 11-17-2025 (County )Cx started 11-24-2025/Path completed 12-1-2025//Stingray scheduled for 12-5-2025/ 12-10-2025 Stingray Installed Pending Splicing./Light levels received. 12/15 CX Construction Path 100% Completed--Handhole and FDH Installed.
D-HWP1313 | Lakeland | 2025-11-30 | Brothers | 2025-11-05 | Travis | PLK104491 | 83 | Completed on Track | Received | 2025-11-08 | Yes | 66402 | 53621 | 10950.2 | 64571.2 | Yes | Completed | 2025-11-08 | 5324 | 5304 | 100% | 2025-11-18 | 100% | 100% | 100% | 2025-12-07 | 2026-02-10 | 8/26 Pending Permit./LC 11/8/2025. 11/13 City Of Lakeland Permit Received./Cx starts 11-18-2025/Cx path completed 11-24-2025/Stingray scheduled for 12-5-2025/Stingray placed 12-10-2025/Light levels received
D-HWP1314 | Lakeland | 2025-11-30 | Brothers | 2025-11-05 | Miguel | PLK105218 | 75 | Completed on Track | Received | 2025-11-06 | Yes | 60620 | 55563.8 |  | 55563.8 | Yes | Completed | 2025-11-06 | 4814 | 4708 | 97.8% | 2025-11-25 | 100% | 100% | 100% | 2025-12-07 | 2025-12-10 | 8/28 Pending Permit. LC 11-6/Permir recieved 11-18-2025/Cx Starts 11-25-2025/Cx 855' of Bore job at 41% Complete 11-26-2025/12/01 CX Construction Continues--Progress At 74% Complete/ 12/02 CX Construction Continues--Progress At 98% Complete./ Path completed 12-2-2025/ HH/FDH will be done Fri 12-5-2025//Stingray scheduled for 12-5-2025
D-HWP1315 | Lakeland | 2025-12-10 | Brothers | 2025-11-05 | Travis | PLK105455 | 77 | Completed on Track | Received | 2025-11-06 | Yes | 63997.35 | 52838.35 | 7744.05 | 60582.4 | Yes | Completed | 2025-11-06 | 5053 | 4652 | 92% | 2025-12-04 | 100% | 100% | 100% | 2025-12-18 | 2026-02-10 | 9/10 Pending Permit. LC 11-6/Permit released 12-3-2025/Cx starts 12-4-2025
D-HWP1316 | Lakeland | 2025-12-10 | Brothers | 2025-12-18 | Travis | PLK105457 | 48 | Completed on Track | Received | 2025-11-04 | Yes | 18021.7 | 16738 |  | 16738 | Yes | Completed | 2025-11-04 | 1111 | 1188 | 106.9% | 2025-12-29 | 100% | 100% | 100% | 2026-01-23 | 2026-02-10 | 8/20 Pending Permit.LC 11-4/Refreshed Locates 12-18-2025/Cx Starts 12-29-2029/Cx Completed 12-29-2025/ Placing Stingray 12-30/Splicing Scheduled/ 12/30 CX Construction Started--Progress At 100% Complete./ 12/30 CX Construction Complete--Handhole and FDH Installed.
D-HWP1317 | Lakeland | 2025-12-10 | Brothers | 2025-12-18 | Travis | PLK105460 | 56 | Completed on Track | Received | 2025-11-04 | Yes | 20705 | 14769.6 |  | 14769.6 | Yes | Completed | 2025-11-04 | 900 | 900 | 100% | 2025-12-29 | 100% | 100% | 100% | 2026-01-03 | 2026-02-11 | 8/20 Pending Permit.LC 11-4/Refreshed Locates 12-18-2025/Cx Starts 12-29-2029/ 12/30 CX Construction Started--Progress At 58% Complete./Cx Completed 12-29-2025/ Placing Stingray 12-30/Splicing Scheduled / 12/30 CX Complete...Placed 12F Stingray.
FB-HWP101 | Lakeland | 2025-01-31 | Power Connect /SB/LS | 2025-01-27 | Anthony | PLK88377 | 0 | Completed | Received | 2025-01-16 | Yes | 24886.5 | 7262 |  | 7262 | Yes | Completed | 2025-01-16 | 330 | 330 | 100% | 2025-01-27 | 100% | 100% | 100% | 2025-06-13 | 2025-06-13
FB-HWP175 | Lakeland | 2025-07-30 | Brothers | 2025-07-11 | Travis |  | 0 | Completed on Track | Received | 2025-07-10 | Yes | 23436.55 | 15484.65 |  | 15484.65 | Yes | Completed | 2025-07-10 | 1743 | 924 | 53% | 2025-07-16 | 100% | 100% | 100% | 2025-09-15 | 2025-09-15
FB-HWP375 | Lakeland | 2025-08-30 | Lightspeed In-House | 2025-08-07 | Travis | PLK100177 | 0 | Completed on Track | Received | 2025-08-07 | Yes | 1462.85 | 5035.75 |  | 5035.75 | Yes | Completed | 2025-08-07 | 116 | 130 | 112% | 2025-08-27 | 100% | 100% | 100% | 2025-09-26 | 2025-09-26 | white lined + call loc 8-7/startred 8-25/need soft dig/spl sch for 8-28 pm
FB-HWP377 | Lakeland | 2025-10-29 | Brothers | 2025-10-31 | Miguel |  | 0 | Completed on Track | Received | N/A | Yes | 15670.45 | 12965 |  | 12965 | Yes | Completed | 2026-01-09 | 1202 | 1208 | 100% | 2026-01-13 | 100% | 100% | 100% | 2026-01-21 | Pending Tillman QC Form | 1/13 CX Construction Started--Progress At 100% Complete.
FB-HWP477 | Lakeland | 2025-08-30 | Splicing Project | 2025-08-07 | Anthony | PLK97348 | 0 | Completed on Track | Received | N/A | Yes | 1343 | 2310 |  | 2310 | Yes | Completed | Not Required | 74 | 0 | 0% | Not Required | 0% | 0% | 0% | Not Required | Not Required | 6/24 Pending Permit.
FB-HWP478 | Lakeland | 2026-04-05 | Brothers | 2026-03-19 | Travis | PLK105467 | 0 | Completed on Track | Received | N/A | Yes | 13022.05 | 10438.05 |  | 10438.05 | Yes | Completed | 2026-03-16 | 923 | 918 | 99% | 2026-03-25 | 0% | 0% | 0 | 2026-05-27 | 2026-05-27
FB-HWP480 | Lakeland | 2025-09-30 | Lightspeed In-House | 2025-09-02 | Travis |  | 0 | Completed on Track | Received | 2025-09-02 | Yes | 5604.6 | 7746.35 |  | 7746.35 | Yes | Completed | 2025-09-02 | 328 | 335 | 102% | 2025-09-22 | 100% | 100% | 0 | 2025-11-11 | 2025-11-11 | 9-2 permit received/locates called 9-2/Locates clear 9-9
FB-HWP482 | Lakeland | 2025-08-30 | Brothers | 2025-08-01 | Anthony | PLK97720 | 0 | Completed on Track | Received | 2025-08-01 | Yes | 49307.5 | 47409 |  | 47409 | Yes | Completed | 2025-08-01 | 3914 | 3675 | 94% | 2025-08-04 | 100% | 100% | 100% | 2025-09-16 | 2025-09-16 | Have County, Need City./ 7-23 Assigned county work to Brothers. Need LOCs so we can activate cnty permit/ Conuty sch 8-4, 8/1- city locates called by Brothers
FB-HWP483 | Lakeland | 2025-11-14 | LightSpeed In-House | 2025-11-21 | Travis | PLK104995 | 0 | Completed on Track | Received | 2025-11-07 | Yes | 12840.7 | 12272.4 |  | 12272.4 | Yes | Completed | 2025-10-07 | 911 | 974 | 106.9% | 2025-11-24 | 100% | 100% | 100% | 2025-12-10 | 2025-12-18
FB-HWP484 | Lakeland | 2025-01-18 | Brothers | 2025-12-15 | Miguel |  | 0 | Completed on Track | Received | 2025-12-15 | Yes | 45512.75 | 52537 |  | 52537 | Yes | Completed | 2025-12-15 | 3675 | 3820 | 104% | 2026-01-05 | 100% | 100% | 100% | 2026-01-07 | Pending Tillman QC Form | 12/5 FDOT Permit Received--Pending Fiber Details Splicing Document./LC called and door tagged 12/15/2025/ CX started 1-5/
FB-HWP701 | Lakeland | 2025-05-28 | Brothers | 2025-02-07 | Anthony | PLK89265 | 0 | Completed on Track | Received | 2025-02-17 | Yes | 88491.8 | 85791.25 |  | 85791.25 | Yes | Completed | 2025-02-17 | 7207 | 6778 | 94.05% | 2025-03-05 | 100% | 100% | 100% | 2025-08-29 | 2025-08-29 | gave to power connect 2-17-25/START 2-26/exp 811 2-26/not clear 3-4@730am/3-4 3rd notice called into to 811 8am/ partial locates work sch 3-5 tin in to 713 locates not complete 3-4 @3pm/ Expedited 4pm 3-4/*do not build peice ro 703(ada x-ing)/ Expedited locates 4pm 3-5/pending zayo marks 3-7/talked to state manager for zayo, he is dending them asap to locate/Zayo marked. 3-10 Power connect drilling, Returning 3-11 to connect Griffin Rd to N Florida and pull 48f. 3/12-IP, 100' left to bore on Kalt Dr. to tie in D-HWP713, 48f pull. 3/13- x-ing at Martha call locates 3-13 for ls to complete/. 3/13- locs called/whitelined, IH crew to dig up 144 and place 48f so D701,D705 and D702 can be heated up. 3/17- still pending clear loc for Martha(will expedite tmrw), Tillman aprvd a bore to get a 48f from FB to D701 loc called 3.14./504' 4-10/dot sch for 5-13 9am/ 5/7- DOT Xing scheduled for Tuesday 5/13. Expedited tickets 5-8*fs sch 5-22/ DOT crossing sch 5-20. 5/14 1190' today, will return on 5/20 to complete remaining path. / 5/19 Brothers said they were doing this bore on 5.20 and made a mistake with the date, it is scheduled for 5.21 and the fiber to be pulled in on the same day. / 6/5- Tillman walking today
FB-HWP775 | Lakeland | 2025-08-30 | Brothers | 2025-08-01 | Anthony | PLK98767 | 0 | Completed on Track | Received | 2025-08-01 | Yes | 12886.4 | 18418.35 |  | 18418.35 | Yes | Completed | 2025-08-01 | 884 | 797 | 90% | 2025-08-07 | 100% | 100% | 100% | 2025-09-16 | 2025-09-16 | Need city, App only. 8/1- Had Brothers call in locates for this and 12 Oaks MHP.
FB-HWP776 | Lakeland | 2025-08-30 | Brothers | 2025-08-13 | Anthony | PLK99777 | 0 | Completed on Track | Received | 2025-08-13 | Yes | 13056.5 | 15624.85 |  | 15624.85 | Yes | Completed | 2025-08-13 | 1100 | 1110 | 101% | 2025-08-18 | 100% | 100% | 100% | 2025-09-26 | 2025-09-26 | permit received 8-13/dispatched 8-13 / 8-21 placing complete, ready to splice. Tillman's MDU portion may not be placed./spl sch 8-28pm
FB-HWP801 | Lakeland | 2025-06-30 | Brothers | 2025-05-09 | Anthony | PLK94839 | 0 | Completed on Track | Received | 2025-05-13 | Yes | 63283 | 84546.7 |  | 84546.7 | Yes | Completed | 2025-05-13 | 5776 | 5776 | 100% | 2025-05-19 | 100% | 100% | 100% | 2025-07-08 | 2025-07-08 | Dispatched 5-9/Door Tag 5-14 & whitelned 5-13 / 5/19 Both permits received, requested ticket info from Brothers. 5/19 Brothers 644', return tmrw/ 5/20 Brothers drilling 1430' 3 HH., return on 5/21. Brother drilling 970', DOT Xing sched 5/27 9am. / 5/27 DOT Xing comp. Brothers 948' 3 HH. / 6/2- 1957' 8 HH. Will QC on 6.3 and brothers is getting back to LS on fiber sched. / 6/5- fiber placed, scheduling Tillman walkout for 6-6 / 10/3 COP revised and complete
FB-HWP802 | Lakeland | 2025-09-30 | Lightspeed In-House | 2025-07-30 | Travis | PLK98828 | 0 | Completed on Track | Received | 2025-07-30 | Yes | 14179.65 | 15936.8 |  | 15936.8 | Yes | Completed | 2025-07-30 | 973 | 1060 | 109% | 2025-08-11 | 100% | 100% | 100% | 2025-09-26 | 2025-09-26 | white lined + Loc called 7-30/sch to start 8-11/
FB-HWP804 | Lakeland | 2025-07-30 | Lightspeed In-House | 2025-07-15 | Travis | PLK97717 | 0 | Completed on Track | Received | 2025-07-15 | Yes | 68216.5 | 243 | 9558.8 | 9801.8 | Yes | Completed | 2025-07-15 | 581 | 581 | 100% | 2025-07-30 | 100% | 100% | 100% | 2025-09-16 | 2025-09-16 | Sch 7-21 with Telecom/ih drilling 7-28/complete
FB-HWP875 | Lakeland | 2025-12-29 | J Garcia Underground | 2026-04-21 | Miguel | PLK98757 | 0 | Completed on Track | Received | N/A | Yes | 17916.55 | 15379.05 |  | 15379.05 | Yes | Completed | 2026-04-14 | 1433 | 1362 | 95.05% | 2026-04-22 | 100% | 0% | 0% | 2026-05-07 | 2026-05-07 | LC called 4-14/ pending water LC 4-20/LC clear 4-21/Cx to start 4-22/CX Complete, Fiber placed 4-30/Pending Splicing 4-30/
FB-HWP879 | Lakeland | 2025-12-19 | J Garcia Underground | 2026-04-21 | Miguel | PLK105480 | 0 | Completed on Track | Received | N/A | Yes | 34863 | 30530.5 |  | 30530.5 | Yes | Completed | 2026-04-14 | 2307 | 2334 | 101.2% | 2026-04-22 | 100% | 0% | 0% | 2026-05-07 | 2026-05-07 | 9/8 Pending Permit. 12/4 Permit Received. LC 12-4/ 12/11 Pending Water Locates 12-15 LC renew 4-14/ Pending Water LC 4-20/LC clear 4-21/Cx to start 4-22/Cx Complete, Fiber Placed 4-30/Pending Splicing 4-30
FB-HWP880 | Lakeland | 2026-01-09 | Brothers | 2025-12-11 | Miguel | PLK105472 | 0 | Completed on Track | Received | N/A | Yes | 23475.5 | 27620.4 |  | 27620.4 | Yes | Completed | 2025-12-08 | 1890 | 2048 | 108.4% | 2025-12-18 | 100% | 100% | 100% | 2026-01-03 | 2026-06-03 | 11/17 Pending Permitand Fiber Details Splicing Document./ 12/11 Pending Locates 12/15/2025/Cx Started 12-18-2025/Path Completed /Placing Fiber 12-24-2025/Splicing Scheduled
FB-HWP882 | Lakeland | 2025-12-12 | Brothers | 2025-12-11 | Miguel |  | 0 | Completed on Track | Received | N/A | Yes | 11500.3 | 12331.25 |  | 12331.25 | Yes | Completed | 2025-12-03 | 908 | 925 | 101.9% | 2025-12-22 | 100% | 100% | 100% | 2026-01-03 | 2026-06-03 | 11/6 FDOT Permit Received With NTP Package. 12/4 Permit Received. LC 12-3/ FDOT sch for 12-17 per locates./ 12/11 Pending Water locates/DOT crossing and Cx starts 12-22-2025/DOT crossing 12-23-2025/Path Completed /Placing Fiber 12-24-2025/Splicing Scheduled
FB-HWP901 | Lakeland | 2025-11-30 | Brothers | 2025-10-23 | Miguel | PLK97705 | 0 | Completed on Track | Received | N/A | Yes | 51970 | 43259 | 16589.25 | 59848.25 | Yes | Completed | 2025-10-23 | 4544 | 4569 | 100.6% | 2025-10-30 | 100% | 100% | 100% | 2026-03-24 | 2026-03-24 | received permit 10-23/called locates and dispatched 10-23/ 10/30 cx started/600 ft will be done on monday./ CX completed 11-10-2025/ Placing fiber 11-11-2025/ Fiber Placed/Fiber spliced 11-14-*2025/
FB-HWP902 | Lakeland | 2025-07-30 | Lightspeed In-House | 2025-07-01 | Travis | PLK97335 | 0 | Completed on Track | Received | 2025-06-30 | Yes | 72566 | 9904.1 |  | 9904.1 | Yes | Completed | 2025-06-30 | 765 | 786 | 103% | 2025-07-07 | 100% | 100% | 100% | 2025-09-16 | 2025-09-16 | Restoration 7-14/passed tillman qc
FB-HWP903 | Lakeland | 2025-10-30 | Lightspeed In-House | 2025-10-15 | Travis | PLK102858 | 0 | Completed on Track | Received | 2025-10-06 | Yes | 4235.8 | 3228.9 |  | 3228.9 | Yes | Completed | 2025-10-09 | 228 | 240 | 105% | 2025-09-26 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | Needs City, App only/ Locates and whitelined 10-6. 10/7 Pending Permit. 10-14 CX Started/ 10/15 work complete/ 10-17 Walkout Complete/10-20 COP Sent
FB-HWP975 | Lakeland | 2025-09-30 | Lightspeed In-House | 2025-09-02 | Travis |  | 0 | Completed on Track | Received | 2025-09-02 | Yes | 3067.9 | 8729.7 |  | 8729.7 | Yes | Completed | 2025-09-02 | 662 | 662 | 100% | 2025-09-09 | 100% | 100% | 100% | 2025-09-26 | 2025-09-26 | 8/28 Pending permit/received permit 9-4/CL 9-2/ cx started 9-9/CX complete 9-11
FB-HWP976 | Lakeland | 2026-07-30 | J. Garcia Underground | 2026-06-29 | Miguel | PLK112262 | 0 | Completed on Track | Received | 2026-06-16 | Yes | 21342.95 | 18048.45 |  | 18048.45 | Yes | Completed | 2026-06-16 | 1667 | 1625 | 97% | 2026-06-30 | 100% | 100% | 100% | 2026-07-15 | 2026-07-15 | 6/15 NTP Package Received/loc called 6-16/Pending Water Locates 6-23/Locates cleared 6-29/Cx start 6-30/
FB-HWP1075 | Lakeland | 2025-09-30 | Lightspeed In-House | 2025-09-02 | Travis |  | 0 | Completed on Track | Received | 2025-09-02 | Yes | 12695 | 10686 | 5458.3 | 16144.3 | Yes | Completed | 2025-09-02 | 1010 | 978 | 97% | 2025-09-11 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | 9-2 permit received/locates called 9-2/Locates clear 9-9/CX started 9-11
FB-HWP1302 | Lakeland | 2025-07-30 | Lightspeed In-House | 2025-07-11 | Travis | PLK97344 | 0 | Completed on Track | Received | 2025-07-10 | Yes | 1206 | 1195 |  | 1195 | Yes | Completed | 2025-07-10 | 90 | 90 | 100% | 2025-07-16 | 100% | 100% | 100% | 2025-08-29 | 2025-08-29 | SCH 7/16
FB-HWP1375 | Lakeland | 2025-08-30 | Lightspeed In-House | 2025-08-13 | Travis | PLK97346 | 0 | Completed on Track | Received | N/A | Yes | 18903.7 | 7007.75 |  | 7007.75 | Yes | Completed | 2025-08-13 | 575 | 575 | 100% | 2025-08-18 | 100% | 100% | 100% | 2025-09-26 | 2025-09-26 | 6/16- need city and county permit/ White lined/loc 8-13/cx start 8-26/spl sch for 8-29/splicing needs complete
FB-HWP1376 | Lakeland | 2025-08-30 | Lightspeed In-House | 2025-05-29 | Travis | PLK96627 | 0 | Completed on Track | Received | 6/16/25 County | Yes | 21888.65 | 21950.85 |  | 21950.85 | Yes | Completed | 2025-06-16 | 1669 | 1701 | 102% | 2025-06-25 | 100% | 100% | 100% | 2025-09-26 | 2025-09-26 | 6/16- whitelines/locates/doortags/County permit activation req sent all on 6/16. 6/18- County permit is active and Xing scheduled for 6/24 11am. Still need city permit for final completion.. 6/24- County permit rescheduled for 7/2 11am./ Drilled 335' 6-25/ 7/3- need city permit. / 8/1- called in LS locates for city portion
FB-HWP1377 | Lakeland | 2025-11-30 | Lightspeed In-House/HH/JUAN G | 2025-10-06 | Travis |  | 0 | Completed on Track | Received | N/A | Yes | 74164.05 | 62844.55 |  | 62844.55 | Yes | Completed | 2025-10-09 | 5613 | 5774 | 103% | 2025-10-30 | 100% | 100% | 100% | 2025-12-07 | 2025-12-08 | 10/8 FDOT Permit Received--Pending City Of Lakeland Permit. Locates called 10-9/ 10/21 pending water locates. Feeds Skyview/ Locates cleared .Cx starts 10-30-2025/11-10 Path Complete/11-13 Pulling Fiber/Fiber Pulled 11-17-2025/ Splice scheduled 11-18/Splice done 11-19-2025
FB-HWP1379 | Lakeland | 2025-11-30 | Brothers | 2025-10-31 | Travis |  | 0 | Completed on Track | Received | N/A | Yes | 39221.8 | 42623.8 |  | 42623.8 | Yes | Completed | 2025-10-20 | 3078 | 3272 | 106.3% | 2025-11-05 | 100% | 100% | 100% | 2025-12-08 | 2025-12-08 | 10/8 Pending Permit./ Locates called, White lined 10-20-2025/ Feeds Citrus Wood and is fed by FB1377. 10/23-pending usic/water/pwr/ Locates cleared 10-29-2025/CX started 11-5/11-12 Path complete/ Pulling Fiber after 1377/Fiber being pulled 11-18-2025/ Splice Schedule 11-18/Splice done 11-19-2025/
FX4-FWP-08 | Lakeland | 2025-05-15 | Brothers | 2025-02-07 | Travis | PLK89273 | 0 | Completed | Received | Completed | Yes | 3425.55 | 7741.4 |  | 7741.4 | Yes | Completed | 2025-02-01 | 73 | 73 | 100% | 2025-02-10 | 100% | 100% | 100% | 2025-06-27 | 2025-06-27
FX4-FWP-09 | Lakeland | 2025-12-24 | Brothers | 2025-11-04 | Travis | PLK104997 | 0 | Completed on Track | Received | N/A | Yes | 4773.8 | 3671.8 |  | 3671.8 | Yes | Completed | Not Required | 103 | 82 | 80% | 2025-11-24 | 0% | 0% | 0 | 2026-01-13 | 2026-02-20 | 10/31 Pending Permit./Permit Recieved 11-19-2025/ Pad poured and pipe trencched. Need to set cabinet and get electric permit from city/cabinet set/city to schedule inspection/12-16 Site pipe placed waiting on inspection from city/ Inspectione passed, returned to city to be metered 12-30/metered complete/qc complete
FX4-FWP-13 | Lakeland | 2025-05-10 | Brothers | 2025-04-16 | Anthony | PLK93160 | 0 | Completed on Track | Received | Completed | Yes | 3707.3 | 8209.69 |  | 8209.69 | Yes | Completed | 2025-04-16 | 143 | 143 | 100% | 2025-04-21 | 0% | 0% | 100% | 2025-09-26 | 2025-09-26 | gave to power connect 2-17-25/START 2-26/exp 811 2-26/not clear 3-4@730am/3-4 3rd notice called into to 811 8am/ partial locates work sch 3-5 tin in to 713 locates not complete 3-4 @3pm/ Expedited 4pm 3-4/*do not build peice ro 703(ada x-ing)/ Expedited locates 4pm 3-5/pending zayo marks 3-7/talked to state manager for zayo, he is dending them asap to locate/Zayo marked. 3-10 Power connect drilling, Returning 3-11 to connect Griffin Rd to N Florida and pull 48f. 3/12-IP, 100' left to bore on Kalt Dr. to tie in D-HWP713, 48f pull. 3/13- x-ing at Martha call locates 3-13 for ls to complete/. 3/13- locs called/whitelined, IH crew to dig up 144 and place 48f so D701,D705 and D702 can be heated up. 3/17- still pending clear loc for Martha(will expedite tmrw), Tillman aprvd a bore to get a 48f from FB to D701 loc called 3.14./504' 4-10/dot sch for 5-13 9am/ 5/7- DOT Xing scheduled for Tuesday 5/13. Expedited tickets 5-8*fs sch 5-22/ DOT crossing sch 5-20. 5/14 1190' today, will return on 5/20 to complete remaining path. / 5/19 Brothers said they were doing this bore on 5.20 and made a mistake with the date, it is scheduled for 5.21 and the fiber to be pulled in on the same day. / 6/5- Tillman walking today
Citrus Woods MHP | Lakeland | 2025-10-30 | J Garcia Underground | 2025-10-09 | Anthony |  | 385 | Completed on Track | Not Required | 2025-10-07 | Yes | 210533.1 | 199293.1 |  | 199293.1 | Yes | Completed | 2025-10-06 | 18693 | 18693 | 100% | 2025-10-14 | 100% | 100% | 100% | 2025-12-08 | 2025-12-08 | cl 10-6/ dt 10/7 / pending locates and NTP 10-9. 10/14 cx started. 10/21 CX IP, fed by FB1379. / 10/30 path is complete, setting HHs,proofing and blowing SR. / 10/30 - some HHs were set, Garcia to place remaining HHs on 10/31 and we blow SR. / 11/3 - still pending SRs/SR done/Splice done 11-19-2025/ Light Levels received 11-20
Fountain View Estates MHP | Lakeland | 2025-12-29 | H&H Underground | 2025-11-17 | Miguel | PLK105357 | 197 | Completed on Track | Not Required | 2025-11-17 | Yes | 87807.5 | 81808 |  | 81808 | Yes | Completed | 2025-11-17 | 10187 | 8303 | 82% | 2025-11-24 | 100% | 100% | 100% | 2026-01-07 | Pending Tillman QC Form | 11/17 Pending SOW./White lined and door taged 11-17-2025/Cx starts 11-24-2025/ 1/13 CX Construction Complete...12F Stingray Installed.
Golden Wings MDU | Lakeland | 2025-01-31 | SB Martinez | 2025-01-25 | Travis | PLK88370 | 48 | Completed -Missed TSD | Not Required | Completed | Yes | 21648.75 | 35235 |  | 35235 | Yes | Completed | 2025-01-21 | 2264 | 2163 | 95.54% | 2025-01-24 | 100% | 100% | 100% | 2025-06-10 | 2025-06-10
Heatherwood Village MHP | Lakeland | 2025-12-05 | J Garcia Underground | 2025-10-28 | Miguel | PLK104425 | 303 | Completed on Track | Not Required | 2025-10-23 | Yes | 168480.55 | 159413.8 | 15232 | 174645.55 | Yes | Completed | 2025-10-23 | 13760 | 13760 | 100% | 2025-11-17 | 100% | 100% | 100% | 2026-12-15 | Pending Tillman QC Form | 10/24 SOW Received./called locates, Door tag, white line, 10-23-2025/Waiting on Water locates 11-5-2025/Waiting on Water locates to clear 11-11-2025/Locates cleared. Cx starts 11-17-2025/ 12/3 CX Construction Continuing--Progress At 85% Complete./Path complete 12-3-2025/ setting HH/FDH 12-4/ 12/5 FDH And Hand Holes Completed./ 12/8 FDH and Hand Holes Complete./ 12/9 48 Ct Fiber Placed with Trace Wire, and 3 Stingrays./
Mas Verde MHP | Lakeland | 2025-10-30 | Baseline / Juan Garcia / Patriot Underground | 2025-09-15 | Travis/Miguel |  | 384 | Completed on Track | Not Required | 2025-09-05 | Yes | 145985.5 | 135482.5 |  | 135482.5 | Yes | Completed | 2025-09-06 | 14150 | 15378 | 109% | 2025-09-26 | 100% | 100% | 100% | 2026-04-01 | 2026-04-01 | dispatched 8-5/locatge scalled 9-5/CX START 9-25-25/first fdh spliced, issue with light from cabinet 10-1/second and third FDH installed on 10-6-2025/ last two FDH installed 10-7-2025/Stingray done on Hub A, Hub B, and Hub C 10-9-2025/Stingray done from Hub A to Hub D, From Hub D to Hub E. Restoration done. 10-13-2025
Oakhill MHP | Lakeland | 2025-09-30 | HH UG | 2025-09-16 | Travis |  | 84 | Completed on Track | Not Required | Completed | Yes | 30892 | 28405 |  | 28405 | Yes | Completed | 2025-09-11 | 2811 | 2732 | 97.19% | 2025-09-22 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 9/10 Pending SOW From Tillman/ locates called 9-11. 9/16 SOW Received. / 9/19- HH scheduled to start 9.22/cx complete 9-219/spl 9-30 com/Working on COP 10-21
12 Oaks MHP | Lakeland | 2025-08-30 | Brothers | 2025-08-04 | Anthony |  | 50 | Completed on Track | Not Required | 2025-08-05 | Yes | 11894.25 | 10285.25 | 5989 | 16274 | Yes | Completed | 2025-08-04 | 1471 | 1437 | 98% | 2025-08-12 | 100% | 100% | 100% | 2025-09-26 | 2025-09-26
Skyview Estates MHP | Lakeland | 2025-09-30 | Brothers | 2025-08-05 | Anthony |  | 208 | Completed on Track | Not Required | 2025-08-07 | Yes | 124980 | 118545 |  | 118545 | Yes | Completed | 2025-08-07 | 11700 | 11820 | 101% | 2025-08-21 | 100% | 100% | 100% | 2025-09-26 | 2025-09-26 | in progress 8-27/moved to priorities/dilling complete 9-10 / 9-15- Proofing in progress/Splice done 11-19-2025/ Light Levels Received 11-20
D-HPP307 | Pinellas | 2026-08-28 | Lightspeed | 2026-06-05 | Treyvon |  | 42 | Completed on Track | Received | 2026-06-05 | Yes | 60970.5 | 60606.5 |  | 60606.5 | Yes | Completed | 2026-06-08 | 4650 | 4496 | 97% | 2026-06-15 | 0% | 0% | 0 | 2026-08-03 | Pending Tillman QC Form | 6/4 NTP Package Received
BHCD-FSF-04-W | Port Charlotte | 2026-03-30 | Lightspeed In-House | 2026-03-04 | Cody | MAN109126 | 0 | Completed on Track | Received | N/A | Yes | 12316.35 | 11751.85 |  | 11751.85 | Yes | Completed | 2026-03-05 | 7 | 7 | 100% | 2026-03-25 | 100% | 100% | 100% | 2026-04-22 | 2026-04-22 | 2/24 NTP Package and SOW Received.
BHCD-FSF-05-E | Port Charlotte | 2026-03-30 | GN Systems | 2026-03-04 | Cody | MAN109139 | 0 | Completed on Track | Received | N/A | Yes | 151170.8 | 129393.3 |  | 129393.3 | Yes | Completed | 2026-03-05 | 11789 | 11958 | 101.4% | 2026-03-18 | 100% | 0% | 0 | 2026-04-15 | 2026-04-21 | 2/24 NTP Package and SOW Received.
D-HSF321 | Port Charlotte | 2026-05-30 | GN Systems | 2026-04-30 | Joshua |  | 74 | Completed on Track | Received | N/A | Yes | 75564 | 75030 |  | 75030 | Yes | Completed | 2026-05-05 | 6250 | 6357 | 101.7% | 2026-05-20 | 0% | 0% | 0 | 2026-06-22 | 6/22 Failed QC | 4/21 NTP Received.
FB-HSF301 | Port Charlotte | 2026-05-30 | Lightspeed In-House | 2026-05-01 | Joshua |  | 0 | Completed on Track | Received | N/A | Yes | 15405.5 | 9526.5 |  | 9526.5 | Yes | Completed | 2026-05-01 | 761 | 760 | 100% | 2026-06-02 | 0% | 0% | 0 | 2026-06-18 | 2026-06-18 | 4/21 NTP Received.
FB-HSF375 | Port Charlotte | 2026-04-18 | Lightspeed In-House | 2026-04-09 | Joshua |  | 0 | Completed on Track | Received | N/A | Yes | 4434.4 | 3739.4 | 1340.7 | 5080.1 | Yes | Completed | 2026-04-09 | 439 | 468 | 102.3% | 2026-04-20 | 100% | 100% | 100% | 2026-06-19 | 2026-06-19 | 4/6 NTP Package Received.4-9-26 locates called
FB-HSF376 | Port Charlotte | 2026-05-30 | Lightspeed In-House | 2026-05-01 | Joshua |  | 0 | Completed on Track | Received | N/A | Yes | 1552.9 | 1217.9 |  | 1217.9 | Yes | Completed | 2026-05-01 | 94 | 108 | 115% | 2026-05-13 | 100% | 100% | 100% | 2026-06-19 | 2026-06-19 | 4/21 NTP Received.
FB-HSF378 | Port Charlotte | 2026-04-18 | Lightspeed In-House | 2026-04-09 | Joshua |  | 0 | Completed on Track | Received | N/A | Yes | 4004.55 | 3356.05 |  | 3356.05 | Yes | Completed | 2026-04-09 | 303 | 290 | 96% | 2026-04-21 | 100% | 100% | 100% | 2026-06-19 | 2026-06-19 | 4/7 NTP Package Received.4-9-26 locates called
FB-HSF379 | Port Charlotte | 2026-03-30 | GN Systems | 2026-03-25 | Joshua | MAN109143 | 0 | Completed on Track | Received | N/A | Yes | 24122.75 | 21041.25 | 4501.05 | 25542.3 | Yes | Completed | 2026-03-06 | 1925 | 1896 | 98.49% | 2026-03-30 | 100% | 100% | 100% | 2026-04-23 | 2026-04-23 | 2/24 NTP Package and SOW Received. 3-19-26 Locates Clear
FB-HSF381 | Port Charlotte | 2026-03-30 | GN Systems | 2026-03-25 | Joshua | MAN109145 | 0 | Completed on Track | Received | N/A | Yes | 26639.1 | 23241.1 |  | 23241.1 | Yes | Completed | 2026-03-06 | 2136 | 2179 | 102% | 2026-03-31 | 100% | 100% | 100% | 2026-06-23 | 2026-06-23 | 2/24 NTP Package and SOW Received. 3-19-26 Locates Clear.
FB-HSF383 | Port Charlotte | 2026-04-28 | GN Systems | 2026-03-25 | Joshua | MAN109148 | 0 | Completed on Track | Received | N/A | Yes | 1698.25 | 1346.75 | 1346.35 | 2693.1 | Yes | Completed | 2026-03-06 | 105 | 102 | 97.14% | 2026-04-07 | 100% | 100% | 100% | 2026-05-13 | 2026-05-13 | 2/24 NTP Package and SOW Received. 3-19-26 Locates Clear
FB-HSF384 | Port Charlotte | 2026-04-28 | GN Systems | 2026-03-25 | Joshua | MAN109120 | 0 | Completed on Track | Received | N/A | Yes | 5779.1 | 23241.1 |  | 23241.1 | Yes | Completed | 2026-03-25 | 406 | 417 | 102.7% | 2026-04-07 | 100% | 100% | 100% | 2026-06-23 | 2026-06-23 | 2/24 NTP Package and SOW Received. 3-19-26 Locates Clear.
FB-HSF404 | Port Charlotte | 2026-03-30 | Lightspeed In-House | 2026-03-06 | Joshua | MAN109175 | 0 | Completed on Track | Received | N/A | Yes | 6808.8 | 5552.8 | 2495.9 | 8048.7 | Yes | Completed | 2026-03-06 | 508 | 513 | 101% | 2026-03-24 | 100% | 100% | 100% | 2026-04-22 | 2026-04-22 | 2/24 NTP Package Received.
FB-HSF475 | Port Charlotte | 2026-03-30 | Lightspeed In-House | 2026-03-06 | Joshua | MAN109159 | 0 | Completed on Track | Received | N/A | Yes | 9496.2 | 7964.2 |  | 7964.2 | Yes | Completed | 2026-03-06 | 742 | 752 | 101.3% | 2026-04-03 | 100% | 100% | 100% | 2026-06-24 | 2026-06-24 | 2/24 NTP Package and SOW Received.
FB-HSF476 | Port Charlotte | 2026-03-30 | Lightspeed In-House | 2026-03-16 | Joshua | MAN109178 | 0 | Completed on Track | Received | N/A | Yes | 16760.15 | 14572.65 | 3931.15 | 18503.8 | Yes | Completed | 2026-03-16 | 1329 | 1349 | 101.5% | 2026-03-30 | 100% | 100% | 100% | 2026-04-22 | 2026-04-22 | 2/24 NTP Package Received.
FB-HSF477 | Port Charlotte | 2026-03-30 | Lightspeed In-House | 2026-03-16 | Joshua | MAN109175 | 0 | Completed on Track | Received | N/A | Yes | 14178.2 | 12286.2 | 3770 | 16056.2 | Yes | Completed | 2026-03-16 | 1132 | 1186 | 104.8% | 2026-03-26 | 100% | 100% | 100% | 2026-04-21 | 2026-04-21 | 2/24 NTP Package Received.
D-H0220A | St Petersburg | 2025-06-30 | Longo Underground | 2025-06-10 | Tim | PPM95827 | 56 | Completed on Track | Received | 2025-06-09 | Yes | 75953 | 61562 |  | 61562 | Yes | Completed | 2025-06-09 | 6005 | 6044 | 101% | 2025-06-16 | 100% | 100% | 100% | 2025-07-30 | 2025-07-30 | New Proposed Walkout Date 3/17/2026
D-H0220B | St Petersburg | 2025-07-30 | US Builders / Longo Underground | 2025-03-03 | Tim | PPM91680 | 60 | Completed on Track | Received | 2025-02-28 | Yes | 64727 | 68203 |  | 68203 | Yes | Completed | 2025-03-03 | 5853 | 5975 | 102% | 2025-03-25 | 100% | 100% | 100% | 2025-07-30 | 2025-07-30
D-H0220C | St Petersburg | 2025-05-30 | Power Connect | 2025-03-11 | Robert | PPM91630 | 80 | Completed | Received | 2025-03-12 | Yes | 88033.5 | 88045.5 |  | 88045.5 | Yes | Completed | 2025-03-11 | 7442 | 7447 | 100.1% | 2025-03-24 | 100% | 100% | 100% | 2025-05-14 | 2025-05-14
D-H0221A | St Petersburg | 2025-05-30 | Brothers | 2025-03-11 | Johnnie | PPM91357 | 90 | Completed | Received | 2025-03-12 | Yes | 82979.5 | 78032 |  | 78032 | Yes | Completed | 2025-03-12 | 6524 | 6492 | 99.51% | 2025-03-24 | 100% | 100% | 100% | 2025-09-16 | 2025-09-16 | 6/17/2025 JW ¦ TILLMAN WALKOUT SET FOR 6/18/2025 (0830) 4/28 JW ¦ PLEASE SEE COMMENT
D-H0221C | St Petersburg | 2025-06-30 | Bartlett Fiber | 2025-03-11 | Johnnie | PPM91690 | 71 | Completed on Track | Received | 2025-03-12 | Yes | 60843.5 | 59355.5 |  | 59355.5 | Yes | Completed | 2025-03-06 | 4979 | 5020 | 101% | 2025-03-25 | 100% | 100% | 100% | Legacy Project | Legacy Project | 9-24 - JW - Tillman Walkout scheduled for 9-29-25
D-H0221D | St Petersburg | 2025-03-26 | Bartlett Fiber | 2025-02-28 | Caten | PPM91321 | 87 | Completed | Received | 2025-02-28 | Yes | 74446 | 73894 |  | 73894 | Yes | Completed | 2025-03-07 | 6149 | 6362 | 103.5% | 2025-03-17 | 100% | 100% | 100% | 2025-07-21 | 2025-07-21
D-H0221F | St Petersburg | 2025-04-25 | Brothers | 2025-02-28 | Johnnie | PPM91656 | 83 | Completed | Received | 2025-02-28 | Yes | 84935.5 | 81445 |  | 81445 | Yes | Completed | 2025-03-10 | 7049 | 7081 | 100.5% | 2025-03-24 | 100% | 100% | 100% | 2025-04-23 | 2025-04-23
D-H0222A | St Petersburg | 2025-04-25 | Power Connect | 2025-02-05 | Johnnie | PPM89513 | 86 | Completed on Track | Received | 2025-02-26 | Yes | 94170.5 | 90860.5 |  | 90860.5 | Yes | Completed | 2025-02-05 | 7980 | 7901 | 99% | 2025-02-25 | 100% | 100% | 100% | Legacy Project | Legacy Project | Reassinged to Longo . -- Waiting on redesign from tillman--2-26-25. 8-18-25 rescheuled rewalk for 9-3-25
D-H0222B | St Petersburg | 2025-04-25 | Brothers | 2025-01-28 | Johnnie | PPM89528 | 76 | Completed on Track | Received | 2025-02-04 | Yes | 90302 | 98764.5 |  | 98764.5 | Yes | Completed | 2025-02-06 | 8420 | 8553 | 101.6% | 2025-02-21 | 100% | 100% | 100% | 2025-07-29 | 2025-07-29 | 6/17/2025 JW ¦ PENDING RESTORATION BY IN HOUSE CREWS
D-H0222C | St Petersburg | 2025-04-25 | Power Connect | 2025-02-10 | Johnnie | PPM89539 | 89 | Completed on Track | Received | 2025-02-07 | Yes | 89698.5 | 86876.5 |  | 86876.5 | Yes | Completed | 2025-02-06 | 7562 | 7556 | 100% | 2025-02-21 | 100% | 100% | 100% | Legacy Project | Legacy Project | Confirmed With Tillman Project Date Changed To 3/31/2025. Tentative Start Date 2/18/2025.
D-H0222D | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-02-07 | Caten | PPM89539 | 86 | Completed on Track | Received | 2025-02-10 | Yes | 71361 | 72125 |  | 72125 | Yes | Completed | 2025-01-31 | 6214 | 6214 | 100% | 2025-02-20 | 100% | 100% | 100% | 2025-05-14 | 2025-05-14
D-H0223A | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-01-29 | Johnnie | PPM89575 | 77 | Completed on Track | Received | 2025-01-29 | Yes | 61924 | 61494 |  | 61494 | Yes | Completed | 2025-02-04 | 5005 | 4996 | 100% | 2025-02-20 | 100% | 100% | 100% | Legacy Project | Legacy Project | 9-25-25 - JW- Working on gig list, will schedule once complete and ready for Tillman - Tentative Start Date 2/18/2025.
D-H0223C | St Petersburg | 2025-04-25 | Longo Underground | 2025-01-29 | Tim | PPM89447 | 81 | Completed on Track | Received | 2025-02-12 | Yes | 76139.5 | 79581.5 |  | 79581.5 | Yes | Completed | 2025-02-04 | 6303 | 6761 | 107.3% | 2025-02-12 | 100% | 100% | 100% | 2025-07-21 | 2025-07-21 | Tentative Start Date 2/18/2025. 2-20-25 need GPR on sheet 6 crossing 51st ave.
D-H0223D | St Petersburg | 2025-04-25 | Brothers | 2025-01-28 | Johnnie | PPM89579 | 81 | Completed on Track | Received | 2025-02-11 | Yes | 73583.5 | 84066 |  | 84066 | Yes | Completed | 2025-02-03 | 6205 | 6180 | 100% | 2025-02-11 | 100% | 100% | 100% | 2025-09-16 | 2025-09-16 | 6/17/2025 JW ¦ PENDING TILLMAN WALKOUT RESTORATION COMPLETE \\ 5/14/2025 FINAL COP IN PROGRESS PENDING TILLMAN QAQC AND LIGHT LEVELS. 8-27-25 rewalk scheduled for -9-10-25.
D-H0223E | St Petersburg | 2025-04-25 | US Builders | 2025-02-06 | Johnnie | PPM89581 | 84 | Completed on Track | Received | 2025-02-10 | Yes | 63402.5 | 62670.5 |  | 62670.5 | Yes | Completed | 2025-02-07 | 4979 | 4984 | 100% | 2025-02-26 | 100% | 100% | 100% | Legacy Project | Legacy Project | 9-25-25 - JW- Working on gig list, will schedule once complete and ready for Tillman - 2-24-25 sent to borecom will be on site thursday. reassigned to Keys Underground 2-26-25--GPR Requested on 2/25/2025. 2-28-25 Reassigned to US Builders. New Proposed Walkout Date 3/18/2026.
D-HDH03 | St Petersburg | 2025-01-31 | Power Connect | 2025-02-04 | Robert | PPM89589 | 90 | Completed -Missed TSD | Received | Completed | Yes | 51958 | 20330.26 |  | 20330.26 | Yes | Completed | 2025-02-06 | 760 | 708 | 93.16% | 2025-03-13 | 100% | 100% | 100% | 2025-05-15 | 2025-05-15 | 2-10-2025 David Barrett To Fill Out An MOT Trooper Request 2-18-25 Pipe is all in need feeding route verified and proofed. PowerConnect addressing today.
D-HDH04 | St Petersburg | 2025-01-31 | J Garcia | 2025-01-28 | David | PPM88371 | 86 | Completed -Missed TSD | Received | 2025-01-20 | Yes | 78075.5 | 75360 |  | 75360 | Yes | Completed | 2025-01-18 | 6526 | 6316 | 97% | 2025-01-28 | 100% | 100% | 0 | 2025-08-25 | 2025-08-25
D-HDH31 | St Petersburg | 2025-01-31 | Reycamp | 2025-02-04 | Betsy | PPM89043 | 86 | Completed -Missed TSD | Received | Completed | Yes | 82480.5 | 77870.5 |  | 77870.5 | Yes | Completed | 2025-01-18 | 6390 | 6114 | 95.68% | 2025-01-30 | 100% | 100% | 100% | 2025-08-13 | 2025-08-13 | Partial Completed--SOW / Footage Work Is For The County Permit That Is Pending Approval, All The City Work Has Been Completed.
D-HDH32 | St Petersburg | 2025-01-31 | Power Connect | 2025-02-07 | Johnnie | PPM89595 | 88 | Completed -Missed TSD | Received | Completed | Yes | 43130 | 43560 |  | 43560 | Yes | Completed | 2025-02-03 | 2931 | 3257 | 111% | 2025-04-03 | 100% | 100% | 100% | Legacy Project | Legacy Project | 9-25-25 - JW- Working on gig list, will schedule once complete and ready for Tillman - 2-18-25 Pipe is all in need feeding route verified and proofed.
D-HDH34 | St Petersburg | 2025-01-31 | Lightspeed In-House | 2025-01-29 | Johnnie | PPM88372 | 88 | Completed -Missed TSD | Received | 2025-02-18 | Yes | 69212.5 | 70500 |  | 70500 | Yes | Completed | 2025-01-22 | 5661 | 5752 | 102% | 2025-01-24 | 100% | 100% | 100% | Legacy Project | Legacy Project | 9-25-25 - JW- Tillman Walkout scheduled for 10-2-2025 - 6/17/2025 JW ¦ PENDING RESTORATION BY IN HOUSE CREWS/ 1/16 CX Complete...Repair of 24 Way.
D-HDH41 | St Petersburg | 2025-04-25 | MTX | 2025-03-27 | Allen / Sean | PPM91655 | 85 | Completed on Track | Received | 2025-03-25 | Yes | 74508.5 | 75008.5 |  | 75008.5 | Yes | Completed | 2025-04-02 | 5795 | 5411 | 93% | 2025-04-16 | 100% | 100% | 100% | Legacy Project | Legacy Project | 9-25-25 - JW- Tillman Walkout scheduled for 10-8-2025 -
D-HDH42 | St Petersburg | 2025-04-25 | FCA Fiber | 2025-03-27 | Betsy | PPM92270 | 88 | Completed on Track | Received | 2025-03-25 | Yes | 73070.5 | 72678 |  | 72678 | Yes | Completed | 2025-04-02 | 6028 | 6070 | 100.7% | 2025-04-22 | 100% | 100% | 100% | 2025-06-16 | Legacy Project
D-HDH43 | St Petersburg | 2025-04-25 | US Builders | 2025-03-27 | Johnnie | PPM92271 | 57 | Completed on Track | Received | 2025-03-25 | Yes | 49071 | 51376.61 |  | 51376.61 | Yes | Completed | 2025-03-29 | 3967 | 3936 | 99% | 2025-04-09 | 100% | 100% | 100% | Legacy Project | Legacy Project | 9-25-25 - JW- Working on gig list, will schedule once complete and ready for Tillman
D-HDH45 | St Petersburg | 2025-02-23 | Reycamp | 2025-02-03 | Betsy | PPM89601 | 73 | Completed -Missed TSD | Received | 2025-02-10 | Yes | 60575.5 | 59352 |  | 59352 | Yes | Completed | 2025-02-03 | 4614 | 4614 | 100% | 2025-02-18 | 100% | 100% | 100% | 2025-08-19 | 2025-08-19 | Tentative Start Date 2/18/2025. GPR Requested on 2/25/2025. 1-7 COP Approved.
D-HDH46 | St Petersburg | 2025-02-23 | FCA Fiber | 2025-02-19 | Betsy | PPM89610 | 65 | Completed -Missed TSD | Received | 2025-02-10 | Yes | 65001 | 68269 |  | 68269 | Yes | Completed | 2025-02-20 | 5284 | 5458 | 103.3% | 2025-03-06 | 100% | 100% | 100% | 2025-04-17 | 2025-04-17
D-HDH47 | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-03-27 | Caten | PPM92273 | 70 | Completed on Track | Received | 2025-03-25 | Yes | 62104 | 64186 |  | 64186 | Yes | Completed | 2025-03-28 | 5210 | 5139 | 98.64% | 2025-04-09 | 100% | 100% | 100% | 2025-05-15 | 2025-05-15
D-HDH48 | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-03-27 | Caten | PPM92278 | 84 | Completed on Track | Received | 2025-03-25 | Yes | 63756.5 | 64902.5 |  | 64902.5 | Yes | Completed | 2025-04-08 | 5237 | 5439 | 103.9% | 2025-04-18 | 100% | 100% | 100% | 2025-05-15 | 2025-05-15
D-HDH49 | St Petersburg | 2025-04-25 | Brothers | 2025-03-27 | Johnnie | PPM92276 | 75 | Completed on Track | Received | 2025-03-25 | Yes | 67840.5 | 66607.5 |  | 66607.5 | Yes | Completed | 2025-03-31 | 5601 | 5628 | 100.5% | 2025-04-14 | 100% | 100% | 100% | 2025-06-23 | 2025-06-23
D-HDH50 | St Petersburg | 2025-06-23 | FCA Fiber | 2025-04-14 | Betsy | PPM93107 | 69 | Completed on Track | Received | 2025-04-10 | Yes | 53906.75 | 54578.5 |  | 54578.5 | Yes | Completed | 2025-04-10 | 4615 | 4588 | 99.41% | 2025-04-25 | 100% | 100% | 100% | 2025-06-16 | 2025-06-16
D-HDH52 | St Petersburg | 2025-06-23 | In House | 2025-05-30 | Johnnie | PPM93114 | 50 | Completed on Track | Received | 2025-04-10 | Yes | 47432.5 | 54385.09 |  | 54385.09 | Yes | Completed | 2025-04-10 | 3932 | 4034 | 102.6% | 2025-04-24 | 0% | 0% | 0% | 2025-07-11 | 2025-07-11 | 6/17/2025 JW ¦ RESTORATION ON GOING, SODZILLA WILL BE WRAPPING UP, PENDING TILLMAN WALKOUT
D-HDH53 | St Petersburg | 2025-06-23 | Longo Underground | 2025-04-14 | Tim | PPM93118 | 76 | Completed | Received | 2025-04-10 | Yes | 62383 | 61939 |  | 61939 | Yes | Completed | 2025-04-10 | 5164 | 5164 | 100% | 2025-04-25 | 100% | 100% | 100% | 2025-06-30 | 2025-06-30
D-HDH54 | St Petersburg | 2025-06-23 | HAS Global | 2025-04-14 | Johnnie | PPM93122 | 88 | Completed | Received | 2025-04-10 | Yes | 80443.5 | 81941 |  | 81941 | Yes | Completed | 2025-04-10 | 6617 | 6743 | 101.9% | 2025-04-24 | 0% | 0% | 0% | 2025-07-11 | 2025-07-11 | 6/17/2025 JW ¦ RESTORATION COMPLETE \\ PENDING TILLMAN WALKOUT
D-HDH55 | St Petersburg | 2025-06-23 | In House | 2025-05-30 | Johnnie | PPM93069 | 86 | Completed on Track | Received | 2025-04-10 | Yes | 68736.5 | 68249 |  | 68249 | Yes | Completed | 2025-04-09 | 5939 | 5791 | 97.51% | 2025-04-21 | 0% | 0% | 0% | 2025-07-11 | 2025-07-11 | 6/17/2025 JW ¦ RESTORATION COMPLETE \\ PENDING TILLMAN WALKOUT
D-HDH56 | St Petersburg | 2025-04-25 | Longo Underground | 2025-03-27 | Tim | PPM92087 | 84 | Completed on Track | Received | 2025-03-25 | Yes | 73491.5 | 202651 |  | 202651 | Yes | Completed | 2025-04-01 | 5390 | 5327 | 98.83% | 2025-04-21 | 0% | 0% | 0% | 2025-07-21 | 2025-07-21
D-HDH57 | St Petersburg | 2025-06-23 | Bartlett Fiber | 2025-05-30 | Caten | PPM92588 | 87 | Completed on Track | Received | 2025-04-10 | Yes | 78331 | 82072.25 |  | 82072.25 | Yes | Completed | 2025-04-10 | 6334 | 6228 | 98% | 2025-04-22 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | 4-29-25 Was MTX need to reassign.
D-HDH58 | St Petersburg | 2025-04-25 | Brothers | 2025-03-27 | Johnnie | PPM92280 | 81 | Completed on Track | Received | 2025-03-25 | Yes | 74961 | 77123 |  | 77123 | Yes | Completed | 2025-03-31 | 6327 | 6414 | 101.4% | 2025-04-14 | 100% | 100% | 100% | 2025-08-25 | 2025-08-25 | 6/17/2025 JW ¦ RESTORATION COMPLETE \\ PENDING TILLMAN WALKOUT
D-HDH60 | St Petersburg | 2025-04-25 | Longo Underground | 2025-03-27 | Tim | PPM92088 | 80 | Completed on Track | Received | 2025-03-25 | Yes | 70235 | 134171.5 |  | 134171.5 | Yes | Completed | 2025-03-29 | 5585 | 5566 | 99.66% | 2025-04-10 | 100% | 100% | 100% | 2025-07-21 | 2025-07-21
D-HDH66 | St Petersburg | 2025-01-31 | Bartlett Fiber | 2025-01-27 | Caten | PPM88373 | 90 | Completed -Missed TSD | Received | Completed | Yes | 60625.5 | 59084 |  | 59084 | Yes | Completed | 2025-01-22 | 5038 | 4909 | 97.44% | 2025-01-27 | 100% | 100% | 100% | 2025-06-23 | 2025-06-23
D-HDH67 | St Petersburg | 2025-04-25 | Power Connect | 2025-02-28 | Robert | PPM91122 | 86 | Completed on Track | Received | 2025-03-05 | Yes | 79507 | 86709.5 |  | 86709.5 | Yes | Completed | 2025-03-04 | 6756 | 6667 | 98.68% | 2025-03-12 | 100% | 100% | 100% | 2025-05-14 | 2025-05-14
D-HDH68 | St Petersburg | 2025-02-23 | Longo Underground | 2025-01-29 | Tim | PPM89616 | 90 | Completed -Missed TSD | Received | 2025-02-12 | Yes | 77320 | 75804 |  | 75804 | Yes | Completed | 2025-02-18 | 6041 | 6024 | 99.72% | 2025-02-26 | 100% | 100% | 100% | 2025-08-25 | 2025-08-25 | -2-24-25 sent info to us building they will be subbing in for longo on this project starting 02-26-25..2-27-25 longo on site
D-HDH70 | St Petersburg | 2025-04-25 | Longo Underground | 2025-02-28 | Tim | PPM91121 | 82 | Completed on Track | Received | 2025-02-28 | Yes | 64609 | 76965 |  | 76965 | Yes | Completed | 2025-03-04 | 5327 | 5450 | 102.3% | 2025-03-12 | 100% | 100% | 100% | 2025-07-21 | 2025-07-21
D-HDH71 | St Petersburg | 2025-04-25 | HDD Underground | 2025-02-06 | Betsy | PPM89623 | 64 | Completed on Track | Received | 2025-02-13 | Yes | 48609 | 48682.5 |  | 48682.5 | Yes | Completed | 2025-02-10 | 4035 | 4045 | 100% | 2025-02-21 | 100% | 100% | 100% | 2025-08-25 | 2025-08-25 | Notified Chris Tillman of the crew going off run line a bit due to gas / water. sent him pics/video, spoke with chris and said to stay as close as safley possible. 2/17 340pm SL .
D-HDH73 | St Petersburg | 2025-04-25 | Power Connect | 2025-02-04 | Robert | PPM89626 | 59 | Completed on Track | Received | 2025-02-10 | Yes | 52222 | 51838 |  | 51838 | Yes | Completed | 2025-02-03 | 4772 | 4329 | 90.72% | 2025-02-19 | 100% | 100% | 100% | 2025-05-14 | 2025-05-14
D-HDH74 | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-01-29 | Caten | PPM89643 | 85 | Completed on Track | Received | 2025-02-10 | Yes | 67892.5 | 65771.43 |  | 65771.43 | Yes | Completed | 2025-02-21 | 5494 | 5431 | 99% | 2025-03-06 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | Locates called in 02-20-25
D-HDH75 | St Petersburg | 2025-04-25 | Longo Underground | 2025-02-28 | Tim | PPM91431 | 88 | Completed | Received | 2025-02-28 | Yes | 67463 | 69992 |  | 69992 | Yes | Completed | 2025-03-04 | 5491 | 5605 | 102.1% | 2025-03-19 | 100% | 100% | 100% | 2025-06-23 | 2025-06-23
D-HDH76 | St Petersburg | 2025-02-23 | J Garcia / US Builders | 2025-02-04 | David | PPM89553 | 86 | Completed -Missed TSD | Received | 2025-02-10 | Yes | 66638 | 65072 |  | 65072 | Yes | Completed | 2025-02-03 | 5428 | 5399 | 99.47% | 2025-02-12 | 100% | 100% | 100% | Legacy Project | Legacy Project
D-HDH78 | St Petersburg | 2025-02-23 | FCA Fiber | 2025-02-18 | Betsy | PPM90248 | 85 | Completed on Track | Received | 2025-02-19 | Yes | 67,657,50 | 67080 |  | 67080 | Yes | Completed | 2025-02-19 | 5564 | 5576 | 100.2% | 2025-03-11 | 100% | 100% | 100% | 2025-04-10 | 2025-04-10
D-HDH80 | St Petersburg | 2025-04-25 | MTX | 2025-03-27 | Sean | PPM92262 | 91 | Completed on Track | Received | 2025-03-25 | Yes | 79069.5 | 73300 |  | 73300 | Yes | Completed | 2025-03-28 | 6330 | 6180 | 97.63% | 2025-04-04 | 100% | 100% | 100% | 2025-07-21 | 2025-07-21
D-HDH82 | St Petersburg | 2025-04-25 | MTX | 2025-03-27 | Sean | PPM92198 | 20 | Completed on Track | Received | 2025-03-25 | Yes | 16398 | 15664 |  | 15664 | Yes | Completed | 2025-03-28 | 1265 | 1257 | 99.37% | 2025-04-03 | 100% | 100% | 100% | 2025-07-11 | 2025-07-11
D-HST11 | St Petersburg | 2025-10-30 | GN Systems | 2025-09-27 | Noah | PPM102171 | 86 | Completed on Track | Received | 2025-09-17 | Yes | 45500 | 43489 |  | 43489 | Yes | Completed | 2025-09-17 | 3242 | 3228 | 99.57% | 2025-09-30 | 0% | 0% | 0 | 2025-10-28 | 2025-10-28
D-HNP104/D-H0102A | St Petersburg | 2025-07-24 | Longo Underground | 2025-03-27 | Tim | PPM93993 | 88 | Completed on Track | Received | 2025-03-25 | Yes | 75396.5 | 75756.5 |  | 75756.5 | Yes | Completed | 2025-04-02 | 6061 | 6217 | 103% | 2025-05-08 | 0% | 0% | 0% | 2025-08-18 | 2025-08-18
D-HNP123 | St Petersburg | 2025-07-24 | HDD Underground | 2025-02-06 | Betsy | PPM89671 | 90 | Completed on Track | Received | 2025-02-10 | Yes | 68216.5 | 65624.5 |  | 65624.5 | Yes | Completed | 2025-02-10 | 5410 | 5337 | 99% | 2025-03-03 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | reassigned to MTX. 4-29-25 needs new reassignment./ 2/27 Light Level Received.
D-HNP137 | St Petersburg | 2025-04-30 | FCA Fiber | 2025-02-12 | Betsy | PPM89749 | 78 | Completed | Received | 2025-02-20 | Yes | 56854 | 62254 |  | 62254 | Yes | Completed | 2025-02-08 | 5239 | 5205 | 99.35% | 2025-02-28 | 100% | 100% | 100% | 2025-05-14 | 2025-05-14
D-HNP138 | St Petersburg | 2025-03-26 | FCA Fiber | 2025-02-06 | Betsy | PPM89683 | 87 | Completed | Received | 2025-02-20 | Yes | 73639 | 73025 |  | 73025 | Yes | Completed | 2025-02-08 | 5868 | 5979 | 101.9% | 2025-02-26 | 100% | 100% | 100% | 2025-04-11 | 2025-04-11
D-HNP141 | St Petersburg | 2025-03-31 | Power Connect | 2025-02-12 | Robert | PPM89690 | 60 | Completed | Received | 2025-02-10 | Yes | 54861 | 55197 |  | 55197 | Yes | Completed | 2025-02-10 | 4552 | 4552 | 100% | 2025-03-11 | 100% | 100% | 100% | 2025-06-03 | 2025-06-03
D-HNP143 | St Petersburg | 2025-03-31 | Brothers | 2025-02-10 | Johnnie | PPM89772 | 87 | Completed | Received | 2025-02-11 | Yes | 72566 | 83382 |  | 83382 | Yes | Completed | 2025-02-11 | 6133 | 6133 | 98% | 2025-03-05 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | 6/17/2025 JW ¦ RESTORATION COMPLETE \\ PENDING TILLMAN WALKOUT. 8-18-25 rescheduled walkout for 9-4-25
D-HNP151 | St Petersburg | 2025-06-30 | Longo Underground | 2025-03-20 | Tim | PPM90865 | 50 | Completed on Track | Received | 2025-03-19 | Yes | 41285 | 40484 |  | 40484 | Yes | Completed | 2025-03-20 | 3415 | 3445 | 100.9% | 2025-04-02 | 100% | 100% | 100% | 2025-07-21 | 2025-07-21
FB-H0221A | St Petersburg | 2025-03-26 | HAS Global | 2025-02-19 | Johnnie | PPM89791 | 0 | Completed -Missed TSD | Received | 2025-02-28 | Yes | 21944.6 | 26564 |  | 26564 | Yes | Completed | 2025-02-28 | 1695 | 1634 | 96.4% | 2025-03-18 | 100% | 100% | 100% | 2025-07-11 | 2025-07-11 | 5/14/2025 PENDING RESTO / TILLMAN / LIGHT LEVELS
FB-H0222A | St Petersburg | 2025-02-23 | Bartlett Fiber | 2025-02-07 | Caten | PPM88374 | 0 | Completed -Missed TSD | Received | 2025-02-07 | Yes | 20939.75 | 13575.75 |  | 13575.75 | Yes | Completed | 2025-02-05 | 1235 | 1160 | 93.93% | 2025-03-11 | 100% | 100% | 100% | 2025-08-19 | 2025-08-19
FB-H0223A | St Petersburg | 2025-02-23 | Power Connect | 2025-02-06 | Robert | PPM89789 | 0 | Completed -Missed TSD | Received | 2025-01-29 | Yes | 22755.7 | 23864.1 |  | 23864.1 | Yes | Completed | 2025-02-05 | 1735 | 1725 | 99% | 2025-03-13 | 100% | 100% | 100% | 2025-08-26 | 2025-08-26 | COP EMAILED TO BILLING 10/10/2025
FB-HDH02A | St Petersburg | 2025-06-25 | Multiple | TBD | EVERYONE | PPM87852 | 0 | Completed on Track | Received | Completed | Yes | 289634.75 | 296306.83 |  | 296306.83 | Yes | Completed | 2025-02-05 | 22725 | 22085 | 100% | 2025-01-17 | 100% | 100% | 100% | 2025-08-13 | 2025-08-13 | 5/14/2025 JW ¦ LOCATES SENT TO LAUREN TO BE CALLED IN 5/15/2025. 7-18-25 finishing gig list.
D-HNP117/D-H0103G | St Petersburg | 2025-11-30 | FCA/Lightspeed In-House | 2025-03-27 | Johnnie | PPM93990 | 60 | Completed on Track | Received | 2025-03-25 | Yes | 47849 | 51778 |  | 51778 | Yes | Completed | 2025-03-28 | 4194 | 4448 | 106% | 2025-05-07 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11 | 9-25 - 25 JW Passed Tillman Insecption, pending QAQC Form from Brian DiLillo
FB-HDH01A-2A | St Petersburg | 2025-06-30 | In House | 2025-06-16 | Johnnie | PPM96333 | 0 | Completed on Track | Received | N/A | Yes | 1594 | 1187.5 |  | 1187.5 | Yes | Completed | 2025-06-10 | 65 | 65 | 100% | 2025-06-23 | 100% | 100% | 100% | 2025-07-21 | 2025-07-21 | Partial Completed--SOW Shows The Whole Project, But This Is To Complete 4100' Left On The Project.
Sunset Palms MHP | St Petersburg | 2025-12-17 | Multiple | 2025-10-28 | Johnnie | PPM103768 | 517 | Completed -Missed TSD | Not Required | 2025-11-03 | Yes | 215088 | 215088 | 53710 | 268798 | Yes | Completed | 2025-10-30 | 22238 | 22321 | 100.4% | 2025-11-04 | 100% | 100% | 100% | 2026-02-23 | 2026-02-23 | 12/3 CX Construction Continuing--7 Flower Pots Installed./ 12/4 CX Construction Continuing--Progress At 80% Complete./ 12/9 CX Construction Continuing--1 FDH and 1 HH Installed./ 12/10 CX Construction Continuing--Progress At 99% Complete./ 12/10 CX Construction Continuing--12 Flowerpots Installed./ 12/11 CX Construction Continuing--14 Flowerpots Installed./ 12/15 CX Construction Continuing--Progress At 100% Complete./ 12/15 CX Construction Continuing--1 Flowerpot Installed./ 12/15 CX Construction Continuing--2 FDH's and 2 HH's Installed./ 12/16 CX Construction Complete--1 FDH and 1 HH Installed./ 12/17 CX Construction Complete--4 Flowerpots Installed./ 12/18 CX Construction Complete--3 Flowerpots Installed./ 1/13 CX Complete...Change Order Request Sent to Tillman for Added Footage.
D-HBK130 | Spring Hill | 2026-01-30 | Brothers | 2026-01-05 | Treyvon |  | 68 | Completed on Track | Received | 2026-01-05 | Yes | 68608 | 68438 | 0 | 68212 | Yes | Completed | 2026-01-05 | 5699 | 5669 | 99% | 2026-01-12 | 100% | 100% | 100% | 2026-01-30 | 2026-04-29 | 11/24 Permit Received With NTP Package. 1/5 assigned to brothers to call in locates/door tag. / 1/12 CX started / 1/12- tickets escalated/ 1/27 CX Complete--HH, FDH Installed./ 1/28 CX Complete--12F Stingray Placed.
D-HBK131 | Spring Hill | 2026-01-30 | Brothers | 2026-01-05 | Treyvon |  | 85 | Completed on Track | Received | 2026-01-05 | Yes | 73334 | 73164 | 0 | 73574 | Yes | Completed | 2026-01-05 | 5860 | 5883 | 100% | 2026-01-12 | 100% | 100% | 100% | 2026-01-30 | 2026-04-29 | 11/24 Permit Received With NTP Package. 1/5 assigned to brothers to call in locates/door tag. / 1/12 CX started / 1/12- tickets escalated/ 1/27 CX Complete--HH, FDH Installed.
D-HBK132 | Spring Hill | 2026-01-30 | Brothers | 2026-01-05 | Treyvon |  | 81 | Completed on Track | Received | 2026-01-05 | Yes | 73885 | 73715 |  | 73715 | Yes | Completed | 2026-01-05 | 6021 | 6092 | 101% | 2026-01-13 | 100% | 100% | 100% | 2026-01-30 | 2026-04-29 | 11/24 Permit Received With NTP Package. 1/5 assigned to brothers to call in locates/door tag. / 1/12- tickets escalated/ 1/28 CX Complete--12F Stingray Placed
D-HBK133 | Spring Hill | 2026-01-30 | Brothers | 2026-01-05 | Treyvon |  | 87 | Completed on Track | Received | 2026-01-05 | Yes | 78025 | 75733.5 | 0 | 75733.5 | Yes | Completed | 2026-01-05 | 6432 | 6309 | 98% | 2026-01-13 | 100% | 100% | 100% | 2026-01-30 | 2026-04-29 | 11/24 Permit Received With NTP Package. 1/5 assigned to brothers to call in locates/door tag. / 1/12- tickets escalated/ 1/22- Path IP. 1/23 email sent to brothers to update us on the remaining footage. His email redline matches the inspector as of 1/23/ complete,proofing fdh today/ 1/29 CX Construction Continues--12F Stingray Placed.
D-HBK134 | Spring Hill | 2026-01-30 | Brothers | 2026-01-05 | Treyvon |  | 68 | Completed on Track | Received | 2026-01-05 | Yes | 59114.5 | 58944.5 | 960.5 | 59905 | Yes | Completed | 2026-01-05 | 4836 | 4894 | 101% | 2026-01-14 | 100% | 100% | 100% | 2026-01-30 | 2026-04-24 | 11/24 Permit Received With NTP Package. 1/5 assigned to brothers to call in locates/door tag. / 1/12- tickets escalated/ 1/27 CX Complete--HH, FDH Installed./ 1/29 CX Complete--12F Stingray Placed
D-HBK135 | Spring Hill | 2026-01-30 | Brothers | 2026-01-05 | Treyvon |  | 90 | Completed on Track | Received | 2026-01-05 | Yes | 88362 | 88192 | 5687 | 93879 | Yes | Completed | 2026-01-05 | 7145 | 7173 | 100% | 2026-01-14 | 100% | 100% | 100% | 2026-02-06 | 2026-04-29 | 11/24 Permit Received With NTP Package. 1/5 assigned to brothers to call in locates/door tag. / 1/12- tickets escalated/ .1/22- Path IP/pending fs/ 1/27 CX Continues--HH, FDH Installed.
D-HBK136 | Spring Hill | 2026-01-30 | Brothers | 2026-01-05 | Treyvon |  | 90 | Completed on Track | Received | 2026-01-05 | Yes | 86984 | 86814 |  | 86814 | Yes | Completed | 2026-01-05 | 7341 | 7212 | 98% | 2026-01-15 | 100% | 100% | 100% | 2026-01-26 | 2026-06-09 | 11/24 Permit Received With NTP Package. 1/5 assigned to brothers to call in locates/door tag. / 1/12- locates are clear pending brothers to start/ 1/15 CX Construction Started/ 1/27 CX Complete--Toby, Dap, HH, FDH Installed./ 1/29 12F Stingray Installed
FB-HBK104 | Spring Hill | 2026-01-30 | Brothers | 2026-01-05 | Anthony |  | 0 | Completed on Track | Received | 2026-01-05 | Yes | 54261.05 | 45087.05 |  | 45087.05 | Yes | Completed | 2026-01-05 | 4022 | 4019 | 100% | 2026-01-15 | 100% | 100% | 100% | 2026-02-06 | 2026-06-09 | 11/24 Permit Received With NTP Package. 1/5 assigned to brothers to call in locates/door tag./ 1/12- tickets escalated/
FB-HBK130 | Spring Hill | 2026-01-30 | Brothers | 2026-01-05 | Anthony |  | 0 | Completed on Track | Received | 2026-01-05 | Yes | 18078.28 | 19162.75 |  | 19162.75 | Yes | Completed | 2026-01-05 | 1284 | 1277 | 99% | 2026-01-20 | 100% | 100% | 100% | 2026-02-06 | 2026-06-09 | 11/24 Permit Received With NTP Package. 1/5 assigned to brothers to call in locates/door tag./ 1/12- tickets escalated/ 1/27 CX Complete--48F Placed, Pending Splicing. 4 HH.
D-HSH220 | Spring Hill | 2026-01-23 | Brothers |  | Byvertek |  | 80 | Completed on Track | Received | N/A | Yes | 170 | 588.8 |  | 588.8 | Yes | Completed | TBD | 7137 | 7141 | 100% | 2025-11-03 | 100% | 100% | 100% | 2025-12-08 | 2026-04-03 | 11/5 Project Print Pulled Out Of SharePoint--Pending NTP Package. / 11/12 per Brothers, they completed this with Byvertek. / 11/21 SR blown to 221/222.
D-HSH221 | Spring Hill | 2026-01-23 | Brothers |  | Byvertek |  | 89 | Completed on Track | Received | N/A | Yes | 26696 | 499.4 |  | 499.4 | Yes | Completed | TBD | 8153 | 8114 | 100% | 2025-11-03 | 100% | 100% | 100% | 2025-12-08 | 2026-04-03 | 11/5 Project Print Pulled Out Of SharePoint--Pending NTP Package. / 11/11 no UG footage for LS, this appears completed in October by previous company. / 11/12 per Brothers, they completed this with Byvertek. / 11/21 SR blown to 220.
D-HSH222 | Spring Hill | 2026-01-23 | Brothers | 2025-10-29 | Byvertek | PLK104052 | 78 | Completed on Track | Received | 2025-11-03 | Yes | 170 | 88586 |  | 88586 | Yes | Completed | 2025-11-03 | 7522 | 7522 | 100% | 2025-11-03 | 100% | 100% | 100% | 2025-12-08 | 2026-05-01 | 11/5 Project Print Pulled Out Of SharePoint--Pending NTP Package. / 11/11 path is complete, fed via SR from D-HSH219, need info on this job aswell as 222 NTP. Needs SR blown to 219. / 11/21 SR blown to 220, pending another company to complete 219 to blow to 219. / 12/15 - Construction Complete...HH and FDH Installed./
D-HSH223 | Spring Hill | 2025-12-28 | Brothers | 2025-10-29 | Byvertek | PLK104062 | 89 | Completed on Track | Received | 2025-11-03 | Yes | 62937.05 | 52828.55 |  | 52828.55 | Yes | Completed | 2025-11-03 | 8523 | 8523 | 100% | 2025-11-05 | 100% | 100% | 100% | 2025-12-11 | 2026-03-06 | 11/5 Project Print Pulled Out Of SharePoint--Pending NTP Package. / 11/11 cx started, pending material and NTP / 11/12 / 12/4- SR placed to 213, pending power locates to complete Forest Oaks Blvd./ 12/10 48 Ct Fiber Placed with Trace Wire/ 1/6 FDH HH Dap Toby Installed
D-HSH224 | Spring Hill | 2026-01-30 | Brothers | 2025-10-29 | Byvertek | CIT105499 | 83 | Completed on Track | Received | N/A | Yes | 45545.15 | 37182.15 |  | 37182.15 | Yes | Completed | 2025-10-16 | 4120 | 4120 | 100% | 2025-11-04 | 100% | 100% | 100% | 2026-02-04 | 2026-05-06 | 1/20 FDH with Swing Arm Installed. 1/22 - reconciling brothers info as they have worked out here without telling LSCG./85% complete,verifying.
D-HSH225 | Spring Hill | 2026-01-23 | Brothers | 2025-10-29 | Byvertek |  | 77 | Completed on Track | Received | N/A | Yes | 4046.5 | 7377.15 |  | 7377.15 | Yes | Completed | TBD | 5136 | 5136 | 100% | 2025-11-03 | 100% | 100% | 100% | 2025-12-08 | 2026-03-25 | 11/5 Project Print Pulled Out Of SharePoint--Pending NTP Package. / 11/12 per Brothers, they completed this with Byvertek. / 11/26- SR and 48f placed, RTS.
D-HSH227 | Spring Hill | 2026-01-23 | Brothers |  | Byvertek |  | 62 | Completed on Track | Received | N/A | Yes | 170 | 948 |  | 948 | Yes | Completed | TBD | 4095 | 4088 | 100% | 2025-11-03 | 100% | 100% | 100% | 2025-12-11 | 2026-04-02 | 11/5 Project Print Pulled Out Of SharePoint--Pending NTP Package. / 11/12 per Brothers, they completed this with Byvertek. / 11/28- SR placed RTS.
D-HSH228 | Spring Hill | 2026-01-23 | Brothers |  | Byvertek |  | 80 | Completed on Track | Received | N/A | Yes | 25891 | 618.6 |  | 618.6 | Yes | Completed | TBD | 5254 | 5254 | 100% | 2025-11-03 | 100% | 100% | 100% | 2025-12-11 | 2026-05-01 | 11/5 Project Print Pulled Out Of SharePoint--Pending NTP Package. / 11/12 per Brothers, they completed this with Byvertek. / 11/28- SR placed RTS. Phase 2 Failed Gig List Uploaded On 3/6/2026.
D-HSH229 | Spring Hill | 2026-01-23 | Brothers |  | Byvertek |  | 83 | Completed on Track | Received | N/A | Yes | 170 | 499.4 |  | 499.4 | Yes | Completed | TBD | 5947 | 5947 | 100% | 2025-11-03 | 100% | 100% | 100% | 2025-12-11 | 2026-05-01 | 11/5 Project Print Pulled Out Of SharePoint--Pending NTP Package. / 11/12 per Brothers, they completed this with Byvertek. / 11/26- SR placed, RTS. Phase 2 Failed Gig List Uploaded On 3/6/2026.
D-HSH230 | Spring Hill | 2026-01-23 | Brothers |  | Byvertek |  | 85 | Completed on Track | Received | N/A | Yes | 30788 | 678.2 |  | 678.2 | Yes | Completed | TBD | 5599 | 5599 | 100% | 2025-11-03 | 100% | 100% | 100% | 2025-12-08 | 2026-04-02 | 11/5 Project Print Pulled Out Of SharePoint--Pending NTP Package. / 11/12 per Brothers, they completed this with Byvertek. / 11/21- SR complete RTS.
D-HSH231 | Spring Hill | 2026-01-23 | Brothers | 2025-10-29 | Byvertek |  | 88 | Completed on Track | Received | N/A | Yes | 5668 | 588.8 |  | 588.8 | Yes | Completed | TBD | 6646 | 6623 | 100% | 2025-11-03 | 100% | 100% | 100% | 2025-12-08 | 2026-04-02 | 11/5 Project Print Pulled Out Of SharePoint--Pending NTP Package. / 11/12 per Brothers, they completed this with Byvertek. / 11/28- SR placed RTS.
D-HSH232 | Spring Hill | 2026-01-23 | Brothers | 2025-10-29 | Byvertek |  | 30 | Completed on Track | Received | N/A | Yes | 170 | 499.4 |  | 499.4 | Yes | Completed | TBD | 2136 | 2136 | 100% | 2025-11-12 | 100% | 100% | 100% | 2025-12-11 | 2026-04-02 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s/cx started 11-12 / 11/13 CX IP. 11/24 - two crossings left.
D-HSH236 | Spring Hill | 2026-01-30 | Brothers | 2025-12-02 | Anthony | CIT105412 | 89 | Completed on Track | Received | 2025-12-02 | Yes | 93349.5 | 78956.5 |  | 78956.5 | Yes | Completed | 2025-12-02 | 7828 | 7828 | 100% | 2025-12-03 | 100% | 100% | 100% | 2026-01-26 | 2026-04-02 | 12/1 NTP Package Received./
D-HSH237 | Spring Hill | 2026-01-23 | Brothers | 2025-10-29 | Anthony |  | 89 | Completed on Track | Received | 2025-11-03 | Yes | 84750.5 | 69665.5 |  | 69665.5 | Yes | Completed | 2025-11-03 | 6935 | 6935 | 100% | 2025-11-12 | 100% | 100% | 100% | 2026-01-12 | 2026-03-25 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s/cx started 11-12 / 11/13 CX IP. 11/24 - two crossings left.
D-HSH238 | Spring Hill | 2025-11-28 | Brothers | 2025-10-29 | Anthony | CIT105495 | 59 | Completed on Track | Received | 2025-11-03 | Yes | 65066.5 | 54887.5 | 10298.2 | 65185.7 | Yes | Completed | 2025-11-03 | 5421 | 5466 | 101% | 2025-11-24 | 100% | 100% | 100% | 2026-01-12 | 2026-03-19 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/24- CX IP. / 12/2- path is complete, working on toby/DAP/vult, pending fiber pulling on FB-HSH238 for heat up.
D-HSH239 | Spring Hill | 2025-12-19 | Brothers | 2025-10-29 | Anthony | CIT105410 | 89 | Completed on Track | Received | 2025-11-03 | Yes | 81602 | 67737 | 14059 | 81796 | Yes | Completed | 2025-11-03 | 6752 | 6752 | 100% | 2025-12-01 | 100% | 100% | 100% | 2026-01-12 | 2026-04-06 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 12/1- CX IP.
D-HSH240 | Spring Hill | 2026-01-23 | Brothers | 2025-10-29 | Anthony |  | 88 | Completed on Track | Received | 2025-10-31 | Yes | 88231.9 | 75168.9 | 12548.6 | 87717.5 | Yes | Completed | 2025-10-31 | 7274 | 7274 | 100% | 2025-11-07 | 100% | 100% | 100% | 2026-01-02 | 2026-04-03 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/11- no drilling on Veterans Day, 97% complete, SR is dependent on completion of D-HSH239/242.
D-HSH241 | Spring Hill | 2025-11-28 | Brothers | 2025-10-29 | Anthony | PLK104415 | 87 | Completed on Track | Received | 2025-11-03 | Yes | 93578 | 78339 | 15143 | 93482 | Yes | Completed | 2025-11-03 | 7782 | 7782 | 100% | 2025-11-14 | 100% | 100% | 100% | 2026-01-02 | 2026-04-03
D-HSH242 | Spring Hill | 2026-01-23 | Brothers | 2025-10-29 | Anthony |  | 90 | Completed on Track | Received | 2025-11-03 | Yes | 84896 | 70895 | 14120.6 | 85015.6 | Yes | Completed | 2025-11-03 | 7060 | 7060 | 100% | 2025-11-12 | 100% | 100% | 100% | 2026-01-02 | 2026-04-03 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/11 - pending completed locates and material / 11/12 cx started / 11/13 cx IP. 11/14 Path complete, Future SR to be blown to 251 pending 251cx. Need to blow stingray to D-HSH240./ 12/17 Path Complete, HH and FDH Installed.
D-HSH243 | Spring Hill | 2025-12-28 | Brothers | 2025-10-29 | Anthony | PLK104185 | 90 | Completed on Track | Received | 2025-10-31 | Yes | 91897 | 76050 |  | 76050 | Yes | Completed | 2025-10-31 | 7457 | 7468 | 100% | 2025-11-13 | 100% | 100% | 100% | 2026-01-12 | 2026-06-04 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/11 - pending completed locates and material / 11/13 cx started / 11/18 CX IP / 11/24 last stretch of piping needs to be completed on Nevada St./ 12/12 CX Construction Complete--32 Toby Boxes Installed./
D-HSH244 | Spring Hill | 2025-11-28 | Brothers | 2025-10-29 | Anthony | PLK104741 | 90 | Completed on Track | Received | 2025-11-03 | Yes | 96685 | 80682 | 16197 | 96879 | Yes | Completed | 2025-11-03 | 7926 | 8042 | 101% | 2025-11-20 | 100% | 100% | 100% | 2026-01-02 | 2026-06-04 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/11 - pending completed locates and material / 11/20 - cx started / 11/24 - cx ip/
D-HSH245 | Spring Hill | 2025-12-28 | Brothers | 2025-10-29 | Anthony | PLK104743 | 90 | Completed on Track | Received | 2025-11-03 | Yes | 85815 | 71126 | 14443 | 85569 | Yes | Completed | 2025-11-03 | 6981 | 6963 | 100% | 2025-11-20 | 100% | 100% | 100% | 2026-01-02 | 2026-04-06 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/11 - pending completed locates and material 11/21- CX started/
D-HSH246 | Spring Hill | 2025-12-30 | Brothers | 2025-10-29 | Anthony | CIT105234 | 89 | Completed on Track | Received | 2025-10-31 | Yes | 83615 | 70350 | 11859 | 82209 | Yes | Completed | 2025-10-31 | 7010 | 6748 | 96% | 2025-11-25 | 100% | 100% | 100% | 2026-01-26 | 2026-06-04 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/11 - pending completed locates and material/ 1/9 CX Construction Complete--12F Stingray Placed, Splicing Will Follow. 1/9- SR placed and RTS, coming from 247.
D-HSH247 | Spring Hill | 2025-12-30 | Brothers | 2025-10-29 | Anthony | CIT105414 | 88 | Completed on Track | Received | 2025-11-03 | Yes | 78736.5 | 65465.5 |  | 65465.5 | Yes | Completed | 2025-11-03 | 6403 | 6403 | 100% | 2025-12-09 | 100% | 100% | 100% | 2026-01-26 | 2026-05-04 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/11 - pending completed locates and material./ / 1/12- Trey sent email to Brothers about continuity issue and to have them proof the SR duct from D-HSH249.
D-HSH248 | Spring Hill | 2025-12-30 | Brothers | 2025-10-29 | Anthony | CIT105415 | 86 | Completed on Track | Received | 2025-11-03 | Yes | 80698 | 67837 | 12683 | 80520 | Yes | Completed | 2025-11-03 | 6739 | 6739 | 100% | 2025-12-17 | 100% | 100% | 100% | 2026-01-31 | 2026-05-04 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/11 - pending completed locates and material/ 1/6 CX Construction Complete--43 Toby Boxes and 10 Daps Installed./ 1/7 CX Construction Complete--FDH Installed. / 1/12- Trey sent email to Brothers about continuity issue and to have them proof the SR duct from D-HSH246/ 1/9 CX Construction Complete--104' Additional Drill. / 1-23 SR placed, sent RTS email to Eric. Failed Gig List Uploaded On 3/24/2026.
D-HSH249 | Spring Hill | 2026-01-30 | Brothers | 2025-10-29 | Anthony | CIT105418 | 87 | Completed on Track | Received | 2025-11-03 | Yes | 79552 | 66689 |  | 66689 | Yes | Completed | 2025-11-03 | 6577 | 6577 | 100% | 2025-12-09 | 100% | 100% | 100% | 2026-01-26 | 2026-05-04 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/11 - pending completed locates and material ./ 1/14 CX Construction Continues--12F Stingray Placed to 248. / 2/5 CX Construction Complete--Progress at 100% Complete.
D-HSH250 | Spring Hill | 2025-12-30 | Brothers | 2025-10-29 | Anthony | CIT105421 | 85 | Completed on Track | Received | 2025-11-03 | Yes | 84770 | 70169 |  | 70169 | Yes | Completed | 2025-11-03 | 6965 | 6758 | 97% | 2025-12-08 | 100% | 100% | 100% | 2026-01-26 | 2026-06-04 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/11 - pending completed locates and material./ 1/7 CX Construction Complete--FDH Installed. / 1/9- SR placed and RTS, coming from 249.
D-HSH251 | Spring Hill | 2025-12-28 | Brothers | 2025-10-29 | Anthony | CIT105424 | 87 | Completed on Track | Received | 2025-11-03 | Yes | 87875 | 74526 |  | 74526 | Yes | Completed | 2025-11-03 | 7319 | 7319 | 100% | 2025-12-09 | 100% | 100% | 100% | 2026-01-12 | 2026-04-08 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s/ 11/11 - pending completed locates and material/ 1/5 CX Construction Complete...12F Stingray Placed.
D-HSH252 | Spring Hill | 2026-01-30 | Brothers | 2025-11-26 | Anthony | CIT105434 | 85 | Completed on Track | Received | 2025-11-26 | Yes | 84092.5 | 69227.5 | 14865 | 84092.5 | Yes | Completed | 2025-11-26 | 6897 | 6897 | 100% | 2025-12-18 | 100% | 100% | 100% | 2026-01-26 | 2026-04-08 | 11/24 Permit Received With NTP Package/ ./proofing 12-30/need stingray/ 2/2 CX Complete...12F Stingray Placed
D-HSH253 | Spring Hill | 2026-01-30 | Brothers | 2025-11-26 | Anthony | CIT105436 | 76 | Completed on Track | Received | 2025-11-26 | Yes | 74892.5 | 62257.5 | 12829 | 75086.5 | Yes | Completed | 2025-11-26 | 6218 | 6218 | 100% | 2026-12-30 | 100% | 100% | 100% | 2026-01-30 | 2026-04-08 | 11/24 Permit Received With NTP Package/ 1/6 CX Construction Complete--Progress At 100% Complete./ 1/28 CX Construction Complete...12F Stingray Placed./ 1/29 CX Construction Complete...FDH Placed.
D-HSH254 | Spring Hill | 2026-01-30 | Brothers | 2025-11-26 | Anthony | CIT105439 | 86 | Completed on Track | Received | 2025-11-26 | Yes | 90841 | 75112 | 15107 | 90219 | Yes | Completed | 2025-11-26 | 7491 | 7491 | 100% | 2025-12-18 | 100% | 100% | 100% | 2026-01-30 | 2026-04-08 | 11/24 Permit Received With NTP Package/ 1/22- pending splice/
D-HSH255 | Spring Hill | 2026-01-30 | Brothers | 2025-11-26 | Anthony | CIT105440 | 78 | Completed on Track | Received | 2025-11-26 | Yes | 68606.5 | 54793.5 | 13958.5 | 68752 | Yes | Completed | 2025-11-26 | 5456 | 5441 | 100% | 2026-01-06 | 100% | 100% | 100% | 2026-01-30 | 2026-04-07 | 11/24 Permit Received With NTP Package. 1/5 assigned to brothers to call in locates/door tag./ 1/7 CX Construction Continues--Progress At 100% Complete./ 1/28 CX Construction Complete--12F Stingray Placed.
D-HSH256 | Spring Hill | 2026-01-30 | Brothers | 2025-11-26 | Anthony | CIT105441 | 73 | Completed on Track | Received | 2025-11-26 | Yes | 71371 | 58248 |  | 58248 | Yes | Completed | 2025-11-26 | 5810 | 5674 | 98% | 2026-01-08 | 100% | 100% | 100% | 2026-01-30 | 2026-06-04 | 11/24 Permit Received With NTP Package. 1/8 cx started/ ll rec 1-26/ 1/21 CX Continues--HH, FDH Installed.
FB-HSH238 | Spring Hill | 2025-12-28 | Brothers | 2025-10-29 | Anthony | CIT105442 | 0 | Completed on Track | Received | 2025-10-31 | Yes | 64985.65 | 41925.15 |  | 41925.15 | Yes | Completed | 2025-11-03 | 5155 | 5169 | 100% | 2025-12-01 | 100% | 100% | 100% | 2026-01-18 | 2026-05-12 | 11/7 NTP Package Received--Pending Fiber Details Splicing Document. / 11/11 - pending completed locates and material 11/18 CX IP and being worked under D238 D237 D241/ proofing 12-30 / 1/12 - Brotehrs placing fiber to D-HSH236
FB-HSH241 | Spring Hill | 2025-12-28 | Brothers | 2025-10-29 | Anthony | PLK104184 | 0 | Completed on Track | Received | 2025-10-31 | Yes | 54043.5 | 46053.5 |  | 46053.5 | Yes | Completed | 2025-10-31 | 4140 | 4140 | 100% | 2025-11-13 | 100% | 100% | 100% | 2026-01-18 | 2026-05-12 | 10/28 Permit Received With NTP Package. / 10/29 assigned to Brothers pending their locate #s / 11/11 - pending completed locates and material / 11/13 cx started / 11/24- need to complete pipe along Beach Rd. to tie into FB-HSH238 and D-HSH241./ Failed Gig List Uploaded On 4/12/2026.
Repairs | [14 empty] | 78461.5
[12 empty] | 17875125.43 |  |  | 17882805.07
Sent To Biz Ops--Pending To Be Sent To Tillman
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Door Tag Date | SOW Received | SOW Estimated Cost | Invoice Amount Paid | Phase 2 Invoice | Total Invoice | NTP Received | Constuction Status | Locate Date | Footage UG | Actual Redline Completed Footage UG | UG Percentage Complete | Construction Start Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Construction Total Percent Complete | QC Received From Tillman | Phase 2 QC Received From Tillman | Comments
BHU-FLX-01-W | Bradenton | 2026-05-30 | North Path | 2026-04-27 | Cody | MAN108638 | 0 | Completed on Track | Received | N/A | Yes | 85069.95 |  |  | 85069.95 | Yes | Completed | 2026-03-12 | 6787 | 6802 | 0% | 2026-04-27 | 100% | 100% | 100% | 2026-07-23 | 2026-07-23 | 3/4 NTP and SOW Received.3/12 LC.
BHUD-FOE-06-E-2 | Bradenton | 2025-12-08 | Lightspeed In-House | 2025-11-14 | Betsy | MAN104073 | 0 | Completed on Track | Received | 2025-10-30 | Yes | 4911.9 |  |  | 4911.9 | Yes | Completed | 2025-10-30 | 294 | 321 | 109.2% | 2025-11-18 | 100% | 100% | 100% | Failed On 6/25/2026 | Failed On 6/25/2026 | 10/24 FDOT Permit Received./ 1/8 Close Out Package Received...Need Tillman QC Complete. Failed Gig List Received From Tillman On 4/27.
D-HAL115 | Bradenton | 2026-09-30 | North Path | 2026-08-17 | Cody | MAN113034 | 61 | Completed on Track | Received | N/A | Yes | 43230 |  |  | 43230 | Yes | Completed | 2026-08-21 | 3138 | 3192 | 101.7% | 2026-08-31 | 100% | 100% | 100% | 2026-09-18 | 2026-09-18 | 8/17 NTP Package Received
D-HOE116 | Bradenton | 2025-05-30 | Power Connect | TBD | Joshua | MAN90788 | 84 | Completed on Track | Received | 2025-02-28 | Yes | 2812.95 |  |  | 2812.95 | Yes | Completed | 2025-05-15 | 285 | 285 | 100% | 2025-05-21 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | Failed Gig List Uploaded On 10/29/2026.
D-HOE215 | Bradenton | 2025-11-30 | Raven | 2025-02-28 | Joshua | MAN91697 | 44 | Completed on Track | Received | 2025-02-28 | Yes | 57973.5 |  |  | 57973.5 | Yes | Completed | 2025-02-28 | 4885 | 4650 | 95.19% | 2025-03-25 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | Failed Gig List Uploaded On 1/15/2026.
D-HOE503 | Bradenton | 2026-06-08 | North Path | 2026-06-22 | Cody |  | 47 | Completed on Track | Received | N/A | Yes | 36936 |  |  | 36936 | Yes | Completed | 2026-06-23 | 2724 | 2732 | 100.3% | 2026-07-07 | 100% | 100% | 100% | 2026-08-06 | 2026-08-06 | 4/24 NTP Package Received.
D-HLX408 | Bradenton | 2026-08-30 | North Path | 2026-07-30 | Cody | MAN112892 | 58 | Completed on Track | Received | 2026-08-17 | Yes | 71336.1 |  |  | 71336.1 | Yes | Completed | 2026-07-31 | 5678 | 5719 | 100.7% | 2026-08-17 | 100% | 100% | 100% | 2026-09-29 | 2026-09-29 | 7/29 NTP Package Received.
D-HLX501 | Bradenton | 2026-06-18 | Power Connect | 2026-04-30 | Cody |  | 58 | Completed on Track | Received | N/A | Yes | 56668.15 |  |  | 56668.15 | Yes | Completed | 2026-05-02 | 4061 | 4061 | 100% | 2026-05-11 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 4/29 NTP Package Received.
D-HLX502 | Bradenton | 2026-06-18 | North Path | 2026-05-29 | Cody |  | 61 | Completed on Track | Received | N/A | Yes | 44936 |  |  | 44936 | Yes | Completed | 2026-05-04 | 3375 | 3523 | 104.4% | 2026-08-11 | 100% | 100% | 100% | 2026-08-31 | 2026-08-31 | 4/29 NTP Package Received. On hold due to community shutdown. CX start 7-13-26 again
D-HLX504 | Bradenton | 2026-06-18 | North Path | 2026-05-29 | Cody |  | 86 | Completed on Track | Received | N/A | Yes | 64118 |  |  | 64118 | Yes | Completed | 2026-06-01 | 4753 | 4870 | 102.5% | 2026-07-27 | 100% | 100% | 100% | 2026-09-02 | 2026-09-02 | 4/29 NTP Package Received. On hold due to community shutdown. CX start 7-13-26 again
D-HLX506 | Bradenton | 2026-06-18 | North Path | 2026-05-21 | Cody | MAN111852 | 82 | Completed on Track | Received | N/A | Yes | 60234 |  |  | 60234 | Yes | Completed | 2026-05-22 | 4497 | 4556 | 101.3% | 2026-07-16 | 100% | 100% | 100% | 2026-08-11 | 2026-08-11 | 4/29 NTP Package Received. On hold due to community shutdown. CX start 7-13-26 again
D-HLX507 | Bradenton | 2026-06-18 | Power Connect | 2026-04-30 | Cody |  | 81 | Completed on Track | Received | N/A | Yes | 66206 |  |  | 66206 | Yes | Completed | 2026-05-02 | 5035 | 4865 | 96.62% | 2026-05-22 | 0% | 0% | 0 | 2026-07-17 | 2026-09-18 | 4/29 NTP Package Received.
D-HLX508 | Bradenton | 2026-06-18 | North Path | 2026-05-29 | Cody |  | 55 | Completed on Track | Received | N/A | Yes | 45757.7 |  |  | 45757.7 | Yes | Completed | 2026-06-01 | 3537 | 3463 | 97.91% | 2026-07-27 | 100% | 100% | 100% | 2026-09-02 | 2026-09-02 | 4/29 NTP Package Received. On hold due to community shutdown. CX start 7-13-26 again
D-HLX509 | Bradenton | 2026-06-18 | North Path | 2026-05-29 | Cody |  | 54 | Completed on Track | Received | N/A | Yes | 39903.55 |  |  | 39903.55 | Yes | Completed | 2026-06-01 | 3000 | 3097 | 103.2% | 2026-07-14 | 100% | 100% | 100% | 2026-08-12 | 2026-08-12 | 4/29 NTP Package Received. On hold due to community shutdown. CX start 7-13-26 again
D-HLX510 | Bradenton | 2026-06-18 | North Path | 2026-05-29 | Cody |  | 78 | Completed on Track | Received | N/A | Yes | 58190 |  |  | 58190 | Yes | Completed | 2026-06-01 | 4283 | 4590 | 107.2% | 2026-08-11 | 100% | 100% | 100% | 2026-09-04 | 2026-09-04 | 4/29 NTP Package Received. On hold due to community shutdown. CX start 7-13-26 again
D-HLX511 | Bradenton | 2026-06-18 | Power Connect | 2026-04-30 | Cody |  | 75 | Completed on Track | Received | N/A | Yes | 61026 |  |  | 61026 | Yes | Completed | 2026-05-02 | 4683 | 4841 | 103.4% | 2026-06-04 | 100% | 100% | 100% | 2026-08-11 | 2026-08-11 | 4/29 NTP Package Received. On hold due to community shutdown. CX start 7-13-26 again. 9-23-26 CO Requested
D-HLX512 | Bradenton | 2026-06-18 | North Path | 2026-06-11 | Cody |  | 65 | Completed on Track | Received | N/A | Yes | 45252 |  |  | 45252 | Yes | Completed | 2026-06-11 | 3360 | 3403 | 101.3% | 2026-06-19 | 100% | 100% | 100% | 2026-08-06 | 2026-08-06 | 4/29 NTP Package Received.
D-HLX513 | Bradenton | 2026-06-18 | North Path | 2026-06-11 | Cody |  | 21 | Completed on Track | Received | N/A | Yes | 38308 |  |  | 38308 | Yes | Completed | 2026-06-12 | 3379 | 3364 | 99.56% | 2026-06-25 | 100% | 100% | 100% | 2026-08-06 | 2026-08-06 | 5/7 PO Received-- NTP Package Received.
D-HLX517 | Bradenton | 2026-06-18 | North Path | 2026-05-27 | Cody | MAN111884 | 87 | Completed on Track | Received | N/A | Yes | 59286 |  |  | 59286 | Yes | Completed | 2026-05-28 | 4413 | 4531 | 102.7% | 2026-06-11 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 4/29 NTP Package Received. 9-23-26 CO Requested
D-HLX520 | Bradenton | 2026-06-18 | North Path | 2026-06-11 | Cody |  | 77 | Completed on Track | Received | N/A | Yes | 52948 |  |  | 52948 | Yes | Completed | 2026-06-12 | 3957 | 3966 | 100.2% | 2026-06-30 | 100% | 100% | 100% | 2026-08-06 | 2026-08-06 | 4/29 NTP Package Received.
D-HLX521 | Bradenton | 2026-06-18 | North Path | 2026-06-11 | Cody |  | 74 | Completed on Track | Received | N/A | Yes | 51256 |  |  | 51256 | Yes | Completed | 2026-06-12 | 3826 | 3955 | 103.4% | 2026-06-30 | 100% | 100% | 100% | 2026-08-06 | 2026-08-06 | 5/7 PO Received-- NTP Package Received.
D-HLX522 | Bradenton | 2026-06-18 | North Path | 2026-06-11 | Cody |  | 73 | Completed on Track | Received | N/A | Yes | 61225.25 |  |  | 61225.25 | Yes | Completed | 2026-06-11 | 4654 | 4682 | 100.6% | 2026-06-18 | 100% | 100% | 100% | 2026-07-29 | 2026-07-29 | 4/29 NTP Package Received.
FB-HAL179 | Bradenton | 2026-06-08 | Lightspeed In-House | 2026-05-01 | Cody |  | 0 | Completed on Track | Received | N/A | Yes | 6580.6 |  |  | 6580.6 | Yes | Completed | 2026-05-05 | 466 | 665 | 142.7% | 2026-05-15 | 100% | 100% | 100% | 2026-05-26 | 2026-07-21 | 4/24 NTP Package Received.
FB-HLX375 | Bradenton | 2026-06-30 | North Path | 2026-06-22 | Cody |  | 0 | Completed on Track | Received | N/A | Yes | 36161.25 |  |  | 36161.25 | Yes | Completed | 2026-05-20 | 2885 | 2952 | 102.3% | 2026-07-07 | 100% | 100% | 100% | 2026-07-17 | 2026-07-17 | 5/8 NTP Package Received
FB-HOE117 | Bradenton | 2025-02-23 | Brothers | 2025-02-19 | Allen | MAN89824 | 0 | Completed on Track | Received | 2025-02-13 | Yes | 111163 |  |  | 111163 | Yes | Completed | 2025-03-02 | 7805 | 7969 | 102.1% | 2025-03-24 | 100% | 100% | 100% | 2025-07-16 | Pending Tillman QC Form
FB-HOE176 | Bradenton | 2026-03-31 | Lightspeed In-House | 2026-02-24 | Cody | MAN104757 | 0 | Completed on Track | Received | N/A | Yes | 3995.4 |  |  | 3995.4 | Yes | Completed | 2026-02-24 | 294 | 312 | 106.1% | 2026-03-18 | 100% | 100% | 100% | 2026-07-09 | 2026-07-09 | 10/27 FDOT Permit Received--NTP Package Missing The BOM.
FB-HOE375 | Bradenton | 2025-11-30 | Lightspeed In-House | 2025-08-11 | Betsy | MAN99383 | 0 | Completed on Track | Received | 2025-08-12 | Yes | 4815.65 |  |  | 4815.65 | Yes | Completed | 2025-08-12 | 321 | 367 | 114.3% | 2025-09-05 | 100% | 100% | 100% | 2026-08-06 | 2026-08-06 | 1/12 CX Complete, 48F Placed.
FB-HOE401-V3 | Bradenton | 2026-05-30 | North Path | 2026-02-03 | Cody | MAN108661 | 0 | Completed on Track | Received | N/A | Yes | 118710.8 |  |  | 118710.8 | Yes | Completed | 2026-02-09 | 6978 | 6978 | 100% | 2026-02-11 | 100% | 100% | 100% | 2026-07-29 | 2026-07-29 | 2/11 CX Construction Started
FB-HOE401-V4 | Bradenton | 2026-05-30 | Lightspeed In-House | 2026-07-28 | Brenton Copelin | MAN112099 | 0 | Completed on Track | Received | N/A | Yes | 3443 |  |  | 3443 | Yes | Completed | 2026-07-31 | 224 | 218 | 97.32% | 2026-08-18 | 100% | 0% | 0 | 2026-09-18 | 2026-09-18 | 4/24 Pending Fiber Details Splicing Document, 7/28/26 Reassigned to In House
FB-HOE401-V5 | Bradenton | 2026-09-30 | North Path | 2026-09-01 | Cody |  | 0 | Completed on Track | Received | N/A | Yes | 17605.4 |  |  | 17605.4 | Yes | Completed | 2026-09-02 | 1344 | 1354 | 100.7% | 2026-09-10 | 100% | 100% | 100% | 2026-09-28 | 2026-09-28 | 9/1 NTP Package Received--9/2 PO Received.
Colonial Manor MHP | Bradenton | 2026-01-18 | APT Communications | 2026-01-12 | Cody |  | 76 | Completed on Track | Received | 2026-01-14 | Yes | 64325 |  |  | 64325 | Yes | Completed | 2026-01-12 | 8189 | 8349 | 102% | 2026-01-20 | 100% | 100% | 100% | 6/22 Failed QC | 2026-06-22 | 1/20 CX Construction Started/ 2/4 CX Complete...2 FDH Installed, 132 Splices.
Moss Creek | Bradenton | 2026-01-18 | Kattle One | 2026-01-05 | Cody |  | 109 | Completed on Track | Received | 2025-01-06 | Yes | 123587.5 |  |  | 123587.5 | Yes | Completed | 2025-12-17 | 5450 | 5628 | 103.3% | 2026-01-12 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 1/6 NTP Package is in Project FB-HOE675./ 1/12 CX Construction Started/ 2/2 CX Complete--FDH HH Placed./ 2/3 CX Complete--FDH HH Placed.
North Oaks Estates | Bradenton | 2026-05-18 | North Path | 2026-08-13 | Cody | MAN111119 | 107 | Completed on Track | Not Required | 2026-08-17 | Yes | 175204.4 |  |  | 175204.4 | Yes | Completed | 2026-08-14 | 8827 | 8827 | 100% | 2026-09-14 | 100% | 100% | 100% | 2026-10-06 | Pending Tillman QC Form | 4/14 SOW Received. 9-23-26 CO Requested
Willow Walk North | Bradenton | 2026-06-01 | Kattle One | 2026-02-17 | Cody |  | 115 | Completed on Track | Not Required | N/A | Yes | 125188 |  |  | 125188 | Yes | Completed | 2026-03-02 | 7078 | 7587 | 107.2% | 2026-03-09 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form
D-HPP606 | Clearwater | 2026-10-30 | Lightspeed In-House | 2026-05-01 | Johnnie William | PPM111643 | 21 | Completed on Track | Received | 2026-05-05 | Yes | 81882 |  |  | 81882 | Yes | Completed | 2026-05-04 | 6481 | 6750 | 104.2% | 2026-05-12 | 0% | 0% | 0 | 2026-07-15 | Pending Tillman QC Form | 5/11 - Saul Ramirez started Drilling - 5/5/ Door Tag Complete - 5/4 Locates Called - 5/1 NTP Package Received.
D-HPP610 | Clearwater | 2026-10-30 | NIA Underground | 2026-05-17 | Johnnie William |  | 31 | Completed on Track | Received | 2025-05-18 | Yes | 73945 |  |  | 73945 | Yes | Completed | 2026-05-18 | 5923 | 6177 | 104.3% | 2026-06-15 | 0% | 0% | 0 | 2026-07-27 | Pending Tillman QC Form | 5/1 NTP Package Received.
D-HPP612 | Clearwater | 2026-10-30 | Power Connect | 2026-05-06 | Johnnie | PPM111688 | 73 | Completed on Track | Received | 2026-05-12 | Yes | 132347.5 |  |  | 132347.5 | Yes | Completed | 2026-05-12 | 11206 | 11490 | 102.5% | 2026-05-27 | 0% | 0% | 0 | 2026-07-13 | Pending Tillman QC Form | 5/15 - Pending Locates - Power Connect plans to start 5/18/2026 ¦ /1 NTP Package Received.
D-HPP616 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Miguel |  | 76 | Completed on Track | Received | 2026-06-02 | Yes | 67567.5 |  |  | 67567.5 | Yes | Completed | 2026-05-29 | 5460 | 5429 | 99.43% | 2026-07-06 | 0% | 0% | 0 | 2026-08-10 | Pending Tillman QC Form | 5/1 NTP Package Received./ CX start 7-6/ Pending Walkout by Tillman 7/29
D-HPP617 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Anthony |  | 51 | Completed on Track | Received | 2026-06-01 | Yes | 97514.75 |  |  | 97514.75 | Yes | Completed | 2026-06-01 | 7958 | 8116 | 102% | 2026-06-08 | 0% | 0% | 0 | 2026-07-27 | Pending Tillman QC Form | 5/1 NTP Package Received.
D-HPP618 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Anthony |  | 63 | Completed on Track | Received | 2026-06-01 | Yes | 54827.5 |  |  | 54827.5 | Yes | Completed | 2026-06-10 | 4414 | 4493 | 101.8% | 2026-06-12 | 0% | 0% | 0 | 2026-08-03 | 2026-08-03 | 5/1 NTP Package Received.
D-HPP620 | Clearwater | 2026-10-30 | Brothers | 2026-05-28 | Anthony Adum |  | 67 | Completed on Track | Received | N/A | Yes | 95128 |  |  | 95128 | Yes | Completed | 2026-05-29 | 7857 | 7421 | 94.45% | 2026-06-25 | 0% | 0% | 0 | 2026-07-24 | Pending Tillman QC Form | 5/1 NTP Package Received.
D-HPP632 | Clearwater | 2026-10-30 | Power Connect | 2026-06-04 | Johnnie |  | 28 | Completed on Track | Received | N/A | Yes | 73691.5 |  |  | 73691.5 | Yes | Completed | 2026-06-04 | 6042 | 6042 | 100% | 2026-06-12 | 0% | 0% | 0 | 2026-07-27 | Pending Tillman QC Form | 5/1 NTP Package Received.
D-HDF702 | Fort Myers | 2025-12-15 | GN Systems | 2025-11-26 | Joshua | MAN10462 | 35 | Completed on Track | Received | N/A | Yes | 35942 |  |  | 35942 | Yes | Completed | 2025-12-01 | 2801 | 2817 | 100.6% | 2025-12-09 | 0% | 0% | 0% | Pending Tillman QC Form | Pending Tillman QC Form | 10/29 Permit Received With NTP Package./
D-HDF703 | Fort Myers | 2025-12-15 | GN Systems | 2025-11-26 | Joshua | MAN105616 | 30 | Completed on Track | Received | N/A | Yes | 31387.05 |  |  | 31387.05 | Yes | Completed | 2025-12-01 | 2580 | 2628 | 101.9% | 2025-12-10 | 0% | 0% | 0% | Pending Tillman QC Form | Pending Tillman QC Form | 12/3 Permit Received With NTP Package./
D-HDF704 | Fort Myers | 2025-12-15 | GN Systems | 2025-11-14 | Joshua | MAN104763 | 86 | Completed on Track | Received | N/A | Yes | 111432 |  |  | 111432 | Yes | Completed | 2025-11-18 | 9272 | 9385 | 101.2% | 2025-11-24 | 0% | 0% | 0% | Pending Tillman QC Form | Pending Tillman QC Form | 11/7 Permit Received With NTP Package. Phasae 1 Failed Gig List Uploaded On 2/24/2026.
D-HDF705 | Fort Myers | 2026-01-18 | GN Systems | 2026-01-09 | Joshua Wheatcroft | MAN104764 | 73 | Completed on Track | Received | N/A | Yes | 77814 |  |  | 77814 | Yes | Completed | 2025-12-24 | 6263 | 6237 | 99.58% | 2026-01-02 | 0% | 0% | 0% | Pending Tillman QC Form | Pending Tillman QC Form | Part Of Bluestream Damage.
D-HDF710 | Fort Myers | 2026-02-28 | GN Systems | 2026-01-21 | Joshua | MAN104767 | 61 | Completed on Track | Received | 2026-01-16 | Yes | 56650 |  |  | 56650 | Yes | Completed | 2026-01-16 | 4641 | 4757 | 102.5% | 2026-01-29 | 0% | 0% | 0% | 6/24 Failed QC | 2026-06-24 | 10/29 Permit Received With NTP Package./ 2/3 CX Complete--Progress at 100% Complete./ 2/6 CX Complete. Failed Gig List Received From Tillman 4/16/2026.
D-HDF711 | Fort Myers | 2026-01-31 | GN Systems | 2025-11-03 | Joshua Wheatcroft |  | 82 | Completed on Track | Received | N/A | Yes | 101871 |  |  | 101871 | Yes | Completed | 2025-11-04 | 8100 | 8230 | 101.6% | 2025-11-12 | 0% | 0% | 0% | Pending Tillman QC Form | Pending Tillman QC Form | Part Of Bluestream Damage.
D-HDF714 | Fort Myers | 2025-12-15 | GN Systems | 2025-11-19 | Joshua | MAN104768 | 75 | Completed on Track | Received | N/A | Yes | 82330 |  |  | 82330 | Yes | Completed | 2025-11-04 | 7126 | 7033 | 98.69% | 2025-11-21 | 0% | 0% | 0% | Pending Tillman QC Form | Pending Tillman QC Form | 10/29 Permit Received With NTP Package./ Phase 1 Failed Gig List Uploaded On 1/27/2026.
D-HDF715 | Fort Myers | 2026-01-18 | GN Systems | 2025-12-05 | Joshua Wheatcroft | MAN104769 | 78 | Completed on Track | Received | N/A | Yes | 84477 |  |  | 84477 | Yes | Completed | 2025-12-09 | 6758 | 7002 | 103.6% | 2025-12-15 | 0% | 0% | 0% | Pending Tillman QC Form | Pending Tillman QC Form | Part Of Bluestream Damage.
D-HTG202 | Fort Myers | 2026-05-29 | Lopez Underground | 2026-04-17 | Joshua Wheatcroft |  | 80 | Completed on Track | Received | N/A | Yes | 77548 |  |  | 77548 | Yes | Completed | 2026-04-20 | 6605 | 6596 | 99.86% | 2026-04-23 | 100% | 100% | 100% | 2026-06-01 | Pending Tillman QC Form | 4/15 NTP Received
FB-HTG237 | Fort Myers | 2026-05-29 | North Path | 2026-04-24 | Joshua |  | 0 | Completed on Track | Received | N/A | Yes | 60407.15 |  |  | 60407.15 | Yes | Completed | 2026-04-24 | 4327 | 4481 | 103.6% | 2026-05-04 | 100% | 0% | 0 | 6/24 Failed QC | Pending Tillman QC Form | 4/14 NTP Received.
FB-HWP106 | Lakeland | 2026-02-20 | Brothers |  | Travis | PLK05491 | 0 | Completed on Track | Received | N/A | Yes | 38359.1 |  |  | 38359.1 | Yes | Completed | 2026-01-19 | 3146 | 3263 | 103.7% | 2026-01-20 | 100% | 100% | 100% | 2026-03-20 | 2026-03-20 | 11/24 Pending Splicing Dteails Document./permit received 1-13/ 1/20 CX Construction Started 2/26 CX Construction Complete
FB-HWP1302 | Lakeland | 2025-06-30 | Brothers | 2025-06-09 | Travis | PLK96355 | 0 | Completed on Track | Received | 2025-06-13 | Yes | 23436.55 |  |  | 23436.55 | Yes | Completed | 2025-06-09 | 1769 | 1044 | 59.02% | 2025-06-23 | 100% | 100% | 100% | 2025-08-28 | 2025-08-28 | portion on 10th st is built previously,needs proffed and tie piont on mlk with 144/6-17 tentative con date. 6/18- Brothers driller not working today, ESD 6/23/ring cut to hand off to mdu project/952' 6-23/fiber to pull 6-26
FB-HWP476 | Lakeland | 2026-07-30 | J. Garcia Underground | 2026-05-27 | Miguel Herrero | PLK111960 | 0 | Completed on Track | Received | N/A | Yes | 88403.8 |  |  | 88403.8 | Yes | Completed | 2026-05-27 | 6992 | 7145 | 102.2% | 2026-06-22 | 100% | 100% | 100% | 2026-09-15 | 2026-09-15 | 5/26 NTP Package Received/White lined and Locates done 5-27-2026/ -- 6-15-26 waiting on water locates and encroachment./Cx start 6-22/Locates were refreshed due to expiration 6-26/City portion completed. DOT crossing US 98N scheduled for 7/13./Pending Encroachment Agreement for I4 from Tillman. aggrement received 8-17 per chris v, waiting for DOT inspector to tell us the date/sch for 8-23/8-24 nighttime. This was rescheduled fro Wednesday 8-26 at 10 pm per FDOT Inspector Tyler Wells/clearing done 8-25/Cx completed. Fiber placed and spliced. COP pending QC sheet from Tillman 9-7-2026/
FB-HWP776 | Lakeland | 2025-08-30 | Brothers | 2025-08-13 | Anthony | PLK99777 | 0 | Completed on Track | Received | 2025-08-13 | Yes | 13056.5 |  |  | 13056.5 | Yes | Completed | 2025-08-13 | 1100 | 1110 | 100.9% | 2025-08-18 | 100% | 100% | 100% | 2025-09-26 | 2025-09-26 | permit received 8-13/dispatched 8-13 / 8-21 placing complete, ready to splice. Tillman's MDU portion may not be placed./spl sch 8-28pm
Heatherpoint Lake Estates | Lakeland | 2026-06-30 | Brothers | 2026-03-19 | Miguel/Travis |  | 36 | Completed on Track | Received | 2026-03-17 | Yes | 61453.6 |  |  | 61453.6 | Yes | Completed | 2026-03-16 | 3439 | 3439 | 100% | 2026-04-28 | 100% | 100% | 100% | 2026-05-15 | Pending Tillman QC Form | 12/24 NTP Package Received. Assigned to Yosep 1/7/26
Sherwood Mobile Manor MHP | Lakeland | 2025-12-26 | H&H Underground | 2025-10-06 | Travis |  | 157 | Completed on Track | Not Required | 2025-10-13 | Yes | 64059.5 |  |  | 64059.5 | Yes | Completed | 2025-10-13 | 4725 | 4535 | 96% | 2025-11-10 | 100% | 100% | 100% | 2025-12-10 | Pending Tillman QC Form
D-HBR253 | Miami | 2026-05-31 | Yosep AER | 2026-01-07 | Efrian |  | 55 | Completed on Track | Received | 2026-02-10 | Yes | 55435.9 |  |  | 55435.9 | Yes | Completed | 2026-01-02 | 4571 | 4582 | 100.2% | 2026-04-16 | 100% | 100% | 100% | 2026-06-26 | 2026-07-17 | 12/24 NTP Package Received.
D-HBR254 | Miami | 2026-05-31 | Yosep AER | 2026-01-07 | Efrian |  | 71 | Completed on Track | Received | 2026-02-10 | Yes | 74320.9 |  |  | 74320.9 | Yes | Completed | 2026-01-02 | 5990 | 5909 | 98.65% | 2026-04-28 | 100% | 100% | 100% | 2026-06-26 | Pending Tillman QC Form | 12/24 NTP Package Received.
D-HBR255 | Miami | 2026-06-30 | Yosep AER | 2026-01-07 | Efrian |  | 88 | Completed on Track | Received | 2026-04-16 | Yes | 88069 |  |  | 88069 | Yes | Completed | 2026-06-02 | 7242 | 7028 | 97.05% | 2026-05-26 | 100% | 100% | 100% | 2026-07-17 | Pending Tillman QC Form | 12/24 NTP Package Received.
Sabal Lakes At Gateway | Naples | 2026-02-28 | APT Communications | 2026-02-06 | Joshua |  | 171 | Completed on Track | Not Required | 2026-02-09 | Yes | 160211 |  |  | 160211 | Yes | Completed | 2026-02-09 | 10731 | 10731 | 100% | 2026-02-17 | 100% | 100% | 100% | 2026-04-06 | 2026-04-28 | 2/3/2026 Pending SOW/ 2/17 CX Construction Started
D-HPP301 | Pinellas | 2026-08-28 | R&F Underground Construction Inc | 2026-05-29 | Joshua Pacheco |  | 69 | Completed on Track | Received | 2026-05-29 | Yes | 66000.5 |  |  | 66000.5 | Yes | Completed | 2026-05-29 | 5057 | 5060 | 100.1% | 2026-07-02 | 100% | 100% | 100% | 2026-07-24 | Pending Tillman QC Form | 5/29 NTP Package Received--PO Received 6/1
D-HPP318 | Pinellas | 2026-08-28 | NIA Underground | 2026-06-03 | Matthew Nunes |  | 49 | Completed on Track | Received | 2026-06-05 | Yes | 103484.5 |  |  | 103484.5 | Yes | Completed | 2026-06-05 | 8094 | 7829 | 96.73% | 2026-06-16 | 0% | 0% | 0 | 2026-07-17 | Pending Tillman QC Form | 6/2 NTP Package Received
FB-HSF201 | Port Charlotte | 2026-05-30 | Lightspeed In-House | 2026-05-01 | Joshua |  | 0 | Completed on Track | Received | N/A | Yes | 21122.05 |  |  | 21122.05 | Yes | Completed | 2026-05-01 | 1693 | 1037 | 61.25% | 2026-06-01 | 0% | 0% | 0 | 6/22 Failed QC | 6/22 Failed QC | 4/21 NTP Received.
FB-HSF377 | Port Charlotte | 2026-04-18 | Lightspeed In-House | 2026-04-09 | Joshua |  | 0 | Completed on Track | Received | N/A | Yes | 3969.75 |  |  | 3969.75 | Yes | Completed | 2026-04-09 | 295 | 288 | 97.63% | 2026-04-20 | 100% | 100% | 100% | 6/19 Failed QC | 6/19 Failed QC | 4/9 locates called
BHU-FDH-01-W | St Petersburg | 2025-02-28 | Lightspeed In-House | 2025-02-13 | Johnnie | PPM89496 | 0 | Completed | Received | 2025-02-17 | Yes | 1295 |  |  | 1295 | Yes | Completed | 2025-02-18 | 153 | 153 | 100% | 2025-04-07 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 9-25-25 JW - On my list for restoration, will schedule TIllman Wallk out once complete and ready - Crossing Assigned to Key Underground. Betsy door tagged--Tentative Start Date 2/24/2025. 2-28-25 reassigned to US Builders
D-H0221B | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-02-28 | Caten | PPM91351 | 56 | Completed on Track | Received | 2025-02-28 | Yes | 45321.5 |  |  | 45321.5 | Yes | Completed | 2025-03-06 | 3642 | 3666 | 100.7% | 2025-03-18 | 100% | 100% | 100% | 2025-11-11 | 2025-11-11
D-HDH62 | St Petersburg | 2025-04-25 | US Builders | 2025-03-27 | Caten | PPM92283 | 63 | Completed on Track | Received | 2025-03-25 | Yes | 41813 |  |  | 41813 | Yes | Completed | 2025-03-29 | 3243 | 3290 | 101.4% | 2025-04-14 | 100% | 100% | 100% | 2025-09-17 | 2025-09-17 | original walkout was on 6-20-25 no qc recieved. reissued walkout for 8-26-25
D-HDH69 | St Petersburg | 2025-04-25 | Longo Underground | 2025-02-20 | Tim | PPM89618 | 82 | Completed on Track | Received | 2025-02-10 | Yes | 71979 |  |  | 71979 | Yes | Completed | 2025-02-06 | 5628 | 3927 | 69.78% | 2025-03-26 | 100% | 100% | 100% | 2025-09-01 | 2025-09-01
D-HDH84 | St Petersburg | 2025-03-26 | Reycamp | 2025-01-23 | Johnnie | PPM88311 | 79 | Completed -Missed TSD | Received | Completed | Yes | 64790.5 |  |  | 64790.5 | Yes | Completed | 2025-01-18 | 4975 | 4975 | 100% | 2025-01-23 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | Stingray from 81 to 84, Waiting for Redesign and permits for the redesign. Will possibly feed from 66
D-HNP106/D-H0102C | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-03-27 | Johnnie | PPM93922 | 69 | Completed on Track | Received | 2025-03-25 | Yes | 67734.5 |  |  | 67734.5 | Yes | Completed | 2025-03-28 | 4822 | 4993 | 103.5% | 2025-05-07 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 12.1 JW // AS IT TURNS OUT THERE IS A MISSING SECTION OF CONDUIT, PENDING CLEAR LOCATES THE WE CAN FINISH THIS JOB./ 1/15 CX Complete...Missing Section Added./ 1/23 CX Complete...Missing Section Added.
D-HNP110/D-H0102G | St Petersburg | 2025-12-17 | Lightspeed In-House | 2025-03-27 | Johnnie | PPM94012 | 54 | Completed on Track | Received | 2025-03-25 | Yes | 45215.5 |  |  | 45215.5 | Yes | Completed | 2025-03-28 | 3796 | 3772 | 99.37% | 2025-12-05 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 1.9.26 JW \\ WORK COMPLETE, WE ARE PROOFING AND SPONGING TODAY 12.1 JW // THE 1st 1500' OF LOCATE ARE STILL PENDING O/ 12/8 CX Construction Started
D-HNP113 | St Petersburg | 2025-11-30 | BFI / Longo Underground | 2025-03-19 | Johnnie | PPM90871 | 70 | Completed on Track | Received | 2025-02-28 | Yes | 56262.5 |  |  | 56262.5 | Yes | Completed | 2025-03-28 | 4870 | 4921 | 101% | 2025-04-07 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 12.1 JW // I WILL BE WORKING ON THIS CLOSEOUT PACKAGE 12.2
D-HNP114/H0103D | St Petersburg | 2026-02-27 | North Path/LSCG | 2025-02-12 | Johnnie | PLK88966 | 81 | Completed on Track | Received | 2025-02-14 | Yes | 70635 |  |  | 70635 | Yes | Completed | 2025-02-08 | 6092 | 6008 | 98.62% | 2025-03-31 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 3.16 JW // Closeout Package in progress
D-HNP135/D-H0106G | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-03-27 | Johnnie | PPM94426 | 70 | Completed on Track | Received | 2025-03-25 | Yes | 67735.5 |  |  | 67735.5 | Yes | Completed | 2025-05-02 | 6152 | 6020 | 98% | 2025-05-15 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 6/17/2025 JW ¦ WORK STARTED TODAY
FB-H0220A | St Petersburg | 2025-03-26 | Longo Underground | 2025-02-20 | Tim | PPM89778 | 0 | Completed | Received | 2025-02-24 | Yes | 14262 |  |  | 14262 | Yes | Completed | 2025-02-24 | 826 | 810 | 98.06% | 2025-03-25 | 100% | 100% | 100% | 2025-07-29 | 2025-07-29
FB-HDH275 | St Petersburg | 2025-03-26 | HDD Underground | 2025-02-20 | Betsy | PPM89801 | 0 | Completed on Track | Received | 2025-02-26 | Yes | 93462.85 |  |  | 93462.85 | Yes | Completed | 2025-02-21 | 7497 | 7251 | 96.72% | 2025-03-12 | 100% | 100% | 100% | 2025-09-16 | 2025-09-16
FB-HNP104 | St Petersburg | 2026-02-27 | Kattle One/LSCG | 2025-04-01 | Johnnie | PPM90880 | 0 | Completed on Track | Received | 2026-01-06 | Yes | 29634.15 |  |  | 29634.15 | Yes | Completed | 2025-03-27 | 1831 | 1929 | 105.4% | 2025-05-13 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 4.22 JW // Requested PH1 QC
FB-HNP111 | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-04-01 | Johnnie | PPM92372 | 0 | Completed on Track | Received | 2025-03-25 | Yes | 17203.45 |  |  | 17203.45 | Yes | Completed | 2025-03-26 | 1157 | 1262 | 109.1% | 2025-09-25 | 100% | 100% | 100% | 2026-06-23 | 2026-06-12 | 4.22 JW // Requested PH1 QC
FB-HNP118 | St Petersburg | 2026-01-26 | Lightspeed In-House | 2025-04-01 | Johnnie | PPM92375 | 0 | Completed on Track | Received | 2025-03-26 | Yes | 13442.35 |  |  | 13442.35 | Yes | Completed | 2026-01-05 | 831 | 910 | 109.5% | 2026-01-12 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 3.16 JW // Stingrays where given to VEA // Closeout Package in progress
FB-HNP138 | St Petersburg | 2026-01-22 | Lightspeed In-House | 2025-02-12 | Johnnie | PPM89817 | 0 | Completed on Track | Received | 2025-02-12 | Yes | 19745.25 |  |  | 19745.25 | Yes | Completed | 2025-02-08 | 1534 | 1574 | 102.6% | 2025-03-20 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form | 4.28 JW // Requested PH1 QC
FB-HNP144 | St Petersburg | 2026-02-27 | Kattle One/LSCG | 2025-04-01 | Johnnie William | PPM90914 | 0 | Completed on Track | Received | 2025-03-25 | Yes | 31186.25 |  |  | 31186.25 | Yes | Completed | 2025-03-27 | 2003 | 225 | 11.23% | 2025-05-08 | 100% | 100% | 100% | 2026-06-12 | 2026-06-12 | 3.16 JW // Tillman removed work from LSCG and gave it U1 with out telling us.
FX4-FML-05 | St Petersburg | 2025-09-24 | Brothers | 2025-04-25 | Johnnie | PPM93377 | 0 | Completed on Track | Received | N/A | Yes | 4397.65 |  |  | 4397.65 | Yes | Completed | 2025-07-14 | 129 | 129 | 100% | 2025-07-18 | 0% | 0% | 0% | 2025-11-11 | 2025-11-11 | 9-25-25 JW - On my list for restoration, will schedule TIllman Wallk out once complete and ready
Lake Shore Park | St Petersburg | 2025-12-17 | Patriot / Sosa Line | 2025-10-08 | Johnnie |  | 193 | Completed on Track | Not Required | 2026-10-08 | Yes | 86136 |  |  | 86136 | Yes | Completed | 2025-10-08 | 7655 | 8528 | 111% | 2025-10-13 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form
Wilders MHP | St Petersburg | 2025-12-17 | Kattle One / APT Communications | 2025-10-22 | Johnnie |  | 139 | Completed on Track | Not Required | N/A | Yes | 42766.5 |  |  | 42766.5 | Yes | Completed | 2025-10-09 | 6699 | 7175 | 107.1% | 2025-10-24 | 100% | 100% | 100% | Pending Tillman QC Form | Pending Tillman QC Form
D-HSH226 | Spring Hill | 2026-01-23 | Brothers |  | Byvertek |  | 85 | Completed on Track | Received | N/A | Yes | 29180.45 |  |  | 29180.45 | Yes | Completed | TBD | 6249 | 6183 | 98.94% | 2025-11-03 | 100% | 100% | 100% | 2025-12-11 | 2026-03-25 | 11/5 Project Print Pulled Out Of SharePoint--Pending NTP Package. / no info / 11/28- SR and 48f placed, RTS.
Splicing Projects
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Door Tag Date | SOW Received | SOW Estimated Cost | Invoice Amount Paid | Phase 2 Invoice | Total Invoice | NTP Received | Constuction Status | Locate Date | Footage UG | Actual Redline Completed Footage UG | UG Percentage Complete | Construction Start Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Construction Total Percentage Completetion | QC Received From Tillman | Phase 2 Received From Tillman | Comments
D-HOE111 | Bradenton | 2025-05-30 | Splice Only | TBD | David | PPM92353 | 60 | Completed on Track | Not Required | 2025-02-28 | Yes | 2075.7 |  |  |  | Yes | Completed | Not Required | 0 | 0 | 0% | 2025-03-28 | 100% |  |  |  |  | This was already completed when assigned.
D-HOE117 | Bradenton | 2025-05-30 | Splice Only | TBD | David | MAN90778 | 79 | Completed on Track | Not Required | 2025-02-28 | Yes | 2947.5 |  |  |  | Yes | Completed | Not Required | 0 | 0 | 0% | 2025-03-28 | 100%
D-HOE120 | Bradenton | 2025-05-30 | Splice Only | TBD | David | MAN90857 | 83 | Completed on Track | Not Required | 2025-02-28 | Yes | 2908.95 |  |  |  | Yes | Completed | Not Required | 0 | 0 | 0% | 2025-03-28 | 100%
D-H0220D | St Petersburg | 2025-05-30 | Splice Only | TBD | Eric | PPM90335 | 68 | Completed | Not Required | 2025-02-28 | Yes | 1134 |  |  |  | Yes | Completed | Not Required | 0 | 0 | 0% | 2025-06-04 | 100%
D-H0221E | St Petersburg | 2025-04-25 | Splice Only | TBD | Eric | PPM90342 | 38 | Completed | Not Required | 2025-02-28 | Yes | 870 |  |  |  | Yes | Completed | Not Required | 0 | 0 | 0% | 2025-03-26 | 100% |  |  |  |  | completed 4-21*need to bill BAU Work
D-HDH72 | St Petersburg | 2025-04-25 | Power Connect | 2025-02-10 | Robert | PPM89624 | 82 | Completed on Track | Received | 2025-02-28 | Yes | 2025.6 |  |  |  | Yes | Completed | Not Required | 0 | 0 | 0% | 2025-02-28 | 100% |  |  |  |  | completed, need t o bill BAU Work
D-HDH77 | St Petersburg | 2025-03-26 | Splice Only | 2025-02-27 | Eric | PPM92290 | 84 | Completed | Not Required | 2025-02-27 | Yes | 3801.75 |  |  |  | Yes | Completed | Not Required | 0 | 0 | 0% | 2025-02-28 | 100%
Maintenance Projects
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | Column2 | Invoice Amount Paid | Constuction Status | Locate Date | QC Requested Date | QC Walkout Date | Passed QC Walkout | QC Received From Tillman | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | UG Percentage Complete | Construction Start Date | Comments | Notes
Vault Move EMMA / N FLA | Lakeland |  | Lightspeed In-House | 2025-04-21 | Anthony |  | 0 | Completed | Not Required |  | Not Required | No | 0 | No | Completed | Not Required | N/A | N/A | N/A |  | 3 | 3 | 0 | 100% |  | 2025-04-21
Vault Move FDH302B | Lakeland |  | Lightspeed In-House | 2025-04-21 | Anthony |  | 0 | Completed | Not Required |  | Not Required | No | 0 | No | Completed | Not Required | N/A | N/A | N/A |  | 3 | 3 | 0 | 100% |  | 2025-04-21
Note on U2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-10-2025 Confirmed Actual Completed Footage.
Note on V2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-10-2025 Conduit Placement Confirmed Completed.
Note on U3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 Confirmed Actual Completed Footage.
Note on V3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 Conduit Placement Confirmed Completed.
Note on U4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-3-2025 Confirmed Actual Completed Footage.
Note on V4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-3-2025 Conduit Placement Confirmed Completed.
Note on U5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-26-2026 Confirmed Actual Completed Footage.
Note on V5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-26-2026 Conduit Placement Confirmed Completed.
Note on U6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-23-2026 Confirmed Actual Completed Footage.
Note on V6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-23-2026 Conduit Placement Confirmed Completed.
Note on U7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-22-2026 Confirmed Actual Completed Footage.
Note on V7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-22-2026 Conduit Placement Confirmed Completed.
Note on U8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-7-2026 Confirmed Actual Completed Footage.
Note on V8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-7-2026 Conduit Placement Confirmed Completed.
Note on U9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-17-2025 Confirmed Actual Completed Footage.
Note on V9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-17-2025 Conduit Placement Confirmed Completed.
Note on U10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-23-2026 Confirmed Actual Completed Footage.
Note on V10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-23-2026 Conduit Placement Confirmed Completed.
Note on U11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-23-2025 Confirmed Actual Completed Footage.
Note on V11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-23-2025 Conduit Placement Confirmed Completed.
Note on U12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-11-2026 Confirmed Actual Completed Footage.
Note on V12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-11-2026 Conduit Placement Confirmed Completed.
Note on U13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-29-2026 Confirmed Actual Completed Footage.
Note on V13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-29-2026 Conduit Placement Confirmed Completed.
Note on U14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-20-2026 Confirmed Actual Completed Footage.
Note on V14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-20-2026 Conduit Placement Confirmed Completed.
Note on U15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Confirmed Actual Completed Footage.
Note on V15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Conduit Placement Confirmed Completed.
Note on U16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-26-2026 Confirmed Actual Completed Footage.
Note on V16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-26-2026 Conduit Placement Confirmed Completed.
Note on AA16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-26-2026 QC Walkout Scheduled For 3-27-2026. Reply: 4-14-2026 QC Date Entered Into SiteTracker.
Note on AB16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-26-2026 QC Walkout Scheduled For 3-27-2026. Reply: 4-14-2026 QC Date Entered Into SiteTracker.
Note on U17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2026 Confirmed Actual Completed Footage.
Note on V17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2026 Conduit Placement Confirmed Completed.
Note on U18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-24-2026 Confirmed Actual Completed Footage.
Note on V18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-24-2026 Conduit Placement Confirmed Completed.
Note on U19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Confirmed Actual Completed Footage.
Note on V19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Conduit Placement Confirmed Completed.
Note on R20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on U20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-9-2025 Confirmed Actual Completed Footage.
Note on V20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-9-2025 Conduit Placement Confirmed Completed. Reply: 7-10-2025 Change Order Approved By Tillman(Chad Plummer).
Note on U21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-1-2025 Confirmed Actual Completed Footage.
Note on V21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-1-2025 Conduit Placement Confirmed Completed.
Note on U22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2026 Confirmed Actual Completed Footage.
Note on V22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2026 Conduit Placement Confirmed Completed.
Note on U23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-17-2026 Confirmed Actual Completed Footage.
Note on V23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-17-2026 Conduit Placement Confirmed Completed.
Note on U24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2026 Confirmed Actual Completed Footage.
Note on V24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2026 Conduit Placement Confirmed Completed.
Note on U25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-20-2026 As Per John K 995' Was Claimed On The Backhaul FB-HOE501. Reply: 4-15-2026 Confirmed Actual Completed Footage.
Note on V25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2026 Conduit Placement Confirmed Completed.
Note on U26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Confirmed Actual Completed Footage.
Note on V26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Conduit Placement Confirmed Completed.
Note on U27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-6-2026 Confirmed Actual Completed Footage.
Note on V27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-6-2026 Conduit Placement Confirmed Completed.
Note on U28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-6-2026 Confirmed Actual Completed Footage.
Note on V28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-6-2026 Conduit Placement Confirmed Completed.
Note on U29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Confirmed Actual Completed Footage.
Note on V29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Conduit Placement Confirmed Completed.
Note on U30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 Confirmed Actual Completed Footage.
Note on V30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 Conduit Placement Confirmed Completed.
Note on U32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-23-2026 Confirmed Actual Completed Footage.
Note on V32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-23-2026 Conduit Placement Confirmed Completed.
Note on U33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Confirmed Actual Completed Footage.
Note on V33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Conduit Placement Confirmed Completed.
Note on U34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Confirmed Actual Completed Footage.
Note on V34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Conduit Placement Confirmed Completed.
Note on U35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Confirmed Actual Completed Footage.
Note on V35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Conduit Placement Confirmed Completed.
Note on U36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-8-2026 Confirmed Actual Completed Footage.
Note on V36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-8-2026 Conduit Placement Confirmed Completed.
Note on U37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-30-2026 Confirmed Actual Completed Footage.
Note on V37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-30-2026 Conduit Placement Confirmed Completed.
Note on U38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 Confirmed Actual Completed Footage.
Note on V38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 Conduit Placement Confirmed Completed.
Note on U39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 Confirmed Actual Completed Footage.
Note on V39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 Conduit Placement Confirmed Completed.
Note on AA39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 QC Walkout Scheduled.
Note on U41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-28-2026 Confirmed Actual Completed Footage.
Note on V41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-28-2026 Conduit Placement Confirmed Completed.
Note on U42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-18-2026 Confirmed Actual Completed Footage.
Note on V42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-18-2026 Conduit Placement Confirmed Completed.
Note on U43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-17-2026 Confirmed Actual Completed Footage.
Note on V43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-17-2026 Conduit Placement Confirmed Completed.
Note on T44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: changed to footage listed on the design print
Note on U44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2026 Confirmed Actual Completed Footage.
Note on V44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2026 Conduit Placement Confirmed Completed.
Note on U45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-9-2026 Confirmed Actual Completed Footage.
Note on V45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-9-2026 Conduit Placement Confirmed Completed.
Note on U46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-6-2026 Confirmed Actual Completed Footage.
Note on V46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-6-2026 Conduit Placement Confirmed Completed.
Note on U47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-12-2026 Confirmed Actual Completed Footage.
Note on V47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-12-2026 Conduit Placement Confirmed Completed.
Note on U48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Confirmed Actual Completed Footage.
Note on V48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Conduit Placement Confirmed Completed.
Note on U49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-29-2025 Confirmed Actual Completed Footage.
Note on V49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-29-2025 Conduit Placement Confirmed Completed.
Note on U50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 Confirmed Actual Completed Footage.
Note on V50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 Conduit Placement Confirmed Completed.
Note on U51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-9-2025 Confirmed Actual Completed Footage.
Note on V51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-9-2025 Conduit Placement Confirmed Completed.
Note on U52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-3-2025 Confirmed Actual Completed Footage.
Note on V52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-3-2025 Conduit Placement Confirmed Completed.
Note on U53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Confirmed Actual Completed Footage.
Note on V53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Conduit Placement Confirmed Completed.
Note on U54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-4-2026 Confirmed Actual Completed Footage.
Note on V54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-4-2026 Conduit Placement Confirmed Completed.
Note on U55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-13-2026 Confirmed Actual Completed Footage.
Note on V55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-13-2026 Conduit Placement Confirmed Completed.
Note on U56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-16-2025 Project Was Re-Designed New Footage Will Be 117' Total. Reply: 10-16-2025 Confirmed Actual Completed Footage.
Note on V56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-16-2025 Conduit Placement Confirmed Completed.
Note on U57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Confirmed Actual Completed Footage.
Note on V57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Conduit Placement Confirmed Completed.
Note on U58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-19-2026 Confirmed Actual Completed Footage. Reply: 6-11-2026 Final Footage Completed 7,623'--SiteTracker number is wrong.
Note on V58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-19-2026 Conduit Placement Confirmed Completed.
Note on U59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-26-2026 Final Footage Completed 11,264'--SiteTracker number is wrong. Reply: 7-29-2026 Confirmed Actual Completed Footage.
Note on V59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-29-2026 Conduit Placement Confirmed Completed.
Note on U60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-2-2026 Final Footage Completed 9,211'--SiteTracker number is wrong. Reply: 8-4-2026 Confirmed Actual Completed Footage.
Note on V60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-4-2026 Conduit Placement Confirmed Completed.
Note on U61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-1-2026 Final Footage Completed 7,505'--SiteTracker number is wrong. Reply: 8-4-2026 Confirmed Actual Completed Footage.
Note on V61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-4-2026 Conduit Placement Confirmed Completed.
Note on U62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-3-2026 Confirmed Actual Completed Footage.
Note on V62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-3-2026 Conduit Placement Confirmed Completed.
Note on U63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Approx. 100' Added For Tie In To D-HWP701. Reply: 5-20-2025 Confirmed Actual Completed Footage.
Note on V63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Conduit Placement Confirmed Completed. Reply: 6-3-2025 Approx. 100' Added For Tie In To D-HWP701.
Note on U64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2025 Confirmed Actual Completed Footage.
Note on V64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2025 Conduit Placement Confirmed Completed.
Note on U65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Confirmed Actual Completed Footage.
Note on V65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Conduit Placement Confirmed Completed.
Note on U66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-31-2025 Confirmed Actual Completed Footage. Reply: Updated Footage On 2-5-2026.
Note on V66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-31-2025 Conduit Placement Confirmed Completed. Reply: Updated Footage On 2-5-2026.
Note on U67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-18-2025 Confirmed Actual Completed Footage.
Note on V67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-18-2025 Conduit Placement Confirmed Completed.
Note on U68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-20-2025 Confirmed Actual Completed Footage.
Note on V68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-20-2025 Conduit Placement Confirmed Completed.
Note on J69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-20-2025 Only the FDOT Permit Has Been Received--City Permit to Follow. Reply: 3-11-2025 City of Lakeland Permit Added to the Folder. Reply: 3-11-2025 City of Lakeland Permit Is Only the Cover Page.
Note on U69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-31-2025 Drill Footage Changed. Project Completed Reply: 4-9-2025 Confirmed Actual Completed Footage.
Note on V69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on U70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-5-2025 Confirmed Actual Completed Footage.
Note on V70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-5-2025 Conduit Placement Confirmed Completed.
Note on U71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-3-2025 Confirmed Actual Completed Footage.
Note on V71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-3-2025 Conduit Placement Confirmed Completed.
Note on U72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-15-2025 Confirmed Actual Completed Footage.
Note on V72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-15-2025 Conduit Placement Confirmed Completed.
Note on U73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-16-2025 Confirmed Actual Completed Footage. Change Order Submitted For Additional Footage Added To Project--Approved By Tillman.
Note on V73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-16-2025 Conduit Placement Confirmed Completed.
Note on U74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Confirmed Actual Completed Footage.
Note on V74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Conduit Placement Confirmed Completed.
Note on R75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To FDC On 2-5-2025.
Note on U75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on V75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on R76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on U76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Confirmed Actual Completed Footage.
Note on V76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Conduit Placement Confirmed Completed.
Note on U77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2025 Confirmed Actual Completed Footage.
Note on V77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2025 Conduit Placement Confirmed Completed.
Note on U78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-25-2026 Confirmed Actual Completed Footage.
Note on V78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-25-2026 Conduit Placement Confirmed Completed.
Note on U79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-13-2026 Confirmed Actual Completed Footage.
Note on V79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-13-2026 Conduit Placement Confirmed Completed.
Note on U80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 Confirmed Actual Completed Footage.
Note on V80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 Conduit Placement Confirmed Completed.
Note on T81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-23-2026 Footage Changed Due To Adding 150' Of Additional Conduit To The Project.
Note on U81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-6-2026 Confirmed Actual Completed Footage.
Note on V81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-6-2026 Conduit Placement Confirmed Completed.
Note on U82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 Confirmed Actual Completed Footage.
Note on V82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 Conduit Placement Confirmed Completed.
Note on U83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2025 Confirmed Actual Completed Footage.
Note on V83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2025 Conduit Placement Confirmed Completed.
Note on U84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Confirmed Actual Completed Footage.
Note on V84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Conduit Placement Confirmed Completed.
Note on R85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project Completed As Per Brothers On 2-3-2025.
Note on U85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Confirmed Actual Completed Footage.
Note on V85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Conduit Placement Confirmed Completed.
Note on U86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2025 Confirmed Actual Completed Footage.
Note on V86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2025 Conduit Placement Confirmed Completed.
Note on U87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Confirmed Actual Completed Footage.
Note on V87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Conduit Placement Confirmed Completed.
Note on R88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Brothers As Per Tom On 2-3-2025. Locates To Be Called In On 2-6-2025.
Note on U88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on V88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on U89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Confirmed Actual Completed Footage.
Note on V89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Conduit Placement Confirmed Completed.
Note on U90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-23-2025 Confirmed Actual Completed Footage.
Note on V90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-23-2025 Conduit Placement Confirmed Completed.
Note on U91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Confirmed Actual Completed Footage.
Note on V91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Conduit Placement Confirmed Completed.
Note on T92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2025 SiteTracker Footage Has 4,123'.
Note on U92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2025 Confirmed Actual Completed Footage.
Note on V92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2025 Conduit Placement Confirmed Completed.
Note on U93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on V93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on R94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Brothers As Per Tom On 2-3-2025. Locates To Be Called In On 2-6-2025.
Note on U94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on V94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on A95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-20-2025 Pending SiteTracker Change By Tillman.
Note on U95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-9-2025 Confirmed Actual Completed Footage.
Note on V95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-9-2025 Conduit Placement Confirmed Completed.
Note on U96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-29-2025 Confirmed Actual Completed Footage.
Note on V96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-29-2025 Conduit Placement Confirmed Completed.
Note on U97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-17-2025 673' Was Removed From The Project As Per Travis. Reply: 10-15-2025 Confirmed Actual Completed Footage.
Note on V97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-15-2025 Conduit Placement Confirmed Completed.
Note on U98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reply: 10-21-2025 Project omitted the below path(need 12way) going south and also west from the SW corner of Patterson and South Blvd. Reply: 10-21-2025 Confirmed Actual Completed Footage.
Note on V98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-21-2025 Conduit Placement Confirmed Completed.
Note on U99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-4-2025 Confirmed Actual Completed Footage.
Note on V99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-4-2025 Conduit Placement Confirmed Completed.
Note on U100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-6-2025 Confirmed Actual Completed Footage.
Note on V100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-6-2025 Conduit Placement Confirmed Completed.
Note on T101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-24-2025 Design Change--Part of The Footage On Project D-HWP811 Was Removed And Changed To Project D-HWP808. Approx 1000' As Per Anthony.
Note on U101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-4-2025 Confirmed Actual Completed Footage.
Note on V101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-4-2025 Conduit Placement Confirmed Completed.
Note on U102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-8-2025 Confirmed Actual Completed Footage.
Note on V102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-8-2025 Conduit Placement Confirmed Completed.
Note on U103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-10-2025 Confirmed Actual Completed Footage.
Note on V103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-10-2025 Conduit Placement Confirmed Completed.
Note on U104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-26-2025 Confirmed Actual Completed Footage.
Note on V104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-26-2025 Conduit Placement Confirmed Completed.
Note on U105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-8-2025 Confirmed Actual Completed Footage.
Note on V105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-8-2025 Conduit Placement Confirmed Completed.
Note on U106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-20-2025 Confirmed Actual Completed Footage.
Note on V106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-20-2025 Conduit Placement Confirmed Completed.
Note on U107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-2-2025 Confirmed Actual Completed Footage.
Note on V107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-2-2025 Conduit Placement Confirmed Completed.
Note on U108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-15-2025 Confirmed Actual Completed Footage.
Note on V108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-15-2025 Conduit Placement Confirmed Completed.
Note on U109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-31-2025 Confirmed Actual Completed Footage.
Note on V109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-31-2025 Conduit Placement Confirmed Completed.
Note on U110: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-2-2025 Confirmed Actual Completed Footage.
Note on V110: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-2-2025 Conduit Placement Confirmed Completed.
Note on U111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-12-2025 Confirmed Actual Completed Footage.
Note on V111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-12-2025 Conduit Placement Confirmed Completed.
Note on U112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2025 Confirmed Actual Completed Footage.
Note on V112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2025 Conduit Placement Confirmed Completed.
Note on U113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-10-2025 Confirmed Actual Completed Footage.
Note on V113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-10-2025 Conduit Placement Confirmed Completed.
Note on U114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-10-2025 Confirmed Actual Completed Footage.
Note on V114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-10-2025 Conduit Placement Confirmed Completed.
Note on U115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-11-2025 As Per Anthony Part Of The Project Was Removed By Tillman--Approved By Jessie. Reply: 10-13-2025 Confirmed Actual Completed Footage.
Note on V115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-13-2025 Conduit Placement Confirmed Completed.
Note on U116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-23-2025 Confirmed Actual Completed Footage.
Note on V116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-23-2025 Conduit Placement Confirmed Completed.
Note on U117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-18-2025 Additional Conduit Placement Has Been Added Due To Existing Utility Conflicts, This Additional Conduit Placement Has Been Approved By Tillman As Per Anthony. Reply: 10-9-2025 Confirmed Actual Completed Footage.
Note on V117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-9-2025 Conduit Placement Confirmed Completed.
Note on U118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-30-2025 Confirmed Actual Completed Footage.
Note on V118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-30-2025 Conduit Placement Confirmed Completed.
Note on U119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-5-2025 Confirmed Actual Completed Footage.
Note on V119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-5-2025 Conduit Placement Confirmed Completed.
Note on U120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-19-2025 Confirmed Actual Completed Footage.
Note on V120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-19-2025 Conduit Placement Confirmed Completed.
Note on R121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Brothers As Per Tom On 2-3-2025. Locates To Be Called In On 2-6-2025.
Note on U121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-16-2025 Confirmed Actual Completed Footage.
Note on V121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-16-2025 Conduit Placement Confirmed Completed.
Note on U122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-16-2025 Confirmed Actual Completed Footage.
Note on V122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-16-2025 Conduit Placement Confirmed Completed.
Note on U123: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-15-2025 Confirmed Actual Completed Footage.
Note on V123: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-15-2025 Conduit Placement Confirmed Completed.
Note on U124: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-20-2026 Confirmed Actual Completed Footage.
Note on V124: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-20-202 6Conduit Placement Confirmed Completed.
Note on U125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-14-2025 Confirmed Actual Completed Footage.
Note on V125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-14-2025 Conduit Placement Confirmed Completed.
Note on U126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-4-2025 Confirmed Actual Completed Footage.
Note on V126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-4-2025 Conduit Placement Confirmed Completed.
Note on T127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-8-2025 As Per Anthony Footage Removed Per Mike Garrison.
Note on U127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-20-2025 Confirmed Actual Completed Footage.
Note on V127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-20-2025 Conduit Placement Confirmed Completed.
Note on U128: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-5-2025 Confirmed Actual Completed Footage.
Note on V128: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-5-2025 Conduit Placement Confirmed Completed.
Note on U129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-3-2025 Confirmed Actual Completed Footage.
Note on V129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-3-2025 Conduit Placement Confirmed Completed.
Note on U130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-6-2025 Confirmed Actual Completed Footage.
Note on V130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-6-2025 Conduit Placement Confirmed Completed.
Note on U131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-10-2025 Confirmed Actual Completed Footage.
Note on V131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-10-2025 Conduit Placement Confirmed Completed.
Note on U132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-7-2025 Confirmed Actual Completed Footage.
Note on V132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-7-2025 Conduit Placement Confirmed Completed.
Note on U133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-4-2025 Confirmed Actual Completed Footage.
Note on V133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-4-2025 Conduit Placement Confirmed Completed.
Note on U134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Confirmed Actual Completed Footage.
Note on V134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Conduit Placement Confirmed Completed.
Note on U135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-4-2025 Confirmed Actual Completed Footage.
Note on V135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-4-2025 Conduit Placement Confirmed Completed.
Note on U136: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-13-2026 Confirmed Actual Completed Footage.
Note on V136: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-13-2026 Conduit Placement Confirmed Completed.
Note on U137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-28-2026 Confirmed Actual Completed Footage.
Note on V137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-28-2026 Conduit Placement Confirmed Completed.
Note on U138: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-22-2026 Confirmed Actual Completed Footage.
Note on V138: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-22-2026 Conduit Placement Confirmed Completed.
Note on U139: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-3-2026 Confirmed Actual Completed Footage.
Note on V139: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-3-2026 Conduit Placement Confirmed Completed.
Note on U140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-5-2026 Confirmed Actual Completed Footage.
Note on V140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-5-2026 Conduit Placement Confirmed Completed.
Note on U141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-3-2026 Confirmed Actual Completed Footage.
Note on V141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-3-2026 Conduit Placement Confirmed Completed.
Note on U142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2026 Confirmed Actual Completed Footage.
Note on V142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2026 Conduit Placement Confirmed Completed.
Note on U143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-15-2025 Confirmed Actual Completed Footage.
Note on V143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-15-2025 Conduit Placement Confirmed Completed.
Note on U144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-4-2025 Confirmed Actual Completed Footage.
Note on V144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-4-2025 Conduit Placement Confirmed Completed.
Note on U145: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-20-2025 Confirmed Actual Completed Footage.
Note on V145: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-20-2025 Conduit Placement Confirmed Completed.
Note on U146: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-5-2025 Confirmed Actual Completed Footage.
Note on V146: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-5-2025 Conduit Placement Confirmed Completed.
Note on U147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-17-2025 Footage Changed Due To Adding Additional Conduit To Project BHZD-FWP-13-W. Reply: 9-30-2025 Confirmed Actual Completed Footage.
Note on V147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-30-2025 Conduit Placement Confirmed Completed.
Note on U148: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-16-2025 Confirmed Actual Completed Footage.
Note on V148: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-16-2025 Conduit Placement Confirmed Completed.
Note on U149: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-16-2025 Confirmed Actual Completed Footage.
Note on V149: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-16-2025 Conduit Placement Confirmed Completed.
Note on U150: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Confirmed Actual Completed Footage.
Note on V150: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Conduit Placement Confirmed Completed.
Note on U151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-12-2025 Confirmed Actual Completed Footage.
Note on V151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-12-2025 Conduit Placement Confirmed Completed.
Note on U152: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Confirmed Actual Completed Footage.
Note on V152: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Conduit Placement Confirmed Completed.
Note on U153: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-2-2026 Confirmed Actual Completed Footage.
Note on V153: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-2-2026 Conduit Placement Confirmed Completed.
Note on T154: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-29-2025 Sheet 9 and Sheet 10 Were Captured Under A Previous Project.
Note on U154: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-2-2026 Confirmed Actual Completed Footage.
Note on V154: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-2-2026 Conduit Placement Confirmed Completed.
Note on T155: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Partial Project, Most Of The Drilling Was Completed By Circet Prior To Lightspeed Receiving The Project.
Note on U155: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Confirmed Actual Completed Footage.
Note on V155: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Conduit Placement Confirmed Completed.
Note on U156: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Confirmed Actual Completed Footage.
Note on V156: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Conduit Placement Confirmed Completed.
Note on A157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-29-2025 Fiber Splicing Completed.
Note on U157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-4-2025 Confirmed Actual Completed Footage.
Note on V157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-4-2025 Conduit Placement Confirmed Completed.
Note on U158: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Confirmed Actual Completed Footage.
Note on V158: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Conduit Placement Confirmed Completed.
Note on A159: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-5-2025 Project Cancelled By Tillman After Lightspeed GPR Location. Lightspeed To Submit Invoice For GPR.
Note on U159: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-26-2025 Confirmed Actual Completed Footage.
Note on V159: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-26-2025 Conduit Placement Confirmed Completed.
Note on U160: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-26-2026 Confirmed Actual Completed Footage.
Note on V160: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-26-2026 Conduit Placement Confirmed Completed.
Note on U161: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-10-2025 Confirmed Actual Completed Footage.
Note on V161: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-10-2025 Conduit Placement Confirmed Completed.
Note on A162: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2025 Fiber Splicing Completed.
Note on U162: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-26-2025 Confirmed Actual Completed Footage.
Note on V162: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-26-2025 Conduit Placement Confirmed Completed.
Note on U163: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-5-2026 Confirmed Actual Completed Footage.
Note on V163: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-5-2026 Conduit Placement Confirmed Completed.
Note on U164: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-10-2025 Confirmed Actual Completed Footage.
Note on V164: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-10-2026 Conduit Placement Confirmed Completed.
Note on U165: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-20-2025 Confirmed Actual Completed Footage.
Note on V165: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-20-2025 Conduit Placement Confirmed Completed.
Note on A166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2025 Fiber Splicing Completed.
Note on U166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-26-2025 Confirmed Actual Completed Footage.
Note on V166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-26-2025 Conduit Placement Confirmed Completed.
Note on U167: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-8-2025 Confirmed Actual Completed Footage.
Note on V167: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-8-2025 Conduit Placement Confirmed Completed.
Note on U168: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-2-2025 Change Order Submitted For Addition Conduit Placement---New Total Is 5,776'. Reply: 10-26-2025 Confirmed Actual Completed Footage.
Note on V168: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-26-2025 Conduit Placement Confirmed Completed.
Note on U169: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2025 Confirmed Actual Completed Footage.
Note on V169: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2025 Conduit Placement Confirmed Completed.
Note on U170: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-4-2025 Confirmed Actual Completed Footage.
Note on V170: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-4-2025 Conduit Placement Confirmed Completed.
Note on U171: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-1-2026 Confirmed Actual Completed Footage.
Note on V171: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-1-2026 Conduit Placement Confirmed Completed.
Note on S172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: originals called 12-4 Reply: Second Tickets Called In On 2/3/2026.
Note on T172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-30-2026 Design Change Removed 403' From SOW.
Note on U172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-4-2026 Confirmed Actual Completed Footage.
Note on V172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-4-2026 Conduit Placement Confirmed Completed.
Note on U173: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-31-2025 Confirmed Actual Completed Footage.
Note on V173: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-31-2025 Conduit Placement Confirmed Completed.
Note on U174: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-31-2025 Confirmed Actual Completed Footage.
Note on V174: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-31-2025 Conduit Placement Confirmed Completed.
Note on U175: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-11-2025 Confirmed Actual Completed Footage.
Note on V175: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-11-2025 Conduit Placement Confirmed Completed.
Note on U176: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-26-2025 Confirmed Actual Completed Footage.
Note on V176: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-26-2025 Conduit Placement Confirmed Completed.
Note on U177: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-20-2025 Confirmed Actual Completed Footage.
Note on V177: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-20-2025 Conduit Placement Confirmed Completed.
Note on U178: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-23-2025 Confirmed Actual Completed Footage.
Note on V178: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-23-2025 Conduit Placement Confirmed Completed.
Note on U179: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-20-2026 Confirmed Actual Completed Footage.
Note on V179: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-20-2026 Conduit Placement Confirmed Completed.
Note on U180: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-25-2025 Confirmed Actual Completed Footage.
Note on V180: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-25-2025 Conduit Placement Confirmed Completed.
Note on U181: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Confirmed Actual Completed Footage.
Note on V181: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Conduit Placement Confirmed Completed.
Note on U182: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-8-2025 Confirmed Actual Completed Footage.
Note on V182: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-8-2025 Conduit Placement Confirmed Completed.
Note on U183: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2025 Confirmed Actual Completed Footage.
Note on V183: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2025 Conduit Placement Confirmed Completed.
Note on U184: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Confirmed Actual Completed Footage.
Note on V184: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Conduit Placement Confirmed Completed.
Note on U185: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-3-2025 Confirmed Actual Completed Footage.
Note on V185: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-3-2025 Conduit Placement Confirmed Completed.
Note on U186: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on V186: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on U187: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Confirmed Actual Completed Footage.
Note on V187: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Conduit Placement Confirmed Completed.
Note on U188: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Confirmed Actual Completed Footage. This Project Called For A Design Change--Approved By Tillman.
Note on V188: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Conduit Placement Confirmed Completed. This Project Called For A Design Change--Approved By Tillman.
Note on U189: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-30-2026 Confirmed Actual Completed Footage.
Note on V189: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-30-2026 Conduit Placement Confirmed Completed.
Note on U190: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2026 Confirmed Actual Completed Footage.
Note on V190: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2026 Conduit Placement Confirmed Completed.
Note on U191: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Confirmed Actual Completed Footage.
Note on V191: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Conduit Placement Confirmed Completed.
Note on U192: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-2-2025 Confirmed Actual Completed Footage.
Note on V192: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-2-2025 Conduit Placement Confirmed Completed.
Note on U193: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-16-2025 Confirmed Actual Completed Footage. Reply: Updated Footage On 2-4-2026.
Note on V193: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-16-2025 Conduit Placement Confirmed Completed. Reply: Updated Footage On 2-4-2026.
Note on U194: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-3-2025 Confirmed Actual Completed Footage.
Note on V194: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-3-2025 Conduit Placement Confirmed Completed.
Note on U195: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-11-2025 Confirmed Actual Completed Footage.
Note on V195: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-11-2025 Conduit Placement Confirmed Completed.
Note on U196: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-25-2025 All Rear Easement Toby Boxes Were Changed To Front Yard As Per Tillman And Skyview Management As Per Anthony. Reply: 10-13-2025 Confirmed Actual Completed Footage.
Note on V196: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-13-2025 Conduit Placement Confirmed Completed.
Note on U197: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-27-2026 Final Footage Completed 4,496'--SiteTracker number is wrong. Reply: 8-4-2026 Confirmed Actual Completed Footage.
Note on V197: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-4-2026 Conduit Placement Confirmed Completed.
Note on U198: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-26-2026 HandHole Was Only 7' Not 47' As Per The SOW/PO. Reply: 4-14-2026 Confirmed Actual Completed Footage.
Note on V198: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2026 Conduit Placement Confirmed Completed.
Note on U199: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-4-2026 Confirmed Actual Completed Footage.
Note on V199: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-4-2026 Conduit Placement Confirmed Completed.
Note on U201: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-25-2026 Confirmed Actual Completed Footage.
Note on V201: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-25-2026 Conduit Placement Confirmed Completed.
Note on T202: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-14-2026 Additional 110' Added To Project As Per Tillman John Morrelli.
Note on U202: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-14-2026 Confirmed Actual Completed Footage.
Note on V202: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-14-2026 Conduit Placement Confirmed Completed.
Note on U203: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-23-2026 Confirmed Actual Completed Footage.
Note on V203: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-23-2026 Conduit Placement Confirmed Completed.
Note on U204: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-23-2026 Confirmed Actual Completed Footage.
Note on V204: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-23-2026 Conduit Placement Confirmed Completed.
Note on U205: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-22-2026 Confirmed Actual Completed Footage.
Note on V205: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-22-2026 Conduit Placement Confirmed Completed.
Note on U206: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-22-2026 Confirmed Actual Completed Footage.
Note on V206: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-22-2026 Conduit Placement Confirmed Completed.
Note on AA206: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-20-2026 QC Walkout Scheduled In SiteTracker.
Note on AB206: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-20-2026 QC Walkout Scheduled In SiteTracker.
Note on U207: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2026 Confirmed Actual Completed Footage.
Note on V207: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2026 Conduit Placement Confirmed Completed.
Note on U208: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2026 Confirmed Actual Completed Footage.
Note on V208: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2026 Conduit Placement Confirmed Completed.
Note on AA208: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-20-2026 QC Walkout Scheduled In SiteTracker.
Note on U209: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2026 Confirmed Actual Completed Footage.
Note on V209: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2026 Conduit Placement Confirmed Completed.
Note on U210: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2026 Confirmed Actual Completed Footage.
Note on V210: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2026 Conduit Placement Confirmed Completed.
Note on AA210: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-20-2026 QC Walkout Scheduled In SiteTracker.
Note on U211: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2026 Confirmed Actual Completed Footage.
Note on V211: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2026 Conduit Placement Confirmed Completed.
Note on U212: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-20-2026 Confirmed Actual Completed Footage.
Note on V212: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-20-2026 Conduit Placement Confirmed Completed.
Note on U213: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Confirmed Actual Completed Footage.
Note on V213: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Conduit Placement Confirmed Completed.
Note on U214: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Confirmed Actual Completed Footage.
Note on V214: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Conduit Placement Confirmed Completed.
Note on R215: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on U215: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-13-2025 Confirmed Actual Completed Footage.
Note on V215: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-13-2025 Conduit Placement Confirmed Completed.
Note on U216: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on V216: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on AC216: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4/28 CREW WILL NO COME BACK TO RESTRO THIS JOB, SPOKE WITH CURTIS AND WILL NEED TO HAVE A LANDSCAPE CREW TO REST. HAS NOT PASSED TILLMAN WO Reply: SUBMITTED RESTORATION AS BUILT TO CURTIS 4/27/2025
Note on U217: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-20-2025 Confirmed Actual Completed Footage.
Note on V217: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-20-2025 Conduit Placement Confirmed Completed.
Note on U218: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-23-2025 Confirmed Actual Completed Footage.
Note on V218: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-23-2025 Conduit Placement Confirmed Completed.
Note on T219: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Design Change Approved By Tillman.
Note on U219: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on V219: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on U220: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-14-2025 Confirmed Actual Completed Footage.
Note on V220: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-14-2025 Conduit Placement Confirmed Completed.
Note on AA220: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on U221: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on V221: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on U222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-14-2025 Confirmed Actual Completed Footage.
Note on V222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-14-2025 Conduit Placement Confirmed Completed.
Note on AA222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on U223: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on V223: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on R224: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on U224: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-2-2025 Confirmed Actual Completed Footage.
Note on V224: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-2-2025 Conduit Placement Confirmed Completed.
Note on U225: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on V225: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on U226: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2025 Confirmed Actual Completed Footage.
Note on V226: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2025 Conduit Placement Confirmed Completed.
Note on U227: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-2-2025 Confirmed Actual Completed Footage.
Note on V227: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-2-2025 Conduit Placement Confirmed Completed.
Note on AA227: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on R228: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Partial Build Project Per Tillman On 2-10-2025.
Note on T228: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-19-2025 Drill Footage Based Off SiteTracker--5,325 Total
Note on U228: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per Tillman on 2-10-2025 Job Is Completed Except 6 Crossings On 6th Ave. SOW Shows Total For The Entire Project. Reply: 6-27-2025 Confirmed Actual Completed Footage.
Note on V228: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-27-2025 Conduit Placement Confirmed Completed.
Note on U229: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-17-2025 Confirmed Actual Completed Footage.
Note on V229: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-17-2025 Conduit Placement Confirmed Completed.
Note on U230: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-13-2025 Confirmed Actual Completed Footage.
Note on V230: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-13-2025 Conduit Placement Confirmed Completed.
Note on U231: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-21-2025 Confirmed Actual Completed Footage.
Note on V231: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-21-2025 Conduit Placement Confirmed Completed.
Note on AA231: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on U232: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-12-2025 Confirmed Actual Completed Footage.
Note on V232: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-12-2025 Conduit Placement Confirmed Completed.
Note on U233: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-25-2025 Confirmed Actual Completed Footage.
Note on V233: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-25-2025 Conduit Placement Confirmed Completed.
Note on U234: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-21-2025 Confirmed Actual Completed Footage.
Note on V234: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-21-2025 Conduit Placement Confirmed Completed.
Note on AA234: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on U235: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-27-2025 Confirmed Actual Completed Footage.
Note on V235: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-27-2025 Conduit Placement Confirmed Completed.
Note on AA235: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on U236: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-22-2025 Confirmed Actual Completed Footage.
Note on V236: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-22-2025 Conduit Placement Confirmed Completed.
Note on R237: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on U237: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-16-2025 Confirmed Actual Completed Footage.
Note on V237: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-16-2025 Conduit Placement Confirmed Completed.
Note on U238: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-14-2025 Confirmed Actual Completed Footage.
Note on V238: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-14-2025 Conduit Placement Confirmed Completed.
Note on U239: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-14-2025 Confirmed Actual Completed Footage.
Note on V239: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-14-2025 Conduit Placement Confirmed Completed.
Note on U240: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-23-2025 Confirmed Actual Completed Footage.
Note on V240: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-23-2025 Conduit Placement Confirmed Completed.
Note on U241: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on V241: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on U242: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-30-2025 Confirmed Actual Completed Footage.
Note on V242: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-30-2025 Conduit Placement Confirmed Completed.
Note on AA242: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on U243: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Confirmed Actual Completed Footage.
Note on V243: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Conduit Placement Confirmed Completed.
Note on U244: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-2-2025 Confirmed Actual Completed Footage.
Note on V244: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-2-2025 Conduit Placement Confirmed Completed.
Note on U245: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-5-2025 Confirmed Actual Completed Footage.
Note on V245: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-5-2025 Conduit Placement Confirmed Completed.
Note on U246: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Confirmed Actual Completed Footage.
Note on V246: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Conduit Placement Confirmed Completed.
Note on U247: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-30-2025 Confirmed Actual Completed Footage.
Note on V247: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-30-2025 Conduit Placement Confirmed Completed.
Note on U248: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-25-2025 Confirmed Actual Completed Footage.
Note on V248: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-25-2025 Conduit Placement Confirmed Completed.
Note on U249: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Confirmed Actual Completed Footage.
Note on V249: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Conduit Placement Confirmed Completed.
Note on AA249: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on U250: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on V250: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on Y250: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-14-2025 Splicing Completed by Utilities One as Per Tillman.
Note on U251: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-11-2025 Confirmed Actual Completed Footage.
Note on V251: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-11-2025 Conduit Placement Confirmed Completed.
Note on U252: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-4-2025 Confirmed Actual Completed Footage.
Note on V252: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-4-2025 Conduit Placement Confirmed Completed.
Note on U253: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on V253: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on R254: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HDD 2-6
Note on U254: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Confirmed Actual Completed Footage.
Note on V254: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Conduit Placement Confirmed Completed.
Note on R255: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Power Connect as Per Curtis on 2-4-2025.
Note on U255: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-12-2025 Confirmed Actual Completed Footage.
Note on V255: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-12-2025 Conduit Placement Confirmed Completed.
Note on U256: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2025 Confirmed Actual Completed Footage.
Note on V256: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2025 Conduit Placement Confirmed Completed.
Note on AA256: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on U257: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on V257: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on U258: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-16-2025 Confirmed Actual Completed Footage.
Note on V258: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-16-2025 Conduit Placement Confirmed Completed.
Note on AA258: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on U259: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2025 Confirmed Actual Completed Footage.
Note on V259: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-16-2025 Conduit Placement Confirmed Completed.
Note on U260: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-11-2025 Confirmed Actual Completed Footage.
Note on V260: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-11-2025 Conduit Placement Confirmed Completed.
Note on U261: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Confirmed Actual Completed Footage.
Note on V261: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Conduit Placement Confirmed Completed.
Note on U262: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-17-2025 Confirmed Actual Completed Footage.
Note on V262: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-17-2025 Conduit Placement Confirmed Completed.
Note on U263: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-19-2025 Confirmed Actual Completed Footage.
Note on V263: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-19-2025 Conduit Placement Confirmed Completed.
Note on U264: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-14-2025 Confirmed Actual Completed Footage.
Note on V264: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-14-2025 Conduit Placement Confirmed Completed.
Note on T265: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-19-2025 Project Completed-Re-Design on Project Changed the Footage.
Note on U265: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-29-2025 Confirmed Actual Completed Footage.
Note on V265: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-29-2025 Conduit Placement Confirmed Completed.
Note on A266: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 As Per Theresa Only Construction Has Been Invoiced--Fiber To Follow.
Note on R266: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FCA
Note on U266: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-13-2025 Confirmed Actual Completed Footage.
Note on V266: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-13-2025 Conduit Placement Confirmed Completed.
Note on U267: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-11-2025 Confirmed Actual Completed Footage.
Note on V267: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-11-2025 Conduit Placement Confirmed Completed.
Note on AA267: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on U268: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-21-2025 Confirmed Actual Completed Footage.
Note on V268: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-21-2025 Conduit Placement Confirmed Completed.
Note on U269: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-9-2025 Confirmed Actual Completed Footage.
Note on V269: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-9-2025 Conduit Placement Confirmed Completed.
Note on T270: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 222' Of Additional 1 1/2 Conduit Was Placed On This Project.
Note on U270: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on V270: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on U271: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-30-2025 Confirmed Actual Completed Footage.
Note on V271: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-30-2025 Conduit Placement Confirmed Completed.
Note on U272: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-10-2025 Confirmed Actual Completed Footage.
Note on V272: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-10-2025 Conduit Placement Confirmed Completed.
Note on U273: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-3-2025 Confirmed Actual Completed Footage.
Note on V273: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-3-2025 Conduit Placement Confirmed Completed.
Note on U274: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-19-2025 Confirmed Actual Completed Footage.
Note on V274: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-19-2025 Conduit Placement Confirmed Completed.
Note on R275: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on U275: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-16-2025 Confirmed Actual Completed Footage.
Note on V275: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-16-2025 Conduit Placement Confirmed Completed.
Note on U276: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-13-2025 Confirmed Actual Completed Footage. Change Order Request Sent to Tillman.
Note on V276: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-7-2026 Conduit Placement Confirmed Completed.
Note on U277: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-5-2026 Confirmed Actual Completed Footage.
Note on V277: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-5-2026 Conduit Placement Confirmed Completed.
Note on U278: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Confirmed Actual Completed Footage.
Note on V278: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Conduit Placement Confirmed Completed.
Note on U279: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Confirmed Actual Completed Footage.
Note on V279: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Conduit Placement Confirmed Completed.
Note on U280: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Confirmed Actual Completed Footage.
Note on V280: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Conduit Placement Confirmed Completed.
Note on U281: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-20-2026 Confirmed Actual Completed Footage.
Note on V281: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-20-2026 Conduit Placement Confirmed Completed.
Note on U282: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Confirmed Actual Completed Footage.
Note on V282: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Conduit Placement Confirmed Completed.
Note on U283: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-20-2026 Confirmed Actual Completed Footage.
Note on V283: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-20-2026 Conduit Placement Confirmed Completed.
Note on U284: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Confirmed Actual Completed Footage.
Note on V284: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Conduit Placement Confirmed Completed.
Note on U285: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Confirmed Actual Completed Footage.
Note on V285: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Conduit Placement Confirmed Completed.
Note on U286: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-15-2025 Fiber Placement and Splicing.
Note on V286: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-15-2025 Fiber Placement and Splicing.
Note on U287: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-15-2025 Fiber Placement and Splicing.
Note on V287: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-15-2025 Fiber Placement and Splicing.
Note on U288: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-18-2026 Confirmed Actual Completed Footage.
Note on V288: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-18-2026 Conduit Placement Confirmed Completed.
Note on U289: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2026 Confirmed Actual Completed Footage.
Note on V289: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2025 Conduit Placement Confirmed Completed.
Note on U290: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Confirmed Actual Completed Footage.
Note on V290: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Conduit Placement Confirmed Completed.
Note on U291: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2025 Fiber Placement and Splicing.
Note on V291: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2025 Fiber Placement and Splicing.
Note on U292: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-9-2026 Conduit Placement Confirmed Completed.
Note on V292: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-9-2026 Fiber Placement and Splicing.
Note on U293: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-13-2026 Confirmed Actual Completed Footage.
Note on V293: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-13-2026 Fiber Placement and Splicing.
Note on U294: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-6-2026 Confirmed Actual Completed Footage.
Note on V294: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-6-2026 Fiber Placement and Splicing.
Note on U295: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-6-2026 Confirmed Actual Completed Footage.
Note on V295: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-6-2026 Fiber Placement and Splicing.
Note on U296: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Confirmed Actual Completed Footage.
Note on V296: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2026 Fiber Placement and Splicing.
Note on U297: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2026 Confirmed Actual Completed Footage.
Note on V297: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-13-2026 Fiber Placement and Splicing.
Note on U298: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Confirmed Actual Completed Footage.
Note on V298: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Conduit Placement Confirmed Completed.
Note on U299: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-18-2026 Confirmed Actual Completed Footage.
Note on V299: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-18-2026 Conduit Placement Confirmed Completed.
Note on U300: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Confirmed Actual Completed Footage.
Note on V300: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Conduit Placement Confirmed Completed.
Note on U301: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-23-2026 Confirmed Actual Completed Footage.
Note on V301: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-23-2026 Conduit Placement Confirmed Completed.
Note on U302: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-24-2026 Confirmed Actual Completed Footage.
Note on V302: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-24-2026 Conduit Placement Confirmed Completed.
Note on U303: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-20-2026 Confirmed Actual Completed Footage.
Note on V303: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-20-2026 Conduit Placement Confirmed Completed.
Note on U304: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-24-2026 Confirmed Actual Completed Footage.
Note on V304: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-24-2026 Conduit Placement Confirmed Completed.
Note on U305: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Confirmed Actual Completed Footage.
Note on V305: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Conduit Placement Confirmed Completed.
Note on U306: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-25-2026 Confirmed Actual Completed Footage.
Note on V306: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-25-2026 Conduit Placement Confirmed Completed.
Note on U307: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Confirmed Actual Completed Footage.
Note on V307: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Conduit Placement Confirmed Completed.
Note on U308: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-10-2026 Confirmed Actual Completed Footage.
Note on V308: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-10-2026 Conduit Placement Confirmed Completed.
Note on U309: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-25-2026 Confirmed Actual Completed Footage.
Note on V309: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-25-2026 Conduit Placement Confirmed Completed.
Note on U310: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Confirmed Actual Completed Footage.
Note on V310: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Conduit Placement Confirmed Completed.
Note on U311: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-23-2026 Confirmed Actual Completed Footage.
Note on V311: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-23-2026 Conduit Placement Confirmed Completed.
Note on U312: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Confirmed Actual Completed Footage.
Note on V312: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Conduit Placement Confirmed Completed.
Note on U313: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-26-2026 Confirmed Actual Completed Footage.
Note on V313: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-26-2026 Conduit Placement Confirmed Completed.
Note on U314: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Confirmed Actual Completed Footage.
Note on V314: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Conduit Placement Confirmed Completed.
Note on U315: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-17-2026 Confirmed Actual Completed Footage.
Note on V315: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-17-2026 Conduit Placement Confirmed Completed.
Note on U316: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-17-2026 Confirmed Actual Completed Footage.
Note on V316: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-17-2026 Conduit Placement Confirmed Completed.
Note on U317: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Confirmed Actual Completed Footage.
Note on V317: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Conduit Placement Confirmed Completed.
Note on U318: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-17-2026 Confirmed Actual Completed Footage.
Note on V318: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-17-2026 Conduit Placement Confirmed Completed.
Note on U319: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Confirmed Actual Completed Footage.
Note on V319: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-16-2026 Conduit Placement Confirmed Completed.
Note on U320: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-18-2026 Confirmed Actual Completed Footage.
Note on V320: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-18-2026 Conduit Placement Confirmed Completed.
Note on U328: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2026 Confirmed Actual Completed Footage.
Note on V328: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2026 Conduit Placement Confirmed Completed.
Note on U329: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-8-2025 Confirmed Actual Completed Footage.
Note on V329: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-8-2026 Conduit Placement Confirmed Completed.
Note on U330: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-25-2026 Confirmed Actual Completed Footage.
Note on V330: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-25-2026 Conduit Placement Confirmed Completed.
Note on U331: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-23-2025 Completed Missing Bore Connection To Feed. Reply: Change Order Approved By Joe Cutright On 7-18-2025.
Note on V331: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-23-2025 Conduit Placement Confirmed Completed.
Note on U332: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-24-2026 Confirmed Actual Completed Footage.
Note on V332: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-24-2026 Conduit Placement Confirmed Completed.
Note on U333: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2026 Confirmed Actual Completed Footage.
Note on V333: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2026 Conduit Placement Confirmed Completed.
Note on U334: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-1-2026 Confirmed Actual Completed Footage.
Note on V334: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-1-2026 Conduit Placement Confirmed Completed.
Note on U335: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Confirmed Actual Completed Footage.
Note on V335: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Conduit Placement Confirmed Completed.
Note on U336: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-7-2026 Confirmed Actual Completed Footage.
Note on V336: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-7-2026 Conduit Placement Confirmed Completed.
Note on U337: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-7-2026 Confirmed Actual Completed Footage.
Note on V337: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-7-2026 Conduit Placement Confirmed Completed.
Note on U338: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-27-2026 Confirmed Actual Completed Footage.
Note on V338: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Conduit Placement Confirmed Completed.
Note on U339: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-17-2026 Confirmed Actual Completed Footage.
Note on V339: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-17-2026 Conduit Placement Confirmed Completed.
Note on U340: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-7-2026 Confirmed Actual Completed Footage.
Note on V340: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-7-2026 Conduit Placement Confirmed Completed.
Note on U341: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2026 Confirmed Actual Completed Footage.
Note on V341: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2026 Conduit Placement Confirmed Completed.
Note on U342: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2026 Confirmed Actual Completed Footage.
Note on V342: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2026 Conduit Placement Confirmed Completed.
Note on U343: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-28-2026 Confirmed Actual Completed Footage.
Note on V343: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-28-2026 Conduit Placement Confirmed Completed.
Note on U344: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-17-2026 Confirmed Actual Completed Footage.
Note on V344: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-8-2026 Conduit Placement Confirmed Completed.
Note on U345: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-17-2026 Confirmed Actual Completed Footage.
Note on V345: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-17-2026 Conduit Placement Confirmed Completed.
Note on U346: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-28-2026 Confirmed Actual Completed Footage.
Note on V346: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-28-2026 Conduit Placement Confirmed Completed.
Note on U347: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-27-2026 Confirmed Actual Completed Footage.
Note on V347: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-27-2026 Conduit Placement Confirmed Completed.
Note on U348: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-17-2026 Confirmed Actual Completed Footage.
Note on V348: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-17-2026 Conduit Placement Confirmed Completed.
Note on U349: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-31-2026 Confirmed Actual Completed Footage.
Note on V349: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-31-2026 Conduit Placement Confirmed Completed.
Note on U350: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-16-2026 Additional Footage Added For Road Crossing. Reply: 7-15-2026 Confirmed Actual Completed Footage.
Note on V350: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-15-2026 Conduit Placement Confirmed Completed.
Note on U351: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-11-2026 Confirmed Actual Completed Footage.
Note on V351: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-11-2026 Conduit Placement Confirmed Completed.
Note on U352: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-18-2025 Confirmed Actual Completed Footage.
Note on V352: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-18-2025 Conduit Placement Confirmed Completed.
Note on U353: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 Confirmed Actual Completed Footage.
Note on V353: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 Conduit Placement Confirmed Completed.
Note on U354: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-15-2025 Confirmed Actual Completed Footage.
Note on V354: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-15-2025 Conduit Placement Confirmed Completed.
Note on T355: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-1-2026 Partial Build As Per Tillman--Utility Permit Removed.
Note on U355: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-11-2026 Confirmed Actual Completed Footage.
Note on V355: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-11-2026 Conduit Placement Confirmed Completed.
Note on U356: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-30-2026 Confirmed Actual Completed Footage.
Note on V356: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-30-2026 Conduit Placement Confirmed Completed.
Note on U357: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-30-2026 Confirmed Actual Completed Footage.
Note on V357: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-30-2026 Conduit Placement Confirmed Completed.
Note on U358: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Confirmed Actual Completed Footage.
Note on V358: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 Conduit Placement Confirmed Completed.
Note on U359: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-24-2026 Additional Footage Added For The Gate As Per John K. Reply: 3-24-2026 Confirmed Actual Completed Footage.
Note on V359: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-24-2026 Conduit Placement Confirmed Completed.
Note on AA359: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-24-2026 QC Walkout Scheduled For 3-25-2026.
Note on U360: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-8-2026 Confirmed Actual Completed Footage.
Note on V360: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-9-2026 Conduit Placement Confirmed Completed.
Note on U361: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-27-2026 Confirmed Actual Completed Footage.
Note on V361: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-27-2026 Conduit Placement Confirmed Completed.
Note on U362: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-4-2026 Confirmed Actual Completed Footage.
Note on V362: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-4-2026 Conduit Placement Confirmed Completed.
Note on U363: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-26-2026 Final Footage Completed 6,113'--SiteTracker number is wrong. Reply: 9-4-2026 Confirmed Actual Completed Footage.
Note on V363: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-4-2026 Conduit Placement Confirmed Completed.
Note on U364: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-30-2026 Confirmed Actual Completed Footage.
Note on V364: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-3028-2026 Conduit Placement Confirmed Completed.
Note on U365: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-10-2026 Confirmed Actual Completed Footage.
Note on V365: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-10-2026 Conduit Placement Confirmed Completed.
Note on U366: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-26-2026 Final Footage Completed 8,116'--SiteTracker number is wrong. Reply: 8-3-2026 Confirmed Actual Completed Footage.
Note on V366: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-3-2026 Conduit Placement Confirmed Completed.
Note on U367: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-5-2026 Confirmed Actual Completed Footage.
Note on V367: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-5-2026 Conduit Placement Confirmed Completed.
Note on U368: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-1-2026 Final Footage Completed 7,383'--SiteTracker number is wrong. Reply: 9-10-2026 Confirmed Actual Completed Footage.
Note on V368: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-10-2026 Conduit Placement Confirmed Completed.
Note on U369: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-28-2026 Confirmed Actual Completed Footage.
Note on V369: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-28-2026 Conduit Placement Confirmed Completed.
Note on U370: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-26-2026 Confirmed Actual Completed Footage.
Note on V370: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-26-2026 Conduit Placement Confirmed Completed.
Note on U371: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-19-2026 Confirmed Actual Completed Footage.
Note on V371: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-19-2026 Conduit Placement Confirmed Completed.
Note on AA371: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2026 QC Walkout Scheduled In SiteTracker.
Note on U372: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Confirmed Actual Completed Footage.
Note on V372: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-11-2026 Conduit Placement Confirmed Completed.
Note on U373: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-10-2026 Confirmed Actual Completed Footage.
Note on V373: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-10-2026 Conduit Placement Confirmed Completed.
Note on U374: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-22-2026 Confirmed Actual Completed Footage.
Note on V374: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-22-2026 Conduit Placement Confirmed Completed.
Note on AA374: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2026 QC Walkout Scheduled In SiteTracker.
Note on U375: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-29-2026 Confirmed Actual Completed Footage.
Note on V375: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-29-2026 Conduit Placement Confirmed Completed.
Note on U376: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Confirmed Actual Completed Footage.
Note on V376: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-19-2026 Conduit Placement Confirmed Completed.
Note on U377: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2026 Confirmed Actual Completed Footage.
Note on V377: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2026 Conduit Placement Confirmed Completed.
Note on U378: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-2-2026 Confirmed Actual Completed Footage.
Note on V378: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-2-2026 Conduit Placement Confirmed Completed.
Note on U379: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 Confirmed Actual Completed Footage.
Note on V379: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 Conduit Placement Confirmed Completed.
Note on AA379: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2026 QC Walkout Scheduled In SiteTracker.
Note on U380: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-26-2026 Confirmed Actual Completed Footage.
Note on V380: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-26-2026 Conduit Placement Confirmed Completed.
Note on AA380: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-2-2026 QC Walkout Scheduled In SiteTracker.
Note on U381: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Confirmed Actual Completed Footage.
Note on V381: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Conduit Placement Confirmed Completed.
Note on U382: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2026 Confirmed Actual Completed Footage.
Note on V382: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2026 Conduit Placement Confirmed Completed.
Note on U383: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-8-2025 Confirmed Actual Completed Footage.
Note on V383: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-8-2025 Conduit Placement Confirmed Completed.
Note on U384: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2026 Confirmed Actual Completed Footage.
Note on V384: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2026 Conduit Placement Confirmed Completed.
Note on U385: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-6-2025 Confirmed Actual Completed Footage.
Note on V385: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-6-2025 Conduit Placement Confirmed Completed.
Note on U386: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-14-2026 Confirmed Actual Completed Footage.
Note on V386: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-14-2026 Conduit Placement Confirmed Completed.
Note on U387: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-3-2026 Confirmed Actual Completed Footage.
Note on V387: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-3-2026 Conduit Placement Confirmed Completed.
Note on U388: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-31-2026 Confirmed Actual Completed Footage.
Note on V388: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-31-2026 Conduit Placement Confirmed Completed.
Note on U389: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2026 Confirmed Actual Completed Footage.
Note on V389: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2026 Conduit Placement Confirmed Completed.
Note on U390: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2026 Confirmed Actual Completed Footage.
Note on V390: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2026 Conduit Placement Completed Confirmed.
Note on U391: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-23-2026 Confirmed Actual Completed Footage.
Note on V391: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-23-2026 Conduit Placement Confirmed Completed.
Note on T392: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-29-2026 Project Re-Vised 654' Removed From Project and added to D-HSF208(Built By Different Vendor).
Note on U392: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-29-2026 Confirmed Actual Completed Footage.
Note on V392: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-29-2026 Conduit Placement Confirmed Completed.
Note on U393: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-23-2026 Confirmed Actual Completed Footage.
Note on V393: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-23-2026 Conduit Placement Confirmed Completed.
Note on U394: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-7-2025 Design Change Per Tillman. Reply: 6-10-2025 Confirmed Actual Completed Footage.
Note on V394: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-10-2025 Conduit Placement Confirmed Completed.
Note on U395: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2025 Confirmed Actual Completed Footage.
Note on V395: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2025 Conduit Placement Confirmed Completed.
Note on U396: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-24-2025 Confirmed Actual Completed Footage.
Note on V396: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-24-2025 Conduit Placement Confirmed Completed.
Note on A397: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-14-2025 Partial Build Project As Per Tillman Email On 2-10-2025.
Note on R397: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025. Reply: Partial Build Project Per Tillman On 2-10-2025.
Note on U397: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per Tillman On 2-10-2025 SOW Shows The Whole Project, But This Is To Complete The 4100ft Left On The Project. Partial Build Project. Reply: 10-13-2025 Confirmed Actual Completed Footage.
Note on V397: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-13-2025 Partial Build Project--Conduit Placement Confirmed Completed.
Note on U398: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-28-2025 Confirmed Actual Completed Footage.
Note on V398: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-28-2025 Conduit Placement Confirmed Completed.
Note on AA398: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-23-2026 QC Date Entered In SiteTracker On 3/23/2026.
Note on U399: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-5-2026 Confirmed Actual Completed Footage.
Note on V399: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-5-2026 Conduit Placement Confirmed Completed.
Note on U400: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2025 Confirmed Actual Completed Footage.
Note on V400: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-12-2025 Conduit Placement Confirmed Completed.
Note on U401: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-5-2026 Confirmed Actual Completed Footage.
Note on V401: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-5-2026 Conduit Placement Confirmed Completed.
Note on U402: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-26-2026 Confirmed Actual Completed Footage.
Note on V402: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-26-2026 Conduit Placement Confirmed Completed.
Note on U403: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-24-2025 Confirmed Actual Completed Footage. Reply: 2-12-2026 Footage Updated From Previous COP Package.
Note on V403: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-23-2025 Conduit Placement Confirmed Completed. Reply: 2-12-2026 Footage Updated From Previous COP Package.
Note on R404: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on U404: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2025 Confirmed Actual Completed Footage.
Note on V404: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2025 Conduit Placement Confirmed Completed.
Note on U405: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-27-2025 Confirmed Actual Completed Footage.
Note on V405: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-27-2025 Conduit Placement Confirmed Completed.
Note on U406: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-20-2026 Confirmed Actual Completed Footage.
Note on V406: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-20-2026 Conduit Placement Confirmed Completed.
Note on AA406: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-22-2026 QC Walkout Scheduled In SiteTracker.
Note on U407: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-29-2026 Confirmed Actual Completed Footage.
Note on V407: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-29-2026 Conduit Placement Confirmed Completed.
Note on U408: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-26-2026 Confirmed Actual Completed Footage.
Note on V408: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-26-2026 Conduit Placement Confirmed Completed.
Note on U409: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-30-2026 Confirmed Actual Completed Footage.
Note on V409: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-30-2026 Conduit Placement Confirmed Completed.
Note on U410: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-18-2026 Partial Completion--Project Was Removed By Tillman and Assigned To Utilities One Without Lightspeed Being Informed. Reply: 9-23-2026 Confirmed Actual Completed Footage.
Note on V410: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-23-2026 Conduit Placement Confirmed Completed.
Note on U411: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-3-2025 Confirmed Actual Completed Footage.
Note on V411: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-3-2025 Conduit Placement Confirmed Completed.
Note on U412: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-22-2026 Confirmed Actual Completed Footage.
Note on V412: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-22-2026 Conduit Placement Confirmed Completed.
Note on T413: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-7-2025 Additional Footage Added For Connection Conduit That Was Not Completed By The MDU Vendor.
Note on U413: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-7-2025 Additional Footage Added For Connection Conduit That Was Not Completed By The MDU Vendor. Reply: 12-31-2025 Confirmed Actual Completed Footage.
Note on V413: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12-31-2025 Conduit Placement Confirmed Completed.
Note on U414: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-6-2026 Confirmed Actual Completed Footage.
Note on V414: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-6-2026 Fiber Placement and Splicing.
Note on A419: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on D419: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-13-2025 Light Levels Sent On 5-23-2025 and 10-13-2025.
Note on R419: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on A420: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on D420: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-13-2025 Light Levels Sent On 5-27-2025 and 10-13-2025.
Note on R420: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on A421: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on D421: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-13-2025 Light Levels Sent On 5-27-2025 and 10-13-2025.
Note on R421: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on A422: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on D422: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-13-2025 Light Levels Sent On 7-1-2025 and 10-13-2025.
Note on D423: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-13-2025 Light Levels Sent On 5-6-2025 and 10-13-2025.
Note on A424: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Splice Only Project.
Note on D424: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-13-2025 Light Levels Sent On 10-13-2025.
Note on A425: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on D425: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-13-2025 Light Levels Sent On 10-13-2025.

## Production Summary
[7 empty] | Schedule Date | (Multiple Items)
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | Grand Total | Sum of UG FOOTAGE COMPLETED |  | Sum of UG FOOTAGE COMPLETED | Production Month
D-H0223C |  |  |  |  | 1049 | 1049 | CONTRACTOR | Total | CONTRACTOR | February | March | April | Grand Total
D-H0223D |  |  | 1426 | 1190 | 23 | 2639 | Bartlett Fiber | 6147 | Bartlett Fiber | 7120 | 22896 | 12183 | 42199
D-HDH04 |  | 202 |  |  |  | 202 | Brothers | 22274 | Brothers | 24798 | 53397 | 33743 | 111938
D-HDH31 | 2677 |  |  |  |  | 2677 | EHL | 0 | FCA Fiber | 3158 | 21322 | 12406 | 36886
D-HDH34 |  | 241 | 366 | 202 | 120 | 929 | FCA Fiber | 3629 | HAS Global |  | 4135 | 7641 | 11776
D-HWP415 |  |  |  | 106 |  | 106 | HAS Global | 0 | Lightspeed | 7188 | 23895 | 13411 | 44494
D-HWP436 |  | 534 | 460 | 886 | 202 | 2082 | Lightspeed | 4129 | Longo Underground | 6561 | 14625 | 17060 | 38246
FB-HDH02A |  | 1990 | 1045 |  |  | 3035 | Longo Underground | 7128 | MTX |  | 5968 | 20002 | 25970
Grand Total | 2677 | 2967 | 3297 | 2384 | 1394 | 12719 | MC Logistics | 2298 | US Builders | 2073 | 6882 | 7027 | 15982
[7 empty] | MTX | 13034 | Grand Total | 50898 | 153120 | 123473 | 327491
[7 empty] | Power Connect | 4828
Sum of UG FOOTAGE COMPLETED | Schedule Date | [5 empty] | US Builders | 6718
Project | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | Grand Total | Power Connect
D-H0223C |  |  |  | 547 | 792 | 1339 | HDD Underground | 933
D-H0223D |  |  |  |  | 823 | 823 | Grand Total | 71118
D-HDH04 |  |  |  | 23 | 24 | 47
D-HDH31 |  |  | 1319 |  |  | 1319
D-HDH34 | 283 |  | 732 | 309 |  | 1324
D-HDH45 |  | 1240 | 1978 | 851 |  | 4069
D-HDH66
D-HDH73 |  |  | 1606 | 1334 |  | 2940
D-HDH76 |  | 300 | 696 | 227 | 333 | 1556
D-HWP415 |  |  |  |  | 21 | 21
D-HWP436 | 383 | 1017 | 242 | 424 | 19 | 2085
D-HWP713 |  | 1050 |  |  |  | 1050
D-H0222D |  |  |  | 1400 | 1462 | 2862
D-H0223A |  |  |  | 1806 | 345 | 2151
D-HWP102 |  |  |  | 47 | 1494 | 1541
D-HDH84
D-H0222B |  |  |  |  | 1095 | 1095
D-H0222C |  |  |  |  | 2989 | 2989
Grand Total | 666 | 3607 | 6573 | 6968 | 9397 | 27211
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | Grand Total
D-H0223C |  | 1277 | 1721 | 670 | 0 | 3668
D-H0223D |  |  |  | 1422 | 946 | 2368
D-HDH04 |  |  |  |  | 9 | 9
D-HDH31 |  |  |  |  | 0 | 0
D-HDH34 | 73 |  | 25 |  |  | 98
D-HDH45 |  |  |  |  | 54 | 54
D-HDH66 |  |  |  | 437 | 0 | 437
D-HDH73 |  |  | 992 | 513 | 0 | 1505
D-HDH76 |  | 800 | 208 | 529 | 327 | 1864
D-HWP415 |  |  |  |  | 3 | 3
D-HWP436 |  | 236 |  |  | 0 | 236
D-HWP713 |  |  |  |  | 0 | 0
FB-HDH02A |  | 74 | 671 |  | 0 | 745
D-H0222D |  |  |  |  | 886 | 886
D-H0223A |  |  | 400 |  | 384 | 784
D-HWP102 | 2087 |  |  |  | 0 | 2087
D-HDH84 |  |  |  |  | 0 | 0
D-H0222B |  | 860 | 1540 | 1360 | 0 | 3760
D-H0222C |  | 967 | 1708 |  | 229 | 2904
D-HDH71 | 555 |  |  | 577 | 239 | 1371
Golden Wings MDU |  |  |  |  | 0 | 0
D-HWP412 |  |  |  |  | 0 | 0
D-HWP425 |  |  |  |  | 0 | 0
D-HWP441 |  |  |  |  | 0 | 0
FB-HWP101 |  | 214 |  |  | 0 | 214
D-H0222A |  | 956 |  | 1168 | 0 | 2124
FB-HDH01 |  |  |  |  | 0 | 0
D-H0223E |  |  | 1090 | 840 | 530 | 2460
FB-HWP401- |  |  | 120 |  |  | 120
D-HDH68 |  |  | 399 | 335 | 1339 | 2073
D-HNP138 |  |  | 891 | 1213 | 1054 | 3158
FB-HWP401 |  |  |  |  | 0 | 0
Grand Total | 2715 | 5384 | 9765 | 9064 | 6000 | 32928
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | Grand Total
D-H0223C | 0 |  | 0 | 0 | 0 | 0
D-H0223D | 0 |  | 0 | 0 | 0 | 0
D-HDH04 | 0 | 0 | 0 | 0 | 0 | 0
D-HDH31 | 0 |  | 0 | 0 | 0 | 0
D-HDH34 | 0 | 414 | 367 | 245 | 0 | 1026
D-HDH45 | 0 |  | 0 | 0 | 0 | 0
D-HDH66 | 0 |  | 0 | 0 | 0 | 0
D-HDH73 | 0 |  | 0 | 0 | 201 | 201
D-HDH76 | 286 | 358 | 0 | 32 | 9 | 685
D-HWP415 | 0 |  | 0 | 0 | 0 | 0
D-HWP436 | 0 |  | 0 | 0 | 0 | 0
D-HWP713 | 0 |  | 0 | 0 | 0 | 0
FB-HDH02A | 363 | 171 | 0 | 397 | 88 | 1019
D-H0222D | 134 | 408 | 452 | 0 | 875 | 1869
D-H0223A |  | 840 | 0 | 0 | 0 | 840
D-HWP102 | 0 |  | 0 | 0 | 0 | 0
D-HDH84 | 0 |  | 0 | 0 | 0 | 0
D-H0222B | 1460 | 970 | 430 | 0 | 0 | 2860
D-H0222C | 182 |  | 0 | 0 | 0 | 182
D-HDH71 | 0 |  | 0 | 0 | 0 | 0
Golden Wings MDU | 0 |  | 0 |  | 0 | 0
D-HWP412 | 0 |  | 0 | 0 | 0 | 0
D-HWP425 | 0 |  | 0 | 35 | 0 | 35
D-HWP441 | 0 |  | 0 | 0 | 0 | 0
FB-HWP101 | 0 |  | 32 | 85 | 0 | 117
D-H0222A | 0 |  | 0 | 0 | 0 | 0
FB-HDH01 | 0 |  | 0 | 0 | 0 | 0
D-H0223E | 0 |  | 372 | 0 | 0 | 372
FB-HWP401- | 0 |  | 0 | 0 | 0 | 0
D-HDH68 | 1292 | 1022 | 1246 | 0 | 288 | 3848
D-HNP138 | 0 | 0 | 0 | 0 | 0 | 0
D-HNP137 | 0 | 1570 | 461 | 1109 | 980 | 4120
D-HWP105 | 1454 | 1360 | 1263 | 0 | 0 | 4077
D-HNP123 | 2215 | 0 | 0 | 0 | 0 | 2215
BHT-FWP-06-W |  | 285 |  |  |  | 285
BHT-FWP-06 |  |  | 617 | 286 | 0 | 903
D-HNP143 |  |  | 700 | 1590 | 1370 | 3660
FB-HWP701 |  |  | 200 | 489 | 0 | 689
D-HDH74 |  |  |  | 884 | 738 | 1622
D-HWP103 |  |  |  | 1357 | 0 | 1357
D-HDH46 |  |  |  | 874 | 1602 | 2476
FX4-FWP-08 |  |  |  |  | 20 | 20
D-HWP701 |  |  |  | 0 |  | 0
Grand Total | 7386 | 7398 | 6140 | 7383 | 6171 | 34478
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | Grand Total
D-H0223C | 0 | 0 | 0 |  |  | 0
D-H0223D | 0 | 0 | 0 |  |  | 0
D-HDH04 | 0 | 3 |  |  |  | 3
D-HDH31 | 0 | 0 |  |  |  | 0
D-HDH34 | 0 | 0 |  |  |  | 0
D-HDH45 | 0 | 0 | 0 | 0 |  | 0
D-HDH66 | 0 | 0 | 0 |  |  | 0
D-HDH73 | 0 | 0 | 0 | 0 |  | 0
D-HDH76 | 0 | 12 | 9 |  |  | 21
D-HWP415 | 0 | 0 | 0 |  |  | 0
D-HWP436 | 0 | 0 | 0 |  |  | 0
D-HWP713 | 0 | 0 | 0 | 0 |  | 0
FB-HDH02A | 0 | 0 | 0 |  |  | 0
D-H0222D | 0 | 199 | 0 | 0 |  | 199
D-H0223A | 0 | 0 | 0 | 0 |  | 0
D-HWP102 | 0 | 0 | 0 | 0 |  | 0
D-HDH84 | 0 | 0 | 0 |  |  | 0
D-H0222B | 0 | 0 | 0 | 0 | 0 | 0
D-H0222C | 0 | 0 | 0 | 0 | 0 | 0
D-HDH71 | 0 | 0 | 0 | 0 | 0 | 0
Golden Wings MDU | 0 | 0 | 0 |  |  | 0
D-HWP412 | 0 | 0 | 0 |  |  | 0
D-HWP425 | 0 | 0 | 0 |  |  | 0
D-HWP441 | 0 | 0 | 0 |  |  | 0
FB-HWP101 | 0 | 0 | 0 |  |  | 0
D-H0222A | 0 | 0 | 201 | 1207 | 220 | 1628
FB-HDH01 | 0 | 106 | 0 | 0 | 0 | 106
D-H0223E | 649 | 528 | 489 | 534 |  | 2200
FB-HWP401- | 0 | 0 | 0 |  |  | 0
D-HDH68 | 0 | 0 | 0 | 0 | 0 | 0
D-HNP138 | 0 | 0 | 0 | 0 | 0 | 0
FB-HWP401 |  |  |  | 0 | 0 | 0
D-HNP137 | 0 | 0 | 0 | 0 | 0 | 0
D-HWP105 | 0 | 0 | 0 | 0 | 0 | 0
D-HNP123 | 0 | 0 | 0 | 0 | 0 | 0
BHT-FWP-06 | 0 | 491 | 291 | 571 | 0 | 1353
D-HNP143 | 0 | 0 | 0 | 1170 | 0 | 1170
FB-HWP701 | 921 | 614 | 1004 | 0 |  | 2539
D-HDH74 | 0 | 0 | 961 | 914 | 1903 | 3778
D-HWP103 | 1288 | 685 | 0 | 0 | 0 | 1973
D-HDH46 | 834 | 1081 | 688 | 0 | 0 | 2603
FX4-FWP-08 | 0 | 0 | 0 | 0 | 0 | 0
D-HWP705 |  | 1710 | 1700 | 0 | 0 | 3410
FB-H0222A |  | 304 | 205 | 451 | 0 | 960
FB-H02223A |  | 1617 | 0 | 101 | 0 | 1718
D-HNP141 |  | 228 | 0 | 0 | 0 | 228
D-HDH78 |  | 1257 | 2121 | 2742 | 75 | 6195
D-HDH67 |  |  | 984 | 1078 | 2048 | 4110
FB-HDH275 |  |  | 2760 | 945 | 1073 | 4778
D-HDH70 |  |  | 1246 | 664 | 834 | 2744
D-HWP701 |  |  | 1353 | 1123 | 0 | 2476
D-HDH03 |  |  |  | 338 | 0 | 338
Grand Total | 3692 | 8835 | 14012 | 11838 | 6153 | 44530
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | Grand Total
D-H0223D
D-HDH04
D-HDH34
D-HDH45
D-HDH73
D-HDH76
FB-HDH02A
D-H0222D
D-HWP102
D-HDH84
FB-HWP101
D-H0222A | 195 |  | 187 | 340 | 270 | 992
FB-HDH01
D-HNP138 |  |  | 1409 | 1016 |  | 2425
FB-HWP401
D-HNP137 |  | 1342 |  |  |  | 1342
D-HWP105
D-HNP123
BHT-FWP-06 | 436 |  |  | 6275 |  | 6711
D-HNP143 |  | 315 |  |  |  | 315
FB-HWP701 |  | 1230 | 200 |  |  | 1430
D-HWP103
D-HDH46 | 15 |  |  |  |  | 15
FX4-FWP-08
D-HWP705
FB-H0222A
FB-H02223A
D-HNP141 |  |  | 1460 | 0 | 420 | 1880
D-HDH67 | 919 |  |  | 1672 | 0 | 2591
FB-HDH275 | 2387 | 841 | 18 | 0 |  | 3246
D-HDH70 | 1095 | 65 |  |  |  | 1160
D-HWP701 | 1105 |  |  |  |  | 1105
D-HDH03 |  |  |  |  | 360 | 360
BHUD-FWP-08-E | 920 |  |  |  |  | 920
D-H0221D | 656 |  | 728 | 1400 | 709 | 3493
D-H0221B |  | 977 | 953 | 2472 | 399 | 4801
FB-H0221A |  | 803 | 551 | 0 |  | 1354
D-HDH04-J Garcia
D-HDH75 |  |  | 1373 | 3928 | 1528 | 6829
D-HNP138- |  |  |  | 1016 |  | 1016
FB-HNP138 |  |  |  | 706 |  | 706
FB-HDH02A D-HDH75 Tie In |  |  |  |  | 583 | 583
Grand Total | 7728 | 5573 | 6879 | 18825 | 4269 | 43274
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | Grand Total
D-H0223C
D-HDH34
D-HDH76
FB-HDH02A | 762 | 0 | 0 | 76 |  | 838
D-H0222D
D-H0223A
D-H0222A | 58 | 574 | 704 | 1009 | 200 | 2545
BHT-FWP-06 |  | 380 | 300 | 150 |  | 830
D-HDH74
D-HDH46 |  | 0 | 0 | 137 |  | 137
FB-H0222A |  |  |  | 310 |  | 310
D-HNP141 | 982 | 749 | 713 |  |  | 2444
FB-HDH275 |  | 0 | 0 | 0 |  | 0
D-H0221D | 905 | 630 | 894 |  |  | 2429
D-HDH04
D-H0220C | 691 |  |  |  |  | 691
D-H0221A | 1430 | 1383 | 1334 | 1548 |  | 5695
D-H0221F | 1460 | 1350 | 1507 |  | 2287 | 6604
D-H0223F
D-HDH34
FB-H0220A |  | 575 |  |  |  | 575
D-H0221C |  | 1065 | 825 | 705 |  | 2595
FB-H0223A
D-H0220B |  | 442 | 854 | 290 | 673 | 2259
FB-HOE117 |  | 1740 | 2934 |  | 161 | 4835
D-HOE215 |  | 483 | 1799 |  | 0 | 2282
D-HOE102 |  | 1333 | 1701 |  | 546 | 3580
D-HDH69 |  |  | 1972 | 178 | 266 | 2416
34th St Crossing |  |  |  | 0 |  | 0
BHT-FWP-07 |  |  |  | 195 |  | 195
D-H0220A |  |  |  |  | 0 | 0
302B FDH
Grand Total | 6288 | 10704 | 15537 | 4598 | 4133 | 41260
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | Grand Total
FB-HDH02A | 644 |  |  |  |  | 644
D-H0223A | 0 |  |  |  |  | 0
D-H0222B | 745 |  |  |  |  | 745
D-H0222A | 265 | 0 | 0 |  | 635 | 900
BHT-FWP-06
D-HDH74 |  |  | 0 |  |  | 0
D-HDH67 | 0 |  |  |  |  | 0
D-HDH03
D-H0221D
D-H0221B |  |  | 0 |  |  | 0
FB-H0221A |  |  |  | 192 |  | 192
D-H0220C |  |  |  | 3867 | 594 | 4461
D-H0221F | 695 |  |  |  |  | 695
FB-HOE117 | 418 | 0 | 0 |  |  | 418
D-HOE215 | 499 | 0 | 0 |  |  | 499
D-HDH69 | 1089 | 0 | 0 |  |  | 1089
BHT-FWP-07 | 453 | 166 | 166 | 302 |  | 1087
D-H0220A | 1880 | 0 | 0 |  |  | 1880
D-HNP114 | 349 | 952 | 952 | 1328 | 397 | 3978
D-HWP706 | 1413 | 0 | 1394 |  |  | 2807
FB-HOE201 | 1355 |  | 0 |  |  | 1355
BHZD-FOE-03-W | 2227 |  |  |  |  | 2227
D-HDH32 |  | 0 | 0 | 344 |  | 344
BHUD-FOE-02-W |  | 1149 | 1149 |  |  | 2298
D-HNP151 |  |  |  | 313 |  | 313
D-HDH82 |  |  |  | 1265 |  | 1265
D-HWP707 |  |  |  | 1334 |  | 1334
D-HWP702 |  |  |  | 1970 |  | 1970
D-HOE206
D-HDH80 |  |  |  |  | 2144 | 2144
Grand Total | 12032 | 2267 | 3661 | 10915 | 3770 | 32645
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | Grand Total
FB-HDH02A | 550 |  |  | 426 |  | 976
BHT-FWP-06 |  | 45 |  |  |  | 45
FB-HWP701 |  | 150 | 295 | 504 |  | 949
D-HNP141
FB-HDH275
D-H0221D | 132 |  |  |  |  | 132
D-H0220C | 367 |  |  |  |  | 367
D-H0220B |  |  |  |  | 314 | 314
FB-HOE117
BHT-FWP-07 | 43 |  |  |  |  | 43
FB-HOE201
D-HDH32
BHUD-FOE-02-W
D-HDH82
D-HWP707 | 618 | 700 |  |  |  | 1318
D-HWP702
D-HOE206
D-HDH80 | 990 | 1871 | 1307 |  |  | 4168
D-HNP113 | 590 | 343 |  |  |  | 933
BHU-FDH-01-W | 198 |  |  |  |  | 198
D-HWP703 | 1840 | 1520 | 2060 | 1330 |  | 6750
D-HDH47 |  |  | 1376 | 875 | 1301 | 3552
D-HDH43 |  |  | 617 | 627 | 431 | 1675
D-HDH60 |  |  |  | 711 | 695 | 1406
Grand Total | 5328 | 4629 | 5655 | 4473 | 2741 | 22826
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | Grand Total
D-HDH04
D-HDH73
FB-HDH02A |  | 561 | 260 | 40 | 408 | 1269
BHT-FWP-06 |  | 37 | 115 |  |  | 152
D-HNP141
D-HDH67
D-HDH70
D-HDH75 |  |  | 173 |  |  | 173
D-H0220C
D-H0223F |  |  |  | 96 |  | 96
D-HDH69 |  |  |  | 433 |  | 433
BHT-FWP-07
D-HDH47 |  | 1018 |  | 569 |  | 1587
D-HDH43 | 276 | 779 | 868 | 338 | 26 | 2287
D-HDH60 | 796 | 1929 | 876 | 651 |  | 4252
D-HDH49 | 1335 | 1133 | 1624 |  | 350 | 4442
D-HDH58 |  | 1526 | 1503 | 1590 | 370 | 4989
D-HDH62 | 547 | 845 | 400 | 906 | 198 | 2896
D-HWP1306 | 259 | 243 |  | 193 |  | 695
D-HDH41 |  | 1538 | 2713 | 862 | 1507 | 6620
D-HWP1309 |  |  |  | 647 |  | 647
D-HDH48 |  |  |  |  | 706 | 706
FX4-FWP-13
Grand Total | 3213 | 9609 | 8532 | 6325 | 3565 | 31244
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | Grand Total
FB-HDH02A |  | 205 | 190 | 48 | 150 | 593
D-H0222B
BHT-FWP-06
D-HNP141
D-HDH67
D-HDH03 |  |  | 113 |  |  | 113
D-HDH75
FB-H0223A
D-HDH43
D-HDH60
D-HDH49 | 1050 |  |  |  |  | 1050
D-HDH58
D-HDH62 |  |  |  | 64 | 21 | 85
D-HWP1306 |  | 510 | 275 |  |  | 785
D-HWP1309 |  | 932 | 1190 | 909 |  | 3031
D-HDH48 |  | 1701 | 314 | 662 | 728 | 3405
FX4-FWP-13 |  | 23 |  |  |  | 23
D-HDH42 |  |  | 2348 | 1378 | 726 | 4452
D-HDH55 | 621 | 464 |  |  |  | 1085
D-HDH56 | 1285 | 951 | 1598 | 1671 |  | 5505
D-HDH57 |  | 1864 | 1514 | 1095 |  | 4473
D-HDH52 |  |  |  | 988 |  | 988
D-HDH54 |  |  |  | 588 | 431 | 1019
D-HDH50 |  |  |  |  | 1108 | 1108
D-HDH53 |  |  |  |  | 385 | 385
Grand Total | 2956 | 6650 | 7542 | 7403 | 3549 | 28100
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | Grand Total
FB-HDH02A | 423 |  |  |  |  | 423
BHT-FWP-06
D-HNP151 |  |  |  |  | 1367 | 1367
D-HDH47
D-HDH62
D-HWP1306 |  | 242 | 310 | 302 |  | 854
D-HWP1309 |  | 470 |  |  |  | 470
D-HDH48 | 961 | 370 |  |  |  | 1331
D-HDH42 | 1602 |  |  |  |  | 1602
D-HDH57 |  |  | 594 |  |  | 594
D-HDH52 |  | 608 | 609 | 614 |  | 1831
D-HDH54 | 1936 | 2103 | 1498 | 229 |  | 5766
D-HDH50 |  | 440 | 1175 | 822 | 1020 | 3457
D-HDH53 | 813 | 1597 | 1632 | 692 |  | 4734
D-HWP-1304 | 1216 |  |  |  |  | 1216
D-HWP1304 |  | 1520 | 1216 | 1098 |  | 3834
D-HWP903 |  | 1190 | 1033 | 1031 |  | 3254
Grand Total | 6951 | 8540 | 8067 | 4788 | 2387 | 30733
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | Grand Total
FB-HDH02A |  | 320 |  |  |  | 320
D-H0222A |  |  | 131 |  |  | 131
FB-H0221A
D-HNP151 |  | 424 |  |  |  | 424
D-HNP113 |  |  |  | 468 | 940 | 1408
D-HDH47
D-HDH49
D-HWP1306 | 610 | 451 | 802 | 75 |  | 1938
D-HWP1309
D-HDH42
D-HDH52 | 404 | 158 | 353 | 40 | 153 | 1108
D-HDH54
D-HWP903 | 1053 | 812 |  |  |  | 1865
D-HNP144 | 640 | 490 | 127 |  |  | 1257
FB-HNP111
D-HWP904 | 575 | 1847 | 1052 | 1846 |  | 5320
D-HWP902 |  | 565 | 1935 | 1483 |  | 3983
D-HNP106 |  |  | 592 | 592 | 730 | 1914
D-HNP117 |  |  | 645 | 853 |  | 1498
D-HNP104 |  |  |  | 616 | 900 | 1516
FB-HNP144 |  |  |  | 225 |  | 225
Grand Total | 3282 | 5067 | 5637 | 6198 | 2723 | 22907
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | Grand Total
FB-HDH02A
(blank)
D-H0222A |  | 55 |  |  |  | 55
FB-HWP701 |  |  | 1190 |  |  | 1190
D-H0223F |  | 30 |  |  |  | 30
D-H0221C |  |  |  |  | 887 | 887
FB-HOE201 |  | 385 | 678 | 381 |  | 1444
D-HWP1306 |  | 251 | 424 | 497 |  | 1172
D-HDH55 |  |  |  | 1342 | 1484 | 2826
D-HDH57 |  |  |  | 85 |  | 85
D-HWP902 |  | 933 |  |  |  | 933
D-HNP117
D-HNP104 |  | 212 |  | 1316 | 1232 | 2760
FB-HNP133 |  |  | 153 |  |  | 153
D-H0222A / D-H0233F
HGP16 / HGP38
D-HNP135 |  |  |  | 201 | 30 | 231
BHT-FWP-10 |  |  |  | 1580 |  | 1580
D-HDH02 |  |  |  |  | 151 | 151
Grand Total |  | 1866 | 2445 | 5402 | 3784 | 13497
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | Grand Total
D-H0222B | 301 | 191 |  |  |  | 492
D-H0222A |  |  |  |  | 175 | 175
D-HNP123 | 54 | 101 |  |  |  | 155
FB-HWP701 |  |  | 678 |  |  | 678
D-H0221C |  |  |  |  | 236 | 236
D-H0220B |  |  | 999 |  | 719 | 1718
FB-HOE201 | 605 |  | 600 | 772 |  | 1977
D-HWP1306 | 286 | 226 |  |  |  | 512
D-HDH55 | 1280 | 1029 |  |  |  | 2309
D-HDH57 |  |  | 181 |  |  | 181
D-HDH53
D-HNP104 | 1156 | 947 |  |  |  | 2103
BHT-FWP-10 | 270 |  |  | 948 |  | 1218
FB-HWP801 | 644 | 1430 | 970 |  |  | 3044
D-HOE116 |  |  |  |  | 285 | 285
D-DHD52 |  |  |  | 260 | 129 | 389
D-DHD55
Grand Total | 4596 | 3924 | 3428 | 1980 | 1544 | 15472
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | Grand Total
FB-HDH02A | 100 |  |  |  | 100
D-H0221C | 224 | 200 |  |  | 424
FB-HOE201 | 757 | 610 | 959 | 493 | 2819
D-HNP151 |  |  |  | 218 | 218
D-HWP1306
BHT-FWP-10 | 954 | 2783 | 2248 |  | 5985
FB-HWP801 | 948 |  | 736 |  | 1684
BHZD-FWP-13-E
D-HDH50 \ D-HDH52
D-HDH57 \ D-HDH58
D-HDH50-52
D-HDH57-60
FB-HWP-701
Grand Total | 2983 | 3593 | 3943 | 711 | 11230
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | Grand Total
FB-HWP701
D-HWP701
D-H0220B |  | 1483 | 83 |  |  | 1566
FB-HOE201 | 720 | 948 |  | 1101 | 437 | 3206
D-HNP113 |  |  |  | 341 |  | 341
D-HDH02
FB-HWP801 | 1957 |  |  |  |  | 1957
BHZD-FWP-13-E | 275 | 280 | 310 |  |  | 865
BHT-FWP-09 | 800 | 631 | 1401 |  |  | 2832
D-HDH18 | 6 |  |  |  |  | 6
D-HDH50\52
D-HNP110
D-HWP905 |  |  | 610 | 2523 |  | 3133
D-HDH52/49/58
Grand Total | 3758 | 3342 | 2404 | 3965 | 437 | 13906
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | Grand Total
FB-HWP701
FB-HOE201 | 730 | 583 |  |  |  | 1313
FX4-FWP-13 | 115 |  |  |  |  | 115
BHT-FWP-10 |  |  | 370 |  |  | 370
BHZD-FWP-13-E | 263 | 270 |  | 395 |  | 928
BHT-FWP-09 | 1100 |  | 1975 | 1395 |  | 4470
D-HWP905 |  | 1293 |  |  |  | 1293
225 Granada St | 155 |  |  |  |  | 155
BHUD-FWP-06
Grand Total | 2363 | 2146 | 2345 | 1790 |  | 8644
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | Grand Total
D-H0222B
D-HDH69
D-H0220A | 1394 | 1756 | 846 |  |  | 3996
FB-HOE201 | 465 | 218 | 729 | 464 |  | 1876
BHUD-FOE-02-W |  |  |  | 977 |  | 977
D-HNP135 |  |  | 81 |  | 114 | 195
BHT-FWP-10
FB-HWP801
BHZD-FWP-13-E | 280 | 70 | 594 |  | 52 | 996
BHT-FWP-09 | 450 | 1246 |  |  |  | 1696
BHT-FWP-08 |  | 1465 | 1380 |  |  | 2845
Grand Total | 2589 | 4755 | 3630 | 1441 | 166 | 12581
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | Grand Total
D-H0220B
D-H0220A |  | 1946 |  |  |  | 1946
FB-HOE201 |  |  |  | 112 |  | 112
BHUD-FOE-02-W |  |  |  | 676 | 430 | 1106
D-HNP113 |  |  | 649 |  |  | 649
D-HNP135 | 237 | 322 | 245 | 1091 | 303 | 2198
BHZD-FWP-13-E | 68 | 50 |  |  |  | 118
BHT-FWP-08 | 1269 | 1141 | 1308 | 1296 |  | 5014
FB-HDH01A-2A | 65 |  |  |  |  | 65
FB-HWP175 | 924 |  |  |  |  | 924
D-HWP801 |  | 1044 | 1100 | 1050 |  | 3194
FB-HWP1376 |  |  | 335 | 200 |  | 535
Grand Total | 2563 | 4503 | 3637 | 4425 | 733 | 15861
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | Grand Total
(blank) |  |  |  |  | 0 | 0
FB-HOE201 |  | 282 |  |  |  | 282
BHUD-FOE-02-W | 885 | 478 | 490 | 372 |  | 2225
D-HNP144
D-HNP135 | 360 |  |  |  |  | 360
FB-HWP801
BHT-FWP-08
FB-HWP175 | 120 |  |  |  |  | 120
FB-HWP1376 |  | 120 | 71 |  |  | 191
D-HWP821 |  |  | 355 |  |  | 355
Grand Total | 1365 | 880 | 916 | 372 | 0 | 3533
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | Grand Total
BHZD-FOE-03-W |  |  |  |  | 198 | 198
BHUD-FOE-02-W
D-HOE206
D-HNP117 |  |  |  | 400 |  | 400
D-HWP821 | 846 | 827 |  |  |  | 1673
FB-HWP902 |  | 465 | 321 |  |  | 786
BHUD-FWP-13-W | 1644 | 60 |  |  |  | 1704
Grand Total | 2490 | 1352 | 321 | 400 | 198 | 4761
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | Grand Total
D-HOE215 |  | 403 | 39 |  |  | 442
BHZD-FOE-03-W | 862 |  |  |  |  | 862
D-HNP117 |  | 203 | 170 | 106 |  | 479
BHZD-FWP-13-E |  |  | 280 | 1972 |  | 2252
FB-HWP902
D-HWP822 |  | 1210 | 397 |  |  | 1607
FB-HWP1302 |  |  | 90 |  |  | 90
D-HWP814 |  |  | 426 | 583 |  | 1009
FX4-FML-05 |  |  |  |  | 47 | 47
Grand Total | 862 | 1816 | 1402 | 2661 | 47 | 6788
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | Grand Total
D-HOE215 |  | 318 |  |  |  | 318
BHZD-FOE-03-W |  |  | 461 | 880 | 585 | 1926
D-HOE206 |  |  |  | 868 |  | 868
D-HNP117 |  |  | 272 | 79 |  | 351
BHZD-FWP-13-E | 936 | 1723 | 130 | 420 |  | 3209
BHT-FWP-09 |  |  | 853 | 1279 |  | 2132
D-HWP821
BHUD-FWP-13-W |  |  | 579 | 619 |  | 1198
D-HWP822
D-HWP814 | 1843 | 1714 | 678 |  |  | 4235
D-HWP812 | 1070 | 1224 | 235 |  |  | 2529
BHUD-FOE-03-W |  | 605 |  |  |  | 605
D-HWP815 |  |  | 363 | 1077 |  | 1440
FB-HWP804
Grand Total | 3849 | 5584 | 3571 | 5222 | 585 | 18811
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | Grand Total
D-H0223C |  |  |  |  | 318 | 318
D-H0223A |  |  |  |  | 183 | 183
BHZD-FOE-03-W | 345 |  |  |  |  | 345
BHZD-FWP-13-E | 420 |  |  |  |  | 420
BHT-FWP-09 | 817 |  | 1385 |  |  | 2202
BHUD-FWP-13-W | 1181 | 1933 | 2853 | 1587 |  | 7554
D-HWP814
D-HWP815 | 1430 | 1004 |  |  |  | 2434
FB-HWP804 |  | 581 |  |  |  | 581
BHT-FOE-03 |  |  | 314 |  |  | 314
FB-HOE301 |  |  |  | 2390 | 1377 | 3767
Grand Total | 4193 | 3518 | 4552 | 3977 | 1878 | 18118
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | Grand Total
D-HNP117
BHUD-FWP-13-W
BHT-FOE-03
FB-HOE301 |  | 190 | 840 | 531 | 718 | 2279
FB-HWP482 | 918 |  |  |  |  | 918
BHZD-FWP-11-W |  | 2675 | 1964 | 377 |  | 5016
FB-HWP775 |  |  |  | 674 |  | 674
Grand Total | 918 | 2865 | 2804 | 1582 | 718 | 8887
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | Grand Total
D-HOE215 |  | 319 |  |  |  | 319
D-HNP117 | 376 | 35 | 48 | 144 | 64 | 667
FB-HOE301 | 571 | 1293 | 540 | 554 | 89 | 3047
FB-HWP482 | 1175 | 1154 | 428 |  |  | 2757
FB-HWP775 |  | 111 | 12 |  |  | 123
FB-HWP802 | 288 | 380 | 229 | 163 |  | 1060
12 Oaks MHP |  | 406 | 1031 |  |  | 1437
Skyview MHP
FB-HLR201 |  |  |  |  | 391 | 391
Grand Total | 2410 | 3698 | 2288 | 861 | 544 | 9801
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | Grand Total
D-HOE206 |  |  | 499 | 231 | 316 | 1046
D-HNP113
D-HNP117 | 141 |  | 181 | 82 | 96 | 500
FB-HWP1376 | 343 | 416 | 216 |  |  | 975
BHT-FOE-03 |  | 430 |  |  |  | 430
FB-HOE301 | 377 | 408 | 607 | 1022 |  | 2414
FB-HWP482
FB-HWP775
FB-HLR201 | 396 |  |  |  |  | 396
FB-HWP776 | 1109 |  |  |  |  | 1109
D-HNP111 |  | 205 |  |  |  | 205
Skyview |  | 1456 | 1420 | 1170 | 1081 | 5127
D-HWP803 |  | 1460 | 1428 | 1654 |  | 4542
D-HNP108 |  |  |  |  | 878 | 878
Grand Total | 2366 | 4375 | 4351 | 4159 | 2371 | 17622
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | Grand Total
D-HOE215 |  |  | 358 |  |  | 358
BHZD-FOE-03-W |  |  | 1241 |  |  | 1241
D-HOE206 | 503 | 295 |  |  | 6 | 804
D-HNP113 |  | 1009 |  |  |  | 1009
D-HNP117 | 20 |  |  | 250 | 177 | 447
FB-HOE301 | 639 |  |  |  |  | 639
FB-HLR201 |  |  | 400 | 320 |  | 720
Skyview | 809 | 533 |  |  |  | 1342
D-HNP108 | 715 |  |  |  | 1131 | 1846
FB-HWP375 |  |  | 130 |  |  | 130
D-HWP805 | 735 |  |  | 1453 |  | 2188
FB-HWP1375 |  | 260 |  | 315 |  | 575
FB-HWP1310 |  | 390 |  |  |  | 390
D-HWP826 |  | 558 | 1248 | 1260 |  | 3066
D-HWP824 |  | 1224 | 967 |  |  | 2191
D-HWP825 |  |  | 1017 |  |  | 1017
D-HWP1310
Grand Total | 3421 | 4269 | 5361 | 3598 | 1314 | 17963
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | Grand Total
(blank)
D-HOE215 |  |  |  | 99 |  | 99
BHZD-FOE-03-W
D-HDH82
D-HOE206 |  | 15 | 65 | 6 |  | 86
D-HNP117
D-HNP135 |  |  |  |  | 125 | 125
D-HWP812 |  |  | 130 |  |  | 130
D-HWP803 |  |  |  |  | 128 | 128
D-HWP805 |  |  | 2472 |  |  | 2472
D-HWP826 |  | 977 |  |  |  | 977
D-HWP825 |  |  | 2819 |  |  | 2819
D-HWP1310 |  |  | 1491 | 1549 |  | 3040
HGP-03
D-HWP802 |  |  |  | 903 |  | 903
FB-HOE375 |  |  |  |  | 285 | 285
Grand Total |  | 992 | 6977 | 2557 | 538 | 11064
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | Grand Total
D-HNP113 |  |  |  | 279 |  | 279
D-HNP135 |  |  | 299 | 302 | 209 | 810
Skyview | 2498 | 1192 | 1925 |  |  | 5615
D-HNP108 |  |  |  | 443 |  | 443
D-HWP1310 | 918 |  |  |  |  | 918
D-HWP802 | 254 | 1686 | 611 |  |  | 2551
FB-HOE375 |  |  |  | 82 |  | 82
FB-HWP975 |  | 329 | 333 |  |  | 662
D-HWP827 |  |  | 740 |  |  | 740
FB-HWP1075 |  |  |  | 267 |  | 267
BHT-FLX-01 |  |  | 307 | 920 | 610 | 1837
Grand Total | 3670 | 3207 | 4215 | 2293 | 819 | 14204
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | Grand Total
D-HOE215
BHZD-FOE-03-W |  |  | 139 |  |  | 139
D-HOE206
FB-HNP133 |  |  |  | 97 |  | 97
D-HNP135 | 42 | 219 |  |  | 70 | 331
Skyview
D-HWP802 |  |  | 250 |  |  | 250
D-HWP827 | 1238 | 1531 | 1250 | 361 |  | 4380
FB-HWP1075 | 711 |  |  |  |  | 711
D-HGP22 (Repair) |  |  | 75 |  |  | 75
D-HWP809 |  | 1808 |  | 1204 |  | 3012
D-HOE302 |  | 251 | 253 | 1076 |  | 1580
BHT-FLX-01 | 829 |  | 863 | 499 | 475 | 2666
D-HWP823 |  |  |  | 754 |  | 754
D-HWP811 |  |  |  | 562 |  | 562
Grand Total | 2820 | 3809 | 2830 | 4553 | 545 | 14557
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | Grand Total
D-HOE215
BHZD-FOE-03-W | 60 |  |  |  |  | 60
FB-HNP111 |  |  |  | 175 |  | 175
D-HNP135 |  | 224 |  |  |  | 224
BHT-FOE-03 |  |  | 406 |  |  | 406
FB-HLR201 |  |  | 362 | 399 |  | 761
D-HWP827
D-HWP809
D-HOE302 |  | 120 | 190 |  |  | 310
BHT-FLX-01 | 839 |  | 616 | 969 | 552 | 2976
D-HWP823 | 1285 |  |  |  |  | 1285
D-HWP811 | 978 | 675 | 170 |  |  | 1823
FB-HNP104 | 153 |  | 260 |  |  | 413
OakHill MHP | 329 | 427 | 537 | 646 | 793 | 2732
FB-HWP480 | 335 |  |  |  |  | 335
BHU-FAL-01-E | 415 | 291 |  |  | 755 | 1461
D-HWP816 |  | 1231 | 1538 | 1377 |  | 4146
D-HWP818 |  |  | 1205 | 1000 |  | 2205
BHU-FWP-08-E |  |  | 240 | 504 |  | 744
Mas Verde |  |  |  |  | 4135 | 4135
D-HOE306 |  |  |  |  | 551 | 551
Skyview Estates
Grand Total | 4394 | 2968 | 5524 | 5070 | 6786 | 24742
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | Grand Total
D-HOE215
FB-HNP111 | 229 |  |  |  |  | 229
FB-HNP133 |  | 134 |  | 450 | 352 | 936
D-HNP135 |  |  | 201 |  | 352 | 553
BHT-FOE-03 |  | 665 | 753 | 305 |  | 1723
D-HOE302 | 479 |  |  | 170 |  | 649
BHT-FLX-01 | 1375 | 1016 | 312 | 1304 | 617 | 4624
D-HWP823
BHU-FAL-01-E | 1418 | 701 |  | 614 | 486 | 3219
D-HWP816 | 600 |  |  |  |  | 600
D-HWP818 | 1002 | 268 |  |  |  | 1270
BHU-FWP-08-E | 80 |  |  |  |  | 80
Mas Verde | 2251 | 2014 | 1868 | 2157 | 2953 | 11243
D-HOE306 | 454 | 251 | 224 | 789 |  | 1718
D-HST11 |  | 1253 | 1351 | 443 |  | 3047
D-HWP813 |  | 1850 | 1276 | 1479 |  | 4605
D-HWP910 |  |  | 1118 | 1472 |  | 2590
D-HWP908 |  |  |  | 1393 |  | 1393
Grand Total | 7888 | 8152 | 7103 | 10576 | 4760 | 38479
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | Grand Total
FB-HNP111 |  |  |  | 270 | 268 | 538
D-HNP106 |  |  | 126 | 229 |  | 355
FB-HNP133 | 175 | 270 |  |  |  | 445
D-HNP135 | 65 | 55 |  |  |  | 120
BHT-FOE-03
D-HOE302 |  |  |  | 725 |  | 725
BHT-FLX-01 | 768 | 1014 |  |  |  | 1782
BHU-FAL-01-E | 225 | 1287 | 1185 | 508 |  | 3205
D-HWP818 |  |  | 334 |  |  | 334
Mas Verde |  | 216 |  |  |  | 216
D-HOE306 | 1088 | 557 | 512 | 369 |  | 2526
D-HST11 | 192 |  |  |  |  | 192
D-HWP910 | 1174 | 1597 | 308 |  |  | 3079
D-HWP908 | 1545 | 995 |  |  |  | 2540
BHZD-FWP-08-W |  |  | 333 |  |  | 333
D-HNP135 |  |  | 160 |  |  | 160
FB-HWP376 |  |  | 1282 | 980 |  | 2262
BHU-FAL-01-E
Grand Total | 5232 | 5991 | 4240 | 3081 | 268 | 18812
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | Grand Total
D-HNP106 |  | 163 | 535 | 570 |  | 1268
D-HNP135
FB-HLR201 |  |  |  | 170 |  | 170
BHT-FLX-01 |  |  | 986 |  |  | 986
BHU-FAL-01-E | 916 | 144 |  |  |  | 1060
D-HWP910
D-HWP908
FB-HWP376 | 828 | 150 |  | 688 |  | 1666
BHZD-FWP-8-W | 233 |  |  |  |  | 233
D-HWP913 | 1768 | 510 |  |  |  | 2278
Lake Shore Park | 220 | 435 | 227 | 487 | 123 | 1492
BHU-FAL-01-W-2 | 60 | 219 |  |  |  | 279
FB-HWP903 |  |  | 240 |  |  | 240
Citrus Wood |  | 1603 | 791 | 2803 |  | 5197
D-HLR207 |  | 927 | 1221 | 1023 |  | 3171
D-HWP915 |  | 974 | 1312 | 359 |  | 2645
D-HWP909 |  |  | 1239 | 1220 |  | 2459
D-HLR211 |  |  | 1457 | 1142 | 945 | 3544
Grand Total | 4025 | 5125 | 8008 | 8462 | 1068 | 26688
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | Grand Total
D-HNP106 | 92 |  |  | 209 | 434 | 735
FB-HNP133 | 153 | 244 |  | 237 |  | 634
D-HNP135 | 455 |  |  |  |  | 455
BHT-FOE-03 | 151 | 149 |  |  |  | 300
FB-HNP104 |  |  | 168 |  | 34 | 202
BHZD-FWP-08-W
Lake Shore Park |  | 413 | 190 | 1194 | 306 | 2103
Citrus Wood | 3343 | 714 | 2013 | 1500 | 1933 | 9503
D-HLR207 | 1100 | 527 | 553 |  |  | 2180
D-HWP915 |  | 230 |  |  |  | 230
D-HWP909 | 853 |  |  |  |  | 853
D-HLR211 | 1186 | 1564 | 1012 | 588 |  | 4350
D-HWP912 |  | 1007 | 1672 | 1544 |  | 4223
D-HWP1307 |  | 1182 | 1604 | 1268 |  | 4054
FB-HOE178 |  |  | 1624 | 551 |  | 2175
D-HLR210 |  |  |  |  | 408 | 408
Grand Total | 7333 | 6030 | 8836 | 7091 | 3115 | 32405
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | Grand Total
FB-HNP111 |  |  | 171 |  |  | 171
D-HNP106 | 567 |  |  |  |  | 567
BHT-FOE-03
FB-HOE301 |  |  |  |  | 60 | 60
FB-HLR201
BHT-FLX-01
FB-HNP104 | 188 | 140 |  |  |  | 328
BHZD-FWP-08-W | 270 | 60 |  |  |  | 330
D-HWP913
Lake Shore Park | 203 | 996 | 1147 | 1053 | 955 | 4354
Citrus Wood | 820 | 2077 | 1096 |  |  | 3993
D-HLR207 |  | 1647 | 343 |  |  | 1990
D-HWP912 | 587 | 115 |  |  |  | 702
D-HWP914 |  | 1509 | 1087 | 777 |  | 3373
D-HWP1307 | 1310 |  |  |  |  | 1310
FB-HOE178 |  |  |  |  | 168 | 168
D-HLR210 | 1323 | 1516 | 790 | 930 | 408 | 4967
Wilders Park | 1224 | 988 | 2316 | 2066 |  | 6594
D-HWP911 |  | 1678 |  | 394 |  | 2072
D-HLR203 |  |  | 3179 |  |  | 3179
FB-HWP901 |  |  |  | 978 |  | 978
FB-HWP1377 |  |  |  | 502 |  | 502
D-HLR204 |  |  |  | 346 |  | 346
Grand Total | 6492 | 10726 | 10129 | 7046 | 1591 | 35984
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | Grand Total
D-HNP106
FB-HOE375
BHT-FLX-01
D-HOE306 |  |  |  |  | 569 | 569
Lake Shore Park
BHU-FAL-01-W-2 |  |  | 150 |  |  | 150
D-HLR211
D-HWP1307 | 701 |  |  |  |  | 701
FB-HOE178 | 463 | 633 | 625 |  |  | 1721
D-HLR210
D-HLR203 | 882 | 1072 | 1034 | 209 |  | 3197
FB-HWP901 | 1420 | 990 | 549 |  |  | 2959
FB-HWP1377 | 259 | 1087 | 2206 | 453 |  | 4005
D-HLR204 |  | 379 | 208 |  |  | 587
D-HWP918 | 579 | 1120 | 1488 | 954 |  | 4141
FB--HWP1377 | 365 |  |  |  |  | 365
FB-HOE675 | 207 |  |  |  |  | 207
Sunset Palms MHP |  | 1691 | 1998 | 760 | 3975 | 8424
FB-HWP1379 |  |  | 1031 |  |  | 1031
FB-HOE175 |  |  |  | 1063 | 1263 | 2326
Wilders MHP |  |  |  |  | 451 | 451
D-HSH222 | 3266 | 3910 | 346 |  |  | 7522
D-HSH224 |  | 372 | 656 |  |  | 1028
D-HSH223 |  |  | 2985 | 2373 |  | 5358
D-HSH240 |  |  |  |  | 2948 | 2948
Grand Total | 8142 | 11254 | 13276 | 5812 | 9206 | 47690
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | Grand Total
FB-HNP138
BHU-FAL-01-E
Lake Shore Park | 560 |  |  |  |  | 560
D-HLR211
D-HWP1307 | 138 |  |  |  |  | 138
D-HLR210
D-HLR203 | 96 |  |  |  |  | 96
FB-HWP901 | 632 |  |  |  |  | 632
FB-HWP1377 | 558 |  |  |  |  | 558
D-HLR204 | 562 |  | 474 | 606 | 322 | 1964
FB-HWP1379 | 1351 |  | 890 |  |  | 2241
D-HSH240 | 4084 |  | 242 |  |  | 4326
Sherwood Estates | 748 | 1062 |  |  |  | 1810
D-HLR205 | 435 |  |  | 1123 |  | 1558
D-HWP917 |  |  | 1580 | 1258 |  | 2838
D-HWP916 |  |  | 877 | 814 |  | 1691
BHZD-FLX-04-W |  |  | 711 | 325 | 430 | 1466
D-HDF711 |  |  | 1486 | 2912 | 2125 | 6523
D-HSH237 |  |  | 1264 | 1281 |  | 2545
Citrus Woods
D-HSH242 |  |  | 3678 | 3382 |  | 7060
Sherwood |  |  |  |  | 1505 | 1505
FB-HSH241 |  |  |  | 424 |  | 424
D-HSH243 |  |  |  | 598 |  | 598
Grand Total | 9164 | 1062 | 11202 | 12723 | 4382 | 38533
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | Grand Total
FB-HNP138 |  |  |  | 170 | 271 | 441
FB-HLR201 | 446 | 120 | 550 |  |  | 1116
Lake Shore Park |  | 17 |  |  |  | 17
D-HWP1307
FB-HWP1377 | 127 |  |  |  |  | 127
D-HLR204 | 420 |  |  |  |  | 420
FB-HWP1379
D-HLR205 |  | 1917 |  | 272 |  | 2189
D-HWP916 | 956 |  |  |  |  | 956
BHZD-FLX-04-W |  |  |  | 195 |  | 195
D-HDF711 | 1449 |  |  |  |  | 1449
D-HSH237 | 1662 | 2684 |  |  | 51 | 4397
D-HSH241 | 5466 |  |  | 2252 |  | 7718
Sherwood | 907 |  |  |  |  | 907
FB-HSH241 |  |  |  | 313 | 3007 | 3320
D-HSH243 | 1498 | 3613 |  | 1027 | 490 | 6628
Heatherwood MHP | 1505 | 1518 | 1968 | 345 | 375 | 5711
D-HWP1312 | 1471 |  |  |  |  | 1471
D-HWP1311 | 762 | 1530 | 954 | 1603 |  | 4849
D-HWP1313 |  | 1679 | 1429 | 1624 |  | 4732
D-HDF713 |  | 2351 | 1835 | 2139 | 789 | 7114
Wilders |  | 12 |  |  |  | 12
Sunset Palms |  |  | 480 |  | 448 | 928
D-HSH220
D-HSH221
BHUD-FOE-06-E-2 |  | 136 | 170 |  | 15 | 321
D-HSH244 |  |  |  | 1420 | 3043 | 4463
D-HSH245 |  |  |  | 2376 | 1217 | 3593
D-HDF714 |  |  |  |  | 1281 | 1281
Grand Total | 16669 | 15577 | 7386 | 13736 | 10987 | 64355
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | Grand Total
(blank)
FB-HNP138
FB-HNP111 |  | 68 |  |  |  | 68
D-HNP108
BHU-FAL-01-E
FB-HOE178
D-HLR210
D-HLR203
D-HLR204 |  |  | 426 |  |  | 426
FB-HOE175
D-HSH222
D-HSH224 |  | 1175 |  |  |  | 1175
D-HSH223 |  | 996 |  |  |  | 996
D-HLR205 | 900 |  |  |  |  | 900
D-HWP917
D-HWP916
Heatherwood MHP | 2805 | 1397 |  |  |  | 4202
D-HWP1312 | 665 | 1360 | 1024 |  |  | 3049
D-HWP1311 | 805 |  |  |  |  | 805
D-HWP1313 | 572 |  |  |  |  | 572
Sunset Palms | 1718 | 2478 | 1567 |  |  | 5763
D-HSH244 |  | 3411 |  |  |  | 3411
FX4-FWP-09 | 82 |  |  |  |  | 82
D-HSH245 |  | 3311 |  |  |  | 3311
D-HSH225
D-HDF714 |  | 2568 |  |  |  | 2568
FB-HWP483 | 286 | 357 | 331 |  |  | 974
D-HDF704 | 1655 | 2537 |  |  |  | 4192
D-HSH238 |  | 2382 |  |  |  | 2382
D-HWP1314 |  | 1100 | 855 |  |  | 1955
Fountain View |  | 486 |  |  |  | 486
D-HSH246 |  | 3634 |  |  |  | 3634
Heatherwood Village |  |  | 955 |  |  | 955
Sherwood Mobile Manor
D-HSH229
D-HSH226
D-HSH227
D-HSH228
D-HSH230
D-HSH231
D-HSH232
Grand Total | 9488 | 27260 | 5158 |  |  | 41906
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | Grand Total
D-HNP110 |  |  |  |  | 222 | 222
D-HNP108 | 523 |  |  |  |  | 523
D-HWP918 |  | 175 |  |  |  | 175
Sunset Palms MHP | 602 | 1069 | 1129 | 1041 | 1824 | 5665
D-HSH224 | 1515 |  |  |  |  | 1515
D-HSH241 |  |  |  | 64 |  | 64
D-HSH242
D-HWP1312 | 1610 |  |  |  |  | 1610
D-HWP1311
D-HSH244 |  |  |  | 52 |  | 52
D-HDF714 |  |  |  | 489 | 2020 | 2509
D-HDF704 | 2113 |  | 1677 | 1316 |  | 5106
D-HSH238 | 3084 |  |  |  |  | 3084
D-HWP1314 | 1622 | 1131 |  |  |  | 2753
Fountain View | 600 | 610 | 974 |  |  | 2184
D-HSH246 | 3376 |  |  |  |  | 3376
Heatherwood Village | 1765 | 1153 | 383 | 490 |  | 3791
Vantage Point | 545 | 1172 | 1256 | 272 | 86 | 3331
FB-HSH238 | 1829 | 2302 | 694 |  |  | 4825
D-HSH239 | 1391 | 2916 | 2430 |  |  | 6737
D-HWP820 |  |  | 466 | 345 |  | 811
D-HWP1315 |  |  |  | 1431 |  | 1431
D-HWP906 |  |  | 1379 | 1154 |  | 2533
D-HSH236 |  |  | 243 |  |  | 243
Fountainview |  |  |  |  | 385 | 385
D-HSH233
Grand Total | 20575 | 10528 | 10631 | 6654 | 4537 | 52925
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | Grand Total
D-HNP110 | 237 | 194 | 359 | 255 | 253 | 1298
Sunset Palms MHP | 1283 | 442 |  |  | 706 | 2431
D-HSH223 |  | 2203 |  |  |  | 2203
D-HSH243 |  |  |  | 242 |  | 242
D-HWP1312
D-HDF714 | 428 |  |  |  |  | 428
Heatherwood Village
Vantage Point |  | 265 | 542 | 739 |  | 1546
FB-HSH238 |  |  | 91 |  |  | 91
D-HWP820 | 1172 |  |  |  |  | 1172
D-HWP1315 | 1583 | 1325 | 621 |  |  | 3529
D-HWP906
Fountainview | 640 | 541 | 330 | 520 | 550 | 2581
D-HSH250 | 2855 | 3343 | 931 |  |  | 7129
D-HSH251 |  | 1743 | 522 | 1194 | 2811 | 6270
Heatherwood
D-HDF702 |  | 1640 | 1177 |  |  | 2817
D-HSH247 |  | 1980 | 1251 | 3172 |  | 6403
D-HSH249 |  | 1111 | 1373 | 1090 | 1204 | 4778
D-HWP819 |  | 1500 | 1084 |  |  | 2584
D-HDF703 |  |  | 817 | 1820 |  | 2637
D-HWP817 |  |  |  | 1351 |  | 1351
D-HDF707 |  |  |  |  | 1832 | 1832
Grand Total | 8198 | 16287 | 9098 | 10383 | 7356 | 51322
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | Grand Total
D-HNP110 | 365 | 210 |  |  | 166 | 741
Sunset Palms MHP | 735 |  |  |  |  | 735
D-HSH222
D-HSH242
FB-HSH241 |  |  |  | 396 |  | 396
D-HSH243
D-HWP1312
D-HSH245 | 87 |  |  |  |  | 87
Vantage Point | 671 | 1204 | 1210 | 292 |  | 3377
FB-HSH238 |  |  | 320 | 652 | 780 | 1752
D-HWP820 |  |  | 163 |  |  | 163
D-HSH236 |  |  | 372 |  | 582 | 954
Fountainview | 752 | 1249 | 235 | 563 | 483 | 3282
D-HSH251 |  |  | 1049 |  |  | 1049
D-HSH247 | 29 |  |  |  |  | 29
D-HSH249 |  |  |  |  | 1235 | 1235
D-HWP819
D-HWP817 | 689 | 586 | 199 |  |  | 1474
D-HDF707 |  | 1164 | 308 | 892 | 366 | 2730
D-HWP808-1 | 1095 | 1676 | 1139 |  |  | 3910
D-HWP901 | 1344 | 1583 | 1027 | 1596 |  | 5550
D-HOE501 |  | 890 | 1810 | 967 |  | 3667
D-HDF715 | 1511 | 1887 | 916 | 1704 | 974 | 6992
D-HSH248 |  | 1617 | 1083 | 1905 | 2064 | 6669
D-HSH254 |  |  | 95 | 881 |  | 976
D-HSH252 |  |  |  | 3028 | 1683 | 4711
FB-HWP880 |  |  |  | 1568 |  | 1568
FB-HSH 241
Grand Total | 7278 | 12066 | 9926 | 14444 | 8333 | 52047
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | Grand Total
(blank)
D-HNP110 |  | 212 |  |  |  | 212
Vantage Point
FB-HSH238 | 870 |  |  |  |  | 870
D-HSH236 | 551 |  |  |  |  | 551
Fountainview
D-HDF707 | 154 |  |  |  |  | 154
D-HWP901 | 342 |  |  |  |  | 342
D-HSH248
D-HSH254 | 3523 | 2384 |  |  |  | 5907
D-HSH252 | 362 |  |  |  |  | 362
FB-HWP880 | 380 |  |  |  |  | 380
FB-HWP882 | 523 | 405 |  |  |  | 928
Grand Total | 6705 | 3001 |  |  |  | 9706
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | Grand Total
(blank) |  |  |  | 0 | 0 | 0
D-HNP110 | 108 | 353 |  |  |  | 461
D-HSH240
D-HSH237 | 0 |  |  |  |  | 0
D-HSH238 |  | 0 |  |  |  | 0
D-HSH239 | 0 |  |  |  |  | 0
D-HWP1315
D-HSH236 | 738 | 466 |  |  |  | 1204
D-HSH251 | 0 |  |  |  |  | 0
D-HDF707 |  |  | 173 |  |  | 173
D-HSH252 | 1297 |  |  |  |  | 1297
FB-HWP880 | 100 |  |  |  |  | 100
D-HSH253 | 2583 | 3099 |  |  |  | 5682
D-HWP1316 | 1188 | 0 |  |  |  | 1188
D-HWP1317 | 900 |  |  |  |  | 900
Grand Total | 6914 | 3918 | 173 | 0 | 0 | 11005
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | Grand Total
FB-HNP138 |  | 152 |  | 85 |  | 237
D-HNP110 | 248 |  | 366 | 113 |  | 727
FB-HOE175 |  |  |  |  | 0 | 0
D-HSH223 |  | 0 |  |  |  | 0
D-HSH246
D-HSH236 | 3728 | 1789 |  |  |  | 5517
D-HSH250 |  |  | 0 |  |  | 0
D-HSH249
D-HSH248 |  |  | 0 |  | 104 | 104
D-HSH253 | 568 |  |  |  |  | 568
FB-HLR202 | 1105 | 942 | 2151 | 1926 | 1000 | 7124
FB-HWP484 | 1353 | 1153 |  |  |  | 2506
D-HSH255 |  | 2362 | 3079 |  |  | 5441
D-HWP907 |  | 1534 | 180 |  |  | 1714
D-HWP1003 |  |  | 1687 | 1053 |  | 2740
D-HWP1004 |  |  | 1056 |  |  | 1056
D-HSH256 |  |  |  | 2367 | 447 | 2814
FB-HOE501 |  |  |  |  | 0 | 0
D-HDF705 |  |  |  |  | 1319 | 1319
Grand Total | 7002 | 7932 | 8519 | 5544 | 2870 | 31867
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | Grand Total
D-HDH34 |  |  |  |  | 50 | 50
FB-HNP138 |  | 312 |  |  |  | 312
D-HNP106 |  |  |  | 142 |  | 142
FB-HLR201 |  |  | 1200 | 445 | 686 | 2331
FB-HOE375
BHU-FAL-01-E
FB-HOE675
D-HSH249
FB-HLR202 | 1812 | 1838 |  | 0 |  | 3650
FB-HWP484 | 1314 |  |  |  |  | 1314
D-HWP907 |  |  | 0 |  |  | 0
D-HWP1003 | 0 |  |  |  |  | 0
D-HWP1004 | 1356 | 1435 | 1295 |  |  | 4086
D-HSH256 | 858 |  |  |  |  | 858
D-HDF705 | 926 | 1128 | 1082 | 1325 | 441 | 4902
FB-HNP118 | 205 |  |  |  | 107 | 312
D-HBK131 | 4915 | 914 | 0 |  |  | 5829
D-HBK130 | 813 | 1491 | 1062 | 527 |  | 3893
Fountain View Estates MHP
FB-HWP377
D-HBK132 |  | 6092 | 0 | 0 |  | 6092
D-HBK133 |  | 822 | 2611 |  |  | 3433
D-HBK135 |  |  | 544 | 2832 | 457 | 3833
D-HBK134 |  |  | 1728 |  | 3082 | 4810
D-HBK136 |  |  |  | 1562 | 673 | 2235
FB-HBK104 |  |  |  | 1639 | 987 | 2626
Moss Creek | 607 | 662 | 877 | 499 | 186 | 2831
Grand Total | 12806 | 14694 | 10399 | 8971 | 6669 | 53539
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | Grand Total
(blank) | 0 |  |  |  |  | 0
D-HNP106 |  |  |  |  | 57 | 57
FB-HLR201 |  | 0 |  |  |  | 0
D-HNP108 |  |  | 150 | 0 | 274 | 424
D-HSH224 |  | 2209 |  |  |  | 2209
D-HSH248
FB-HWP484
D-HWP1004 |  | 0 |  |  |  | 0
D-HSH256 |  |  |  | 1940 |  | 1940
FB-HNP118 |  | 183 | 182 | 186 |  | 551
D-HBK130 |  |  |  | 1776 |  | 1776
D-HBK135 |  | 506 |  |  |  | 506
D-HBK136 |  |  | 2265 |  | 2651 | 4916
FB-HBK104 |  | 0 | 575 |  | 818 | 1393
FB-HWP106 |  | 1344 |  |  |  | 1344
Moss Creek |  | 660 | 754 | 520 | 0 | 1934
Colonial Manor |  | 1382 | 993 | 1462 | 1617 | 5454
D-HDF708 |  | 2719 | 408 |  |  | 3127
FB-HBK130 |  | 1277 |  |  |  | 1277
D-HWP1006 |  |  | 686 | 736 |  | 1422
D-HWP1005 |  |  | 867 | 1539 |  | 2406
D-HDF740 |  |  | 2000 | 970 |  | 2970
D-HLR208 |  |  |  | 2031 | 845 | 2876
Grand Total | 0 | 10280 | 8880 | 11160 | 6262 | 36582
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | Grand Total
FB-HLR201 |  | 511 | 324 | 838 | 481 | 2154
D-HNP108 |  | 343 | 62 | 329 |  | 734
D-HSH254
D-HSH252
D-HSH253
FB-HLR202 |  |  | 149 |  |  | 149
FB-HWP484
D-HSH255
D-HWP1003
D-HSH256
D-HBK131
D-HBK130
D-HBK132
D-HBK133 | 1908 |  |  |  |  | 1908
D-HBK135
D-HBK134
D-HBK136
FB-HBK104
FB-HWP106 | 886 |  |  |  |  | 886
Moss Creek | 376 | 647 | 565 | 222 |  | 1810
Colonial Manor | 1642 | 843 |  | 410 |  | 2895
FB-HBK130
D-HWP1006 | 835 | 858 | 976 |  |  | 2669
D-HWP1005 | 1590 | 1230 | 1015 |  |  | 3835
D-HLR208 | 1530 | 388 |  | 470 |  | 2388
D-HWP1007 |  | 1758 | 1363 |  |  | 3121
FB-HOE401-V2 |  |  | 881 | 1143 |  | 2024
D-HDF710 |  |  |  | 1468 | 1637 | 3105
Grand Total | 8767 | 6578 | 5335 | 4880 | 2118 | 27678
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | Grand Total
FB-HLR201 | 859 |  |  |  |  | 859
D-HNP108 | 251 |  |  |  |  | 251
D-HLR204
D-HSH249 |  |  |  | 253 |  | 253
FB-HLR202
FB-HNP118
Moss Creek
Colonial Manor
D-HDF708 |  |  | 1809 | 696 | 3 | 2508
D-HWP1006 | 505 |  |  |  |  | 505
D-HWP1005
D-HWP1007
FB-HOE401-V2 |  | 363 | 933 | 363 |  | 1659
D-HDF710 |  | 1646 |  |  | 6 | 1652
D-HWP1303 |  | 1250 | 518 | 990 |  | 2758
D-H0306A-1 |  | 251 |  | 298 |  | 549
D-HWP109 |  |  | 330 | 625 |  | 955
Grand Total | 1615 | 3510 | 3590 | 3225 | 9 | 11949
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | Grand Total
FB-HLR201
D-HNP108 | 389 | 152 | 45 |  |  | 586
FB-HNP104 |  | 197 | 338 |  |  | 535
FB-HLR202
FB-HOE401-V2 |  |  |  | 30 |  | 30
D-HWP1303 |  |  |  |  | 342 | 342
D-H0306A-1 |  |  | 150 |  |  | 150
D-HWP109 | 712 | 1092 | 384 | 397 |  | 2585
D-HO306A-1 |  | 189 |  |  |  | 189
FB-HAL175 |  | 817 |  |  |  | 817
FB-HOE401-V3 |  |  | 753 | 1289 |  | 2042
D-HDF712 |  |  | 2073 | 1342 | 1601 | 5016
Grand Total | 1101 | 2447 | 3743 | 3058 | 1943 | 12292
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | Grand Total
D-H0221F |  |  |  |  | 295 | 295
D-HNP114 |  | 988 | 712 | 474 |  | 2174
D-HNP108 |  | 214 |  |  |  | 214
FB-HNP104 |  | 214 |  |  |  | 214
FB-HOE501 |  | 1340 | 1529 | 1168 | 1008 | 5045
D-HWP109 | 669 | 467 | 1133 | 448 |  | 2717
D-HWP106 | 1564 | 1532 | 1447 | 864 |  | 5407
Sabal Lakes |  | 199 | 361 | 652 | 379 | 1591
D-HWP107 |  |  |  | 538 |  | 538
BHU-FAL-01-W |  |  |  |  | 45 | 45
D-H0221F-Repair |  |  | 187 | 300 |  | 487
Grand Total | 2233 | 4954 | 5369 | 4444 | 1727 | 18727
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | Grand Total
D-HNP114 | 837 |  |  |  | 199 | 1036
FB-HOE501 | 1274 | 1073 | 271 |  |  | 2618
FB-HWP106 |  |  |  | 1033 |  | 1033
D-HDF708 |  |  | 667 |  |  | 667
D-HWP109 | 1044 |  |  |  |  | 1044
FB-HOE401-V3 |  | 1062 | 1318 | 1165 |  | 3545
D-HDF712 | 1099 |  | 2025 |  |  | 3124
D-HWP106
Sabal Lakes | 534 |  | 223 |  |  | 757
D-HWP107 |  | 1056 | 2018 |  |  | 3074
D-H0221F-Repair | 201 |  | 200 |  |  | 401
Sabal Lakes |  |  |  |  | 1187 | 1187
Grand Total | 4989 | 3191 | 6722 | 2198 | 1386 | 18486
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | Grand Total
D-HOE501 |  | 179 |  |  |  | 179
FB-HOE501
D-HWP109
FB-HOE401-V3 | 1391 |  |  |  |  | 1391
D-HWP107 | 1016 |  |  |  |  | 1016
Sabal Lakes | 1287 | 575 | 857 | 668 | 1392 | 4779
D-HWP110 | 611 | 1612 |  |  |  | 2223
D-HOE502 |  |  | 480 | 774 |  | 1254
Grand Total | 4305 | 2366 | 1337 | 1442 | 1392 | 10842
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | Grand Total
D-H0221F-Repair |  |  |  |  | 100 | 100
Sabal Lakes | 167 | 487 | 263 | 399 | 278 | 1594
D-HWP110 | 1561 |  |  |  |  | 1561
D-HOE502 | 570 |  |  |  |  | 570
FB-HLX401 | 1146 | 308 | 300 |  | 510 | 2264
FB-HLX409 | 535 |  | 342 | 103 |  | 980
Willow Walk | 606 | 459 | 243 | 778 | 664 | 2750
D-HWP108 |  | 1595 | 1704 |  |  | 3299
Grand Total | 4585 | 2849 | 2852 | 1280 | 1552 | 13118
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | Grand Total
FB-HNP111 |  |  |  | 140 |  | 140
D-HOE501 | 326 |  |  |  |  | 326
D-H0221F-Repair | 314 | 240 |  |  |  | 554
Sabal Lakes |  |  |  |  | 308 | 308
D-HWP110
Willow Walk North |  |  |  | 646 | 212 | 858
D-HOE502 | 307 | 872 | 312 | 287 |  | 1778
FB-HLX401 | 1297 | 1300 |  | 1766 | 41 | 4404
Willow Walk | 534 | 466 | 483 |  |  | 1483
D-HWP108 | 1581 |  |  |  |  | 1581
BHT-FLX-02 | 1163 |  |  |  |  | 1163
D-HWP919 |  | 560 | 367 |  |  | 927
FB-HOE176
FB-HOE180 |  | 130 |  |  |  | 130
D-HNP151-Repair |  |  | 86 |  |  | 86
D-HWP902-Repair |  |  | 157 |  |  | 157
BHCD-FSF-05-E |  |  | 462 | 1412 | 1376 | 3250
Grand Total | 5522 | 3568 | 1867 | 4251 | 1937 | 17145
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | Grand Total
D-HNP114
FB-HNP111
D-HLR204 |  |  |  | 438 |  | 438
D-HOE501
Willow Walk North | 225 | 135 | 494 | 333 | 377 | 1564
D-HOE502
FB-HLX401
BHCD-FSF-05-E |  |  | 2020 | 1855 | 1609 | 5484
D-HLR212 | 735 | 755 | 897 | 583 |  | 2970
FB-HSH404 |  | 513 |  |  |  | 513
BHCD-FPW-03-W |  |  | 172 |  |  | 172
FB-HWP478 |  |  | 918 |  |  | 918
FB-HSF404
BHCD-FSF-04-W |  |  | 7 |  |  | 7
FB-HSF477 |  |  |  | 265 | 372 | 637
Grand Total | 960 | 1403 | 4508 | 3474 | 2358 | 12703
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | Grand Total
Sunset Palms
Willow Walk North | 526 | 36 | 12 |  |  | 574
BHCD-FSF-05-E |  | 1420 | 1208 | 596 |  | 3224
FB-HSF477 | 396 |  |  | 145 |  | 541
FB-HAL113 | 978 | 1555 | 1095 |  |  | 3628
FB-HSF379 | 788 | 1083 |  |  |  | 1871
FB-HSF476 | 195 |  | 349 | 790 | 15 | 1349
D-HDH57 Repair |  | 55 |  |  |  | 55
FB-HSF381 |  | 551 | 1606 |  |  | 2157
FB-HSF475 |  |  |  |  | 752 | 752
Grand Total | 2883 | 4700 | 4270 | 1531 | 767 | 14151
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | Grand Total
D-HNP106
Sunset Palms
BHCD-FSF-05-E
FB-HSF404
BHCD-FSF-04-W
FB-HSF477
FB-HAL113 |  | 400 |  |  |  | 400
FB-HSF379
FB-HSF476
FB-HSF381
FB-HSF475
FB-HAL177 | 1360 |  |  |  |  | 1360
FB-HSF383 |  | 102 |  |  |  | 102
FB-HSF384 |  | 417 |  |  |  | 417
FB-HLX417 |  |  | 1036 |  |  | 1036
FB-HLX501 |  |  |  |  | 891 | 891
Grand Total | 1360 | 919 | 1036 |  | 891 | 4206
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | Grand Total
FB-HOE176 |  |  |  |  | 67 | 67
BHCD-FSF-05-E
FB-HAL113
FB-HAL177
FB-HSF383
FB-HSF384
FB-HLX501 | 2719 | 2206 | 2612 | 1765 | 1356 | 10658
FB-HSF177
BHUD-FLX-04-E |  |  |  | 407 |  | 407
Grand Total | 2719 | 2206 | 2612 | 2172 | 1423 | 11132
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | Grand Total
FB-HNP138 |  |  |  |  | 70 | 70
BHCD-FPW-03-W | 572 | 776 | 1009 | 770 |  | 3127
FB-HLX417
FB-HLX501 | 1212 | 866 | 969 | 262 |  | 3309
BHUD-FLX-04-E | 940 | 1575 | 507 |  | 354 | 3376
D-HLX416 |  |  |  | 2434 |  | 2434
BHU-FLX-01-E |  | 767 | 779 | 130 |  | 1676
FB-HSF375 |  |  |  |  | 339 | 339
FB-HSF377 | 288 |  |  |  |  | 288
FB-HSF378 |  | 290 |  |  |  | 290
FB-HWP875 |  |  | 390 |  | 8 | 398
FB-HWP879 |  |  | 454 | 285 | 33 | 772
D-HBR253 |  |  | 544 | 723 | 563 | 1830
D-HBR252 |  | 3749 |  |  |  | 3749
D-HLX404 |  |  |  |  | 1587 | 1587
D-HTG202 |  |  |  |  | 1085 | 1085
Grand Total | 3012 | 8023 | 4652 | 4604 | 4039 | 24330
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | Grand Total
FB-HNP138 | 380 |  |  |  |  | 380
FB-HOE176 | 245 |  |  |  |  | 245
BHUD-FLX-04-E | 864 | 674 | 724 | 165 |  | 2427
D-HLX416 |  |  | 1012 |  |  | 1012
BHU-FLX-01-E |  | 276 |  | 425 |  | 701
FB-HWP875 | 615 | 349 |  |  |  | 964
FB-HWP879 | 327 | 269 | 515 | 451 |  | 1562
D-HBR253 | 1246 |  |  |  |  | 1246
D-HLX404 | 1339 | 857 | 32 |  |  | 2228
D-HTG202 |  |  |  | 2018 | 1563 | 3581
Heatherpoint Lake Estates |  |  | 440 |  | 549 | 989
BHUD-FLX-01-E |  |  | 641 |  |  | 641
D-HLX402 |  |  | 947 | 1381 |  | 2328
BHU-FLX-01-W |  | 2304 | 1216 | 2932 |  | 6452
D-HBR254 |  | 708 | 697 |  |  | 1405
Grand Total | 5016 | 5437 | 6224 | 7372 | 2112 | 26161
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | Grand Total
BHZD-FLX-04-W |  |  |  | 513 |  | 513
FB-HLX501
D-HLX416 | 757 |  |  |  |  | 757
BHU-FLX-01-E |  | 110 |  |  |  | 110
D-HBR253 |  |  |  |  | 630 | 630
D-HBR252 |  |  | 43 | 8 |  | 51
D-HTG202 | 699 | 463 | 561 | 129 |  | 1852
Heatherpoint Lake Estates | 847 | 555 | 831 |  |  | 2233
D-HLX402 | 897 | 408 |  |  |  | 1305
BHU-FLX-01-W | 350 |  |  |  |  | 350
D-HBR254 |  |  | 140 |  |  | 140
FB-HTG237 |  | 1174 | 1060 | 818 | 441 | 3493
FB-HSF304 |  | 521 | 701 | 707 | 512 | 2441
D-HLX401 |  | 473 | 1258 | 1494 |  | 3225
D-HLX421 |  |  | 873 | 449 |  | 1322
D-HTG208 |  |  |  |  | 1540 | 1540
Grand Total | 3550 | 3704 | 5467 | 4118 | 3123 | 19962
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | Grand Total
BHZD-FLX-04-W |  |  | 427 |  |  | 427
BHU-FAL-01-W
FB-HLX409 |  |  | 258 |  |  | 258
D-HLX416 | 1627 |  |  |  |  | 1627
FB-HSF375 |  |  |  | 110 |  | 110
D-HBR253 | 114 |  |  |  |  | 114
Heatherpoint Lake Estates | 217 |  |  |  |  | 217
D-HLX402 |  | 2700 |  |  |  | 2700
D-HBR254 | 763 | 745 | 673 |  | 931 | 3112
FB-HTG237 |  | 679 | 263 | 46 |  | 988
FB-HSF304
D-HLX401 | 1070 | 584 |  |  |  | 1654
D-HLX501 | 525 |  | 787 |  | 540 | 1852
D-HTG208 | 483 |  |  |  | 191 | 674
D-HPP606 |  | 443 | 406 | 361 | 345 | 1555
D-HTG206 |  | 1520 | 413 | 1539 | 770 | 4242
FB-HAL101 |  |  | 675 | 1313 |  | 1988
D-HLX406 |  |  | 1245 | 1150 | 1240 | 3635
FB-HSF376 |  |  | 73 | 35 |  | 108
FB-HBR252 |  |  | 292 |  | 2380 | 2672
FB-HAL176 |  |  |  | 145 |  | 145
FB-HAL179 |  |  |  |  | 225 | 225
Grand Total | 4799 | 6671 | 5512 | 4699 | 6622 | 28303
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | Grand Total
BHU-FAL-01-W |  | 245 |  |  |  | 245
FB-HWP478
D-HBR253 |  |  |  |  | 241 | 241
D-HBR252
D-HLX401 |  |  |  | 60 |  | 60
D-HLX501 | 585 | 464 | 579 | 300 | 216 | 2144
D-HTG208 | 587 | 364 |  | 654 | 1381 | 2986
D-HPP606 | 766 | 566 | 488 |  | 225 | 2045
D-HTG206 | 1126 | 879 | 218 | 71 |  | 2294
FB-HAL101 |  | 1000 |  |  |  | 1000
D-HLX406 | 1210 | 1966 | 189 |  |  | 3365
FB-HBR252 |  | 766 |  |  |  | 766
FB-HAL179 | 280 |  |  |  |  | 280
D-HLX403 |  |  | 2164 | 2748 | 1060 | 5972
D-HSF321 |  |  | 1245 | 1344 | 803 | 3392
D-HLX507 |  |  |  |  | 351 | 351
Grand Total | 4554 | 6250 | 4883 | 5177 | 4277 | 25141
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | Grand Total
(blank)
D-HBR254 |  |  | 145 |  |  | 145
D-HLX501 |  | 65 |  |  |  | 65
D-HTG208 |  |  |  | 1196 |  | 1196
D-HPP606 |  | 465 | 193 | 1067 | 339 | 2064
FB-HAL176
D-HSF321 |  |  |  | 176 | 2202 | 2378
D-HLX507 |  | 649 | 130 | 864 |  | 1643
D-HPP613 |  | 1157 |  |  |  | 1157
D-HLX407 |  | 2456 | 2095 |  |  | 4551
D-HBR255 |  | 591 | 670 | 622 | 664 | 2547
D-HLX405 |  |  | 420 | 690 |  | 1110
D-HTG225 |  |  | 1110 | 1904 | 836 | 3850
D-HPP607 |  |  |  | 319 | 446 | 765
D-HPP612 |  |  |  | 1251 | 2149 | 3400
D-HLX518
Grand Total |  | 5383 | 4763 | 8089 | 6636 | 24871
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | Grand Total
D-HBR253 |  | 18 | 57 | 248 |  | 323
D-HBR252 |  | 63 |  |  |  | 63
D-HBR254 | 54 |  |  |  |  | 54
D-HTG208 |  |  |  |  | 241 | 241
D-HPP606 |  | 411 | 237 |  | 26 | 674
FB-HBR252
FB-HSF201 | 270 | 490 |  |  | 270 | 1030
D-HLX403 | 883 |  |  |  |  | 883
D-HSF321 | 587 |  |  |  |  | 587
D-HLX507 | 500 | 985 | 860 | 212 |  | 2557
D-HBR255 | 783 | 733 | 970 | 917 | 589 | 3992
D-HLX405 | 612 |  |  |  |  | 612
D-HTG225 |  | 1309 | 427 | 421 |  | 2157
D-HPP607 | 693 | 596 | 240 | 180 | 150 | 1859
D-HPP612 | 1826 | 882 | 1681 | 760 | 243 | 5392
D-HLX518 |  | 2110 | 218 | 796 | 800 | 3924
D-HPP614 | 514 | 457 | 580 | 590 | 351 | 2492
D-HTG233 | 1084 |  | 2699 |  |  | 3783
D-HSF320 | 1433 | 2630 | 1848 |  |  | 5911
FB-HSF301 | 500 | 260 |  |  |  | 760
D-HLX511 |  |  |  | 590 | 261 | 851
D-HTG207 |  |  |  | 2715 | 1377 | 4092
D-HTG239 |  |  |  | 804 | 559 | 1363
D-HPP609 |  |  |  |  | 1404 | 1404
Grand Total | 9739 | 10944 | 9817 | 8233 | 6271 | 45004
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | Grand Total
D-HBR253 |  | 14 |  |  |  | 14
D-HBR252 |  | 9 |  |  |  | 9
D-HBR254 |  | 441 | 7 | 36 |  | 484
D-HTG208 |  |  |  | 525 |  | 525
D-HPP606
FB-HSF201 | 100 |  |  |  |  | 100
D-HLX507 | 314 |  |  |  |  | 314
D-HPP613 | 1643 | 1601 | 764 |  |  | 4008
D-HBR255 | 230 |  | 31 | 24 | 19 | 304
D-HTG225 |  |  |  | 43 |  | 43
D-HPP607 |  |  | 510 | 320 | 155 | 985
D-HPP612 |  | 68 |  |  | 2404 | 2472
D-HLX518 | 363 |  |  |  |  | 363
D-HPP614 | 370 |  |  |  |  | 370
D-HLX511
D-HTG207 | 675 | 668 | 44 | 256 | 42 | 1685
D-HTG239 | 1052 | 1291 | 781 | 294 | 413 | 3831
D-HPP609 | 1403 | 1668 | 1670 | 1364 |  | 6105
D-HPP617 | 935 | 2201 | 2415 | 1484 | 792 | 7827
D-HPP301 | 557 | 788 | 911 | 820 |  | 3076
D-HTG241 | 554 | 592 |  |  |  | 1146
D-HLX519 |  |  | 1095 | 1806 |  | 2901
FB-HPP617 |  |  |  | 800 |  | 800
D-HLX516 |  |  |  |  | 1633 | 1633
D-HLX517 |  |  |  | 981 | 1038 | 2019
D-HTG201 |  |  |  | 1809 | 1876 | 3685
D-HBR256 |  |  |  | 682 | 370 | 1052
D-HPP618 |  |  |  |  | 2663 | 2663
D-HPP632 |  |  |  |  | 1192 | 1192
Grand Total | 8196 | 9341 | 8228 | 11244 | 12597 | 49606
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | Grand Total
FB-HAL179 |  | 120 |  | 40 |  | 160
D-HPP613 |  | 1083 |  |  |  | 1083
D-HBR255 | 27 | 32 | 32 | 65 | 31 | 187
D-HPP607 | 350 | 180 | 529 | 415 |  | 1474
D-HPP614 |  |  | 1008 | 653 |  | 1661
D-HTG233 | 1076 | 999 |  |  | 309 | 2384
D-HPP609
D-HPP617 |  |  | 289 |  |  | 289
D-HPP301 | 572 | 236 | 550 | 510 |  | 1868
D-HTG241 |  |  |  | 3 | 402 | 405
D-HLX516 |  |  | 1210 | 1249 |  | 2459
D-HLX517 | 806 | 977 | 621 |  |  | 2404
D-HTG201 | 636 |  |  |  |  | 636
D-HBR256 | 587 | 708 | 512 | 661 | 303 | 2771
D-HPP618 | 1830 |  |  |  |  | 1830
D-HPP632 | 889 | 1618 | 597 | 984 |  | 4088
D-HPP610 | 1161 |  | 2191 | 520 |  | 3872
D-HPP611 | 1639 | 2989 | 1756 | 1605 |  | 7989
D-HPP638 | 300 | 387 | 245 | 245 |  | 1177
D-HHP307 | 75 | 248 |  |  |  | 323
D-HPP311 | 139 | 361 | 2000 | 2076 |  | 4576
D-HPP629 |  |  |  | 1289 |  | 1289
D-HPP318 |  | 579 |  | 2842 |  | 3421
D-HTG229 |  | 608 | 784 | 337 |  | 1729
D-HTG237 |  | 3059 | 820 |  | 553 | 4432
D-HPP619 |  |  | 2590 | 1745 |  | 4335
D-HPP307 |  |  | 179 |  |  | 179
D-HTG235 |  |  | 1611 | 2862 | 894 | 5367
D-HPP621 |  |  |  | 724 |  | 724
D-HPP627
D-HPP631 |  |  |  | 225 |  | 225
D-HPP633
D-HPP305 |  |  |  | 1218 |  | 1218
D-HLX522 |  |  |  | 865 |  | 865
D-HTG238 |  |  |  | 382 |  | 382
D-HLX512 |  |  |  |  | 822 | 822
Grand Total | 10087 | 14184 | 17524 | 21515 | 3314 | 66624
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | Grand Total
D-HLX404
D-HLX402
D-HLX406
FB-HBR252
D-HLX403
D-HPP607 | 171 |  | 93 |  |  | 264
D-HPP614 | 214 | 1276 |  |  |  | 1490
D-HTG233 | 511 |  | 84 | 75 |  | 670
D-HTG228 |  |  |  | 951 |  | 951
D-HPP301 | 87 |  |  |  |  | 87
D-HTG241 | 697 |  |  |  | 3 | 700
D-HBR256 | 672 | 710 | 823 | 601 | 597 | 3403
D-HPP618
D-HPP632 | 391 |  |  |  |  | 391
D-HPP610 |  |  | 2241 |  |  | 2241
D-HPP611 |  |  | 1179 |  |  | 1179
D-HPP311 | 364 |  |  |  |  | 364
D-HPP629 |  |  | 2452 |  |  | 2452
D-HPP318 | 2283 | 1160 | 803 |  |  | 4246
D-HTG229 |  | 689 |  |  |  | 689
D-HTG237 |  | 193 |  |  |  | 193
D-HPP619 | 825 | 950 | 502 | 838 |  | 3115
D-HPP307 | 281 | 115 | 253 |  |  | 649
D-HTG235 |  | 210 |  |  |  | 210
D-HPP621 | 2294 |  | 1974 |  |  | 4268
D-HPP627 | 350 |  | 492 |  |  | 842
D-HPP633 | 1140 | 5027 | 1021 |  | 186 | 7374
D-HPP305
D-HLX522 | 859 | 971 | 667 | 1025 |  | 3522
D-HTG238 |  | 949 | 514 | 790 |  | 2253
D-HLX512 | 648 | 1155 | 778 |  |  | 2581
D-HPP630 | 335 | 558 | 815 |  |  | 1708
D-HPP303 | 500 | 559 | 1506 | 548 | 651 | 3764
D-HPP310 | 620 |  |  |  |  | 620
FB-HWP476 | 1115 | 891 | 1345 | 1328 |  | 4679
D-HPP625 | 876 | 890 | 749 | 346 |  | 2861
D-HPP615 |  |  | 520 | 1599 | 1500 | 3619
D-HPP620 |  |  |  | 575 | 2236 | 2811
D-HPP307 |  |  |  |  | 310 | 310
D-HLX513 |  |  |  | 1436 | 877 | 2313
FB-HTG204 |  |  |  | 492 |  | 492
FB-HTG290 |  |  |  | 343 |  | 343
Grand Total | 15233 | 16303 | 18811 | 10947 | 6360 | 67654
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | Grand Total
D-HNP108
D-HLX507
D-HPP613 |  | 395 |  |  |  | 395
D-HTG233 | 123 |  |  |  |  | 123
D-HTG228 | 1642 | 1664 | 439 |  |  | 3745
D-HPP301 |  | 121 | 235 |  |  | 356
D-HTG241 |  |  |  | 18 |  | 18
D-HTG201 |  |  | 339 |  |  | 339
D-HBR256 | 344 | 7 | 28 | 42 |  | 421
D-HPP611
D-HPP638
D-HPP311
D-HPP629 |  |  | 1646 | 852 |  | 2498
D-HPP318
D-HTG229 |  |  | 544 |  |  | 544
D-HPP619 | 55 |  |  |  |  | 55
D-HPP307 | 215 | 283 | 144 |  |  | 642
D-HPP621 |  | 1028 |  |  |  | 1028
D-HPP627 |  |  |  | 1237 |  | 1237
D-HPP631 |  | 251 |  |  |  | 251
D-HPP305 | 971 |  | 501 | 492 |  | 1964
D-HLX522 | 361 |  |  |  |  | 361
D-HTG238 |  |  | 867 | 206 |  | 1073
D-HPP303 |  | 767 | 108 |  |  | 875
D-HPP310 | 1299 | 918 | 925 |  |  | 3142
FB-HWP476 |  |  |  | 300 |  | 300
D-HPP625 | 1537 | 1097 | 1846 |  |  | 4480
D-HPP615 | 1695 | 1620 | 1295 | 905 |  | 5515
D-HPP620 | 905 | 3166 | 539 |  |  | 4610
D-HLX513 | 1027 |  |  |  |  | 1027
FB-HTG204 |  | 557 |  |  |  | 557
D-HLX520 |  | 983 |  | 841 |  | 1824
FB-HTG290 | 594 |  |  |  |  | 594
FB-HWP976 |  | 960 | 665 |  |  | 1625
D-HLX521 |  | 1039 | 754 | 1000 |  | 2793
D-HBR257 |  | 452 | 635 | 741 |  | 1828
Grand Total | 10768 | 15308 | 11510 | 6634 |  | 44220
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | Grand Total
FB-HOE401-V3
D-HLX501
D-HPP613 |  | 37 | 1440 |  |  | 1477
D-HPP607 |  |  | 424 |  |  | 424
D-HTG228 | 487 |  |  |  |  | 487
D-HBR256 | 53 |  |  |  |  | 53
D-HPP638 |  | 340 | 385 | 255 | 180 | 1160
D-HPP629 |  |  | 887 |  |  | 887
D-HPP318
D-HTG229 | 845 | 206 |  |  |  | 1051
D-HPP307 | 86 | 322 | 222 | 323 | 340 | 1293
D-HPP627 | 235 |  |  |  |  | 235
D-HPP631 |  |  |  | 525 | 4486 | 5011
D-HPP305 | 646 | 340 |  |  |  | 986
D-HLX522
D-HTG238 | 509 | 254 | 187 |  | 336 | 1286
D-HPP303 |  |  | 930 |  |  | 930
D-HPP310 | 936 | 668 | 240 |  |  | 1844
FB-HWP476 | 1036 | 350 |  |  |  | 1386
D-HLX520 | 1027 |  |  |  | 1007 | 2034
FB-HTG290 | 698 | 235 | 351 |  |  | 1284
D-HLX521 | 973 |  | 87 |  |  | 1060
D-HBR257 |  |  | 1774 | 557 | 678 | 3009
D-HPP616 | 1613 | 1647 | 1647 | 495 |  | 5402
D-HPP639 | 1050 | 770 | 839 | 874 | 781 | 4314
D-HOE503 |  | 449 | 665 | 782 |  | 1896
FB-HLX375 |  | 721 | 1146 | 1085 |  | 2952
BHCD-FPW-03-E |  |  | 998 |  |  | 998
FB-HTG288 |  | 352 |  |  |  | 352
FB-HTG204 |  |  |  | 934 | 183 | 1117
D-HPP628 |  |  |  | 1169 | 1408 | 2577
FB-HTG289 |  |  |  | 929 | 131 | 1060
D-HPP626 |  |  |  |  | 439 | 439
Grand Total | 10194 | 6691 | 12222 | 7928 | 9969 | 47004
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | Grand Total
D-HPP607 |  |  |  |  | 122 | 122
D-HLX511 | 993 | 1035 | 1130 | 653 |  | 3811
D-HTG241
D-HBR256 |  |  | 32 |  |  | 32
D-HPP638 |  |  |  |  | 110 | 110
D-HTG229 |  |  |  | 1084 |  | 1084
D-HPP307 | 225 | 660 | 38 |  |  | 923
D-HPP627 | 694 |  |  |  |  | 694
D-HPP631 | 259 |  |  |  |  | 259
D-HPP305 |  | 224 |  |  |  | 224
D-HTG238 |  |  |  | 400 |  | 400
D-HPP630
D-HPP303 | 722 | 298 | 232 |  |  | 1252
FB-HWP476 | 230 |  |  |  |  | 230
D-HBR257 | 784 | 756 | 926 |  |  | 2466
D-HPP616
D-HPP639 | 2842 | 570 |  |  |  | 3412
D-HOE503 | 685 | 72 |  |  |  | 757
FB-HLX375
BHCD-FPW-03-E |  |  | 756 |  |  | 756
FB-HTG288 |  | 385 |  |  |  | 385
FB-HTG204
D-HPP628 | 2014 | 1701 | 1696 |  |  | 5411
FB-HTG289 | 1036 |  |  |  |  | 1036
D-HPP626 | 2286 | 2056 | 1203 |  |  | 5545
D-HPP634
D-HPP635 |  | 1037 | 1272 |  | 912 | 3221
Colonial Pointe | 1066 | 431 | 676 | 494 |  | 2667
D-HPP637 |  | 269 |  | 188 | 186 | 643
D-HLX509 |  | 1541 | 948 | 540 |  | 3029
D-HOE117 |  |  | 238 |  |  | 238
D-HPP636 |  |  |  | 1644 | 1233 | 2877
D-HLX506 |  |  |  | 427 |  | 427
Grand Total | 13836 | 11035 | 9147 | 5430 | 2563 | 42011
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | Grand Total
D-HLX405 |  |  | 21 |  |  | 21
D-HPP607
D-HPP617
D-HPP638
D-HPP311 |  |  |  | 150 |  | 150
D-HPP305
D-HPP630 |  | 1158 | 1297 | 1849 | 1158 | 5462
D-HPP303 |  |  |  | 410 | 202 | 612
D-HPP310 | 188 | 115 |  | 35 |  | 338
FB-HTG204 |  | 478 |  |  |  | 478
D-HBR257 | 812 |  | 242 | 26 |  | 1080
BHCD-FPW-03-E |  |  |  | 2283 | 782 | 3065
FB-HTG288
D-HPP634 |  | 1641 | 1662 | 661 | 717 | 4681
D-HPP635 | 3372 | 454 |  |  |  | 3826
Colonial Pointe |  | 721 | 1126 | 556 | 262 | 2665
D-HPP637 |  |  |  | 428 | 141 | 569
D-HPP636 | 1458 | 1610 | 1420 |  |  | 4488
D-HLX506 | 2233 | 921 | 397 | 467 | 111 | 4129
FB-HTG292 |  | 745 | 358 | 10 |  | 1113
D-HSF308 | 162 | 858 | 1126 | 1017 |  | 3163
D-HLX508 |  | 979 | 395 | 1344 | 679 | 3397
FB-HTG289 |  |  | 325 |  |  | 325
D-HBR258 |  |  |  | 460 | 629 | 1089
D-HTG218 |  |  |  | 1144 | 508 | 1652
D-HLX503 |  |  |  |  | 803 | 803
D-HSF308 |  |  |  |  | 377 | 377
Grand Total | 8225 | 9680 | 8369 | 10840 | 6369 | 43483
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | Grand Total
D-HTG208 |  |  | 436 |  |  | 436
D-HPP614 |  | 2264 |  |  |  | 2264
D-HTG228
D-HPP617
D-HLX516 | 120 |  |  |  |  | 120
D-HTG201
D-HPP638 |  | 215 | 105 | 445 | 445 | 1210
D-HTG229
D-HPP305 | 945 | 64 | 811 | 449 | 295 | 2564
D-HTG238 |  | 232 |  |  |  | 232
D-HPP630 | 1171 |  |  |  |  | 1171
D-HPP303 |  | 65 | 160 |  |  | 225
D-HPP310
D-HLX513 |  |  |  |  | 24 | 24
D-HBR257 |  | 10 | 10 |  |  | 20
D-HPP639 |  | 861 | 334 |  |  | 1195
FB-HTG288 |  | 719 | 534 | 786 |  | 2039
D-HPP634 | 202 |  |  |  |  | 202
D-HPP635
D-HPP637 | 203 | 179 | 272 | 362 | 297 | 1313
FB-HTG292 |  | 200 | 64 |  |  | 264
D-HBR258 | 375 | 538 | 621 | 550 | 893 | 2977
D-HTG218 | 763 | 214 | 324 | 88 |  | 1389
D-HLX503 | 706 | 1159 | 1155 | 333 |  | 3353
D-HSF308 | 1083 | 539 | 700 | 202 | 202 | 2726
D-HLX504 |  | 1635 | 694 | 1685 | 724 | 4738
FB-HTG238 | 2099 | 2327 |  |  |  | 4426
SFU-LEE-6
D-HTG215 |  | 257 |  |  | 1036 | 1293
D-HTG230 |  | 484 | 955 |  |  | 1439
Grand Total | 7667 | 11962 | 7175 | 4900 | 3916 | 35620
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | Grand Total
D-HPP613
D-HPP614
D-HLX511
D-HTG201 |  |  |  | 473 |  | 473
D-HPP638 |  |  | 330 | 398 |  | 728
D-HPP627 |  |  |  |  | 1667 | 1667
D-HPP305
D-HPP303 | 58 |  |  | 308 |  | 366
D-HPP310
D-HPP639
FB-HTG288 | 537 | 277 |  | 526 | 461 | 1801
D-HPP634 |  |  | 3503 |  |  | 3503
D-HPP635
D-HPP637 |  | 426 |  | 233 |  | 659
D-HLX506
FB-HTG292 |  | 269 |  |  |  | 269
D-HLX508
D-HLX503 |  |  |  | 247 |  | 247
D-HSF308 | 54 | 3 |  |  |  | 57
D-HLX504 |  |  |  | 126 |  | 126
D-HTG215 | 1108 | 1065 |  |  | 287 | 2460
D-HTG230 |  |  |  | 718 | 645 | 1363
D-HPP314 | 1053 | 1808 |  | 844 | 944 | 4649
D-HLX505 | 1304 | 1495 |  | 1133 | 1375 | 5307
FB-HPP314 |  |  | 58 |  |  | 58
FB-HLX175 |  |  | 217 | 280 |  | 497
D-HTG217
D-HPP608 |  |  |  |  | 405 | 405
D-HTG216 |  |  |  |  | 952 | 952
FB-HLXC512 |  |  |  |  | 745 | 745
Grand Total | 4114 | 5343 | 4108 | 5286 | 7481 | 26332
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | Grand Total
FB-HBR252 |  |  |  | 292 |  | 292
D-HPP614
D-HPP638 | 272 | 247 |  |  |  | 519
D-HPP311
D-HPP629 | 281 |  |  |  |  | 281
D-HPP627 | 155 | 1156 | 864 |  |  | 2175
D-HPP631 |  |  | 448 | 907 | 369 | 1724
D-HPP310
D-HPP639
FB-HTG288 | 599 | 414 |  |  | 147 | 1160
D-HPP635 |  |  |  | 1495 |  | 1495
D-HPP637 | 92 | 295 | 354 |  |  | 741
D-HPP636 |  |  |  |  | 1797 | 1797
D-HBR258 |  | 447 | 949 |  | 36 | 1432
D-HTG218 |  | 793 |  |  |  | 793
D-HLX504
D-HTG215 | 586 | 195 |  |  |  | 781
D-HTG230 | 244 |  | 360 | 185 |  | 789
D-HPP314 | 1549 | 973 | 883 |  |  | 3405
D-HLX505
FB-HLX175 | 184 | 230 | 260 |  | 691 | 1365
D-HTG217 |  | 2263 | 1113 |  |  | 3376
D-HPP608 | 600 | 500 | 606 |  |  | 1706
D-HTG216 | 1289 | 1995 | 2319 |  |  | 5603
D-HLX502 | 557 | 733 | 1379 | 773 |  | 3442
D-HLC518 |  | 714 | 1174 |  |  | 1888
D-HLX510 |  | 1080 | 1077 | 1445 | 877 | 4479
D-HTG212 |  | 936 | 1582 | 1036 |  | 3554
D-HTG231 |  |  | 180 |  |  | 180
FB-HPP631 |  |  |  | 1705 | 973 | 2678
D-HLC512 |  |  |  | 1243 |  | 1243
D-HLC513 |  |  |  | 566 | 452 | 1018
D-HTG213 |  |  |  | 926 | 457 | 1383
D-HSF322 |  |  |  | 753 | 344 | 1097
D-HBR259 |  |  |  |  | 1273 | 1273
Grand Total | 6408 | 12971 | 13548 | 11326 | 7416 | 51669
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-21 | 2026-08-19 | Grand Total
D-HPP638 | 189 | 309 | 757 |  | 558 | 1813
D-HPP311 |  |  | 50 |  |  | 50
D-HPP627 | 669 |  |  |  |  | 669
D-HLX520 |  | 108 |  |  |  | 108
D-HPP634
D-HPP637 | 294 | 174 | 501 |  | 334 | 1303
D-HBR258 |  | 66 |  |  |  | 66
D-HTG230 | 361 | 846 | 721 | 696 | 479 | 3103
D-HPP314
D-HLX505 |  |  |  | 114 |  | 114
FB-HLX175 | 954 |  | 240 |  |  | 1194
D-HPP608 | 220 | 289 |  |  | 474 | 983
D-HLX502 |  |  | 81 |  |  | 81
D-HLC518 | 358 | 198 |  |  |  | 556
D-HLX510 |  |  |  | 111 |  | 111
D-HTG212 | 914 | 213 |  |  |  | 1127
D-HTG231 | 1039 |  |  |  |  | 1039
D-HLC512 |  |  | 1288 | 1558 | 1512 | 4358
D-HLC513 |  |  | 3917 | 520 |  | 4437
D-HTG213 | 969 | 845 |  |  | 962 | 2776
D-HSF322 | 641 | 719 | 453 | 1519 | 1475 | 4807
D-HBR259 | 896 | 830 | 564 | 764 | 911 | 3965
D-HLC517 | 725 | 397 |  |  |  | 1122
FB-HLC512 | 1608 |  | 757 | 280 | 934 | 3579
D-HLX408 | 1044 | 1374 | 999 | 400 | 1098 | 4915
FB-HOE401-V6 | 200 |  |  |  |  | 200
D-HPW348 | 410 | 347 | 125 | 150 | 650 | 1682
BHUD-FOE-401-W |  | 410 |  |  | 996 | 1406
FB-HOE401-V4 |  | 190 |  |  |  | 190
FB-HPW331 |  | 1554 |  |  | 227 | 1781
D-HTG210 |  |  | 1744 | 954 | 691 | 3389
FB-HTG279 |  |  |  |  | 350 | 350
BHCD-FPW-03-E |  |  | 1218 |  |  | 1218
BHT-FSE-01
Grand Total | 11491 | 8869 | 13415 | 7066 | 11651 | 52492
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | Grand Total
BHCD-FPW-03-W |  | 150 |  |  |  | 150
BHU-FLX-01-W
FB-HSF304 |  |  |  |  | 1743 | 1743
D-HTG233 |  |  |  |  | 288 | 288
D-HPP638
D-HPP311
D-HTG229 |  |  |  |  | 288 | 288
D-HPP631 |  |  | 135 | 206 |  | 341
D-HTG238 |  |  |  |  | 89 | 89
D-HPP303 |  | 119 | 100 |  |  | 219
FB-HWP476 |  |  |  | 550 |  | 550
D-HPP637 | 570 |  | 192 | 240 |  | 1002
D-HBR258 | 38 | 24 |  |  | 24 | 86
D-HTG230 |  |  | 60 |  |  | 60
D-HPP314
FB-HLX175
D-HTG217 | 1428 | 1277 |  |  |  | 2705
D-HPP608 |  |  | 292 | 288 |  | 580
D-HTG216 |  |  |  | 43 |  | 43
D-HTG231 |  |  | 326 | 1051 |  | 1377
FB-HPP631 |  |  | 463 |  |  | 463
D-HLC512 | 530 | 249 |  |  |  | 779
D-HSF322 | 837 |  |  |  |  | 837
D-HBR259 | 102 |  | 1144 |  |  | 1246
D-HLX408 | 741 | 63 |  |  |  | 804
D-HPW348 | 505 | 254 | 581 | 360 | 153 | 1853
BHUD-FOE-401-W
D-HTG210 | 1269 | 319 |  |  |  | 1588
FB-HTG279 |  |  | 456 |  |  | 456
D-HLC506 | 616 |  | 610 |  |  | 1226
BHC-FSW-04-E |  |  | 800 | 185 | 375 | 1360
D-HLC511 | 319 |  | 150 |  |  | 469
D-HAL114 |  | 1229 | 1266 | 704 |  | 3199
D-HLC519
D-HPW330 |  |  |  | 1312 |  | 1312
D-HSW405 |  |  |  | 185 |  | 185
D-HTG305 |  |  |  |  | 652 | 652
D-HBR260 |  |  |  |  | 320 | 320
Grand Total | 6955 | 3684 | 6575 | 5124 | 3932 | 26270
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | Grand Total
D-HBR256
D-HPP638
D-HTG238
D-HPP637
D-HTG230
D-HPP314
FB-HPP314
D-HPP608 | 215 | 190 | 367 | 153 |  | 925
D-HTG216
D-HTG212 |  | 9 |  |  |  | 9
D-HTG231 |  | 746 | 1093 | 751 | 255 | 2845
FB-HPP631 |  |  |  |  | 1010 | 1010
D-HLC513 |  | 250 | 468 |  |  | 718
D-HBR259 | 25 | 15 | 20 |  | 5 | 65
D-HLX408
D-HPW348 | 326 | 565 | 503 | 115 | 106 | 1615
D-HTG210 |  |  | 776 |  |  | 776
BHCD-FPW-03-E |  |  | 1550 | 693 |  | 2243
D-HLC506 | 1512 | 1497 | 1006 |  |  | 4015
BHC-FSW-04-E | 635 | 431 | 350 | 510 |  | 1926
D-HLC511 |  |  | 165 |  |  | 165
D-HLC519 | 805 | 1654 | 1252 | 1003 | 617 | 5331
D-HPW330 |  |  |  | 483 | 639 | 1122
D-HSW405 | 635 | 246 |  | 175 |  | 1056
D-HTG305 |  | 939 | 883 | 846 |  | 2668
D-HBR260 | 840 | 646 | 851 | 499 | 747 | 3583
D-HAL115 | 1173 | 1126 |  | 833 | 60 | 3192
FB-HSW419 |  | 185 | 350 | 335 |  | 870
D-HPW349
D-HAL116 |  |  |  | 306 | 724 | 1030
Grand Total | 6166 | 8499 | 9634 | 6702 | 4163 | 35164
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | Grand Total
(blank)
FB-HTG290
D-HTG218
D-HLX503 |  | 72 |  |  |  | 72
FB-HTG238 |  |  |  | 137 |  | 137
D-HTG215
D-HPP608 |  |  | 225 |  | 504 | 729
D-HTG212
FB-HPP631
D-HBR259 |  |  |  | 45 |  | 45
FB-HLC512 |  |  | 1375 |  |  | 1375
D-HPW348 |  | 390 |  |  |  | 390
FB-HTG279 |  | 146 |  |  |  | 146
BHT-FSE-01 |  |  |  | 430 | 755 | 1185
BHC-FSW-04-E |  |  | 530 |  |  | 530
D-HLC511 |  | 147 |  | 408 |  | 555
D-HLC519 |  |  |  | 1649 |  | 1649
D-HTG305
D-HBR260 |  | 615 | 1037 | 345 |  | 1997
FB-HSW419 |  |  | 530 |  |  | 530
D-HAL116 |  | 933 | 1282 | 123 |  | 2338
D-HLC516 |  | 227 | 1010 | 1086 | 484 | 2807
North Oaks Estates
D-HSW419 |  |  | 530 | 430 | 755 | 1715
FB-HLC519 |  | 1264 | 775 |  |  | 2039
D-HPW361 |  |  | 379 | 168 |  | 547
D-HLC515 |  |  |  | 307 | 605 | 912
North Oaks
FB-HOE401-V5 |  |  |  | 530 | 581 | 1111
Plantation Bay |  |  |  | 362 |  | 362
D-HPW346 |  |  |  | 481 | 322 | 803
D-HLC507 |  |  |  |  | 410 | 410
D-HBR261 |  |  |  |  | 806 | 806
Grand Total |  | 3794 | 7673 | 6501 | 5222 | 23190
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | Grand Total
FB-HTG290 |  |  | 146 |  |  | 146
FB-HTG238 |  | 857 | 337 |  |  | 1194
D-HTG230 |  | 661 |  |  |  | 661
D-HPP608 | 469 | 331 | 845 |  |  | 1645
D-HTG231 |  | 1387 |  |  |  | 1387
FB-HPP631
D-HBR259 | 20 |  | 20 |  |  | 40
D-HLC517
FB-HLC512
D-HPW348 | 78 |  |  |  |  | 78
FB-HOE401-V4 |  |  |  |  | 25 | 25
BHT-FSE-01 | 400 | 769 | 400 |  |  | 1569
BHC-FSW-04-E
D-HLC511 | 242 |  | 205 | 200 | 110 | 757
D-HPW330
D-HTG305 |  |  | 936 | 124 | 201 | 1261
D-HAL116 | 249 |  | 478 |  | 72 | 799
D-HLC516 | 1243 |  |  | 276 |  | 1519
D-HSW419 | 400 | 769 | 400 |  |  | 1569
D-HPW361 |  |  |  | 235 | 515 | 750
D-HLC515 |  | 727 | 895 |  |  | 1622
North Oaks |  | 988 |  |  |  | 988
FB-HOE401-V5 | 243 |  |  |  |  | 243
Plantation Bay
D-HPW346 |  | 751 |  |  |  | 751
D-HLC507 | 324 | 454 | 891 | 1451 | 498 | 3618
D-HBR261 |  |  | 1227 | 1139 | 995 | 3361
North Okas | 946 |  |  |  |  | 946
D-HPW346 | 712 |  |  |  |  | 712
FB-HPP612 |  | 1045 | 1311 | 1408 | 1426 | 5190
D-HLC508 |  |  | 423 |  |  | 423
SFU-MNTE-3 |  |  | 1144 | 1324 | 840 | 3308
D-HAL113 |  | 716 |  | 959 | 815 | 2490
SFU-MNTE-4
D-HTG307 |  |  | 86 | 2001 | 379 | 2466
D-HPP854 |  |  |  | 2096 | 372 | 2468
D-HLC510 |  |  |  |  | 170 | 170
D-DLC516 |  |  |  |  | 465 | 465
D-HPW328
D-HPW329
Grand Total | 5326 | 9455 | 9744 | 11213 | 6883 | 42621
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | Grand Total
BHCD-FPW-03-E |  | 183 |  |  |  | 183
D-HPP626 |  |  |  |  | 2339 | 2339
D-HPP637 |  |  |  |  | 124 | 124
D-HPP608 |  | 147 |  | 165 | 100 | 412
D-HLC518 |  |  |  | 293 | 1208 | 1501
D-HLC512 |  |  |  |  | 660 | 660
D-HTG213 |  | 224 | 369 |  |  | 593
D-HBR259
D-HLC517 | 1157 | 1729 | 369 | 1679 | 77 | 5011
D-HPW348 | 564 | 165 |  |  |  | 729
BHT-FSE-01 | 647 |  |  |  |  | 647
D-HLC511 | 580 | 739 | 968 | 860 | 300 | 3447
D-HAL114
D-HPW330 |  |  | 521 |  |  | 521
D-HBR260 |  | 27 |  | 19 | 14 | 60
D-HAL115
FB-HSW419 |  | 800 | 1134 | 349 | 1212 | 3495
D-HLC516 | 461 | 380 | 441 | 445 | 487 | 2214
D-HSW419 | 647 |  |  |  |  | 647
D-HLC515 | 553 | 303 | 661 | 204 |  | 1721
D-HPW346 |  |  | 3368 | 843 | 232 | 4443
D-HLC507 |  | 653 | 486 |  |  | 1139
D-HBR261 | 654 | 760 |  | 809 | 712 | 2935
FB-HPP612
D-HLC508 | 1505 | 1208 | 1392 |  | 625 | 4730
SFU-MNTE-3 | 1506 | 690 | 1248 |  | 141 | 3585
D-HAL113 | 381 |  |  | 495 |  | 876
SFU-MNTE-4 | 739 | 223 | 303 | 2191 |  | 3456
D-HTG307 | 764 |  |  |  |  | 764
D-HPP854 | 452 | 432 | 529 | 340 |  | 1753
D-HLC514 |  | 1300 | 1847 | 1371 | 1776 | 6294
D-HPP858 | 1349 | 1694 | 1580 |  | 948 | 5571
D-HSF402
D-HSF419 | 1933 | 2929 |  |  |  | 4862
D-HHP883 |  | 2088 |  |  |  | 2088
D-HSW403 |  | 716 | 1134 |  |  | 1850
D-HSW404 |  | 48 |  |  |  | 48
D-HSF420 |  |  | 2275 |  |  | 2275
FB-HPP375 |  |  |  | 387 |  | 387
D-HSF401 |  |  |  |  | 149 | 149
D-HSF402 |  |  |  | 1971 |  | 1971
D-HSW402 |  |  |  |  | 1212 | 1212
Grand Total | 13892 | 17438 | 18625 | 12421 | 12316 | 74692
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | Grand Total
BHCD-FPW-03-E |  |  |  | 925 |  | 925
D-HPP637 |  |  |  | 165 |  | 165
FB-HLX175
D-HPP608 | 288 |  |  |  |  | 288
D-HLC518 | 1251 |  |  | 248 |  | 1499
D-HTG231 |  |  |  |  | 95 | 95
D-HLC517
FB-HLC512
FB-HOE401-V6
BHC-FSW-04-E |  |  |  |  | 100 | 100
D-HLC511 | 542 |  |  |  |  | 542
D-HPW330
D-HSW405 |  | 549 | 250 |  |  | 799
D-HBR260 | 9 | 6 | 21 |  |  | 36
FB-HSW419 | 554 | 892 | 320 | 126 |  | 1892
D-HLC516 |  |  | 680 | 218 | 108 | 1006
D-HLC515 |  | 512 | 605 | 388 | 280 | 1785
D-HPW346 |  |  |  | 234 | 269 | 503
D-HLC507 | 203 |  | 643 |  |  | 846
D-HBR261 | 351 | 871 | 366 | 10 | 20 | 1618
FB-HPP612
D-HLC508 |  |  |  | 76 |  | 76
D-HAL113 | 126 |  |  |  |  | 126
SFU-MNTE-4 | 1919 | 1264 | 722 | 596 |  | 4501
D-HPP854 | 1327 | 839 |  |  |  | 2166
D-HLC510 |  | 534 | 310 | 275 |  | 1119
D-HLC514 |  |  | 583 |  |  | 583
D-HPP858 | 55 |  |  |  |  | 55
D-HSF402 | 314 |  |  |  |  | 314
D-HSW404 |  | 387 | 70 |  |  | 457
FB-HPP375 | 1570 |  |  |  |  | 1570
D-HSF401 |  | 1013 |  | 441 |  | 1454
D-HSF402 |  |  |  | 1100 | 748 | 1848
D-HSW402 | 125 |  |  | 126 |  | 251
D-HPP839 |  | 1757 | 1336 |  |  | 3093
FB-HPP879 | 1527 | 1631 | 1421 | 1324 |  | 5903
D-HLC539 |  | 1996 | 1734 | 1741 |  | 5471
FB-HPP854
BHT-FSW-04-E |  | 199 |  |  |  | 199
D-HPW361 |  |  |  |  | 185 | 185
D-HBR262 |  |  |  | 742 | 652 | 1394
D-HTG401
Grand Total | 10161 | 12450 | 9061 | 8735 | 2457 | 42864
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | Grand Total
D-HTG208 |  |  |  |  | 504 | 504
BHCD-FPW-03-E |  |  |  |  | 844 | 844
D-HPP637 | 400 |  |  |  | 285 | 685
D-HTG215 |  |  |  |  | 62 | 62
D-HLC518
D-HLC517 |  |  |  | 36 |  | 36
FB-HLC512
BHC-FSW-04-E | 100 | 204 |  |  |  | 304
D-HBR260
FB-HSW419 | 282 | 365 |  |  |  | 647
D-HLC516 | 39 |  |  |  |  | 39
FB-HLC519
D-HLC507 |  |  |  | 749 |  | 749
D-HBR261 | 70 | 30 |  | 74 |  | 174
FB-HPP612
D-HLC508
D-HAL113
SFU-MNTE-4 | 608 |  |  |  | 63 | 671
D-HPP854 |  |  |  |  | 278 | 278
D-HLC510 | 525 | 488 |  | 493 | 725 | 2231
D-HLC514 | 71 |  |  |  |  | 71
D-HSF419 |  | 78 |  |  |  | 78
D-HSF402 |  | 1602 | 190 |  |  | 1792
D-HSW402 | 282 | 365 |  | 456 | 374 | 1477
D-HPP839 | 1779 | 324 |  |  |  | 2103
D-HLC539 | 1508 |  |  |  |  | 1508
FB-HPP854 |  |  |  |  | 840 | 840
D-HPW361 | 182 | 483 | 271 | 360 | 282 | 1578
D-HBR262 | 571 | 514 |  | 1291 | 969 | 3345
D-HLC538
FB-HLC538 |  | 1739 |  |  |  | 1739
D-HLX101 | 428 | 1278 |  |  |  | 1706
D-HPW350 | 486 | 670 | 731 | 843 |  | 2730
D-HLC522
D-HSF420 |  |  | 904 | 868 | 315 | 2087
Grand Total | 7331 | 8140 | 2096 | 5170 | 5541 | 28278
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2026-10-12 | Grand Total
(blank)
Grand Total

## Daily Production_RAW DATA
Project | CONTRACTOR | Schedule Date | UG FOOTAGE COMPLETED | Fiber Footage | COMMENTS | Production Month
D-HDH31 | Reycamp | 2025-02-10 | 2677 |  |  | February
D-HDH34 | Lightspeed | 2025-02-10 |  |  | 4 Toby Boxes | February
D-HDH04 | J Garcia Underground | 2025-02-11 | 202 |  |  | February
D-HDH34 | Lightspeed | 2025-02-11 | 241 |  |  | February
FB-HDH02A | Multiple | 2025-02-11 | 1990 |  |  | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-11 | 534 |  |  | February
D-HDH34 | Lightspeed | 2025-02-12 | 366 |  |  | February
FB-HDH02A | H&H Underground-Lightspeed | 2025-02-12 | 1045 |  |  | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-12 | 460 |  |  | February
D-H0223D | Brothers | 2025-02-12 | 1426 |  |  | February
D-HDH34 | Lightspeed | 2025-02-13 | 202 |  |  | February
D-HWP415 | Lightspeed | 2025-02-13 | 106 |  |  | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-13 | 886 |  |  | February
D-H0223D | Brothers | 2025-02-13 | 1190 |  |  | February
D-HDH34 | Lightspeed | 2025-02-14 | 120 |  |  | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-14 | 202 |  |  | February
D-H0223D | Brothers | 2025-02-14 | 23 |  |  | February
D-H0223C | Longo Underground | 2025-02-14 | 1049 |  |  | February
D-HDH34 | Lightspeed | 2025-02-17 | 283 |  |  | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-17 | 383 |  |  | February
D-HDH66 | Bartlett Fiber | 2025-02-18 |  |  | 30-Toby Boxes | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-18 | 1017 |  |  | February
D-HDH76 | J Garcia Underground | 2025-02-18 | 300 |  |  | February
D-HDH45 | Reycamp | 2025-02-18 | 1240 |  |  | February
D-HWP713 | Brothers | 2025-02-18 | 1050 |  | 12 Toby Boxes/FDH | February
D-HDH04 | J Garcia Underground | 2025-02-19 |  |  | 7 Toby Boxes | February
D-HDH31 | Reycamp | 2025-02-19 | 1319 |  |  | February
D-HDH34 | Lightspeed | 2025-02-19 | 732 |  |  | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-19 | 242 |  |  | February
D-HDH76 | J Garcia Underground | 2025-02-19 | 696 |  |  | February
D-HDH45 | Reycamp | 2025-02-19 | 1978 |  | 10 Toby Boxes | February
D-HDH73 | Power Connect | 2025-02-19 | 1606 |  |  | February
D-HDH04 | J Garcia Underground | 2025-02-20 | 23 |  | 9 Toby Boxes | February
D-HDH34 | Lightspeed | 2025-02-20 | 309 |  | 2 Toby Boxes | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-20 | 424 |  |  | February
D-H0223C | Longo Underground | 2025-02-20 | 547 |  | 6 Toby Boxes | February
D-HDH76 | J Garcia Underground | 2025-02-20 | 227 |  |  | February
D-HDH45 | Reycamp | 2025-02-20 | 851 |  | 20 Toby Boxes | February
D-HDH73 | Power Connect | 2025-02-20 | 1334 |  |  | February
D-H0222D | Bartlett Fiber | 2025-02-20 | 1400 |  |  | February
D-H0223A | Bartlett Fiber | 2025-02-20 | 1806 |  |  | February
D-HWP102 | Power Connect | 2025-02-20 | 47 |  |  | February
D-HDH04 | J Garcia Underground | 2025-02-21 | 24 |  | 5 Toby Boxes | February
D-HDH84 | Reycamp | 2025-02-21 |  |  | Sponge Testing | February
D-HWP415 | Lightspeed | 2025-02-21 | 21 |  | 6 Toby Boxes | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-21 | 19 |  | 8 Toby Boxes | February
D-H0223D | Brothers | 2025-02-21 | 823 |  | 6 Toby Boxes | February
D-H0223C | Longo Underground | 2025-02-21 | 792 |  | 6 Toby Boxes | February
D-HDH76 | J Garcia Underground | 2025-02-21 | 333 |  |  | February
D-H0223A | Bartlett Fiber | 2025-02-21 | 345 |  |  | February
D-HWP102 | Power Connect | 2025-02-21 | 1494 |  |  | February
D-H0222B | Brothers | 2025-02-21 | 1095 |  | 6 Toby Boxes | February
D-H0222D | Bartlett Fiber | 2025-02-21 | 1462 |  | 4 Toby Boxes | February
D-H0222C | Power Connect | 2025-02-21 | 2989 |  |  | February
D-HDH34 | Lightspeed | 2025-02-24 | 73 |  |  | February
D-HWP102 | Power Connect | 2025-02-24 | 2087 |  | 29 Toby Boxes | February
D-HDH71 | HDD Underground | 2025-02-24 | 555 |  |  | February
D-HDH04 | J Garcia Underground | 2025-02-25 |  |  | 1 Toby Boxes | February
D-HDH31 | Reycamp | 2025-02-25 |  |  |  | February
D-HDH66 | Bartlett Fiber | 2025-02-25 |  |  |  | February
D-HDH84 | Reycamp | 2025-02-25 |  |  |  | February
FB-HDH02A | Lightspeed | 2025-02-25 | 74 |  |  | February
Golden Wings MDU | SB Martinez | 2025-02-25 |  |  |  | February
D-HWP412 | SB Martinez | 2025-02-25 |  |  |  | February
D-HWP415 | Lightspeed | 2025-02-25 |  |  |  | February
D-HWP425 | Brothers | 2025-02-25 |  |  |  | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-25 | 236 |  | 11 Toby Boxes | February
D-HWP441 | Brothers | 2025-02-25 |  |  |  | February
FB-HWP101 | Power Connect | 2025-02-25 | 214 |  |  | February
D-H0223D | Brothers | 2025-02-25 |  |  |  | February
D-H0223C | Longo Underground | 2025-02-25 | 1277 |  | 12 Toby Boxes | February
D-HDH76 | J Garcia Underground | 2025-02-25 | 800 |  | 2 Toby Boxes | February
D-HDH45 | Reycamp | 2025-02-25 |  |  |  | February
D-HWP713 | Brothers | 2025-02-25 |  |  |  | February
D-HDH73 | Power Connect | 2025-02-25 |  |  |  | February
D-H0222D | Bartlett Fiber | 2025-02-25 |  |  |  | February
D-H0223A | Bartlett Fiber | 2025-02-25 |  |  |  | February
D-H0222B | Brothers | 2025-02-25 | 860 |  |  | February
D-H0222C | Power Connect | 2025-02-25 | 967 |  |  | February
D-H0222A | Key Underground | 2025-02-25 | 956 |  |  | February
FB-HDH01 | J Garcia Underground | 2025-02-25 |  |  | 2 splice locations | February
D-HDH04 | J Garcia Underground | 2025-02-26 |  |  |  | February
D-HDH31 | Reycamp | 2025-02-26 |  |  |  | February
D-HDH34 | Lightspeed | 2025-02-26 | 25 |  |  | February
D-HDH66 | Bartlett Fiber | 2025-02-26 |  |  |  | February
D-HDH84 | Reycamp | 2025-02-26 |  |  |  | February
FB-HDH02A | Lightspeed | 2025-02-26 | 671 |  |  | February
Golden Wings MDU | SB Martinez | 2025-02-26 |  |  |  | February
D-HWP412 | SB Martinez | 2025-02-26 |  |  |  | February
D-HWP415 | Lightspeed | 2025-02-26 |  |  |  | February
D-HWP425 | Brothers | 2025-02-26 |  |  |  | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-26 |  |  | 1 Toby Box | February
D-HWP441 | Brothers | 2025-02-26 |  |  | 1 Toby Box | February
FB-HWP101 | Power Connect | 2025-02-26 |  |  |  | February
D-H0223D | Brothers | 2025-02-26 |  |  |  | February
D-H0223C | Longo Underground | 2025-02-26 | 1721 |  | 13 Toby Boxes | February
D-HDH76 | J Garcia Underground | 2025-02-26 | 208 |  |  | February
D-HDH45 | Reycamp | 2025-02-26 |  |  |  | February
D-HWP713 | Brothers | 2025-02-26 |  |  |  | February
D-HDH73 | Power Connect | 2025-02-26 | 992 |  |  | February
D-H0222D | Bartlett Fiber | 2025-02-26 |  |  |  | February
D-H0223A | Bartlett Fiber | 2025-02-26 | 400 |  | 2 Toby Boxes | February
D-HWP102 | Power Connect | 2025-02-26 |  |  |  | February
D-H0222B | Brothers | 2025-02-26 | 1540 |  | 6 Toby Boxes | February
D-H0222C | Power Connect | 2025-02-26 | 1708 |  |  | February
D-HDH71 | HDD Underground | 2025-02-26 |  |  |  | February
D-H0222A | Key Underground | 2025-02-26 |  |  |  | February
FB-HDH01 | J Garcia Underground | 2025-02-26 |  |  |  | February
D-H0223E | Key Underground | 2025-02-26 | 1090 |  |  | February
FB-HWP401- | H&H Underground-Lightspeed | 2025-02-26 | 120 |  | 1 Toby Box | February
D-HDH68 | US Builders | 2025-02-26 | 399 |  |  | February
D-HNP138 | FCA Fiber | 2025-02-26 | 891 |  | 6 Toby Boxes | February
D-HDH04 | J Garcia Underground | 2025-02-27 |  |  |  | February
D-HDH31 | Reycamp | 2025-02-27 |  |  |  | February
D-HDH34 | Lightspeed | 2025-02-27 |  |  | Sponge Testing / Proofing Conduits | February
D-HDH66 | Bartlett Fiber | 2025-02-27 | 437 |  | 4 Toby Boxes / 8 Splices | February
D-HDH84 | Reycamp | 2025-02-27 |  |  |  | February
FB-HDH02A | Lightspeed | 2025-02-27 |  |  |  | February
Golden Wings MDU | SB Martinez | 2025-02-27 |  |  |  | February
D-HWP412 | SB Martinez | 2025-02-27 |  |  |  | February
D-HWP415 | Lightspeed | 2025-02-27 |  |  | Proofing Conduits | February
D-HWP425 | Brothers | 2025-02-27 |  |  |  | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-27 |  |  | Proofing Conduits | February
D-HWP441 | Brothers | 2025-02-27 |  |  | Proofing Conduits | February
FB-HWP101 | Power Connect | 2025-02-27 |  |  |  | February
D-H0223D | Brothers | 2025-02-27 | 1422 |  | 11 Toby Boxes | February
D-H0223C | Longo Underground | 2025-02-27 | 670 |  | 4 Toby Boxes | February
D-HDH76 | J Garcia Underground | 2025-02-27 | 529 |  |  | February
D-HDH45 | Reycamp | 2025-02-27 |  |  |  | February
D-HWP713 | Brothers | 2025-02-27 |  |  |  | February
D-HDH73 | Power Connect | 2025-02-27 | 513 |  | 4 Toby Boxes | February
D-H0222D | Bartlett Fiber | 2025-02-27 |  |  |  | February
D-H0223A | Bartlett Fiber | 2025-02-27 |  |  |  | February
D-HWP102 | Power Connect | 2025-02-27 |  |  |  | February
D-H0222B | Brothers | 2025-02-27 | 1360 |  | 6 Toby Boxes | February
D-H0222C | Power Connect | 2025-02-27 |  |  |  | February
D-HDH71 | HDD Underground | 2025-02-27 | 577 |  | 4 Toby Boxes | February
D-H0222A | Key Underground | 2025-02-27 | 1168 |  | 1-HH, 1 Swing Arm | February
FB-HDH01 | J Garcia Underground | 2025-02-27 |  |  |  | February
D-H0223E | Key Underground | 2025-02-27 | 840 |  |  | February
FB-HWP401- | H&H Underground-Lightspeed | 2025-02-27 |  |  |  | February
D-HDH68 | US Builders | 2025-02-27 | 335 |  | 2 Toby Boxes | February
D-HNP138 | FCA Fiber | 2025-02-27 | 1213 |  | 6 Toby Boxes | February
D-HDH04 | J Garcia Underground | 2025-02-28 | 9 |  | 6 Toby Boxes | February
D-HDH31 | Reycamp | 2025-02-28 |  |  |  | February
D-HDH34 | Lightspeed | 2025-02-28 |  |  | Sponge Testing / Proofing Conduits | February
D-HDH66 | Bartlett Fiber | 2025-02-28 |  |  |  | February
D-HDH84 | Reycamp | 2025-02-28 |  |  |  | February
FB-HDH02A | Lightspeed | 2025-02-28 |  |  |  | February
Golden Wings MDU | SB Martinez | 2025-02-28 |  |  |  | February
D-HWP412 | SB Martinez | 2025-02-28 |  |  |  | February
D-HWP415 | Lightspeed | 2025-02-28 | 3 |  | 2 Toby Boxes / Proffing Conduits | February
D-HWP425 | Brothers | 2025-02-28 |  |  |  | February
D-HWP436 | H&H Underground-Lightspeed | 2025-02-28 |  |  |  | February
D-HWP441 | Brothers | 2025-02-28 |  |  |  | February
FB-HWP101 | Power Connect | 2025-02-28 |  |  |  | February
D-H0223D | Brothers | 2025-02-28 | 946 |  | 6 Toby Boxes | February
D-H0223C | Longo Underground | 2025-02-28 |  |  |  | February
D-HDH76 | J Garcia Underground | 2025-02-28 | 327 |  |  | February
D-HDH45 | Reycamp | 2025-02-28 | 54 |  | Sponging / Proofing Conduits | February
D-HWP713 | Brothers | 2025-02-28 |  |  |  | February
D-HDH73 | Power Connect | 2025-02-28 |  |  |  | February
D-H0222D | Bartlett Fiber | 2025-02-28 | 886 |  | 8 Toby Boxes | February
D-H0223A | Bartlett Fiber | 2025-02-28 | 384 |  | 5 Toby Boxes | February
D-HWP102 | Power Connect | 2025-02-28 |  |  |  | February
D-H0222B | Brothers | 2025-02-28 |  |  |  | February
D-H0222C | Power Connect | 2025-02-28 | 229 |  |  | February
D-HDH71 | HDD Underground | 2025-02-28 | 239 |  | 8 Toby Boxes | February
D-H0222A | Key Underground | 2025-02-28 |  |  |  | February
FB-HDH01 | J Garcia Underground | 2025-02-28 |  |  |  | February
D-H0223E | Key Underground | 2025-02-28 | 530 |  |  | February
FB-HWP401 | H&H Underground-Lightspeed | 2025-02-28 |  |  |  | February
D-HDH68 | US Builders | 2025-02-28 | 1339 |  | 15 Toby Boxes | February
D-HNP138 | FCA Fiber | 2025-02-28 | 1054 |  |  | February
D-HDH04 | J Garcia Underground | 2025-03-03 |  |  |  | March
D-HDH31 | Reycamp | 2025-03-03 |  |  |  | March
D-HDH34 | Lightspeed | 2025-03-03 |  |  |  | March
D-HDH66 | Bartlett Fiber | 2025-03-03 |  |  |  | March
D-HDH84 | Reycamp | 2025-03-03 |  |  |  | March
FB-HDH02A | Lightspeed | 2025-03-03 | 363 |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-03 |  |  |  | March
D-HWP412 | SB Martinez | 2025-03-03 |  |  |  | March
D-HWP415 | Lightspeed | 2025-03-03 |  |  |  | March
D-HWP425 | Brothers | 2025-03-03 |  |  |  | March
D-HWP436 | H&H Underground-Lightspeed | 2025-03-03 |  |  |  | March
D-HWP441 | Brothers | 2025-03-03 |  |  |  | March
FB-HWP101 | Power Connect | 2025-03-03 |  |  |  | March
D-H0223D | Brothers | 2025-03-03 |  |  |  | March
D-H0223C | Longo Underground | 2025-03-03 |  |  |  | March
D-HDH76 | J Garcia Underground | 2025-03-03 | 286 |  |  | March
D-HDH45 | Reycamp | 2025-03-03 |  |  |  | March
D-HWP713 | Brothers | 2025-03-03 |  |  |  | March
D-HDH73 | Power Connect | 2025-03-03 |  |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-03 | 134 |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-03 |  |  | 12 Toby Boxes | March
D-HWP102 | Power Connect | 2025-03-03 |  |  |  | March
D-H0222B | Brothers | 2025-03-03 | 1460 |  | 9 Toby Boxes | March
D-H0222C | Power Connect | 2025-03-03 | 182 |  |  | March
D-HDH71 | HDD Underground | 2025-03-03 |  |  |  | March
D-H0222A | Key Underground | 2025-03-03 |  |  |  | March
FB-HDH01 | J Garcia Underground | 2025-03-03 |  |  |  | March
D-H0223E | Key Underground | 2025-03-03 |  |  |  | March
FB-HWP401- | H&H Underground-Lightspeed | 2025-03-03 |  |  |  | March
D-HDH68 | US Builders | 2025-03-03 | 1292 |  | 8 Toby Boxes | March
D-HNP138 | FCA Fiber | 2025-03-03 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-03 |  |  |  | March
D-HWP105 | Brothers | 2025-03-03 | 1454 |  | 8 Toby Boxes / 1 Flower Pot | March
D-HNP123 | HDD Underground | 2025-03-03 | 2215 |  | 19 Toby Boxes | March
D-HDH04 | J Garcia Underground | 2025-03-04 |  |  |  | March
D-HDH34 | Lightspeed | 2025-03-04 | 414 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-04 | 171 |  |  | March
D-HWP436 | H&H Underground-Lightspeed | 2025-03-04 |  |  | 27 Toby Boxes / Proofing Conduits | March
D-H0223C | Longo Underground | 2025-03-04 |  |  | Vault / Swing Arm / Groundrod | March
D-HDH76 | J Garcia Underground | 2025-03-04 | 358 |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-04 | 408 |  | 1 Toby Box | March
D-H0223A | Bartlett Fiber | 2025-03-04 | 840 |  | 28 Toby Boxes / 46 Splices | March
D-H0222B | Brothers | 2025-03-04 | 970 |  | 6 Toby Boxes | March
D-HDH68 | US Builders | 2025-03-04 | 1022 |  | 8 Toby Boxes | March
D-HNP138 | FCA Fiber | 2025-03-04 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-04 | 1570 |  | 9 Toby Boxes | March
D-HWP105 | Brothers | 2025-03-04 | 1360 |  | 6 Toby Boxes / 1 Flower Pot | March
D-HNP123 | HDD Underground | 2025-03-04 |  |  |  | March
BHT-FWP-06-W | Lightspeed | 2025-03-04 | 285 |  |  | March
D-HDH04 | J Garcia Underground | 2025-03-05 | 0 |  |  | March
D-HDH31 | Reycamp | 2025-03-05 | 0 |  |  | March
D-HDH34 | Lightspeed | 2025-03-05 | 367 |  |  | March
D-HDH66 | Bartlett Fiber | 2025-03-05 | 0 |  |  | March
D-HDH84 | Reycamp | 2025-03-05 | 0 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-05 | 0 |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-05 | 0 |  |  | March
D-HWP412 | SB Martinez | 2025-03-05 | 0 |  |  | March
D-HWP415 | Lightspeed | 2025-03-05 | 0 |  | Re-Built FDH | March
D-HWP425 | Brothers | 2025-03-05 | 0 |  |  | March
D-HWP436 | H&H Underground-Lightspeed | 2025-03-05 | 0 |  |  | March
D-HWP441 | Brothers | 2025-03-05 | 0 |  |  | March
FB-HWP101 | Power Connect | 2025-03-05 | 32 |  |  | March
D-H0223D | Brothers | 2025-03-05 | 0 |  |  | March
D-H0223C | Longo Underground | 2025-03-05 | 0 |  |  | March
D-HDH76 | J Garcia Underground | 2025-03-05 | 0 |  |  | March
D-HDH45 | Reycamp | 2025-03-05 | 0 |  |  | March
D-HWP713 | Brothers | 2025-03-05 | 0 |  |  | March
D-HDH73 | Power Connect | 2025-03-05 | 0 |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-05 | 452 |  | 6 Toby Boxes 20 Splices | March
D-H0223A | Bartlett Fiber | 2025-03-05 | 0 |  |  | March
D-HWP102 | Power Connect | 2025-03-05 | 0 |  |  | March
D-H0222B | Brothers | 2025-03-05 | 430 |  | 2 Toby Boxes / 1 HH | March
D-H0222C | Power Connect | 2025-03-05 | 0 |  |  | March
D-HDH71 | HDD Underground | 2025-03-05 | 0 |  |  | March
D-H0222A | Key Underground | 2025-03-05 | 0 |  |  | March
FB-HDH01 | J Garcia Underground | 2025-03-05 | 0 |  |  | March
D-H0223E | Key Underground | 2025-03-05 | 372 |  | 1 Toby Box / 3 Splices | March
FB-HWP401- | H&H Underground-Lightspeed | 2025-03-05 | 0 |  |  | March
D-HDH68 | US Builders | 2025-03-05 | 1246 |  | 10 Toby Boxes / Vault / Swing Arm / Groundrod | March
D-HNP138 | FCA Fiber | 2025-03-05 | 0 |  |  | March
D-HNP137 | FCA Fiber | 2025-03-05 | 461 |  | 3 Toby Boxes | March
D-HWP105 | Brothers | 2025-03-05 | 1263 |  | 9 Toby Boxes / 1 Flower Pot / 1 HH / 1 Swing Arm / 1 FDH | March
D-HNP123 | HDD Underground | 2025-03-05 | 0 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-05 | 617 |  |  | March
D-HNP143 | Brothers | 2025-03-05 | 700 |  | 6 Toby Boxes | March
FB-HWP701 | Lightspeed | 2025-03-05 | 200 |  |  | March
D-HDH04 | J Garcia Underground | 2025-03-06 | 0 |  |  | March
D-HDH31 | Reycamp | 2025-03-06 | 0 |  |  | March
D-HDH34 | Lightspeed | 2025-03-06 | 245 |  | 11 Toby Boxes | March
D-HDH66 | Bartlett Fiber | 2025-03-06 | 0 |  |  | March
D-HDH84 | Reycamp | 2025-03-06 | 0 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-06 | 397 |  | 8 Splices | March
D-HWP701 | SB Martinez | 2025-03-06 | 0 |  |  | March
D-HWP412 | SB Martinez | 2025-03-06 | 0 |  |  | March
D-HWP415 | Lightspeed | 2025-03-06 | 0 |  |  | March
D-HWP425 | Brothers | 2025-03-06 | 35 |  |  | March
D-HWP436 | H&H Underground-Lightspeed | 2025-03-06 | 0 |  |  | March
D-HWP441 | Brothers | 2025-03-06 | 0 |  |  | March
FB-HWP101 | Power Connect | 2025-03-06 | 85 |  |  | March
D-H0223D | Brothers | 2025-03-06 | 0 |  |  | March
D-H0223C | Longo Underground | 2025-03-06 | 0 |  |  | March
D-HDH76 | J Garcia Underground | 2025-03-06 | 32 |  | 12 Toby Boxes | March
D-HDH45 | Reycamp | 2025-03-06 | 0 |  |  | March
D-HWP713 | Brothers | 2025-03-06 | 0 |  |  | March
D-HDH73 | Power Connect | 2025-03-06 | 0 |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-06 | 0 |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-06 | 0 |  |  | March
D-HWP102 | Power Connect | 2025-03-06 | 0 |  |  | March
D-H0222B | Brothers | 2025-03-06 | 0 |  |  | March
D-H0222C | Power Connect | 2025-03-06 | 0 |  |  | March
D-HDH71 | HDD Underground | 2025-03-06 | 0 |  |  | March
D-H0222A | Key Underground | 2025-03-06 | 0 |  |  | March
FB-HDH01 | J Garcia Underground | 2025-03-06 | 0 |  |  | March
D-H0223E | Key Underground | 2025-03-06 | 0 |  |  | March
FB-HWP401- | H&H Underground-Lightspeed | 2025-03-06 | 0 |  |  | March
D-HDH68 | US Builders | 2025-03-06 | 0 |  |  | March
D-HNP138 | FCA Fiber | 2025-03-06 | 0 |  |  | March
D-HNP137 | FCA Fiber | 2025-03-06 | 1109 |  | 16 Toby Boxes | March
D-HWP105 | Brothers | 2025-03-06 | 0 |  |  | March
D-HNP123 | HDD Underground | 2025-03-06 | 0 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-06 | 286 |  |  | March
D-HNP143 | Brothers | 2025-03-06 | 1590 |  | 10 Toby Boxes | March
FB-HWP701 | Lightspeed | 2025-03-06 | 489 |  | 1 HH / 3 Toby Boxes | March
D-HDH74 | Bartlett Fiber | 2025-03-06 | 884 |  | 9 Toby Boxes / 25 Splices | March
D-HWP103 | Brothers | 2025-03-06 | 1357 |  | 13 Toby Boxes | March
D-HDH46 | FCA Fiber | 2025-03-06 | 874 |  |  | March
D-HDH04 | J Garcia Underground | 2025-03-07 | 0 |  |  | March
D-HDH31 | Reycamp | 2025-03-07 | 0 |  |  | March
D-HDH34 | Lightspeed | 2025-03-07 | 0 |  | Sponging | March
D-HDH66 | Bartlett Fiber | 2025-03-07 | 0 |  |  | March
D-HDH84 | Reycamp | 2025-03-07 | 0 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-07 | 88 |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-07 | 0 |  |  | March
D-HWP412 | SB Martinez | 2025-03-07 | 0 |  |  | March
D-HWP415 | Lightspeed | 2025-03-07 | 0 |  |  | March
D-HWP425 | Brothers | 2025-03-07 | 0 |  |  | March
D-HWP436 | H&H Underground-Lightspeed | 2025-03-07 | 0 |  |  | March
D-HWP441 | Brothers | 2025-03-07 | 0 |  |  | March
FB-HWP101 | Power Connect | 2025-03-07 | 0 |  |  | March
D-H0223D | Brothers | 2025-03-07 | 0 |  |  | March
D-H0223C | Longo Underground | 2025-03-07 | 0 |  |  | March
D-HDH76 | J Garcia Underground | 2025-03-07 | 9 |  | 6 Toby Boxes | March
D-HDH45 | Reycamp | 2025-03-07 | 0 |  |  | March
D-HWP713 | Brothers | 2025-03-07 | 0 |  |  | March
D-HDH73 | Power Connect | 2025-03-07 | 201 |  | 25 Toby Boxes | March
D-H0222D | Bartlett Fiber | 2025-03-07 | 875 |  | 13 Toby Boxes / 10 Splices | March
D-H0223A | Bartlett Fiber | 2025-03-07 | 0 |  |  | March
D-HWP102 | Power Connect | 2025-03-07 | 0 |  |  | March
D-H0222B | Brothers | 2025-03-07 | 0 |  | 1 Hand Hole / 1 Swing Arm | March
D-H0222C | Power Connect | 2025-03-07 | 0 |  |  | March
D-HDH71 | HDD Underground | 2025-03-07 | 0 |  |  | March
D-H0222A | Key Underground | 2025-03-07 | 0 |  |  | March
FB-HDH01 | J Garcia Underground | 2025-03-07 | 0 |  |  | March
D-H0223E | Key Underground | 2025-03-07 | 0 |  |  | March
FB-HWP401- | H&H Underground-Lightspeed | 2025-03-07 | 0 |  |  | March
D-HDH68 | US Builders | 2025-03-07 | 288 |  | 1 Toby Box / 5 Splices | March
D-HNP138 | FCA Fiber | 2025-03-07 | 0 |  |  | March
D-HNP137 | FCA Fiber | 2025-03-07 | 980 |  | 9 Toby Boxes | March
D-HWP105 | Brothers | 2025-03-07 | 0 |  |  | March
D-HNP123 | HDD Underground | 2025-03-07 | 0 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-07 | 0 |  | 1 HH | March
D-HNP143 | Brothers | 2025-03-07 | 1370 |  | 8 Toby Boxes | March
FB-HWP701 | Lightspeed | 2025-03-07 | 0 |  |  | March
D-HDH74 | Bartlett Fiber | 2025-03-07 | 738 |  | 6 Toby Boxes / 12 Splices | March
D-HWP103 | Brothers | 2025-03-07 | 0 |  |  | March
D-HDH46 | FCA Fiber | 2025-03-07 | 1602 |  | 6 Toby Boxes | March
FX4-FWP-08 | Lightspeed | 2025-03-07 | 20 |  |  | March
D-HDH04 | J Garcia Underground | 2025-03-10 | 0 |  |  | March
D-HDH31 | Reycamp | 2025-03-10 | 0 |  |  | March
D-HDH34 | Lightspeed | 2025-03-10 | 0 |  | FDH / Restoration | March
D-HDH66 | Bartlett Fiber | 2025-03-10 | 0 |  |  | March
D-HDH84 | Reycamp | 2025-03-10 | 0 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-10 | 0 |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-10 | 0 |  |  | March
D-HWP412 | SB Martinez | 2025-03-10 | 0 |  |  | March
D-HWP415 | Lightspeed | 2025-03-10 | 0 |  |  | March
D-HWP425 | Brothers | 2025-03-10 | 0 |  |  | March
D-HWP436 | H&H Underground-Lightspeed | 2025-03-10 | 0 |  |  | March
D-HWP441 | Brothers | 2025-03-10 | 0 |  |  | March
FB-HWP101 | Power Connect | 2025-03-10 | 0 |  |  | March
D-H0223D | Brothers | 2025-03-10 | 0 |  |  | March
D-H0223C | Longo Underground | 2025-03-10 | 0 |  |  | March
D-HDH76 | J Garcia Underground | 2025-03-10 | 0 |  | FDH / 1 Swing Arm | March
D-HDH45 | Reycamp | 2025-03-10 | 0 |  |  | March
D-HWP713 | Brothers | 2025-03-10 | 0 |  |  | March
D-HDH73 | Power Connect | 2025-03-10 | 0 |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-10 | 0 |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-10 | 0 |  |  | March
D-HWP102 | Power Connect | 2025-03-10 | 0 |  |  | March
D-H0222B | Brothers | 2025-03-10 | 0 |  |  | March
D-H0222C | Power Connect | 2025-03-10 | 0 |  |  | March
D-HDH71 | HDD Underground | 2025-03-10 | 0 |  |  | March
D-H0222A | Key Underground | 2025-03-10 | 0 |  |  | March
FB-HDH01 | J Garcia Underground | 2025-03-10 | 0 |  |  | March
D-H0223E | Key Underground | 2025-03-10 | 649 |  | 9 Toby Boxes | March
FB-HWP401- | H&H Underground-Lightspeed | 2025-03-10 | 0 |  |  | March
D-HDH68 | US Builders | 2025-03-10 | 0 |  |  | March
D-HNP138 | FCA Fiber | 2025-03-10 | 0 |  |  | March
D-HNP137 | FCA Fiber | 2025-03-10 | 0 |  |  | March
D-HWP105 | Brothers | 2025-03-10 | 0 |  |  | March
D-HNP123 | HDD Underground | 2025-03-10 | 0 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-10 | 0 |  |  | March
D-HNP143 | Brothers | 2025-03-10 | 0 |  |  | March
FB-HWP701 | Lightspeed | 2025-03-10 | 921 |  |  | March
D-HDH74 | Bartlett Fiber | 2025-03-10 | 0 |  |  | March
D-HWP103 | Brothers | 2025-03-10 | 1288 |  | 3 Toby Boxes | March
D-HDH46 | FCA Fiber | 2025-03-10 | 834 |  |  | March
FX4-FWP-08 | Lightspeed | 2025-03-10 | 0 |  |  | March
D-HDH04 | J Garcia Underground | 2025-03-11 | 3 |  | 1 Toby Box | March
D-HDH31 | Reycamp | 2025-03-11 | 0 |  |  | March
D-HDH34 | Lightspeed | 2025-03-11 | 0 |  | Proofing Conduits | March
D-HDH66 | Bartlett Fiber | 2025-03-11 | 0 |  |  | March
D-HDH84 | Reycamp | 2025-03-11 | 0 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-11 | 0 |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-11 | 0 |  |  | March
D-HWP412 | SB Martinez | 2025-03-11 | 0 |  |  | March
D-HWP415 | Lightspeed | 2025-03-11 | 0 |  |  | March
D-HWP425 | Brothers | 2025-03-11 | 0 |  |  | March
D-HWP436 | H&H Underground-Lightspeed | 2025-03-11 | 0 |  |  | March
D-HWP441 | Brothers | 2025-03-11 | 0 |  |  | March
FB-HWP101 | Power Connect | 2025-03-11 | 0 |  |  | March
D-H0223D | Brothers | 2025-03-11 | 0 |  |  | March
D-H0223C | Longo Underground | 2025-03-11 | 0 |  |  | March
D-HDH76 | J Garcia Underground | 2025-03-11 | 12 |  | 6 Toby Boxes | March
D-HDH45 | Reycamp | 2025-03-11 | 0 |  |  | March
D-HWP713 | Brothers | 2025-03-11 | 0 |  |  | March
D-HDH73 | Power Connect | 2025-03-11 | 0 |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-11 | 199 |  | 2 Toby Boxes | March
D-H0223A | Bartlett Fiber | 2025-03-11 | 0 |  |  | March
D-HWP102 | Power Connect | 2025-03-11 | 0 |  |  | March
D-H0222B | Brothers | 2025-03-11 | 0 |  |  | March
D-H0222C | Power Connect | 2025-03-11 | 0 |  |  | March
D-HDH71 | HDD Underground | 2025-03-11 | 0 |  |  | March
D-H0222A | Key Underground | 2025-03-11 | 0 |  |  | March
FB-HDH01 | J Garcia Underground | 2025-03-11 | 106 |  | 2 Toby Boxes | March
D-H0223E | Key Underground | 2025-03-11 | 528 |  | 5 Toby Boxes / 2 Splices | March
FB-HWP401- | H&H Underground-Lightspeed | 2025-03-11 | 0 |  |  | March
D-HDH68 | US Builders | 2025-03-11 | 0 |  |  | March
D-HNP138 | FCA Fiber | 2025-03-11 | 0 |  |  | March
D-HNP137 | FCA Fiber | 2025-03-11 | 0 |  |  | March
D-HWP105 | Brothers | 2025-03-11 | 0 |  |  | March
D-HNP123 | HDD Underground | 2025-03-11 | 0 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-11 | 491 |  |  | March
D-HNP143 | Brothers | 2025-03-11 | 0 |  |  | March
FB-HWP701 | Lightspeed | 2025-03-11 | 614 |  |  | March
D-HDH74 | Bartlett Fiber | 2025-03-11 | 0 |  |  | March
D-HWP103 | Brothers | 2025-03-11 | 685 |  | 5 Toby Boxes/1 HH/1 Swing Arm/1 Groundrod | March
D-HDH46 | FCA Fiber | 2025-03-11 | 1081 |  |  | March
FX4-FWP-08 | Lightspeed | 2025-03-11 | 0 |  |  | March
D-HWP705 | Brothers | 2025-03-11 | 1710 |  | 13 Toby Boxes | March
FB-H0222A | Bartlett Fiber | 2025-03-11 | 304 |  |  | March
FB-H02223A | Power Connect | 2025-03-11 | 1617 |  |  | March
D-HNP141 | Power Connect | 2025-03-11 | 228 |  |  | March
D-HDH78 | FCA Fiber | 2025-03-11 | 1257 |  |  | March
D-HDH04 | J Garcia Underground | 2025-03-12 |  |  | QC / Restoration | March
D-HDH31 | Reycamp | 2025-03-12 |  |  |  | March
D-HDH34 | Lightspeed | 2025-03-12 |  |  | QC / Restoration | March
D-HDH66 | Bartlett Fiber | 2025-03-12 |  |  |  | March
D-HDH84 | Reycamp | 2025-03-12 |  |  |  | March
FB-HDH02A | Lightspeed | 2025-03-12 |  |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-12 | COMPLETED |  |  | March
D-HWP412 | SB Martinez | 2025-03-12 | COMPLETED |  |  | March
D-HWP415 | Lightspeed | 2025-03-12 |  |  |  | March
D-HWP425 | Brothers | 2025-03-12 | COMPLETED |  |  | March
D-HWP436 | H&H Underground-Lightspeed | 2025-03-12 |  |  |  | March
D-HWP441 | Brothers | 2025-03-12 | COMPLETED |  |  | March
FB-HWP101 | Power Connect | 2025-03-12 |  |  |  | March
D-H0223D | Brothers | 2025-03-12 |  |  |  | March
D-H0223C | Longo Underground | 2025-03-12 |  |  |  | March
D-HDH76 | J Garcia Underground | 2025-03-12 | 9 |  | 7 Toby Boxes | March
D-HDH45 | Reycamp | 2025-03-12 |  |  |  | March
D-HWP713 | Brothers | 2025-03-12 |  |  |  | March
D-HDH73 | Power Connect | 2025-03-12 |  |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-12 |  |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-12 |  |  |  | March
D-HWP102 | Power Connect | 2025-03-12 |  |  |  | March
D-H0222B | Brothers | 2025-03-12 |  |  |  | March
D-H0222C | Power Connect | 2025-03-12 |  |  |  | March
D-HDH71 | HDD Underground | 2025-03-12 |  |  |  | March
D-H0222A | Key Underground | 2025-03-12 | 201 |  |  | March
FB-HDH01 | J Garcia Underground | 2025-03-12 |  |  |  | March
D-H0223E | Key Underground | 2025-03-12 | 489 |  | 5 Toby Boxes | March
FB-HWP401- | H&H Underground-Lightspeed | 2025-03-12 |  |  |  | March
D-HDH68 | US Builders | 2025-03-12 |  |  |  | March
D-HNP138 | FCA Fiber | 2025-03-12 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-12 |  |  |  | March
D-HWP105 | Brothers | 2025-03-12 |  |  |  | March
D-HNP123 | HDD Underground | 2025-03-12 |  |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-12 | 291 |  |  | March
D-HNP143 | Brothers | 2025-03-12 |  |  |  | March
FB-HWP701 | Lightspeed | 2025-03-12 | 1004 |  | 1 HH | March
D-HDH74 | Bartlett Fiber | 2025-03-12 | 961 |  |  | March
D-HWP103 | Brothers | 2025-03-12 |  |  |  | March
D-HDH46 | FCA Fiber | 2025-03-12 | 688 |  |  | March
FX4-FWP-08 | Lightspeed | 2025-03-12 |  |  |  | March
D-HWP705 | Brothers | 2025-03-12 | 1700 |  | 15 Toby Boxes / 1 HH | March
FB-H0222A | Bartlett Fiber | 2025-03-12 | 205 |  |  | March
FB-H02223A | Power Connect | 2025-03-12 |  |  |  | March
D-HNP141 | Power Connect | 2025-03-12 |  |  |  | March
D-HDH78 | FCA Fiber | 2025-03-12 | 2121 |  |  | March
D-HDH67 | Power Connect | 2025-03-12 | 984 |  | 4 Toby Boxes | March
FB-HDH275 | HDD Underground | 2025-03-12 | 2760 |  | 5 Toby Boxes | March
D-HDH70 | Longo Underground | 2025-03-12 | 1246 |  | 10 Toby Boxes / 20 Splices | March
D-HWP701 | Brothers | 2025-03-12 | 1353 |  | 9 Toby Boxes | March
D-HDH04 | J Garcia Underground | 2025-03-13 |  |  | QC / Restoration | March
D-HDH31 | Reycamp | 2025-03-13 |  |  |  | March
D-HDH34 | Lightspeed | 2025-03-13 |  |  | QC / Restoration | March
D-HDH66 | Bartlett Fiber | 2025-03-13 |  |  |  | March
D-HDH84 | Reycamp | 2025-03-13 |  |  |  | March
FB-HDH02A | Lightspeed | 2025-03-13 |  |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-13 |  |  |  | March
D-HWP412 | SB Martinez | 2025-03-13 |  |  |  | March
D-HWP415 | Lightspeed | 2025-03-13 |  |  |  | March
D-HWP425 | Brothers | 2025-03-13 |  |  |  | March
D-HWP436 | H&H Underground-Lightspeed | 2025-03-13 |  |  |  | March
D-HWP441 | Brothers | 2025-03-13 |  |  |  | March
FB-HWP101 | Power Connect | 2025-03-13 |  |  |  | March
D-H0223D | Brothers | 2025-03-13 |  |  |  | March
D-H0223C | Longo Underground | 2025-03-13 |  |  |  | March
D-HDH76 | J Garcia Underground | 2025-03-13 |  |  | QC / Restoration | March
D-HDH45 | Reycamp | 2025-03-13 |  |  |  | March
D-HWP713 | Brothers | 2025-03-13 |  |  |  | March
D-HDH73 | Power Connect | 2025-03-13 |  |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-13 |  |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-13 |  |  |  | March
D-HWP102 | Power Connect | 2025-03-13 |  |  |  | March
D-H0222B | Brothers | 2025-03-13 |  |  |  | March
D-H0222C | Power Connect | 2025-03-13 |  |  |  | March
D-HDH71 | HDD Underground | 2025-03-13 |  |  |  | March
D-H0222A | Key Underground | 2025-03-13 | 1207 |  | 9 Toby Boxes / 16 Splices / 2 Pits | March
FB-HDH01 | J Garcia Underground | 2025-03-13 |  |  |  | March
D-H0223E | Key Underground | 2025-03-13 | 534 |  | 7 Toby Boxes / 5 Splices | March
FB-HWP401 | H&H Underground-Lightspeed | 2025-03-13 |  |  |  | March
D-HDH68 | US Builders | 2025-03-13 |  |  |  | March
D-HNP138 | FCA Fiber | 2025-03-13 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-13 |  |  |  | March
D-HWP105 | Brothers | 2025-03-13 |  |  |  | March
D-HNP123 | HDD Underground | 2025-03-13 |  |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-13 | 571 |  | 2 HH | March
D-HNP143 | Brothers | 2025-03-13 | 1170 |  | 11 Toby Boxes | March
FB-HWP701 | Lightspeed | 2025-03-13 |  |  |  | March
D-HDH74 | Bartlett Fiber | 2025-03-13 | 914 |  | 12 Toby Boxes / 4 Splices | March
D-HWP103 | Brothers | 2025-03-13 |  |  |  | March
D-HDH46 | FCA Fiber | 2025-03-13 |  |  |  | March
FX4-FWP-08 | Lightspeed | 2025-03-13 |  |  |  | March
D-HWP705 | Brothers | 2025-03-13 |  |  |  | March
FB-H0222A | Bartlett Fiber | 2025-03-13 | 451 |  |  | March
FB-H02223A | Power Connect | 2025-03-13 | 101 |  |  | March
D-HNP141 | Power Connect | 2025-03-13 |  |  |  | March
D-HDH78 | FCA Fiber | 2025-03-13 | 2742 |  |  | March
D-HDH67 | Power Connect | 2025-03-13 | 1078 |  | 6 Toby Boxes / 10 Splices | March
FB-HDH275 | HDD Underground | 2025-03-13 | 945 |  |  | March
D-HDH70 | Longo Underground | 2025-03-13 | 664 |  | 4 Toby Boxes / 8 Splices | March
D-HWP701 | Brothers | 2025-03-13 | 1123 |  | 4 Toby Boxes / 2 Flowerpots | March
D-HDH03 | Power Connect | 2025-03-13 | 338 |  | 2 Toby Boxes / 6 Splices | March
D-HDH04 | J Garcia Underground | 2025-03-14 |  |  | QC / Restoration | March
D-HDH31 | Reycamp | 2025-03-14 |  |  |  | March
D-HDH34 | Lightspeed | 2025-03-14 |  |  | QC / Restoration | March
D-HDH66 | Bartlett Fiber | 2025-03-14 |  |  |  | March
D-HDH84 | Reycamp | 2025-03-14 |  |  |  | March
FB-HDH02A | Lightspeed | 2025-03-14 |  |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-14 |  |  |  | March
D-HWP412 | SB Martinez | 2025-03-14 |  |  | Restoration | March
D-HWP415 | Lightspeed | 2025-03-14 |  |  |  | March
D-HWP425 | Brothers | 2025-03-14 |  |  |  | March
D-HWP436 | H&H Underground-Lightspeed | 2025-03-14 |  |  | Restoration | March
D-HWP441 | Brothers | 2025-03-14 |  |  |  | March
FB-HWP101 | Power Connect | 2025-03-14 |  |  | Restoration | March
D-H0223D | Brothers | 2025-03-14 |  |  |  | March
D-H0223C | Longo Underground | 2025-03-14 |  |  |  | March
D-HDH76 | J Garcia Underground | 2025-03-14 |  |  | QC / Restoration | March
D-HDH45 | Reycamp | 2025-03-14 |  |  |  | March
D-HWP713 | Brothers | 2025-03-14 |  |  |  | March
D-HDH73 | Power Connect | 2025-03-14 |  |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-14 |  |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-14 |  |  |  | March
D-HWP102 | Power Connect | 2025-03-14 |  |  | Restoration | March
D-H0222B | Brothers | 2025-03-14 |  |  |  | March
D-H0222C | Power Connect | 2025-03-14 |  |  |  | March
D-HDH71 | HDD Underground | 2025-03-14 |  |  |  | March
D-H0222A | Key Underground | 2025-03-14 | 220 |  | 1 Toby Box / 2 Splices | March
FB-HDH01 | J Garcia Underground | 2025-03-14 |  |  |  | March
D-H0223E | Key Underground | 2025-03-14 |  |  | 2 Toby Boxes / 1 HH / 1 Swing Arm | March
FB-HWP401 | H&H Underground-Lightspeed | 2025-03-14 |  |  |  | March
D-HDH68 | US Builders | 2025-03-14 |  |  |  | March
D-HNP138 | FCA Fiber | 2025-03-14 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-14 |  |  |  | March
D-HWP105 | Brothers | 2025-03-14 |  |  |  | March
D-HNP123 | HDD Underground | 2025-03-14 |  |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-14 |  |  |  | March
D-HNP143 | Brothers | 2025-03-14 |  |  |  | March
FB-HWP701 | Lightspeed | 2025-03-14 |  |  | Dug Up Conduit | March
D-HDH74 | Bartlett Fiber | 2025-03-14 | 1903 |  | 20 Toby Boxes / 9 Splices | March
D-HWP103 | Brothers | 2025-03-14 |  |  |  | March
D-HDH46 | FCA Fiber | 2025-03-14 |  |  |  | March
FX4-FWP-08 | Lightspeed | 2025-03-14 |  |  |  | March
D-HWP705 | Brothers | 2025-03-14 |  |  |  | March
FB-H0222A | Bartlett Fiber | 2025-03-14 |  |  |  | March
FB-H02223A | Power Connect | 2025-03-14 |  |  |  | March
D-HNP141 | Power Connect | 2025-03-14 |  |  |  | March
D-HDH78 | FCA Fiber | 2025-03-14 | 75 |  | 41 Toby Boxes / 1 HH / FDH / 1 Ground Rod | March
D-HDH67 | Power Connect | 2025-03-14 | 2048 |  | 14 Toby Boxes / 21 Pits | March
FB-HDH275 | HDD Underground | 2025-03-14 | 1073 |  |  | March
D-HDH70 | Longo Underground | 2025-03-14 | 834 |  | 6 Toby Boxes / 11 Splices | March
D-HWP701 | Brothers | 2025-03-14 |  |  |  | March
D-HDH03 | Power Connect | 2025-03-14 |  |  |  | March
D-HDH04 | J Garcia Underground | 2025-03-17 |  |  | QC / Restoration | March
D-HDH34 | Lightspeed | 2025-03-17 |  |  | QC / Restoration | March
D-HDH84 | Reycamp | 2025-03-17 |  |  |  | March
FB-HDH02A | Lightspeed | 2025-03-17 |  |  |  | March
FB-HWP101 | Power Connect | 2025-03-17 |  |  |  | March
D-H0223D | Brothers | 2025-03-17 |  |  |  | March
D-HDH76 | J Garcia Underground | 2025-03-17 |  |  | QC / Restoration | March
D-HDH45 | Reycamp | 2025-03-17 |  |  |  | March
D-HDH73 | Power Connect | 2025-03-17 |  |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-17 |  |  |  | March
D-HWP102 | Power Connect | 2025-03-17 |  |  |  | March
D-H0222A | Key Underground | 2025-03-17 | 195 |  | 2 Toby Boxes / 4 Splices | March
FB-HDH01 | J Garcia Underground | 2025-03-17 |  |  |  | March
FB-HWP401 | H&H Underground-Lightspeed | 2025-03-17 |  |  |  | March
D-HNP138 | FCA Fiber | 2025-03-17 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-17 |  |  |  | March
D-HWP105 | Brothers | 2025-03-17 |  |  |  | March
D-HNP123 | HDD Underground | 2025-03-17 |  |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-17 | 436 |  |  | March
D-HNP143 | Brothers | 2025-03-17 |  |  |  | March
FB-HWP701 | Lightspeed | 2025-03-17 |  |  |  | March
D-HWP103 | Brothers | 2025-03-17 |  |  |  | March
D-HDH46 | FCA Fiber | 2025-03-17 | 15 |  | 9 Toby Boxes | March
FX4-FWP-08 | Lightspeed | 2025-03-17 |  |  |  | March
D-HWP705 | Brothers | 2025-03-17 |  |  |  | March
FB-H0222A | Bartlett Fiber | 2025-03-17 |  |  |  | March
FB-H02223A | Power Connect | 2025-03-17 |  |  |  | March
D-HNP141 | Power Connect | 2025-03-17 |  |  |  | March
D-HDH67 | Power Connect | 2025-03-17 | 919 |  | 5 Toby oxes / 5 Pits | March
FB-HDH275 | HDD Underground | 2025-03-17 | 2387 |  |  | March
D-HDH70 | Longo Underground | 2025-03-17 | 1095 |  | 7 Toby Boxes / 15 Splices / 1 HH / 1 Swing Arm / 1 Ground Rod | March
D-HWP701 | Brothers | 2025-03-17 | 1105 |  | 9 Toby Boxes / 1 FDH / 1 Ground Rod | March
D-HDH03 | Power Connect | 2025-03-17 |  |  |  | March
BHUD-FWP-08-E | Brothers | 2025-03-17 | 920 |  | 3 Vaults / 882 Fiber Cable | March
D-H0221D | Bartlett Fiber | 2025-03-17 | 656 |  |  | March
D-HDH04 | J Garcia Underground | 2025-03-18 |  |  | QC / Restoration | March
D-HDH34 | Lightspeed | 2025-03-18 |  |  | QC / Restoration | March
D-HDH45 | Reycamp | 2025-03-18 |  |  | QC / Restoration | March
D-HNP137 | FCA Fiber | 2025-03-18 | 1342 |  | 13 Toby Boxes | March
D-HWP105 | Brothers | 2025-03-18 |  |  | 1 FDH / 1 HH / 1 Ground Rod | March
D-HNP143 | Brothers | 2025-03-18 | 315 |  |  | March
FB-HWP701 | Lightspeed | 2025-03-18 | 1230 |  | 12 Toby Boxes / 1 HH / 1 FDH / 1 Swing Arm | March
FB-HDH275 | HDD Underground | 2025-03-18 | 841 |  | 6 Toby Boxes / 9 Splices | March
D-HDH70 | Longo Underground | 2025-03-18 | 65 |  | 3 HH | March
D-H0221B | Bartlett Fiber | 2025-03-18 | 977 |  | 10 Toby Boxes / 6 Splices | March
FB-H0221A | HAS Global | 2025-03-18 | 803 |  | 8 Toby Boxes / 7 Splices | March
D-HDH04-J Garcia | J Garcia Underground | 2025-03-19 |  |  | QC / Restoration | March
D-HDH34 | Lightspeed | 2025-03-19 |  |  | QC / Restoration | March
D-HDH76 | J Garcia Underground | 2025-03-19 |  |  | QC / Restoration | March
D-H0222A | Key Underground | 2025-03-19 | 187 |  |  | March
D-HNP138 | FCA Fiber | 2025-03-19 | 1409 |  | 14 Toby Boxes | March
FB-HWP701 | Power Connect | 2025-03-19 | 200 |  | 1 HH / 594 Pulling Fiber Cable | March
D-HNP141 | Power Connect | 2025-03-19 | 1460 |  | 11 Toby Boxes / 12 Splices | March
FB-HDH275 | HDD Underground | 2025-03-19 | 18 |  | 4 HH / 11 Pits | March
D-H0221D | Bartlett Fiber | 2025-03-19 | 728 |  | 2 Toby Box / 3 Splice | March
D-H0221B | Bartlett Fiber | 2025-03-19 | 953 |  | 1 Toby Box / 1 Splice | March
FB-H0221A | HAS Global | 2025-03-19 | 551 |  |  | March
D-HDH75 | Longo Underground | 2025-03-19 | 1373 |  | 12 Toby Box / 24 Splice | March
D-HNP138- | FCA Fiber | 2025-03-20 | 1016 |  | 11 Toby Boxes | March
FB-HNP138 |  | 2025-03-20 | 353 |  |  | March
FB-HDH275 | HDD Underground | 2025-03-20 |  |  |  | March
D-H0221D | Bartlett Fiber | 2025-03-20 | 700 |  | 9 Toby Box / 4 Splice | March
D-H0221B | Bartlett Fiber | 2025-03-20 | 1236 |  | 17 Toby Box / 13 Splice | March
FB-H0221A | HAS Global | 2025-03-20 |  |  |  | March
D-HDH75 | Longo Underground | 2025-03-20 | 1964 |  | 15 Toby Box / 30 Splice | March
D-HNP141 | Power Connect | 2025-03-20 | No Locates |  |  | March
D-H0222A | Lightspeed | 2025-03-20 | 170 |  | 1 Toby Box / 2 Splices | March
D-HDH67 |  | 2025-03-20 | 836 |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod / 5 Toby Boxes / 4 Pits | March
BHT-FWP-06 | Lightspeed | 2025-03-20 | 6275 |  | Restoration | March
D-HNP138 | FCA Fiber | 2025-03-20 | 1016 |  | 11 Toby Boxes | March
FB-HNP138 |  | 2025-03-20 | 353 |  |  | March
FB-HDH275 | HDD Underground | 2025-03-20 |  |  |  | March
D-H0221D | Bartlett Fiber | 2025-03-20 | 700 |  | 9 Toby Box / 4 Splice | March
D-H0221B | Bartlett Fiber | 2025-03-20 | 1236 |  | 17 Toby Box / 13 Splice | March
FB-H0221A | HAS Global | 2025-03-20 |  |  |  | March
D-HDH75 | Longo Underground | 2025-03-20 | 1964 |  | 15 Toby Box / 30 Splice | March
D-HNP141 | Power Connect | 2025-03-20 |  |  | No Locates | March
D-H0222A | Lightspeed | 2025-03-20 | 170 |  | 1 Toby Box / 2 Splices | March
D-HDH67 |  | 2025-03-20 | 836 |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod / 5 Toby Boxes / 4 Pits | March
BHT-FWP-06 | Lightspeed | 2025-03-20 |  |  | Restoration | March
D-HNP138 | FCA Fiber | 2025-03-21 |  |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | March
FB-HDH275 | HDD Underground | 2025-03-21 |  |  | Soft Dig Requested | March
D-H0221D | Bartlett Fiber | 2025-03-21 | 709 |  | 2 Toby Box / 1 Splices | March
D-H0221B | Bartlett Fiber | 2025-03-21 | 399 |  | 5 Toby Box / 1 Splices | March
D-HDH75 | Longo Underground | 2025-03-21 | 1528 |  | 15 Toby Box / 30 Splice / 1 HH / 1 Swing Arm / 1 Ground Rod | March
D-HNP141 | Power Connect | 2025-03-21 | 420 |  | 4 Toby Box / 5 Pits | March
D-H0222A | Lightspeed | 2025-03-21 | 270 |  | 1 Toby Box / 2 Splices | March
D-HDH67 | Power Connect | 2025-03-21 |  |  |  | March
FB-HDH02A D-HDH75 Tie In | Longo Underground | 2025-03-21 | 583 |  | 3 Dap Locations | March
D-HDH46 | FCA Fiber | 2025-03-21 |  |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | March
D-HDH03 | Power Connect | 2025-03-21 | 360 |  | 4 Pits | March
FB-HDH02A | Longo Underground | 2025-03-24 | 762 | 12 Splices |  | March
D-HDH76 | J Garcia Underground | 2025-03-24 |  |  | Schedule Final Walkout | March
D-HNP141 | Power Connect | 2025-03-24 | 982 | 10 Splices | 10 Toby Boxes | March
D-H0220C | Power Connect | 2025-03-24 | 691 |  | 4 Toby Boxes / 6 Pits | March
D-H0221A | Brothers | 2025-03-24 | 1430 | 9 Toby Boxes | 7 Splices | March
D-H0221F | Brothers | 2025-03-24 | 1460 |  | 10 Toby Boxes | March
FB-HDH02A | FCA Fiber | 2025-03-24 |  |  | Pending Soft Dig | March
D-H0221D | Bartlett Fiber | 2025-03-24 | 905 | 5 Splices | 7 Toby Boxes | March
D-H0223F | Lightspeed | 2025-03-24 |  |  | Moved Drill-Locates Not Clear | March
D-H0222D | Bartlett Fiber | 2025-03-24 |  |  | Sponging | March
D-HDH04 | Bartlett Fiber | 2025-03-24 |  |  | Schedule Final Walkout | March
D-HDH34 | Lightspeed | 2025-03-24 |  |  | Schedule Final Walkout | March
D-H0222A | Lightspeed | 2025-03-24 | 58 | 2 Splices | 1 toby box | March
FB-H0220A | Longo Underground | 2025-03-25 | 575 |  |  | March
D-HDH04 | Bartlett Fiber | 2025-03-25 |  |  | Schedule Final Walkout | March
D-HNP141 | Power Connect | 2025-03-25 | 749 |  | 7 Toby Box / 11 Pits | March
D-H0222A | Power Connect | 2025-03-25 | 574 |  | 2 Toby Box / 5 Pits | March
D-H0221A | Brothers | 2025-03-25 | 1383 | 7 Splice | 9 Toby Box | March
D-H0221F | Brothers | 2025-03-25 | 1350 | 8 Splice | 10 Toby Box | March
D-HDH46 | FCA Fiber | 2025-03-25 |  |  |  | March
FB-HDH02A | FCA Fiber | 2025-03-25 |  |  |  | March
D-H0221D | Bartlett Fiber | 2025-03-25 | 630 | 2 Splice | 10 Toby Box | March
FB-HDH275 | HDD Underground | 2025-03-25 |  |  |  | March
D-H0223C | Lightspeed | 2025-03-25 |  | 4 Splices |  | March
D-H0223A | Bartlett Fiber | 2025-03-25 |  |  | Sponging | March
D-H0221C | Bartlett Fiber | 2025-03-25 | 1065 | 5 Splices | 5 Toby Box | March
D-H0222A | US Builders | 2025-03-25 |  |  | Didn't Show On Site | March
D-HDH74 | Bartlett Fiber | 2025-03-25 |  |  | Sponging | March
FB-H0223A | Lightspeed | 2025-03-25 |  | 8 Splices | 4 pits | March
D-HDH76 | J Garcia Underground | 2025-03-25 |  |  | Schedule Final Walkout | March
D-HDH34 | Lightspeed | 2025-03-25 |  |  | Schedule Final Walkout | March
D-H0220B | US Builders | 2025-03-25 | 442 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-25 | 380 |  |  | March
FB-HOE117 | Brothers | 2025-03-25 | 1740 |  |  | March
D-HOE215 | HAS Global | 2025-03-25 | 483 | 1 splice | 1 toby box | March
D-HOE102 | MTX | 2025-03-25 | 1333 |  |  | March
D-HDH69 | Longo Underground | 2025-03-26 | 1972 | 30 Splices | 15 Toby Boxes | March
D-HDH04 | J Garcia Underground | 2025-03-26 |  |  | Schedule Final Walkout | March
D-HNP141 | Power Connect | 2025-03-26 | 713 |  | 5 Toby Boxes / 8 Pits | March
D-H0222A | Power Connect | 2025-03-26 | 545 |  | 11 Pits | March
D-H0221A | Brothers | 2025-03-26 | 1334 | 8 Splices | 9 Toby Boxes | March
D-H0221F | Brothers | 2025-03-26 | 1507 | 8 Splices | 9 Toby Boxes | March
D-HDH46 | FCA Fiber | 2025-03-26 |  |  |  | March
FB-HDH02A | FCA Fiber | 2025-03-26 |  |  |  | March
D-H0221D | Bartlett Fiber | 2025-03-26 | 894 | 4 Splices | 5 Toby Boxes | March
FB-HDH275 | HDD Underground | 2025-03-26 |  |  |  | March
34th St Crossing | Lightspeed | 2025-03-26 |  |  | Moved To Tomorrow | March
D-H0221C | Bartlett Fiber | 2025-03-26 | 825 | 3 Splices | 8 Toby Boxes | March
D-H0222A | US Builders | 2025-03-26 | 159 | 4 Splices | 3 Toby Boxes | March
D-HDH74 | Bartlett Fiber | 2025-03-26 |  |  | Sponging | March
D-H0220B | US Builders | 2025-03-26 | 854 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-26 | 300 |  |  | March
FB-HOE117 | Brothers | 2025-03-26 | 2934 |  | 8 HH / 20 Pits | March
D-HOE215 | HAS Global | 2025-03-26 | 1799 |  | 17 Pits | March
D-HOE102 | MTX | 2025-03-26 | 1701 | 10 Splices | 13 Toby Boxes/ 24 Pits | March
D-HDH69 | Lightspeed | 2025-03-27 | 178 | 10 Splices | 2 Toby Boxes | March
D-H0220B | US Builders | 2025-03-27 | 290 |  |  | March
D-HNP141 | Power Connect | 2025-03-27 |  |  | Crews Dispatched To D-H0222A | March
D-H0222A | Power Connect | 2025-03-27 | 593 |  | 3 Toby Boxes / 10 Pits | March
D-H0221A | Brothers | 2025-03-27 | 1548 | 11 Splices | 10 Toby Boxes | March
D-HDH46 | FCA Fiber | 2025-03-27 | 137 | 40 Splices | 20 Toby Boxes / 1 FDH / 1 HH / 1 Ground Rod | March
FB-HDH02A | FCA Fiber | 2025-03-27 |  |  |  | March
FB-H0222A | Bartlett Fiber | 2025-03-27 | 310 |  |  | March
FB-HDH275 | HDD Underground | 2025-03-27 |  |  |  | March
34th St Crossing | Lightspeed | 2025-03-27 |  |  |  | March
D-H0221C | Bartlett Fiber | 2025-03-27 | 705 | 5 Splices |  | March
D-H0222A | US Builders | 2025-03-27 | 416 | 6 Splices | 3 Toby Boxes / 10 Pits | March
D-HDH74 | Bartlett Fiber | 2025-03-27 |  |  | Moved FDH | March
D-H0221F | Brothers | 2025-03-27 |  |  | Drill Breakdown | March
FB-HDH02A | AMT | 2025-03-27 | 76 |  | 2 Pits | March
BHT-FWP-06 | Lightspeed | 2025-03-27 | 150 |  |  | March
BHT-FWP-07 | Lightspeed | 2025-03-27 | 195 |  |  | March
D-HDH69 | EHL | 2025-03-28 | 266 |  | 2 Pits | March
D-H0220B | US Builders | 2025-03-28 | 673 |  |  | March
D-H0220A | Power Connect | 2025-03-28 |  |  |  | March
D-H0222A | Power Connect | 2025-03-28 |  |  |  | March
D-H0221F | Brothers | 2025-03-28 | 1530 | 11 Toby Boxes | 10 Splices | March
D-H0221F | Brothers | 2025-03-28 | 757 | 7 Splices | 7 Toby Boxes | March
D-HDH46 | FCA Fiber | 2025-03-28 |  |  | Drill Still Broken Down | March
FB-HDH02A | FCA Fiber | 2025-03-28 |  |  |  | March
FB-HDH275 | HDD Underground | 2025-03-28 |  |  | Restoration | March
34th St Crossing | Lightspeed | 2025-03-28 |  |  | Drill Breakdown | March
D-H0222A | US Builders | 2025-03-28 | 200 |  | 1 Pit | March
BHT-FWP-06 | Lightspeed | 2025-03-28 |  |  | 1 Vault | March
302B FDH | Lightspeed | 2025-03-28 |  |  |  | March
FB-HOE117 | Brothers | 2025-03-28 |  |  | Drill Breakdown | March
D-HOE215 | HAS Global | 2025-03-28 |  |  |  | March
FB-HOE117 | MTX | 2025-03-28 | 161 | 8 Splices | 5 Pits | March
D-HOE102 | MTX | 2025-03-28 | 546 | 98 Splices | 15 Toby Boxes / 10 Pits /1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | March
D-HDH69 | EHL | 2025-03-31 | 715 | 10 Splices | 18 Toby Boxes | March
D-H0223A | Bartlett Fiber | 2025-03-31 | 0 |  | Sponging | March
D-H0220A | Power Connect | 2025-03-31 | 1880 | 12 Splices | 4 Toby Boxes | March
D-H0222A | Power Connect | 2025-03-31 | 265 |  | 10 Pits | March
D-H0221F | Brothers | 2025-03-31 | 695 | 4 Splices | 4 Toby Boxes | March
FB-HDH02A | FCA Fiber | 2025-03-31 | 644 |  | 3 Daps | March
D-HNP114 | FCA Fiber | 2025-03-31 | 349 |  | 1 Toby Boxes / 1 Dap | March
D-HDH69 | Lightspeed | 2025-03-31 | 374 | 8 Splices | 4 Toby Boxes | March
D-H0222A | US Builders | 2025-03-31 | 0 |  | Pulled From Project | March
D-HDH67 | Bartlett Fiber | 2025-03-31 | 0 |  | Verifying Pipe | March
D-H0222B | Power Connect | 2025-03-31 | 745 |  | 6 Pits | March
BHT-FWP-07 | Lightspeed | 2025-03-31 | 453 |  |  | March
D-HWP706 | Lightspeed | 2025-03-31 | 1413 |  | 11 Toby Boxes | March
FB-HOE117 | Brothers | 2025-03-31 | 418 |  |  | March
D-HOE215 | HAS Global | 2025-03-31 | 499 |  | 3 Toby Boxes / 5 Pits | March
FB-HOE117 | MTX | 2025-03-31 | 0 |  | Proofing Conduits | March
FB-HOE201 | Brothers | 2025-03-31 | 1355 |  |  | March
BHZD-FOE-03-W | MTX | 2025-03-31 | 2227 |  |  | March
D-HDH69 | EHL | 2025-04-01 |  |  |  | April
D-H0221B | Bartlett Fiber | 2025-04-01 |  |  | Sponging | April
D-H0220A | Power Connect | 2025-04-01 |  |  |  | April
D-H0222A | Power Connect | 2025-04-01 |  |  |  | April
D-HNP114 | FCA Fiber | 2025-04-01 | 952 |  | 6 Toby Boxes | April
D-HDH69 | Lightspeed | 2025-04-01 |  |  |  | April
D-HDH74 | Bartlett Fiber | 2025-04-01 |  |  | Restoration | April
D-HDH32 | MTX | 2025-04-01 |  |  |  | April
BHT-FWP-07 | Lightspeed | 2025-04-01 | 166 |  |  | April
D-HWP706 | Brothers | 2025-04-01 | 1,394 / 10 Toby Boxes |  |  | April
FB-HOE201 | Brothers | 2025-04-01 |  |  | Hit Sewer Main | April
D-HOE215 | HAS Global | 2025-04-01 |  |  |  | April
FB-HOE117 | Lightspeed | 2025-04-01 |  |  |  | April
BHUD-FOE-02-W | MC Logistics | 2025-04-01 | 1149 |  | 3 Pits | April
D-HDH69 | EHL | 2025-04-02 |  |  |  | April
D-H0221B | Bartlett Fiber | 2025-04-02 | 0 |  | Sponging | April
D-H0220A | Power Connect | 2025-04-02 |  |  |  | April
D-H0222A | Power Connect | 2025-04-02 |  |  |  | April
D-HNP114 | FCA Fiber | 2025-04-02 | 952 |  | 6 Toby Boxes | April
D-HDH69 | Lightspeed | 2025-04-02 |  |  |  | April
D-HDH74 | Bartlett Fiber | 2025-04-02 | 0 |  | Restoration | April
D-HDH32 | MTX | 2025-04-02 |  |  |  | April
BHT-FWP-07 | Lightspeed | 2025-04-02 | 166 |  |  | April
D-HWP706 | Brothers | 2025-04-02 | 1394 |  | 10 Toby Boxes | April
FB-HOE201 | Brothers | 2025-04-02 | 0 |  | Hit Sewer Main | April
D-HOE215 | HAS Global | 2025-04-02 |  |  |  | April
FB-HOE117 | Lightspeed | 2025-04-02 |  |  |  | April
BHUD-FOE-02-W | MC Logistics | 2025-04-02 | 1149 |  | 3 Pits | April
D-HDH69 | Lightspeed | 2025-04-03 |  |  | Tie Ins | April
FB-H0221A | Bartlett Fiber | 2025-04-03 | 192 |  |  | April
D-H0220C | Power Connect | 2025-04-03 | 3867 |  | 17 Toby Boxes / 43 Pits / 51 Splices | April
D-HNP114 | FCA Fiber | 2025-04-03 | 1328 |  | 13 Toby Boxes / 31 Splices | April
D-HNP151 | Longo Underground | 2025-04-03 | 313 |  | 3 Toby Boxes / 18 Splices | April
D-HDH32 | MTX | 2025-04-03 | 344 |  | 1 Toby Boxes / 2 Pits / 24 Splices | April
D-HDH82 | MTX | 2025-04-03 | 1265 |  | 10 Toby Boxes / 20 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | April
BHT-FWP-07 | Lightspeed | 2025-04-03 | 302 |  | 1 Pit | April
D-HWP707 | Brothers | 2025-04-03 | 1334 |  | 8 Toby Boxes / 12 Pits / 14 Dap Splices | April
D-HWP702 | Brothers | 2025-04-03 | 1970 |  | 16 Toby Boxes / 1HH | April
FB-HOE201 | Brothers | 2025-04-03 |  |  | On Hold | April
D-HOE206 | HAS Global | 2025-04-03 |  |  | On Hold | April
FB-HOE117 | Lightspeed | 2025-04-03 |  |  | On Hold | April
BHUD-FOE-02-W | MC Logistics | 2025-04-03 |  |  | On Hold | April
D-H0222A | Longo Underground | 2025-04-04 | 635 |  | 5 Toby Boxes / 10 Splices | April
D-H0221D | Bartlett Fiber | 2025-04-04 |  |  | 3 Splices | April
D-H0220C | Power Connect | 2025-04-04 | 594 |  | 5 Toby Boxes / 7 Pits / 9 Splices | April
D-H0222A | Power Connect | 2025-04-04 |  |  | Job Re-Assigned To Longo Underground | April
D-HDH03 | Power Connect | 2025-04-04 |  |  | Drill Breakdown | April
D-HNP114 | FCA Fiber | 2025-04-04 | 397 |  | 3 Toby Boxes / 20 Splices | April
D-HDH80 | MTX | 2025-04-04 | 2144 |  | 19 Toby Boxes / 19 Pits / 47 Splices | April
BHT-FWP-06 | Lightspeed | 2025-04-04 |  |  | 1 HH | April
BHT-FWP-07 | Lightspeed | 2025-04-04 |  |  | 1 HH | April
FB-HOE201 | Brothers | 2025-04-04 |  |  | On Hold | April
D-HOE206 | HAS Global | 2025-04-04 |  |  | On Hold | April
FB-HOE117 | Lightspeed | 2025-04-04 |  |  | On Hold | April
BHUD-FOE-02-W | MC Logistics | 2025-04-04 |  |  | On Hold | April
D-HWP702 | Brothers | 2025-04-07 |  |  | 1 HH / 1 Swing Arm / 1 FDH / 1 Ground Rod | April
D-HDH80 | MTX | 2025-04-07 | 990 |  | 6 Pits | April
D-H0220C | Power Connect | 2025-04-07 | 367 |  | 5 Toby Boxes / 5 Pits / 30 Splices | April
D-H0221D | Bartlett Fiber | 2025-04-07 | 132 |  |  | April
FB-HDH02A | Bartlett Fiber | 2025-04-07 | 370 |  |  | April
D-HNP113 | HDD Underground | 2025-04-07 | 590 |  |  | April
BHU-FDH-01-W | Lightspeed | 2025-04-07 | 198 | 198 | 2 HH | April
FB-HDH02A | Lightspeed | 2025-04-07 | 180 |  | 3 HH | April
FB-HDH275 | HDD Underground | 2025-04-07 |  | 5575 | 7,497 Tracer Wire / 1 HH | April
BHT-FWP-07 | Lightspeed | 2025-04-07 | 43 |  |  | April
D-HWP707 | Brothers | 2025-04-07 | 618 |  | 3 Toby Boxes / 2 Pits / 3 Splices / 1 HH | April
D-HWP703 | Brothers | 2025-04-07 | 1840 |  | 14 Toby Boxes | April
D-HDH80 | MTX | 2025-04-08 | 1871 |  | 9 Toby Boxes / 20 Pits / 7 Splices | April
D-HNP113 | HDD Underground | 2025-04-08 | 343 |  |  | April
FB-HDH275 | FCA Fiber | 2025-04-08 |  | 2372 |  | April
BHT-FWP-06 | Lightspeed | 2025-04-08 | 45 |  |  | April
D-HWP707 | Brothers | 2025-04-08 | 700 |  | 5 Toby Boxes | April
D-HWP703 | Brothers | 2025-04-08 | 1520 |  | 14 Toby Boxes | April
FB-HWP701 | Brothers | 2025-04-08 | 150 |  |  | April
FB-HOE201 | Brothers | 2025-04-08 |  |  | On Hold | April
D-HOE206 | HAS Global | 2025-04-08 |  |  | On Hold | April
FB-HOE117 | Lightspeed | 2025-04-08 |  |  | On Hold | April
BHUD-FOE-02-W | MC Logistics | 2025-04-08 |  |  | On Hold | April
D-HDH80 | MTX | 2025-04-09 | 1307 |  | 14 Toby Boxes / 9 Pits / 73 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | April
D-H0220C | Power Connect | 2025-04-09 |  |  | 4 Toby Boxes / 1 Pits / 135 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | April
D-HDH47 | Bartlett Fiber | 2025-04-09 | 1376 |  | 9 Toby Boxes / 9 Splices | April
D-HDH43 | US Builders | 2025-04-09 | 617 |  |  | April
BHT-FWP-06 | Lightspeed | 2025-04-09 |  |  | 1 HH | April
D-HWP703 | Brothers | 2025-04-09 | 2060 |  | 14 Toby Boxes | April
FB-HWP701 | Lightspeed | 2025-04-09 | 295 |  |  | April
FB-HOE201 | Brothers | 2025-04-09 |  |  | On Hold | April
D-HOE206 | HAS Global | 2025-04-09 |  |  | On Hold | April
FB-HOE117 | Lightspeed | 2025-04-09 |  |  | On Hold | April
BHUD-FOE-02-W | MC Logistics | 2025-04-09 |  |  | On Hold | April
D-HDH80 | MTX | 2025-04-10 |  |  | Restoration | April
D-HDH82 | MTX | 2025-04-10 |  |  | Restoration | April
D-HDH47 | Bartlett Fiber | 2025-04-10 | 875 |  | 8 Toby Boxes / 25 Splices | April
D-HDH60 | US Builders | 2025-04-10 | 711 |  | 2 Toby Boxes / 3 Splices | April
D-HDH43 | Longo Underground | 2025-04-10 | 627 |  |  | April
FB-HDH02A | Lightspeed | 2025-04-10 | 426 | 360 | 360 Tracer Wire | April
FB-HWP701 | Lightspeed | 2025-04-10 | 504 |  |  | April
D-HWP703 | Brothers | 2025-04-10 | 1330 |  | 7 Toby Boxes / 10 Pits / 52 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | April
D-HDH43 | US Builders | 2025-04-11 | 431 |  |  | April
D-HDH47 | Bartlett Fiber | 2025-04-11 | 1301 |  | 9 Toby Boxes / 18 Splices | April
D-HDH60 | Longo Underground | 2025-04-11 | 695 |  | 7 Toby Boxes / 10 Splices | April
D-HDH80 | MTX | 2025-04-11 |  |  | Restoration | April
D-HDH32 | MTX | 2025-04-11 |  |  | Restoration | April
D-H0220C | Power Connect | 2025-04-11 |  |  | 5 Toby Boxes / 1 FDH | April
D-HNP141 | Power Connect | 2025-04-11 |  |  | 4 Toby Boxes / 1 FDH | April
D-H0220B | Bartlett Fiber | 2025-04-11 | 314 |  |  | April
BHT-FWP-07 | Lightspeed | 2025-04-11 |  | 1275 | 1.275 Tracer Wire | April
D-HWP703 | Lightspeed | 2025-04-11 |  |  | Sponging / Restortion | April
FB-HWP701 | Brothers | 2025-04-11 |  | 899 | 899 Tracer Wire | April
D-HDH43 | US Builders | 2025-04-14 | 276 |  |  | April
D-HDH47 | Bartlett Fiber | 2025-04-14 |  |  | Drill Breakdown--No Production | April
D-HDH49 | Brothers | 2025-04-14 | 1335 |  | 10 Toby Boxes | April
D-HDH58 | Brothers | 2025-04-14 |  |  |  | April
D-HDH60 | Longo Underground | 2025-04-14 | 796 |  | 9 Toby Boxes / 24 Splices | April
D-HDH62 | US Builders | 2025-04-14 | 547 |  |  | April
D-H0220C | Power Connect | 2025-04-14 |  |  |  | April
D-HNP141 | Power Connect | 2025-04-14 |  |  |  | April
BHT-FWP-06 | Lightspeed | 2025-04-14 |  |  | No Production | April
D-HWP1306 | Lightspeed | 2025-04-14 | 259 |  |  | April
D-HDH43 | US Builders | 2025-04-15 | 779 |  | 4 Toby Boxes / 8 Splices | April
D-HDH47 | Bartlett Fiber | 2025-04-15 | 1018 |  | 8 Toby Boxes / 34 Splices | April
D-HDH49 | Brothers | 2025-04-15 | 1133 |  | 8 Toby Boxes / 48 Splices | April
D-HDH58 | Brothers | 2025-04-15 | 1526 |  | 9 Toby Boxes / 30 Splices | April
D-HDH60 | Longo Underground | 2025-04-15 | 1929 |  | 15 Toby Boxes / 60 Splices | April
D-HDH62 | US Builders | 2025-04-15 | 845 |  |  | April
FB-HDH02A | Lightspeed | 2025-04-15 | 561 |  |  | April
D-H0220C | Power Connect | 2025-04-15 |  |  | Toby Boxes / Restoration | April
D-HNP141 | Power Connect | 2025-04-15 |  |  | Toby Boxes / Restoration | April
D-HDH73 | Power Connect | 2025-04-15 |  |  | Restoration | April
BHT-FWP-06 | Lightspeed | 2025-04-15 | 37 |  |  | April
D-HWP1306 | Lightspeed | 2025-04-15 | 243 |  | 2 Pits | April
D-HDH41 | MTX | 2025-04-15 | 1538 |  | 13 Toby Boxes / 7 Pits / 30 Splices | April
D-HDH04 | Bartlett Fiber | 2025-04-16 |  |  | Toby Box Relocation | April
D-HDH41 | MTX | 2025-04-16 | 2713 |  | 20 Toby Boxes / 16 Pits / 62 Splices | April
D-HDH43 | US Builders | 2025-04-16 | 868 |  | 7 Toby Boxes / 13 Splices | April
D-HDH49 | Brothers | 2025-04-16 | 1624 |  | 11 Toby Boxes / 42 Splices | April
D-HDH58 | Brothers | 2025-04-16 | 1503 |  | 10 Toby Boxes / 46 Splices | April
D-HDH60 | Longo Underground | 2025-04-16 | 876 |  | 4 Toby Boxes / 7 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH62 | US Builders | 2025-04-16 | 400 |  |  | April
FB-HDH02A | Lightspeed | 2025-04-16 | 260 |  | 2 Pits / 10 Splices | April
D-HDH75 | Longo Underground | 2025-04-16 | 173 |  |  | April
D-HDH67 | Power Connect | 2025-04-16 |  |  | Restoration | April
D-HDH73 | Power Connect | 2025-04-16 |  |  | Restoration | April
D-HDH70 | Longo Underground | 2025-04-16 |  |  | Restoration | April
BHT-FWP-06 | Lightspeed | 2025-04-16 | 115 |  | 3 HH | April
D-HWP1306 | Lightspeed | 2025-04-16 |  |  | Drill Breakdown | April
D-HDH41 | MTX | 2025-04-17 | 862 |  | 6 Toby Boxes / 3 Pits / 6 Splices | April
D-HDH43 | US Builders | 2025-04-17 | 338 |  | 6 Toby Boxes / 2 Splices | April
D-HDH47 | Bartlett Fiber | 2025-04-17 | 569 |  | 5 Toby Boxes / 6 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH49 | Brothers | 2025-04-17 |  |  | Crew Re-Located To Lakeland | April
D-HDH58 | Brothers | 2025-04-17 | 1590 |  | 11 Toby Boxes | April
D-HDH60 | Longo Underground | 2025-04-17 | 651 |  | 6 Toby Boxes / 8 Splices | April
D-HDH62 | US Builders | 2025-04-17 | 906 |  |  | April
FB-HDH02A | Lightspeed | 2025-04-17 | 40 |  |  | April
D-H0223F | Lightspeed | 2025-04-17 | 96 |  | 3 Pits / 24 Splices--Frontier Damage Completed. | April
D-HDH69 | Longo Underground | 2025-04-17 | 433 |  | 4 Toby Boxes / 8 Splices | April
D-HWP1309 | Brothers | 2025-04-17 | 647 |  | 6 Toby Boxes | April
D-HWP1306 | Lightspeed | 2025-04-17 | 193 |  | 2 Toby Boxes | April
D-HDH41 | MTX | 2025-04-18 | 1507 |  | 9 Toby Boxes / 2 Pits / 35 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH43 | US Builders | 2025-04-18 | 26 |  | 12 Toby Boxes / 26 Splices | April
D-HDH47 | Bartlett Fiber | 2025-04-18 |  |  | Crew Re-Located To Another Project | April
D-HDH49 | Brothers | 2025-04-18 | 350 |  | 2 Toby Boxes | April
D-HDH58 | Brothers | 2025-04-18 | 370 |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | April
D-HDH48 | Bartlett Fiber | 2025-04-18 | 706 |  | 3 Toby Boxes | April
D-HDH62 | US Builders | 2025-04-18 | 198 |  | 4 Toby Boxes / 17 Splices | April
FB-HDH02A | Lightspeed | 2025-04-18 |  | 6350 | 6,350 Tracer Wire | April
FB-HDH02A | Lightspeed | 2025-04-18 | 408 |  | 4 Pits / 4 Splices | April
D-H0220C | Power Connect | 2025-04-18 |  |  | Restoration | April
D-HDH73 | Power Connect | 2025-04-18 |  |  | Restoration-QC Walk | April
FX4-FWP-13 | Brothers | 2025-04-18 |  |  | Concrete | April
BHT-FWP-07 | Lightspeed | 2025-04-18 |  |  | Restoration | April
D-HDH42 | FCA Fiber | 2025-04-21 |  |  | No Production--Issue With Locates | April
D-HDH43 | US Builders | 2025-04-21 |  |  | Toby boxes | April
D-HDH48 | Bartlett Fiber | 2025-04-21 |  |  | No Production--Issue With Locates | April
D-HDH49 | Brothers | 2025-04-21 | 1050 |  | 9 Toby Boxes / 22 Splices | April
D-HDH55 | HAS Global | 2025-04-21 | 621 |  |  | April
D-HDH56 | Longo Underground | 2025-04-21 | 1285 |  | 9 Toby Boxes / 36 Splices | April
D-HDH58 | Brothers | 2025-04-21 |  |  | Restoration-In-House QC Walk | April
D-HDH60 | Longo Underground | 2025-04-21 |  |  | Proofing Conduits | April
D-HDH62 | US Builders | 2025-04-21 |  |  | No Production | April
D-HDH67 | Power Connect | 2025-04-21 |  |  | Restoration | April
D-HNP141 | Power Connect | 2025-04-21 |  |  | Restoration | April
D-HWP1306 | Lightspeed | 2025-04-21 |  |  | No Production | April
D-HDH42 | FCA Fiber | 2025-04-22 |  |  |  | April
D-HDH43 | US Builders | 2025-04-22 |  |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH48 | Bartlett Fiber | 2025-04-22 | 1701 |  | 12 Toby Boxes / 49 Splices | April
D-HDH55 | HAS Global | 2025-04-22 | 464 |  | 6 Toby Boxes / 3 Pits / 22 Splices | April
D-HDH56 | Longo Underground | 2025-04-22 | 951 |  | 11 Toby Boxes / 20 Splices | April
D-HDH57 | MTX | 2025-04-22 | 1864 |  | 13 Toby Boxes / 13 Splices | April
D-HDH62 | US Builders | 2025-04-22 |  |  | No Production | April
D-HDH75 | Longo Underground | 2025-04-22 |  |  | Sponging | April
FB-HDH02A | Lightspeed | 2025-04-22 | 205 |  | 2 Pits / 4 Splices | April
D-HNP141 | Power Connect | 2025-04-22 |  |  | ABF Testing / Restoration | April
D-HWP1306 | Lightspeed | 2025-04-22 | 510 |  | 5 Toby Boxes / 4 Pits / 14 Splices | April
D-HWP1309 | Brothers | 2025-04-22 | 932 |  | 6 Toby Boxes | April
FX4-FWP-13 | Brothers | 2025-04-22 | 23 |  | 1 Vault / 1 Cabinet / 6 Ground Rods | April
D-HDH03 | Lightspeed | 2025-04-23 | 113 |  | 4 Pits / 48 Splices | April
D-HDH42 | FCA Fiber | 2025-04-23 | 2348 |  | 21 Toby Boxes / 15 Pits / 43 Splices | April
D-HDH43 | US Builders | 2025-04-23 |  |  | Sponging | April
D-HDH48 | Bartlett Fiber | 2025-04-23 | 314 |  | 4 Toby Boxes | April
D-HDH52 | MTX | 2025-04-23 |  |  | Crew Will Be Starting Tomorrow | April
D-HDH55 | HAS Global | 2025-04-23 |  |  | No Report | April
D-HDH56 | Longo Underground | 2025-04-23 | 1598 |  |  | April
D-HDH57 | MTX | 2025-04-23 | 1514 |  | 7 Toby Boxes / 8 Pits / 31 Splices | April
FB-HDH02A | Lightspeed | 2025-04-23 | 190 |  | 2 Pits / 2 Splices | April
D-H0222B | Power Connect | 2025-04-23 |  |  | Toby Boxes / Restoration
D-HNP141 | Power Connect | 2025-04-23 |  |  | ABF Testing / Restoration
D-HWP1306 | Lightspeed | 2025-04-23 | 275 |  | 2 Toby Boxes | April
D-HWP1309 | Brothers | 2025-04-23 | 1190 |  | 6 Toby Boxes / 1 HH | April
D-HDH42 | FCA Fiber | 2025-04-24 | 1378 |  | 14 Toby Boxes / 7 Pits / 20 Splices | April
D-HDH48 | Bartlett Fiber | 2025-04-24 | 662 |  | 8 Toby Boxes / 4 Splices | April
D-HDH52 | MTX | 2025-04-24 | 988 |  | 6 Toby Boxes / 6 Pits / 15 Splices | April
D-HDH54 | HAS Global | 2025-04-24 | 588 |  | 3 Toby Boxes / 20 Splices | April
D-HDH55 | HAS Global | 2025-04-24 |  |  | Project Shutdown | April
D-HDH56 | Longo Underground | 2025-04-24 | 1671 |  | 15 Toby Boxes / 36 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH57 | MTX | 2025-04-24 | 1095 |  | 10 Toby Boxes / 8 Pits / 39 Splices | April
D-HDH62 | US Builders | 2025-04-24 | 64 |  | 20 Toby Boxes / 53 Splices | April
FB-HDH02A | Lightspeed | 2025-04-24 | 48 |  | 2 Pits / 2 Splices | April
D-H0222B | Power Connect | 2025-04-24 |  |  | 3 Toby Boxes / 6 Splices | April
FB-H0223A | Power Connect | 2025-04-24 |  |  | Crew Did Not Work On This Project Today | April
BHT-FWP-06 | Lightspeed | 2025-04-24 |  | 2815 | 2,815 Tracer Wire | April
D-HWP1309 | Brothers | 2025-04-24 | 909 |  | 8 Toby Boxes | April
D-HDH42 | FCA Fiber | 2025-04-25 | 726 |  | 6 Toby Boxes / 6 Pits / 6 Splices | April
D-HDH48 | Bartlett Fiber | 2025-04-25 | 728 |  | 5 Toby Boxes / 13 Splices | April
D-HDH50 | FCA Fiber | 2025-04-25 | 1108 |  | 12 Toby Boxes / 7 Pits / 8 Splices | April
D-HDH52 | MTX | 2025-04-25 |  |  | Crew Shutdown By Tillman | April
D-HDH54 | HAS Global | 2025-04-25 | 431 |  | 5 Toby Boxes / 11 Splices | April
D-HDH53 | Longo Underground | 2025-04-25 | 385 |  | 4 Toby Boxes / 8 Splices | April
D-HDH57 | MTX | 2025-04-25 |  |  | Crew Shutdown By Tillman | April
D-HDH60 | Longo Underground | 2025-04-25 |  |  | Restoration | April
D-HDH62 | US Builders | 2025-04-25 | 21 |  | 11 Toby Boxes / 34 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
FB-HDH02A | Lightspeed | 2025-04-25 | 150 |  |  | April
BHT-FWP-06 | Lightspeed | 2025-04-25 |  |  | Restoration | April
FX4-FWP-13 | Brothers | 2025-04-25 |  |  | Bollards | April
D-HDH42 | FCA Fiber | 2025-04-28 | 1602 |  | 12 Toby Boxes / 8 Pits / 30 Splices | April
D-HDH48 | Bartlett Fiber | 2025-04-28 | 961 |  | 9 Toby Boxes / 28 Splices | April
D-HDH50 | FCA Fiber | 2025-04-28 |  |  | Crew Will Be Starting Tomorrow | April
D-HDH52 | Lightspeed | 2025-04-28 |  |  |  | April
D-HDH53 | Longo Underground | 2025-04-28 | 813 |  | 7 Toby Boxes / 6 Splices | April
D-HDH54 | HAS Global | 2025-04-28 | 1936 |  | 14 Toby Boxes / 62 Splices | April
FB-HDH02A | Lightspeed | 2025-04-28 | 423 |  | 4 Pits / 6 Splices | April
BHT-FWP-06 | Lightspeed | 2025-04-28 |  |  | Restoration | April
D-HWP-1304 | Brothers | 2025-04-28 | 1216 |  | 11 Toby Boxes | April
D-HDH42 | FCA Fiber | 2025-04-29 |  |  | FDH / ABF Testing | April
D-HDH48 | Bartlett Fiber | 2025-04-29 | 370 |  | 4 Toby Boxes / 4 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH50 | FCA Fiber | 2025-04-29 | 440 |  | 2 Toby Boxes / 3 Pits / 23 Splices | April
D-HDH52 | Lightspeed | 2025-04-29 | 608 |  | 3 Toby Boxes / 5 Splices | April
D-HDH53 | Longo Underground | 2025-04-29 | 1597 |  | 13 Toby Boxes / 46 Splices | April
D-HDH54 | HAS Global | 2025-04-29 | 2103 |  | 13 Toby Boxes / 39 Splices | April
D-HWP1306 | Lightspeed | 2025-04-29 | 242 |  |  | April
D-HWP1304 | Brothers | 2025-04-29 | 1520 |  | 10 Toby Boxes | April
D-HWP1309 | Brothers | 2025-04-29 | 470 |  | 4 Toby Boxes | April
D-HWP903 | Brothers | 2025-04-29 | 1190 |  | 10 Toby Boxes | April
D-HDH62 | US Builders | 2025-04-30 |  |  | Restoration | April
D-HDH50 | FCA Fiber | 2025-04-30 | 1175 |  | 9 Toby Boxes / 7 Pits / 30 Splices | April
D-HDH52 | Lightspeed | 2025-04-30 | 609 |  | 4 Toby Boxes / 31 Splices | April
D-HDH53 | Longo Underground | 2025-04-30 | 1632 |  | 11 Toby Boxes / 28 Splices | April
D-HDH54 | HAS Global | 2025-04-30 | 1498 |  | 9 Toby Boxes / 34 Splices | April
D-HDH57 | Bartlett Fiber | 2025-04-30 | 594 |  | 7 Toby Boxes / 24 Splices | April
FB-HDH02A | FCA Fiber | 2025-04-30 |  |  | Crew Did Not Work This Location Today | April
D-HWP1306 | Lightspeed | 2025-04-30 | 310 |  |  | April
D-HWP1304 | Brothers | 2025-04-30 | 1216 |  | 13 Toby Boxes | April
D-HWP903 | Brothers | 2025-04-30 | 1033 |  | 8 Toby Boxes / 10 Pits / 26 Splices / 1 Flower Pot | April
D-HDH62 | US Builders | 2025-05-01 |  |  | Restoration | May
D-HDH42 | FCA Fiber | 2025-05-01 |  |  | Crew Did Not Work This Location Today
D-HDH50 | FCA Fiber | 2025-05-01 | 822 |  | 7 Toby Boxes / 3 Pits / 7 Splices | May
D-HDH52 | Lightspeed | 2025-05-01 | 614 |  | 4 Toby Boxes / 7 Splices | May
D-HDH53 | Longo Underground | 2025-05-01 | 692 |  | 7 Toby Boxes / 22 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
D-HDH54 | HAS Global | 2025-05-01 | 229 |  | 1 Toby Boxes / 2 Splices | May
D-HDH57 | FCA Fiber | 2025-05-01 |  |  | Crew Did Not Work This Location Today | May
FB-HDH02A | FCA Fiber | 2025-05-01 |  |  | Crew Did Not Work This Location Today | May
D-HWP1306 | Lightspeed | 2025-05-01 | 302 |  |  | May
D-HWP1304 | Brothers | 2025-05-01 | 1098 |  | 9 Toby Boxes / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
D-HWP903 | Brothers | 2025-05-01 | 1031 |  | 9 Toby Boxes / 6 Pits / 4 Splices | May
D-HDH50 | FCA Fiber | 2025-05-02 | 1020 |  | 10 Toby Boxes / 2 Pits / 46 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
D-HDH52 | Lightspeed | 2025-05-02 |  |  | Crew Did Not Work This Location Today | May
FB-HDH02A | FCA Fiber | 2025-05-02 |  |  | Crew Did Not Work This Location Today | May
D-HNP151 | Longo Underground | 2025-05-02 | 1367 |  | 10 Toby Boxes / 31 Splices | May
D-HDH47 | Bartlett Fiber | 2025-05-02 |  |  | Restoration | May
D-HDH54 | HAS Global | 2025-05-02 |  |  | Proofing / Sponging | May
BHT-FWP-06 | Lightspeed | 2025-05-02 |  |  | Restoration | May
D-HDH52 | Lightspeed | 2025-05-05 | 404 |  | 4 Toby Boxes | May
D-HNP144 | FCA Fiber | 2025-05-05 | 640 |  | 5 Toby Boxes / 4 Pits / 22 Splices | May
FB-HNP111 | FCA Fiber | 2025-05-05 |  |  | Crew Did Not Start This Location | May
FB-H0221A | Lightspeed | 2025-05-05 |  | 636 | 636 48Ct Fiber Cable | May
D-HDH47 | Bartlett Fiber | 2025-05-05 |  |  | Restoration / QC | May
D-HDH54 | HAS Global | 2025-05-05 |  |  | ABF Proofing | May
D-HWP1306 | Lightspeed | 2025-05-05 | 610 |  | 4 Toby Boxes | May
D-HWP903 | Brothers | 2025-05-05 | 1053 |  | 10 Toby Boxes / 4 Pits / 7 Splices | May
D-HWP904 | Brothers | 2025-05-05 | 575 |  | 8 Toby Boxes / 4 Pits / 9 Splices | May
D-HWP1309 | Brothers | 2025-05-05 |  |  | FDH | May
D-HDH52 | Lightspeed | 2025-05-06 | 158 |  | 1 Toby Box / 2 Splices | May
FB-HDH02A | Lightspeed | 2025-05-06 | 155 |  | 4 Splices | May
FB-HDH02A | FCA Fiber | 2025-05-06 | 165
D-HNP144 | FCA Fiber | 2025-05-06 | 490 |  | 4 Toby Boxes / 2 Pits / 6 Splices | May
FB-HNP111 | FCA Fiber | 2025-05-06 |  |  | Crew Did Not Start This Location Today | May
D-HNP151 | Longo Underground | 2025-05-06 | 424 |  | 4 Toby Boxes / 9 Splices | May
D-HDH54 | HAS Global | 2025-05-06 |  |  | ABF Proofing / FDH Placing | May
D-HWP1306 | Lightspeed | 2025-05-06 | 451 |  |  | May
D-HWP903 | Brothers | 2025-05-06 | 812 |  | 10 Toby Boxes / 8 Pits / 32 Splices | May
D-HWP904 | Brothers | 2025-05-06 | 1847 |  | 12 Toby Boxes / 7 Pits / 36 Splices | May
D-HWP902 | Brothers | 2025-05-06 | 565 |  | 5 Toby Boxes | May
D-HDH52 | Lightspeed | 2025-05-07 | 353 |  | 4 Toby Boxes | May
D-H0222A | Lightspeed | 2025-05-07 | 131 |  | 1 Toby Box
D-HNP106 | Power Connect | 2025-05-07 | 592 |  | 6 Toby Boxes / 6 Pits | May
D-HNP144 | FCA Fiber | 2025-05-07 | 127 |  | 1 Toby Box / 1 Pit / 2 Splices | May
D-HNP117 | FCA Fiber | 2025-05-07 | 645 |  | 2 Toby Boxes / 2 Pits | May
D-HDH54 | HAS Global | 2025-05-07 |  |  | ABF Proofing / FDH Placing | May
D-HDH49 | Lightspeed | 2025-05-07 |  |  | Restoration
D-HWP1306 | Lightspeed | 2025-05-07 | 802 |  | 3 Toby Boxes | May
D-HWP904 | Brothers | 2025-05-07 | 1052 |  | 11 Toby Boxes / 7 Pits / 16 Splices | May
D-HWP902 | Brothers | 2025-05-07 | 1935 |  | 16 Toby Boxes / 15 Pits / 49 Splices | May
D-HDH52 | Lightspeed | 2025-05-08 | 40 |  | 1 Toby Box | May
D-HNP104 | Longo Underground | 2025-05-08 | 616 |  | 3 Toby Boxes / 8 Splices | May
D-HNP106 | Power Connect | 2025-05-08 | 592 |  | 6 Toby Boxes | May
D-HNP113 | Bartlett Fiber | 2025-05-08 | 468 |  |  | May
D-HNP117 | FCA Fiber | 2025-05-08 | 853 |  | 7 Toby Boxes / 2 Pits / 18 Splices | May
FB-HNP144 | Lightspeed | 2025-05-08 | 225 |  |  | May
D-HDH49 | Lightspeed | 2025-05-08 |  |  | Restoration | May
D-HDH54 | HAS Global | 2025-05-08 |  |  | ABF Proofing / FDH Placing | May
D-HWP1306 | Lightspeed | 2025-05-08 | 75 |  | 6 Toby Boxes | May
D-HWP902 | Brothers | 2025-05-08 | 1483 |  | 8 Toby Boxes / 8 Pits / 16 Splices | May
D-HWP904 | Brothers | 2025-05-08 | 1846 |  | 16 Toby Boxes / 10 Pits / 74 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
D-HDH42 | FCA Fiber | 2025-05-09 |  |  | 1 FDH / 1 Swing Arm / 1 HH 1 Ground Rod / ABF Testing | May
D-HDH52 | Lightspeed | 2025-05-09 | 153 |  | 4 Splices | May
D-HNP104 | Longo Underground | 2025-05-09 | 900 |  | 7 Toby Boxes / 22 Splices | May
D-HNP106 | Power Connect | 2025-05-09 | 730 |  | 6 Toby Boxes / 10 Pits | May
D-HNP113 | Bartlett Fiber | 2025-05-09 | 940 |  |  | May
D-HNP117 | FCA Fiber | 2025-05-09 |  |  | Locate Issue--Crew Could Not Work On This Project Today | May
D-HWP1306 | Lightspeed | 2025-05-09 |  |  | Restoration | May
D-HWP903 | Brothers | 2025-05-09 |  |  | 1 FDH / 1 Swing Arm / 1 HH 1 Ground Rod | May
|  | 2025-05-12 |  |  |  | May
D-HNP104 | Longo Underground | 2025-05-13 | 212 |  |  | May
D-HNP117 | FCA Fiber | 2025-05-13 |  |  | Locate Issue Crew Did Not Work This Location Today | May
D-H0222A | Lightspeed | 2025-05-13 | 55 |  | 1 Toby Box / 4 Splices | May
FB-HDH02A | Lightspeed | 2025-05-13 |  |  | Conduit Splicing | May
FB-HDH02A | Lightspeed | 2025-05-13 |  |  | Conduit Splicing | May
D-H0223F | Lightspeed | 2025-05-13 | 30 |  | 7 Splices--Maintenance Project | May
D-HWP1306 | Lightspeed | 2025-05-13 | 251 |  | 3 Toby Boxes | May
D-HWP902 | Brothers | 2025-05-13 | 933 |  | 5 Toby Boxes / 5 Pits / 8 Splices | May
FB-HOE201 | Power Connect | 2025-05-13 | 385 |  |  | May
FB-HNP133 | Lightspeed | 2025-05-14 | 153 |  |  | May
D-H0221C | Bartlett Fiber | 2025-05-14 |  |  | Vac Breakdown--No Production | May
D-H0222A / D-H0233F | Lightspeed | 2025-05-14 |  |  | Proofing Conduits | May
HGP16 / HGP38 | Lightspeed | 2025-05-14 |  |  | Repair Work | May
D-HWP1306 | Lightspeed | 2025-05-14 | 424 |  | 3 Toby Boxes | May
FB-HWP701 | Brothers | 2025-05-14 | 1190 |  | 1 HH | May
FB-HOE201 | Power Connect | 2025-05-14 | 678 |  |  | May
D-H0221C | Bartlett Fiber | 2025-05-15 |  |  | Crew Did Not Work This Location Today | May
D-HNP104 | Longo Underground | 2025-05-15 | 1316 |  | 12 Toby Boxes / 43 Splices | May
D-HNP135 | Lightspeed | 2025-05-15 | 201 |  |  | May
D-HDH57 | Lightspeed | 2025-05-15 | 85 |  | 2 Toby Boxes / 3 Splices | May
D-HDH55 | Has Global | 2025-05-15 | 1342 |  | 8 Toby Boxes / 29 Splices | May
D-HWP1306 | Lightspeed | 2025-05-15 | 497 |  | 4 Toby Boxes | May
BHT-FWP-10 | Brothers | 2025-05-15 | 1580 |  | 1 HH | May
FB-HOE201 | Power Connect | 2025-05-15 | 381 |  |  | May
D-H0221C | Bartlett Fiber | 2025-05-16 | 887 |  | 8 Toby Boxes / 34 Splices | May
D-HNP104 | Longo Underground | 2025-05-16 | 1232 |  | 10 Toby Boxes / 37 Splices | May
D-HNP135 | Lightspeed | 2025-05-16 | 30 |  |  | May
D-HDH55 | HAS Global | 2025-05-16 | 1484 |  | 8 Toby Boxes / 32 Splices | May
D-HDH02 | Lightspeed | 2025-05-16 | 151 |  | 48 Splices | May
D-HWP1306 | Lightspeed | 2025-05-16 |  |  | FDH/Restoration | May
FB-HOE201 | Power Connect | 2025-05-16 |  |  | No Crews Working Today In Market 3 | May
D-H0222B | Lightspeed | 2025-05-19 | 301 |  | 48 Splices | May
D-HDH53 | Longo Underground | 2025-05-19 |  |  | ABF proofing | May
D-HDH55 | HAS Global | 2025-05-19 | 1280 |  | 7 Toby Boxes / 30 Splices | May
D-HNP104 | Longo Underground | 2025-05-19 | 1156 |  | 7 Toby Boxes / 15 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
D-HNP123 | Lightspeed | 2025-05-19 | 54 |  | 1 Toby Box / 14 Splices | May
D-HWP1306 | Lightspeed | 2025-05-19 | 286 |  | 3 Toby Boxes | May
BHT-FWP-10 | Brothers | 2025-05-19 | 270 |  | 2 HH | May
FB-HWP801 | Brothers | 2025-05-19 | 644 |  |  | May
FB-HOE201 | Power Connect | 2025-05-19 | 605 |  |  | May
D-HDH55 | HAS Global | 2025-05-20 | 1029 |  | 11 Toby Boxes / 22 Splices | May
D-HNP104 | Longo Underground | 2025-05-20 | 947 |  | 7 Toby Boxes / 22 Splices | May
D-HNP123 | Lightspeed | 2025-05-20 | 101 |  |  | May
D-H0220B | Longo Underground | 2025-05-20 |  |  | No Report | May
D-H0222B | Lightspeed | 2025-05-20 | 191 |  | 4 Splices | May
D-H0221C | Lightspeed | 2025-05-20 |  |  | Crew Completed Cross Trenching | May
D-HWP1306 | Lightspeed | 2025-05-20 | 226 |  | 5 Toby Boxes | May
FB-HWP801 | Brothers | 2025-05-20 | 1430 |  | 3 HH | May
D-H0220B | Longo Underground | 2025-05-21 | 999 |  | 8 Toby Boxes / 66 Splices | May
D-HDH57 | Lightspeed | 2025-05-21 | 181 |  |  | May
D-H0221C | Lightspeed | 2025-05-21 |  |  | Crew Did Not Work On This Location Today | May
D-H0222A | Lightspeed | 2025-05-21 |  |  | Did Not Receive A Report | May
D-HWP1306 | Lightspeed | 2025-05-21 |  |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
FB-HWP701 | Brothers | 2025-05-21 | 678 | 2850 | 2 HH / 2 Ground Rods / 2,850' 48Ct Fiber Cable / 1,796 Tracer Wire / 1,796 Mule Tape | May
FB-HWP801 | Brothers | 2025-05-21 | 970 |  | 1 HH | May
FB-HOE201 | Power Connect | 2025-05-21 | 600 |  |  | May
D-HOE116 | Power Connect | 2025-05-21 |  |  | Spliced Conduits For Continuity | May
D-DHD52 | Lightspeed | 2025-05-22 | 260 |  |  | May
D-DHD55 | HAS Global | 2025-05-22 |  |  | ABF Proofing / Restoration | May
D-HWP1306 | Lightspeed | 2025-05-22 |  |  | Sponge/Restoration | May
BHT-FWP-10 | Brothers | 2025-05-22 | 948 |  | 1 HH | May
FB-HOE201 | Power Connect | 2025-05-22 | 772 |  |  | May
D-DHD52 | Lightspeed | 2025-05-23 | 129 |  | 1 Toby Box / 13 Splices | May
D-H0220B | Longo Underground | 2025-05-23 | 719 |  | 7 Toby Boxes / 1 Splice | May
D-H0221C | Lightspeed | 2025-05-23 | 236 |  | 3 Toby Boxes | May
D-H0222A | Lightspeed | 2025-05-23 | 175 |  | 72 Splices | May
D-HWP1306 | Lightspeed | 2025-05-23 |  |  | Sponge/Restoration | May
FB-HOE201 | Power Connect | 2025-05-23 |  |  | Crew Did Not Work This Location Today | May
D-HOE116 | Power Connect | 2025-05-23 | 285 |  | 18 Splices | May
D-H0221C | Lightspeed | 2025-05-27 | 224 |  | 1 Toby Box | May
FB-HDH02A | Lightspeed | 2025-05-27 | 100 |  |  | May
D-HWP1306 | Lightspeed | 2025-05-27 |  |  | Sponge/Restoration | May
FB-HWP801 | Brothers | 2025-05-27 | 948 |  | 3 HH / 3 Ground Rod | May
BHT-FWP-10 | Brothers | 2025-05-27 | 954 |  | 1 HH / 1 Ground Rod | May
BHZD-FWP-13-E | Lightspeed | 2025-05-27 |  |  | Drill Breakdown | May
FB-HOE201 | Power Connect | 2025-05-27 | 757 |  |  | May
D-H0221C | Lightspeed | 2025-05-28 | 200 |  | 1 Toby Box / 48 Splices | May
D-HWP1306 | Lightspeed | 2025-05-28 |  |  | Sponge/Restoration | May
BHT-FWP-10 | Brothers | 2025-05-28 | 2783 |  | 9 HH / 9 Ground Rods | May
FB-HOE201 | Power Connect | 2025-05-28 | 610 |  |  | May
D-H0221C | Lightspeed | 2025-05-29 |  |  | Hand Dig / Repair / Proofing / Supervising | May
D-HDH50 \ D-HDH52 | Lightspeed | 2025-05-29 |  |  | Hand Dig / Repair / Proofing / Supervising | May
D-HDH57 \ D-HDH58 | Lightspeed | 2025-05-29 |  |  | Hand Dig / Repair / Proofing / Supervising | May
D-HWP1306 | Lightspeed | 2025-05-29 |  |  | Restoration | May
BHT-FWP-10 | Brothers | 2025-05-29 | 2248 |  | 5 HH / 5 Ground Rods | May
FB-HWP801 | Brothers | 2025-05-29 | 736 |  | 2 HH / 2 Ground Rods | May
FB-HOE201 | Power Connect | 2025-05-29 | 959 |  |  | May
D-HDH50-52 | Lightspeed | 2025-05-30 |  |  | Stingray | May
D-HDH57-60 | Lightspeed | 2025-05-30 |  |  | Stingray | May
D-HNP151 | Longo Underground | 2025-05-30 | 218 |  | 1 Toby Box | May
FB-HWP-701 | Lightspeed | 2025-05-30 |  |  | Restoration | May
FB-HOE201 | Power Connect | 2025-05-30 | 493 |  |  | May
BHT-FWP-09 | Brothers | 2025-06-02 | 800 |  |  | June
BHZD-FWP-13-E | Lightspeed | 2025-06-02 | 275 |  |  | June
FB-HWP801 | Brothers | 2025-06-02 | 1957 |  | 7 HH / 7 Ground Rods | June
FB-HOE201 | Power Connect | 2025-06-02 | 720 |  |  | June
D-HDH18 | Lightspeed | 2025-06-02 | 6 |  | 48 Splices | June
D-HDH02 | Lightspeed | 2025-06-03 |  |  | Repair / ABF Proofing | June
D-HDH50\52 | Lightspeed | 2025-06-03 |  |  | Restoration | June
D-H0220B | Longo Underground | 2025-06-03 | 1483 |  | 12 Toby Boxes / 40 Splices | June
D-HNP110 | Power Connect | 2025-06-03 |  |  | No Production Vehicle Breakdown | June
BHT-FWP-09 | Brothers | 2025-06-03 | 631 |  | 2 HH / 2 Ground Rods | June
BHZD-FWP-13-E | Lightspeed | 2025-06-03 | 280 |  |  | June
FB-HWP701 | Power Connect | 2025-06-03 |  |  | Restoration | June
FB-HOE201 | Power Connect | 2025-06-03 | 948 |  |  | June
D-H0220B | Longo Underground | 2025-06-04 | 83 |  |  | June
D-HNP113 | Longo Underground | 2025-06-04 |  |  | Crew Did Not Work This Location Today Due To Rain | June
BHT-FWP-09 | Brothers | 2025-06-04 | 1401 |  |  | June
BHZD-FWP-13-E | Lightspeed | 2025-06-04 | 310 |  |  | June
D-HWP905 | Brothers | 2025-06-04 | 610 |  | 5 Toby Boxes / 5 Pits / 4 Splices | June
FB-HWP801 | Brothers | 2025-06-04 |  | 8415 | 6,328' Tracer Wire / 12,656' Mule Tape / 3 HH / 6 Ground Rods | June
FB-HOE201 | Power Connect | 2025-06-04 |  |  | Crew Did Not Work This Location Today Due To Rain | June
D-HNP113 | Longo Underground | 2025-06-05 | 341 |  | 4 Toby Boxes / 15 Splices | June
D-HDH52/49/58 | Lightspeed | 2025-06-05 |  |  | Restoration | June
BHZD-FWP-13-E | Lightspeed | 2025-06-05 |  |  | No Production | June
D-HWP905 | Brothers | 2025-06-05 | 2523 |  | 15 Toby Boxes / 19 Pits / 46 Splices | June
D-HWP701 | Lightspeed | 2025-06-05 |  |  | No Report--Will Be Sent In The Morning | June
FB-HOE201 | Power Connect | 2025-06-05 | 1101 |  | 2 HH | June
FB-HOE201 | Power Connect | 2025-06-06 | 437 |  | 1 HH | June
BHT-FWP-09 | Brothers | 2025-06-09 | 1100 |  |  | June
FX4-FWP-13 | Brothers | 2025-06-09 | 115 |  |  | June
225 Granada St | Lightspeed | 2025-06-09 | 155 |  |  | June
BHZD-FWP-13-E | Lightspeed | 2025-06-09 | 263 |  |  | June
FB-HOE201 | Power Connect | 2025-06-09 | 730 |  |  | June
D-HWP905 | Brothers | 2025-06-10 | 1293 |  | 12 Toby Boxes / 7 Pits / 35 Splices / 1 FDH | June
BHZD-FWP-13-E | Lightspeed | 2025-06-10 | 270 |  |  | June
FB-HOE201 | Power Connect | 2025-06-10 | 583 |  |  | June
BHT-FWP-09 | Brothers | 2025-06-11 | 1975 |  | 2 HH / 2 Ground Rods | June
BHT-FWP-10 | Brothers | 2025-06-11 | 370 |  | 2 HH / 2 Ground Rods | June
BHZD-FWP-13-E | Lightspeed | 2025-06-11 |  |  | Crew Did Not Work This Location Today | June
BHT-FWP-09 | Brothers | 2025-06-12 | 1395 |  | 2 HH / 2 Ground Rods | June
FB-HWP701 | Brothers | 2025-06-12 |  |  | Restoration | June
BHZD-FWP-13-E | Lightspeed | 2025-06-12 | 395 |  |  | June
FB-HWP701 | Brothers | 2025-06-13 |  |  | Restoration | June
BHUD-FWP-06 | Lightspeed | 2025-06-13 |  |  | Ground Rods | June
BHZD-FWP-13-E | Lightspeed | 2025-06-13 |  |  | Vaults/ Tie Ins | June
FB-HOE201 | Power Connect | 2025-06-13 |  | 7408 | 6,128 Tracer Wire | June
D-H0220A | Longo Underground | 2025-06-16 | 1394 |  | 9 Toby Boxes | June
BHT-FWP-09 | Brothers | 2025-06-16 | 450 |  | 4 HH | June
BHZD-FWP-13-E | Lightspeed | 2025-06-16 | 280 |  |  | June
BHT-FWP-10 | Brothers | 2025-06-16 |  | 4976 | Pulling Fiber Cable / 4,976 Tracer Wire | June
FB-HOE201 | Power Connect | 2025-06-16 | 465 |  | 1 HH | June
D-H0220A | Longo Underground | 2025-06-17 | 1756 |  | 6 Toby Boxes | June
BHT-FWP-09 | Brothers | 2025-06-17 | 1246 |  | 5 HH / 5 Ground Rods | June
BHZD-FWP-13-E | Lightspeed | 2025-06-17 | 70 |  |  | June
BHT-FWP-08 | Brothers | 2025-06-17 | 1465 |  | 4 HH / 4 Ground Rods | June
BHT-FWP-10 | Brothers | 2025-06-17 |  | 4177 | 4,177 Tracer Wire | June
FB-HOE201 | Power Connect | 2025-06-17 | 218 |  | 1 HH | June
D-H0220A | Longo Underground | 2025-06-18 | 846 |  | 4 Toby Boxes | June
D-HNP135 | Lightspeed | 2025-06-18 | 81 |  |  | June
D-HDH69 | Lightspeed | 2025-06-18 |  |  | Restoration | June
D-H0222B | Lightspeed | 2025-06-18 |  |  | Restoration | June
BHT-FWP-08 | Brothers | 2025-06-18 | 1380 |  | 4 HH / 4 Ground Rods | June
BHZD-FWP-13-E | Lightspeed | 2025-06-18 | 594 |  |  | June
FB-HOE201 | Power Connect | 2025-06-18 | 729 |  |  | June
FB-HOE201 | Power Connect | 2025-06-19 | 464 |  |  | June
BHUD-FOE-02-W | Power Connect | 2025-06-19 | 977 |  | 2 HH | June
D-HNP135 | Lightspeed | 2025-06-20 | 114 |  |  | June
BHZD-FWP-13-E | Lightspeed | 2025-06-20 | 52 |  | 1 HH | June
FB-HWP801 | Brothers | 2025-06-20 |  |  | Restoration | June
FB-HOE201 | Power Connect | 2025-06-20 |  | 1086 | 755 Tracer Wire | June
D-HNP135 | Lightspeed | 2025-06-23 | 237 |  | 4 Toby Boxes / 7 Splices | June
FB-HDH01A-2A | Lightspeed | 2025-06-23 | 65 |  |  | June
FB-HWP175 | Brothers | 2025-06-23 | 924 |  | 1 HH | June
BHZD-FWP-13-E | Lightspeed | 2025-06-23 | 68 |  | 1 HH / 1 Ground Rod | June
BHT-FWP-08 | Brothers | 2025-06-23 | 1269 |  | 1 HH / 1 Ground Rod | June
D-HNP135 | Lightspeed | 2025-06-24 | 322 |  |  | June
D-H0220A | Longo Underground | 2025-06-24 | 1946 |  | 10 Toby Boxes / 1 HH / 1 FDH / 1 Swing Arm / 1 Ground Rod | June
D-HWP801 | Brothers | 2025-06-24 | 1044 |  | 10 Toby Boxes / 9 Daps | June
BHZD-FWP-13-E | Lightspeed | 2025-06-24 | 50 |  | 3 HH / 3 Ground Rods | June
BHT-FWP-08 | Brothers | 2025-06-24 | 1141 |  | 5 HH / 5 Ground Rods | June
FB-HOE201 | Power Connect | 2025-06-24 |  | 883 | 683 Tracer Wire | June
D-HNP135 | Lightspeed | 2025-06-25 | 245 |  | 2 Toby Boxes | June
D-HNP113 | Longo Underground | 2025-06-25 | 649 |  | 10 Toby Boxes / 35 Splices | June
D-HWP801 | Brothers | 2025-06-25 | 1100 |  | 12 Toby Boxes / 6 Daps | June
FB-HWP1376 | Lightspeed | 2025-06-25 | 335 |  |  | June
BHT-FWP-08 | Brothers | 2025-06-25 | 1308 |  | 3 HH / 3 Ground Rods | June
D-HNP135 | Lightspeed | 2025-06-26 | 1091 |  |  | June
D-H0220A | Longo Underground | 2025-06-26 |  |  | ABF Testing | June
D-H0220B | Longo Underground | 2025-06-26 |  |  | ABF Testing | June
D-HWP801 | Brothers | 2025-06-26 | 1050 |  | 6 Toby Boxes / 6 Daps / 2 Vaults / 1 HH / 1 Flower Pot | June
FB-HWP1376 | Lightspeed | 2025-06-26 | 200 |  |  | June
BHT-FWP-08 | Brothers | 2025-06-26 | 1296 |  | 4 HH / 4 Ground Rods | June
FB-HWP175 | Brothers | 2025-06-26 |  |  | Issue With Conduit Placement | June
FB-HOE201 | Power Connect | 2025-06-26 | 112 |  | 1 HH | June
BHUD-FOE-02-W | Power Connect | 2025-06-26 | 676 |  | 1 HH / 1 Ground Rod | June
FB-HOE201 | Raven | 2025-06-26 |  | 6183 | 5,376 Tracer Wire
D-HNP135 | Lightspeed | 2025-06-27 | 303 |  | 2 Toby Boxes | June
D-H0220B | Longo Underground | 2025-06-27 |  |  | ABF Testing | June
FB-HWP175 | Brothers | 2025-06-27 |  | 1605 | 1,605 Tracer Wire | June
BHUD-FOE-02-W | Power Connect | 2025-06-27 | 430 |  |  | June
D-HNP135 | Lightspeed | 2025-06-30 | 360 |  | 6 Toby Boxes / 22 Splices | June
FB-HWP175 | Lightspeed | 2025-06-30 | 120 | 120 | 1,725 Tracer Wire | June
BHUD-FOE-02-W | Power Connect | 2025-06-30 | 885 |  | 2 HH | June
FB-HWP1376 | Lightspeed | 2025-07-01 | 120 |  |  | July
FB-HWP801 | Brothers | 2025-07-01 |  | 53 | 53 Tracer Wire / 106 Mule Tape | July
BHT-FWP-08 | Brothers | 2025-07-01 |  | 10059 | 7,859 Tracer Wire / 15,718 Mule Tape
BHUD-FOE-02-W | Power Connect | 2025-07-01 | 478 |  |  | July
FB-HOE201 | Power Connect | 2025-07-01 | 282 |  |  | July
D-HNP144 | Lightspeed | 2025-07-02 |  |  | No Clear Location To Drill On--Already Completed By FCA | July
FB-HWP1376 | Lightspeed | 2025-07-02 | 71 |  | 1 HH | July
D-HWP821 | Brothers | 2025-07-02 | 355 |  | 6 Toby Boxes | July
BHT-FWP-08 | Brothers | 2025-07-02 |  |  | Restoration | July
BHUD-FOE-02-W | Power Connect | 2025-07-02 | 490 |  | 1 HH | July
FB-HWP1376 | Lightspeed | 2025-07-03 |  |  | Restoration | July
BHUD-FOE-02-W | Power Connect | 2025-07-03 | 372 |  | 1 HH | July
BHUD-FOE-02-W | Raven | 2025-07-03 |  | 5776 | 5,276 Tracer Wire
|  | 2025-07-04 | 0 |  |  | July
FB-HWP902 | Lightspeed | 2025-07-07 |  |  | Pot Holing | July
D-HWP821 | Brothers | 2025-07-07 | 846 |  |  | July
BHUD-FWP-13-W | Brothers | 2025-07-07 | 1644 |  |  | July
BHUD-FOE-02-W | Raven | 2025-07-07 |  |  | Pulling Tracer Wire | July
FB-HWP902 | Lightspeed | 2025-07-08 | 465 |  |  | July
D-HWP821 | Brothers | 2025-07-08 | 827 |  | 18 Toby Boxes / 1 FDH / 1 Flower Pot | July
BHUD-FWP-13-W | Brothers | 2025-07-08 | 60 |  | 1 HH / 1 Ground Rod | July
FB-HWP902 | Lightspeed | 2025-07-09 | 321 |  |  | July
D-HOE206 | Power Connect | 2025-07-09 |  |  |  | July
D-HNP117 | Lightspeed | 2025-07-10 | 400 |  |  | July
FB-HWP902 | Lightspeed | 2025-07-10 |  |  | 2 HH/ 2 Ground Rod / Restoration | July
FB-HWP902 | Lightspeed | 2025-07-11 |  | 786 |  | July
BHZD-FOE-03-W | Raven | 2025-07-11 | 198 |  |  | July
FB-HWP902 | Lightspeed | 2025-07-14 |  |  | Restoration | July
BHZD-FOE-03-W | Raven | 2025-07-14 | 862 |  |  | July
D-HNP117 | Lightspeed | 2025-07-15 | 203 |  |  | July
BHZD-FWP-13-E | Lightspeed | 2025-07-15 |  |  | No Production--Issues In The Field | July
D-HWP822 | Brothers | 2025-07-15 | 1210 |  | 10 Toby Boxes / 4 Flower Pots | July
D-HOE215 | Raven | 2025-07-15 | 403 |  |  | July
D-HNP117 | Lightspeed | 2025-07-16 | 170 |  |  | July
BHZD-FWP-13-E | Lightspeed | 2025-07-16 | 280 |  |  | July
D-HWP822 | Brothers | 2025-07-16 | 397 |  | 3 Toby Boxes / 1 Flower Pot | July
FB-HWP1302 | Lightspeed | 2025-07-16 | 90 |  |  | July
D-HWP814 | Brothers | 2025-07-16 | 426 |  | 2 Toby Boxes | July
D-HOE215 | Raven | 2025-07-16 | 39 |  |  | July
BHZD-FWP-13-E | Lightspeed | 2025-07-17 | 1972 |  |  | July
D-HWP814 | Brothers | 2025-07-17 | 583 |  | 5 Toby Boxes | July
D-HNP117 | Lightspeed | 2025-07-17 | 106 |  |  | July
FX4-FML-05 | Lightspeed | 2025-07-18 | 47 |  |  | July
BHZD-FWP-13-E | Lightspeed | 2025-07-18 |  |  | Restoration / 1 HH | July
D-HNP117 | Lightspeed | 2025-07-21 |  |  | No Production--Water Line Hit | July
BHZD-FWP-13-E | Lightspeed | 2025-07-21 | 551 |  |  | July
BHZD-FWP-13-E | Longo Underground | 2025-07-21 | 385 |  |  | July
D-HWP812 | Brothers | 2025-07-21 | 1070 |  | 9 Toby Boxes | July
D-HWP814 | Brothers | 2025-07-21 | 1843 |  | 13 Toby Boxes / 1 Flower Pot | July
D-HOE215 | Raven | 2025-07-21 |  |  | Drill Breakdown--No Production | July
D-HNP117 | Lightspeed | 2025-07-22 |  |  | No Production--Drill Breakdown | July
D-HWP812 | Brothers | 2025-07-22 | 1224 |  | 12 Toby Boxes / 4 Flower Pots | July
D-HWP814 | Brothers | 2025-07-22 | 1714 |  | 12 Toby Boxes | July
BHZD-FWP-13-E | Longo Underground | 2025-07-22 | 300 |  |  | July
BHZD-FWP-13-E | HAS Global | 2025-07-22 | 1107 |  |  | July
BHZD-FWP-13-E | Lightspeed | 2025-07-22 | 316 |  |  | July
D-HOE215 | Raven | 2025-07-22 | 318 |  |  | July
BHUD-FOE-03-W | Raven | 2025-07-22 | 605 |  |  | July
D-HNP117 | Lightspeed | 2025-07-23 | 272 |  | 3 Toby Boxes / 1 Dap | July
BHZD-FWP-13-E | Lightspeed | 2025-07-23 | 130 |  | 2 HH | July
D-HWP812 | Brothers | 2025-07-23 | 235 |  | 5 Toby Boxes / 4 Daps | July
D-HWP814 | Brothers | 2025-07-23 | 678 |  | 8 Toby Boxes / 11 Daps / 41 Splices | July
BHUD-FWP-13-W | Longo Underground | 2025-07-23 | 579 |  |  | July
D-HWP815 | Brothers | 2025-07-23 | 363 |  | 4 Toby Boxes / 2 Daps | July
BHT-FWP-09 | Brothers | 2025-07-23 | 853 |  | 1 HH | July
BHZD-FOE-03-W | Raven | 2025-07-23 | 461 |  |  | July
D-HNP117 | Lightspeed | 2025-07-24 | 79 |  | 1 Dap / 4 Splices | July
BHZD-FWP-13-E | Lightspeed | 2025-07-24 | 420 |  |  | July
FB-HWP804 | Telecom | 2025-07-24 |  |  | Potholed Locations | July
D-HWP815 | Brothers | 2025-07-24 | 1077 |  | 7 Toby Boes / 1 HH / 3 Daps / 1 Ground Rod | July
BHUD-FWP-13-W | Longo Underground | 2025-07-24 | 619 |  | 6 HH / 6 Ground Rods | July
BHZD-FWP-13-E | HAS Global | 2025-07-24 |  |  | 5 HH | July
BHT-FWP-09 | Brothers | 2025-07-24 | 1279 |  | 1 HH | July
BHZD-FOE-03-W | Raven | 2025-07-24 | 880 |  |  | July
D-HOE206 | Power Connect | 2025-07-24 | 868 |  | 7 Toby Boxes / 3 Daps | July
D-HNP117 | Lightspeed | 2025-07-25 |  |  | Restoration | July
BHZD-FWP-13-E | Lightspeed | 2025-07-25 |  |  | HHs / Tie ins | July
D-HWP814 | Brothers | 2025-07-25 |  |  | FDH / Sponging | July
D-HWP812 | Brothers | 2025-07-25 |  |  | FDH / Sponging | July
D-HWP822 | Brothers | 2025-07-25 |  |  | FDH / Sponging | July
D-HWP821 | Lightspeed | 2025-07-25 |  |  | Blowing Stingray | July
BHZD-FOE-03-W | Raven | 2025-07-25 | 585 |  | 2 HH | July
BHZD-FWP-13-E | Lightspeed | 2025-07-28 | 420 |  | 1 HH | July
BHT-FWP-09 | Brothers | 2025-07-28 | 817 |  |  | July
D-HWP815 | Brothers | 2025-07-28 | 1430 |  | 9 Toby Boxes / 2 Flower Pots / 8 Daps / 59 Splices | July
FB-HWP804 | Lightspeed | 2025-07-28 |  |  | Drill Breakdown--No Production | July
BHUD-FWP-13-W | Longo Underground | 2025-07-28 | 1181 |  |  | July
BHZD-FOE-03-W | Raven | 2025-07-28 | 345 |  |  | July
BHUD-FWP-13-W | Longo Underground | 2025-07-29 | 1933 |  |  | July
BHT-FWP-09 | Brothers | 2025-07-29 |  | 5590 | 5,590 Tracer Wire | July
D-HWP815 | Brothers | 2025-07-29 | 1004 |  | 9 Toby Boxes / 2 Flower Pots / 9 Daps / 130 Splices / 1 HH / 1 FDH / 1 Ground Rod | July
FB-HWP804 | Lightspeed | 2025-07-29 | 581 | 1200 | 1,200 Tracer Wire | July
BHUD-FWP-13-W | Longo Underground | 2025-07-30 | 1951 |  |  | July
BHUD-FWP-13-W | Brothers | 2025-07-30 | 902 |  |  | July
BHT-FWP-09 | Brothers | 2025-07-30 | 1385 |  | 1 HH | July
D-HWP814 | Lightspeed | 2025-07-30 |  | 847 | 847 Tracer Wire / 1,694 Mule Tape | July
BHZD-FWP-13-E | Kattle One | 2025-07-30 |  | 6067 |  | July
BHT-FOE-03 | Raven | 2025-07-30 | 314 |  |  | July
D-H0223C | Lightspeed | 2025-07-31 |  |  | Drill Breakdown | July
BHUD-FWP-13-W | Longo Underground | 2025-07-31 | 725 |  |  | July
BHUD-FWP-13-W | Brothers | 2025-07-31 | 862 |  |  | July
BHZD-FWP-13-E | Kattle One | 2025-07-31 |  | 2691 |  | July
FB-HOE301 | Raven | 2025-07-31 | 2390 |  |  | July
D-H0223C | Lightspeed | 2025-08-01 | 318 |  | Repair--1 Toby Box / 2 Splices | August
D-H0223A | Lightspeed | 2025-08-01 | 183 |  | Repair--3 Toby Boxes / 7 Splices | August
BHUD-FWP-13-W | Kattle One | 2025-08-01 |  |  | 14 Hand Holes / 14 Ground Rods | August
FB-HOE301 | Raven | 2025-08-01 | 1377 |  |  | August
BHUD-FWP-13-W | Kattle One | 2025-08-04 |  | 13125 |  | August
FB-HWP482 | Brothers | 2025-08-04 | 918 |  |  | August
BHZD-FWP-11-W | Brothers | 2025-08-05 | 2675 |  |  | August
FB-HOE301 | Raven | 2025-08-05 | 190 |  | 1 HH | August
D-HNP117 | Lightspeed | 2025-08-06 |  |  | 1 HH | August
BHZD-FWP-11-W | Brothers | 2025-08-06 | 1964 |  |  | August
FB-HOE301 | Raven | 2025-08-06 | 840 |  |  | August
BHT-FOE-03 | Raven | 2025-08-06 |  |  | No Production--Crew Did Not Work This Location Today | August
BHZD-FWP-11-W | Brothers | 2025-08-07 | 377 |  | 9 HH / 9 Ground Rods | August
BHZD-FWP-11-W | Kattle One | 2025-08-07 |  | 5289 | 5,289 Tracer Wire | August
FB-HWP775 | Brothers | 2025-08-07 | 674 |  |  | August
FB-HOE301 | Raven | 2025-08-07 | 531 |  |  | August
D-HNP117 | Lightspeed | 2025-08-08 |  |  | No Production--Water Line Hit | August
BHZD-FWP-11-W | Brothers | 2025-08-08 |  |  | Restoration | August
FB-HOE301 | Raven | 2025-08-08 | 718 |  |  | August
D-HNP117 | Lightspeed | 2025-08-11 | 376 |  | 1 Toby Box | August
FB-HWP482 | Brothers | 2025-08-11 | 1175 |  |  | August
FB-HWP802 | Lightspeed | 2025-08-11 | 288 |  |  | August
FB-HOE301 | Raven | 2025-08-11 | 571 |  |  | August
D-HNP117 | Lightspeed | 2025-08-12 | 35 |  |  | August
FB-HWP482 | Brothers | 2025-08-12 | 1154 |  |  | August
FB-HWP802 | Lightspeed | 2025-08-12 | 380 |  |  | August
FB-HWP775 | Brothers | 2025-08-12 | 111 |  | 3 HH / 3 Ground Rods | August
D-HOE215 | Raven | 2025-08-12 | 319 |  |  | August
FB-HOE301 | Raven | 2025-08-12 | 1293 |  |  | August
12 Oaks MHP | Brothers | 2025-08-12 | 406 |  |  | August
D-HNP117 | Lightspeed | 2025-08-13 | 48 |  | 1 Dap / 4 Splices | August
FB-HWP482 | Brothers | 2025-08-13 | 428 |  | 2 HH | August
FB-HWP802 | Lightspeed | 2025-08-13 | 229 |  | 1 HH | August
12 Oaks MHP | Brothers | 2025-08-13 | 1031 |  | 14 Toby Boxes / 1 HH / 1 Ground Rod | August
FB-HWP775 | Brothers | 2025-08-13 | 12 |  | 1 HH / 1 Ground Rod | August
FB-HOE301 | Raven | 2025-08-13 | 540 |  |  | August
D-HNP117 | Lightspeed | 2025-08-14 | 144 |  |  | August
Skyview MHP | Brothers | 2025-08-14 |  |  | Crew Did Not Work This Location Today | August
FB-HWP802 | Lightspeed | 2025-08-14 | 163 |  |  | August
FB-HOE301 | Raven | 2025-08-14 | 554 |  |  | August
FB-HLR201 | Lightspeed | 2025-08-14 |  |  | No Production | August
D-HNP117 | Lightspeed | 2025-08-15 | 64 |  |  | August
FB-HWP482 | Kattle One | 2025-08-15 |  | 1243 | 993 Tracer Wire / 1,986 Mule Tape / 4 HH / 4 Ground Rods | August
FB-HWP802 | Lightspeed | 2025-08-15 |  | 1060 | 1,060 Tracer Wire / 2 HH / 2 Ground Rods | August
FB-HWP775 | Kattle One | 2025-08-15 |  | 1297 | 797 Tracer Wire / 1,594 Mule Tape | August
FB-HOE301 | Raven | 2025-08-15 | 89 |  |  | August
FB-HLR201 | Lightspeed | 2025-08-15 | 391 |  |  | August
D-HNP117 | Lightspeed | 2025-08-18 | 141 |  |  | August
FB-HWP482 | Kattle One | 2025-08-18 |  | 2679 | 2,379 Tracer Wire / 4,658 Mule Tape | August
FB-HWP1376 | Lightspeed | 2025-08-18 | 343 |  |  | August
FB-HWP775 | Kattle One | 2025-08-18 |  | 2145 | 1,757 Tracer Wire | August
FB-HWP776 | Brothers | 2025-08-18 | 1109 |  | 6 HH / Ground Rods | August
FB-HOE301 | Raven | 2025-08-18 | 377 |  |  | August
FB-HLR201 | Lightspeed | 2025-08-18 | 396 |  |  | August
D-HNP111 | Lightspeed | 2025-08-19 | 205 |  |  | August
Skyview | Brothers | 2025-08-19 | 1456 |  |  | August
FB-HWP1376 | Lightspeed | 2025-08-19 | 416 |  |  | August
D-HWP803 | Brothers | 2025-08-19 | 1460 |  | 6 Daps | August
FB-HOE301 | Raven | 2025-08-19 | 408 |  |  | August
D-HOE206 | Lightspeed | 2025-08-19 |  |  | No Production--Crew Potholed | August
BHT-FOE-03 | Raven | 2025-08-19 | 430 |  |  | August
D-HNP117 | Lightspeed | 2025-08-20 | 181 |  |  | August
D-HNP113 | Longo Underground | 2025-08-20 |  |  | No Production--Water Line Hit | August
Skyview | Brothers | 2025-08-20 | 1420 |  |  | August
FB-HWP1376 | Lightspeed | 2025-08-20 | 216 |  |  | August
D-HWP803 | Brothers | 2025-08-20 | 1428 |  | 1 HH / 1 Ground Rod | August
FB-HOE301 | Raven | 2025-08-20 | 607 |  | 11 HH | August
D-HOE206 | Lightspeed | 2025-08-20 | 499 |  |  | August
D-HNP117 | Lightspeed | 2025-08-21 | 82 |  |  | August
D-HNP113 | Longo Underground | 2025-08-21 |  |  | No Production | August
Skyview | Brothers | 2025-08-21 | 1170 |  |  | August
FB-HWP1376 | Lightspeed | 2025-08-21 |  |  | No Production | August
D-HWP803 | Brothers | 2025-08-21 | 1654 |  |  | August
FB-HWP776 | Kattle One | 2025-08-21 |  | 1109 | 1,109 Tracer Wire | August
FB-HOE301 | Raven | 2025-08-21 | 1022 |  |  | August
D-HOE206 | Lightspeed | 2025-08-21 | 231 |  |  | August
D-HNP117 | Lightspeed | 2025-08-22 | 96 |  |  | August
D-HNP108 | Longo Underground | 2025-08-22 | 878 |  | 2 Toby Boxes / 16 Splices | August
Skyview | Brothers | 2025-08-22 | 1081 |  |  | August
FB-HWP1376 | Lightspeed | 2025-08-22 |  | 2001 | 1,701 Tracer Wire | August
FB-HOE301 | Raven | 2025-08-22 |  | 6090 | 8,871 Tracer Wire | August
D-HOE206 | Lightspeed | 2025-08-22 | 316 |  |  | August
D-HNP117 | Lightspeed | 2025-08-25 | 20 |  |  | August
D-HNP108 | Longo Underground | 2025-08-25 | 715 |  |  | August
Skyview | Brothers | 2025-08-25 | 809 |  |  | August
FB-HWP1375 | Lightspeed | 2025-08-25 |  |  | No Production Due To Rain | August
D-HWP805 | Brothers | 2025-08-25 | 735 |  | 7 Toby Boxes / 1 Dap | August
FB-HOE301 | Raven | 2025-08-25 | 639 |  |  | August
D-HOE206 | Lightspeed | 2025-08-25 | 503 |  |  | August
D-HNP117 | Lightspeed | 2025-08-26 |  |  | No Production | August
D-HNP113 | Longo Underground | 2025-08-26 | 1009 |  | 8 Toby Boxes / 2 Daps | August
Skyview | Brothers | 2025-08-26 | 533 |  |  | August
FB-HWP1375 | Lightspeed | 2025-08-26 | 260 |  |  | August
FB-HWP1310 | Lightspeed | 2025-08-26 | 390 |  |  | August
D-HWP826 | Brothers | 2025-08-26 | 558 |  | 7 Toby Boxes | August
D-HWP824 | Brothers | 2025-08-26 | 1224 |  | 15 Toby Boxes / 11 Daps | August
D-HOE206 | Lightspeed | 2025-08-26 | 295 |  |  | August
BHZD-FOE-03-W | Raven | 2025-08-26 |  |  | Drill Breakdown | August
D-HWP825 | Longo Underground | 2025-08-27 | 1017 |  | 5 Toby Boxes / 8 Daps | August
FB-HWP1375 | Lightspeed | 2025-08-27 |  |  | No Production | August
FB-HWP375 | Lightspeed | 2025-08-27 | 130 | 130 | 130 Tracer Wire / 1 HH / 1 Ground Rod | August
D-HWP826 | Brothers | 2025-08-27 | 1248 |  | 10 Toby Boxes / 8 Daps | August
D-HWP824 | Brothers | 2025-08-27 | 967 |  | 8 Toby Boxes / 8 Daps / 1 Flower Pot | August
FB-HLR201 | Lightspeed | 2025-08-27 | 400 |  |  | August
D-HOE215 | Raven | 2025-08-27 | 358 |  | 2 Toby Boxes / 2 Daps | August
BHZD-FOE-03-W | Raven | 2025-08-27 | 1241 |  |  | August
D-HNP117 | Lightspeed | 2025-08-28 | 250 |  |  | August
FB-HWP1375 | Lightspeed | 2025-08-28 | 315 | 575 | 575 Tracer Wire | August
D-HWP805 | Brothers | 2025-08-28 | 1453 |  | 14 Toby Boxes / 11 Daps | August
D-HWP826 | Brothers | 2025-08-28 | 1260 |  | 7 Toby Box / 6 Daps | August
FB-HOE301 | Raven | 2025-08-28 |  |  | 2 HH | August
FB-HLR201 | Lightspeed | 2025-08-28 | 320 |  |  | August
D-HOE215 | Raven | 2025-08-28 |  |  | No Production | August
BHZD-FOE-03-W | Raven | 2025-08-28 |  |  | No Production | August
D-HNP117 | Lightspeed | 2025-08-29 | 177 |  | 1 Toby Box / 1 Dap | August
D-HNP108 | Longo Underground | 2025-08-29 | 1131 |  |  | August
BHZD-FOE-03-W | Raven | 2025-08-29 |  |  | 1 HH | August
D-HOE206 | Lightspeed | 2025-08-29 | 6 |  | 3 Toby Boxes / 2 Daps / 20 Splices | August
FB-HOE301 | Raven | 2025-08-29 |  | 8378 | 3,086 Tracer Wire | August
D-HWP1310 | Lightspeed | 2025-08-29 |  | 390 | 390 Tracer Wire | Septemeber
|  | 2025-09-01 |  |  |  | Septemeber
D-HNP117 | Lightspeed | 2025-09-02 |  |  | Swing Arm / Ground Rod | Septemeber
D-HWP826 | Brothers | 2025-09-02 | 977 |  | 8 Toby Boxes / 6 Daps | Septemeber
D-HOE206 | Lightspeed | 2025-09-02 | 15 |  | 3 Toby Boxes / 3 Daps / 19 Splices | Septemeber
BHZD-FOE-03-W | Raven | 2025-09-02 |  | 7962 | 6,880 Tracer Wire | Septemeber
D-HNP117 | Lightspeed | 2025-09-03 |  |  | Restoration | Septemeber
D-HDH82 | Lightspeed | 2025-09-03 |  |  | FDH Move | Septemeber
D-HWP1310 | Brothers | 2025-09-03 | 1491 |  | 11 Toby Boxes / 9 Daps | Septemeber
D-HWP805 | Brothers | 2025-09-03 | 2472 | 730 | 27 Toby Boxes / 20 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP825 | Longo Underground | 2025-09-03 | 2819 |  | 25 Toby Boxes / 15 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP812 | Lightspeed | 2025-09-03 | 130 |  | 1 Dap | Septemeber
D-HOE206 | Lightspeed | 2025-09-03 | 65 |  | 1 Toby Box / 1 Dap / 2 Splices | Septemeber
BHZD-FOE-03-W | Raven | 2025-09-03 |  |  | Pulling Tracer Wire | Septemeber
D-HNP117 | Lightspeed | 2025-09-04 |  |  | Proofing Conduits | Septemeber
HGP-03 | Lightspeed | 2025-09-04 |  |  | Damage Repair | Septemeber
D-HWP1310 | Brothers | 2025-09-04 | 1549 |  | 12 Toby Boxes / 10 Daps | Septemeber
D-HWP802 | Brothers | 2025-09-04 | 903 |  | 6 Toby Boxes / 4 Daps | Septemeber
D-HWP812 | Lightspeed | 2025-09-04 |  | 800 |  | Septemeber
D-HOE215 | Lightspeed | 2025-09-04 | 99 |  | 2 Toby Boxes / 1 Dap / 3 Splices | Septemeber
D-HOE206 | Lightspeed | 2025-09-04 | 6 |  | 1 Dap / 12 Splices | Septemeber
D-HNP135 | Lightspeed | 2025-09-05 | 125 |  |  | Septemeber
FB-HOE375 | Lightspeed | 2025-09-05 | 285 |  |  | Septemeber
D-HWP803 | Brothers | 2025-09-05 | 128 | 2000 | 34 Toby Boxes / 15 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP825 | Lightspeed | 2025-09-05 |  | 2062 |  | Septemeber
D-HWP802 | Longo Underground | 2025-09-08 | 254 |  | 4 Toby Boxes / 3 Daps | Septemeber
Skyview | Brothers | 2025-09-08 | 2498 |  |  | Septemeber
D-HWP1310 | Brothers | 2025-09-08 | 918 |  | 11 Toby Boxes / 4 Daps | Septemeber
D-HWP802 | Longo Underground | 2025-09-09 | 1686 |  | 7 Toby Boxes / 4 Daps | Septemeber
Skyview | Brothers | 2025-09-09 | 1192 |  | 120 Toby Boxes / 103 Daps | Septemeber
FB-HWP975 | Brothers | 2025-09-09 | 329 |  |  | Septemeber
D-HNP135 | Lightspeed | 2025-09-10 | 299 |  |  | Septemeber
D-HWP802 | Longo Underground | 2025-09-10 | 611 |  | 9 Toby Boxes / 5 Daps | Septemeber
Skyview | Brothers | 2025-09-10 | 1925 |  |  | Septemeber
FB-HWP975 | Lightspeed | 2025-09-10 | 333 |  |  | Septemeber
D-HWP827 | Brothers | 2025-09-10 | 740 |  | 4 Toby Boxes / 1 Dap | Septemeber
BHT-FLX-01 | Baseline | 2025-09-10 | 307 |  |  | Septemeber
FB-HOE375 | Lightspeed | 2025-09-10 |  |  | No Production | Septemeber
D-HNP135 | Lightspeed | 2025-09-11 | 302 |  |  | Septemeber
D-HNP113 | Longo Underground | 2025-09-11 | 279 |  | 5 Toby Boxes / 5 Splices | Septemeber
D-HNP108 | Longo Underground | 2025-09-11 | 443 |  | 3 Toby Boxes / 4 Splices | Septemeber
FB-HWP975 | Lightspeed | 2025-09-11 |  | 662 | 3 HH | Septemeber
FB-HWP1075 | Lightspeed | 2025-09-11 | 267 |  |  | Septemeber
BHT-FLX-01 | Baseline | 2025-09-11 | 920 |  |  | Septemeber
FB-HOE375 | Lightspeed | 2025-09-11 | 82 |  | 2 HH / 2 Ground Rods | Septemeber
D-HNP135 | Lightspeed | 2025-09-12 | 209 |  | 1 Toby Box | Septemeber
FB-HWP975 | Lightspeed | 2025-09-12 |  |  | Restoration | Septemeber
BHT-FLX-01 | Baseline | 2025-09-12 | 610 |  |  | Septemeber
FB-HOE375 | Lightspeed | 2025-09-12 |  |  | Restoration | Septemeber
D-HNP135 | Lightspeed | 2025-09-15 | 42 |  |  | Septemeber
D-HWP827 | Brothers | 2025-09-15 | 1238 |  |  | Septemeber
FB-HWP1075 | Lightspeed | 2025-09-15 | 711 |  |  | Septemeber
BHT-FLX-01 | Baseline | 2025-09-15 | 829 |  | 1 HH / 1 Ground Rod | Septemeber
D-HOE206 | Lightspeed | 2025-09-15 |  |  | ABF Testing | Septemeber
D-HNP135 | Lightspeed | 2025-09-16 | 219 |  | 1 Toby Box / 2 Daps / 6 Splices | Septemeber
D-HWP827 | Brothers | 2025-09-16 | 1531 |  |  | Septemeber
FB-HWP1075 | Lightspeed | 2025-09-16 |  |  | 2 HH / 2 Ground Rods | Septemeber
D-HWP809 | Brothers | 2025-09-16 | 1808 |  |  | Septemeber
BHT-FLX-01 | Baseline | 2025-09-16 |  |  | 1 HH | Septemeber
D-HOE215 | Lightspeed | 2025-09-16 |  |  | 1 FDH / 1 Swing Arm | Septemeber
D-HOE206 | Lightspeed | 2025-09-16 |  |  | 1 FDH / 1 Swing Arm | Septemeber
D-HOE302 | North Path | 2025-09-16 | 251 |  |  | Septemeber
D-HGP22 (Repair) | Lightspeed | 2025-09-17 | 75 |  |  | Septemeber
D-HWP827 | Brothers | 2025-09-17 | 1250 |  | 11 Toby Boxes / 5 Daps | Septemeber
D-HWP802 | Longo Underground | 2025-09-17 | 250 |  | 3 Toby Boxes / 2 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP809 | Brothers | 2025-09-17 |  |  | 18 Toby Boxes / 13 Daps / 2 Flower Pots | Septemeber
BHT-FLX-01 | Baseline | 2025-09-17 | 863 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-17 | 253 |  |  | Septemeber
D-HOE215 | Lightspeed | 2025-09-17 |  |  | ABF Testing | Septemeber
BHZD-FOE-03-W | Lightspeed | 2025-09-17 | 139 |  |  | Septemeber
FB-HNP133 | Lightspeed | 2025-09-18 | 97 |  | 1 Dap / 2 Splices | Septemeber
D-HNP135 | Lightspeed | 2025-09-18 |  |  | 1 HH / 1 Swing Arm | Septemeber
D-HWP827 | Brothers | 2025-09-18 | 361 |  | 1 Toby Box / 3 Daps / 1 Flower Pot | Septemeber
D-HWP809 | Brothers | 2025-09-18 | 1204 |  | 15 Toby Boxes / 11 Daps / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP811 | Brothers | 2025-09-18 | 562 |  |  | Septemeber
D-HWP823 | Brothers | 2025-09-18 | 754 |  | 6 Toby Boxes / 1 Flower Pot / 6 Daps / 41 Splices | Septemeber
BHT-FLX-01 | Baseline | 2025-09-18 | 499 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-18 | 1076 |  |  | Septemeber
D-HOE215 | Lightspeed | 2025-09-18 |  |  | ABF Testing | Septemeber
D-HNP135 | Lightspeed | 2025-09-19 | 70 |  |  | Septemeber
FB-HWP1075 | Lightspeed | 2025-09-19 |  | 1210 | 1,010 Tracer Wire | Septemeber
BHT-FLX-01 | Baseline | 2025-09-19 | 475 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-19 |  |  | No Production | Septemeber
Skyview | Brothers | 2025-09-19 |  |  | 3 FDH / 3 HH / 3 Swing Arms / 3 Ground Rods | Septemeber
FB-HNP104 | Lightspeed | 2025-09-22 | 153 |  |  | Septemeber
OakHill MHP | H&H Underground | 2025-09-22 | 329 |  |  | Septemeber
D-HWP811 | Brothers | 2025-09-22 | 978 |  | 9 Toby Boxes / 6 Daps | Septemeber
D-HWP823 | Brothers | 2025-09-22 | 1285 |  | 13 Toby Boxes / 2 Flower Pots / 8 Daps / 79 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
FB-HWP480 | Lightspeed | 2025-09-22 | 335 |  | 1 HH / 1 Ground Rod | Septemeber
BHT-FLX-01 | Baseline | 2025-09-22 | 839 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-22 |  |  | No Production--Locate Issue | Septemeber
BHZD-FOE-03-W | Lightspeed | 2025-09-22 | 60 | 1005 | 805 Tracer Wire / 1 HH / 1 Ground Rod | Septemeber
BHU-FAL-01-E | HAS GLOBAL | 2025-09-22 | 415 |  |  | Septemeber
D-HNP135 | Lightspeed | 2025-09-23 | 224 |  | 1 Toby Box / 1 Dap | Septemeber
OakHill MHP | H&H Underground | 2025-09-23 | 427 |  |  | Septemeber
D-HWP811 | Brothers | 2025-09-23 | 675 |  |  | Septemeber
D-HWP816 | Brothers | 2025-09-23 | 1231 |  | 8 Toby Boxes / 3 Daps / 51 Splices | Septemeber
FB-HWP480 | Lightspeed | 2025-09-23 |  | 335 | 335 Tracer Wire / 1 HH | Septemeber
BHT-FLX-01 | Baseline | 2025-09-23 |  |  | No Production--Drill Issue | Septemeber
D-HOE302 | North Path | 2025-09-23 | 120 |  |  | Septemeber
D-HOE215 | Lightspeed | 2025-09-23 |  |  | ABF Testing | Septemeber
BHU-FAL-01-E | HAS Global | 2025-09-23 | 291 |  |  | Septemeber
FB-HNP104 | Lightspeed | 2025-09-24 | 260 |  |  | Septemeber
OakHill MHP | H&H Underground | 2025-09-24 | 537 |  |  | Septemeber
D-HWP818 | Brothers | 2025-09-24 | 1205 |  | 11 Toby Boxes / 1 Flower Pot / 7 Daps | Septemeber
D-HWP816 | Brothers | 2025-09-24 | 1538 |  | 13 Toby Boxes / 10 Daps / 67 Splices | Septemeber
BHU-FWP-08-E | Lightspeed | 2025-09-24 | 240 |  |  | Septemeber
D-HWP827 | Brothers | 2025-09-24 |  |  | 3 Toby Boxes / 1 Flower Pot / 4 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP811 | Brothers | 2025-09-24 | 170 |  | 18 Toby Boxes / 1 Flower Pot / 15 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
BHT-FLX-01 | Baseline | 2025-09-24 | 616 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-24 | 190 |  |  | Septemeber
FB-HLR201 | Lightspeed | 2025-09-24 | 362 |  |  | Septemeber
BHU-FAL-01-E | HAS Global | 2025-09-24 |  |  | Crew Did Not Show Up Today | Septemeber
BHT-FOE-03 | North Path | 2025-09-24 | 406 |  |  | Septemeber
D-HWP827 | Lightspeed | 2025-09-24 |  | 1837 | 12 CT Stingray | Septemeber
D-HWP809 | Lightspeed | 2025-09-24 |  | 731 | 12 CT Stingray | Septemeber
D-HWP811 | Lightspeed | 2025-09-24 |  | 178 | 12 CT Stingray | Septemeber
Skyview Estates | Lightspeed | 2025-09-24 |  | 2600 | 12 CT Stingray | Septemeber
FB-HNP111 | Lightspeed | 2025-09-25 | 175 |  |  | Septemeber
OakHill MHP | H&H Underground | 2025-09-25 | 646 |  | 18 Toby Boxes | Septemeber
D-HWP818 | Brothers | 2025-09-25 | 1000 |  |  | Septemeber
D-HWP816 | Brothers | 2025-09-25 | 1377 |  | 11 Toby Boxes / 8 Daps / 61 Splices | Septemeber
BHU-FWP-08-E | Lightspeed | 2025-09-25 | 504 |  |  | Septemeber
Mas Verde | J Garcia Underground | 2025-09-25 |  |  | No Production--Equipment Issues | Septemeber
BHT-FLX-01 | Baseline | 2025-09-25 | 969 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-25 |  |  | Restoration | Septemeber
FB-HLR201 | Lightspeed | 2025-09-25 | 399 |  |  | Septemeber
BHU-FAL-01-E | HAS Global | 2025-09-25 |  |  | No Production--Truck Breakdown | Septemeber
OakHill MHP | H&H Underground | 2025-09-26 | 793 |  | 6 Toby Boxes | Septemeber
Mas Verde | J Garcia Underground | 2025-09-26 | 3471 |  |  | Septemeber
Mas Verde | Baseline | 2025-09-26 | 300 |  |  | Septemeber
Mas Verde | Patriot Underground | 2025-09-26 | 364 |  |  | Septemeber
BHT-FLX-01 | Baseline | 2025-09-26 | 552 |  |  | Septemeber
D-HOE306 | North Path | 2025-09-26 | 551 |  |  | Septemeber
FB-HLR201 | Lightspeed | 2025-09-26 |  |  | No Crews Worked On This Location Today | Septemeber
BHU-FAL-01-E | Lightspeed | 2025-09-26 | 755 |  |  | Septemeber
FB-HNP111 | Lightspeed | 2025-09-29 | 229 |  |  | Septemeber
BHU-FWP-08-E | Lightspeed | 2025-09-29 | 80 | 851 | 2 HH / 851 Tracer Wire | Septemeber
Mas Verde | J Garcia Underground | 2025-09-29 | 1491 |  |  | Septemeber
Mas Verde | Patriot Underground | 2025-09-29 | 760 |  |  | Septemeber
D-HWP816 | Brothers | 2025-09-29 | 600 |  | 2 Toby Boxes / 3 Daps | Septemeber
D-HWP818 | Brothers | 2025-09-29 | 1002 |  | 14 Toby Boxes / 2 Flower Pots / 8 Daps | Septemeber
BHT-FLX-01 | Baseline | 2025-09-29 | 1375 |  |  | Septemeber
D-HOE215 | North Path | 2025-09-29 |  |  | ABF Testing | Septemeber
BHU-FAL-01-E | Lightspeed | 2025-09-29 | 1418 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-29 | 479 |  |  | Septemeber
D-HOE306 | North Path | 2025-09-29 | 454 |  |  | Septemeber
D-HWP818 | Brothers | 2025-09-30 | 268 | 413 | 2 Flower Pots / 1 Dap / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | Septemeber
FB-HNP133 | Lightspeed | 2025-09-30 | 134 |  |  | Septemeber
D-HST11 | GN Systems | 2025-09-30 | 1253 |  |  | Septemeber
D-HWP813 | Brothers | 2025-09-30 | 1850 |  | 15 Toby Boxes / 13 Daps / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | Septemeber
Mas Verde | J Garcia Underground | 2025-09-30 | 1559 |  | 4 Toby Boxes / 12 Daps / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | Septemeber
Mas Verde | Patriot Underground | 2025-09-30 | 455 |  |  | Septemeber
D-HWP823 | Lightspeed | 2025-09-30 |  | 536 |  | Septemeber
D-HWP816 | Lightspeed | 2025-09-30 |  | 886 |  | Septemeber
BHT-FLX-01 | Baseline | 2025-09-30 | 1016 |  |  | Septemeber
D-HWP813 | Lightspeed | 2025-09-30 |  | 191 |  | Septemeber
BHU-FAL-01-E | Lightspeed | 2025-09-30 | 701 |  | 2 HH / 2 Ground Rods | Septemeber
D-HOE306 | North Path | 2025-09-30 | 251 |  |  | Septemeber
BHT-FOE-03 | North Path | 2025-09-30 | 665 |  |  | Septemeber
D-HNP135 | Lightspeed | 2025-10-01 | 201 |  |  | October
D-HST11 | GN Systems | 2025-10-01 | 1351 |  |  | October
D-HWP813 | Brothers | 2025-10-01 | 1276 |  |  | October
Mas Verde | J Garcia Underground | 2025-10-01 | 1329 |  | 13 Toby Boxes / 12 Daps | October
Mas Verde | Patriot Underground | 2025-10-01 | 539 |  |  | October
D-HWP910 | Brothers | 2025-10-01 | 1118 |  |  | October
BHT-FLX-01 | Baseline | 2025-10-01 | 312 |  |  | October
BHT-FOE-03 | North Path | 2025-10-01 | 753 |  |  | October
D-HOE306 | North Path | 2025-10-01 | 224 |  |  | October
FB-HNP133 | Lightspeed | 2025-10-02 | 450 |  |  | October
D-HST11 | GN Systems | 2025-10-02 | 443 |  | 9 Toby Boxes / 42 Splices | October
D-HWP908 | Brothers | 2025-10-02 | 1393 |  | 8 Toby Boxes / 6 Daps | October
Mas Verde | J Garcia Underground | 2025-10-02 | 1410 |  | 13 Toby Boxes / 13 Daps | October
Mas Verde | Patriot Underground | 2025-10-02 | 747 |  | 4 Toby Boxes / 4 Daps | October
D-HWP910 | Brothers | 2025-10-02 | 1472 |  | 9 Toby Boxes / 5 Daps | October
D-HWP813 | Brothers | 2025-10-02 | 1479 |  | 8 Toby Boxes / 7 Daps | October
BHT-FLX-01 | Baseline | 2025-10-02 | 1304 |  |  | October
BHU-FAL-01-E | Lightspeed | 2025-10-02 | 614 |  |  | October
BHT-FOE-03 | North Path | 2025-10-02 | 305 |  |  | October
D-HOE306 | North Path | 2025-10-02 | 789 |  | 3 Toby Boxes / 3 Daps | October
D-HOE302 | North Path | 2025-10-02 | 170 |  |  | October
FB-HNP133 | Lightspeed | 2025-10-03 | 352 |  |  | October
D-HNP135 | Lightspeed | 2025-10-03 | 352 |  |  | October
D-HST11 | GN Systems | 2025-10-03 |  |  | 8 Toby Boxes | October
Mas Verde | J Garcia Underground | 2025-10-03 | 2420 |  | 6 Toby Boxes / 6 Daps | October
Mas Verde | Patriot Underground | 2025-10-03 | 533 |  | 7 Toby Boxes / 7 Daps | October
BHT-FLX-01 | Baseline | 2025-10-03 | 617 |  |  | October
BHU-FAL-01-E | Lightspeed | 2025-10-03 | 486 |  |  | October
D-HOE306 | North Path | 2025-10-03 |  |  | No Production--Driveway Repair | October
D-HOE302 | North Path | 2025-10-03 |  |  | No Production--Driveway Repair | October
D-HNP135 | Lightspeed | 2025-10-06 | 65 |  |  | October
FB-HNP133 | Lightspeed | 2025-10-06 | 175 |  |  | October
D-HST11 | GN Systems | 2025-10-06 | 192 |  | 30 Toby Boxes / 20 Daps / 78 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | October
D-HWP908 | Brothers | 2025-10-06 | 1545 |  |  | October
Mas Verde | J Garcia Underground | 2025-10-06 |  |  | 21 Toby Boxes / 21 Daps | October
Mas Verde | Patriot Underground | 2025-10-06 |  |  | 4 Toby Boxes / 4 Daps | October
D-HWP910 | Brothers | 2025-10-06 | 1174 |  |  | October
BHT-FLX-01 | Baseline | 2025-10-06 | 768 |  |  | October
BHU-FAL-01-E | HAS Global | 2025-10-06 | 225 |  |  | October
BHT-FOE-03 | North Path | 2025-10-06 |  |  | No Production | October
D-HOE306 | North Path | 2025-10-06 | 1088 |  | 4 Toby Boxes / 4 Daps | October
FB-HNP133 | Lightspeed | 2025-10-07 | 270 |  |  | October
D-HNP135 | Lightspeed | 2025-10-07 | 55 |  |  | October
D-HWP908 | Brothers | 2025-10-07 | 995 |  | 14 Toby Boxes / 8 Daps | October
Mas Verde | J Garcia Underground | 2025-10-07 | 216 |  | 10 Toby Boxes / 9 Daps | October
Mas Verde | Patriot Underground | 2025-10-07 |  |  | 4 Toby Boxes / 4 Daps | October
D-HWP910 | Brothers | 2025-10-07 | 1597 |  | 14 Toby Boxes / 5 Daps | October
BHT-FLX-01 | Baseline | 2025-10-07 | 1014 |  |  | October
BHU-FAL-01-E | HAS Global | 2025-10-07 | 416 |  |  | October
BHU-FAL-01-E | Lightspeed | 2025-10-07 | 871 |  |  | October
D-HOE306 | North Path | 2025-10-07 | 557 |  |  | October
D-HNP135 | Lightspeed | 2025-10-08 | 160 |  |  | October
D-HNP106 | Lightspeed | 2025-10-08 | 126 |  |  | October
D-HST11 | GN Systems | 2025-10-08 |  |  | Restorsation | October
FB-HWP376 | Brothers | 2025-10-08 | 1282 |  |  | October
Mas Verde | J Garcia Underground | 2025-10-08 |  |  | 10 Toby Boxes / 10 Daps | October
D-HWP910 | Brothers | 2025-10-08 | 308 |  | 19 Toby Boxes / 12 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | October
D-HWP818 | Brothers | 2025-10-08 | 334 |  | 4 Toby Boxes / 3 Daps | October
BHZD-FWP-08-W | Lightspeed | 2025-10-08 | 333 |  |  | October
BHU-FAL-01-E | Lightspeed | 2025-10-08 | 767 |  |  | October
BHU-FAL-01-E | HAS Global | 2025-10-08 | 418 |  |  | October
D-HOE306 | North Path | 2025-10-08 | 512 |  | 4 Toby Boxes / 3 Daps | October
FB-HNP111 | Lightspeed | 2025-10-09 | 270 |  |  | October
D-HNP106 | Lightspeed | 2025-10-09 | 229 |  |  | October
FB-HWP376 | Brothers | 2025-10-09 | 980 |  | 2 HH / 2 Ground Rods | October
Mas Verde | J Garcia Underground | 2025-10-09 |  |  | Proofing Conduits | October
D-HWP910 | Brothers | 2025-10-09 |  |  | Restoration | October
BHZD-FWP-08-W | Lightspeed | 2025-10-09 |  |  | No Production--Drill Breakdown | October
BHT-FLX-01 | Baseline | 2025-10-09 |  |  | No Production--Drill Breakdown | October
BHU-FAL-01-E | Lightspeed | 2025-10-09 | 508 |  |  | October
BHU-FAL-01-E | HAS Global | 2025-10-09 |  |  | Restoration | October
D-HOE306 | North Path | 2025-10-09 | 369 |  |  | October
D-HOE302 | North Path | 2025-10-09 | 725 |  |  | October
FB-HNP111 | Lightspeed | 2025-10-10 | 268 |  |  | October
D-HNP106 | Lightspeed | 2025-10-10 |  |  | No Production--Drill Breakdown. | October
D-HWP910 | Lightspeed | 2025-10-10 |  |  | Stingray Not Ready To Complete | October
Mas Verde | J Garcia Underground | 2025-10-10 |  |  | Proofing Conduits | October
D-HWP908 | Lightspeed | 2025-10-10 |  |  | Stingray Not Ready To Complete | October
BHU-FAL-01-E | HAS Global | 2025-10-10 |  |  | No Production--Did Not Have A Crew Work This Location Today. | October
BHU-FAL-01-E | Lightspeed | 2025-10-10 |  |  | 4 HH | October
BHT-FOE-03 | Lightspeed | 2025-10-10 |  |  | No Production--Soft Dig Not Complete | October
D-HNP106 | Lightspeed | 2025-10-13 |  |  | No Production | October
D-HNP135 | Lightspeed | 2025-10-13 |  |  | ABF / Sponge / Fix DAPs | October
Lake Shore Park | Patriot Underground | 2025-10-13 | 220 |  |  | October
BHZD-FWP-8-W | Lightspeed | 2025-10-13 | 233 |  |  | October
FB-HWP376 | Brothers | 2025-10-13 | 828 |  |  | October
D-HWP913 | Brothers | 2025-10-13 | 1768 |  |  | October
D-HWP908 | Lightspeed | 2025-10-13 |  |  | 6 Toby Boxes / 4 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod / 2 Stingrays | October
BHU-FAL-01-E | Lightspeed | 2025-10-13 | 916 |  |  | October
BHU-FAL-01-W-2 | Lightspeed | 2025-10-13 | 60 |  |  | October
D-HNP106 | Lightspeed | 2025-10-14 | 163 |  |  | October
Lake Shore Park | Patriot Underground | 2025-10-14 | 435 |  |  | October
D-HNP135 | Lightspeed | 2025-10-14 |  |  | ABF / Sponge / Fix DAPs | October
FB-HWP903 | Lightspeed | 2025-10-14 |  |  | Crew Pulled Off Project | October
FB-HWP376 | Brothers | 2025-10-14 | 150 |  |  | October
D-HWP913 | Brothers | 2025-10-14 | 510 |  | 19 Toby Boxes / 12 Daps / 1 HH / 1 Ground Rod | October
D-HWP915 | Brothers | 2025-10-14 | 974 |  | 10 Toby Boxes / 9 Daps / 52 Splices | October
Citrus Wood | J Garcia Underground | 2025-10-14 | 1603 |  | 15 Toby Boxes / 6 Daps | October
BHU-FAL-01-E | Lightspeed | 2025-10-14 | 144 |  |  | October
D-HLR207 | North Path | 2025-10-14 | 927 |  | 6 Toby Boxes / 6 Daps | October
BHU-FAL-01-W-2 | Lightspeed | 2025-10-14 | 219 |  |  | October
D-HNP106 | Lightspeed | 2025-10-15 | 535 |  |  | October
Lake Shore Park | Patriot Underground | 2025-10-15 | 227 |  | 7 Toby Boxes / 2 Daps | October
FB-HWP903 | Lightspeed | 2025-10-15 | 240 | 270 | 270 Tracer Wire | October
D-HWP915 | Brothers | 2025-10-15 | 1312 |  | 14 Toby Boxes / 10 Daps / 47 Splices | October
D-HWP909 | Brothers | 2025-10-15 | 1239 |  | 12 Toby Boxes / 9 Daps / 23 Splices | October
Citrus Wood | J Garcia Underground | 2025-10-15 | 791 |  | 9 Toby Boxes / 5 Daps | October
BHT-FLX-01 | Lightspeed | 2025-10-15 | 986 |  |  | October
D-HLR211 | GN Systems | 2025-10-15 | 1457 |  | 10 Toby Boxes / 9 Daps / 18 Splices | October
D-HLR207 | North Path | 2025-10-15 | 1221 |  | 7 Toby Boxes / 5 Daps / 13 Splices | October
D-HNP106 | Lightspeed | 2025-10-16 | 570 |  |  | October
D-HNP135 | Lightspeed | 2025-10-16 |  |  | ABF / Sponge / Fix DAPs | October
Lake Shore Park | Patriot Underground | 2025-10-16 | 487 |  | 7 Toby Boxes / 1 Dap / 2 Splices | October
D-HWP915 | Brothers | 2025-10-16 | 359 |  | 5 Toby Boxes / 3 Dap / 16 Splices | October
D-HWP909 | Brothers | 2025-10-16 | 1220 |  | 11 Toby Boxes / 7 Daps / 42 Splices | October
Citrus Wood | J Garcia Underground | 2025-10-16 | 2803 |  |  | October
FB-HWP376 | Brothers | 2025-10-16 | 688 |  | 4 HH / 4 Ground Rods | October
FB-HLR201 | Lightspeed | 2025-10-16 | 170 |  |  | October
D-HLR211 | GN Systems | 2025-10-16 | 1142 |  | 6 Toby Boxes / 5 Dap / 37 Splices | October
D-HLR207 | North Path | 2025-10-16 | 1023 |  | 4 Toby Boxes / 4 Daps / 8 Splices | October
D-HNP106 | Lightspeed | 2025-10-17 |  |  | 2 Toby Boxes / 1 Daps | October
D-HNP135 | Lightspeed | 2025-10-17 |  |  | ABF / Sponge / Fix DAPs | October
Lake Shore Park | Patriot Underground | 2025-10-17 | 123 |  | 4 Toby Boxes / 1 Dap | October
D-HWP910 | Lightspeed | 2025-10-17 |  |  | Stinyray | October
Citrus Wood | J Garcia Underground | 2025-10-17 |  |  | 4 Toby Boxes / 13 Daps | October
D-HLR211 | GN Systems | 2025-10-17 | 945 |  | 5 Toby Boxes / 4 Daps / 9 Splices | October
D-HNP106 | Lightspeed | 2025-10-20 | 92 |  | 1 Dap | October
FB-HNP133 | Lightspeed | 2025-10-20 | 153 |  |  | October
Lake Shore Park | Patriot Underground | 2025-10-20 |  |  | No Production--Crew Is Not Working This Location Today | October
D-HNP135 | Lightspeed | 2025-10-20 | 455 |  |  | October
D-HWP909 | Brothers | 2025-10-20 | 853 |  | 9 Toby Boxes / 7 Daps / 96 Splices | October
Citrus Wood | J Garcia Underground | 2025-10-20 | 3343 |  | 1 Toby Box / 9 Daps | October
BHT-FOE-03 | Lightspeed | 2025-10-20 | 151 |  |  | October
D-HLR211 | GN Systems | 2025-10-20 | 1186 |  | 5 Toby Boxes / 4 Daps | October
D-HLR207 | North Path | 2025-10-20 | 1100 |  |  | October
FB-HNP133 | Lightspeed | 2025-10-21 | 244 |  |  | October
Lake Shore Park | Patriot Underground | 2025-10-21 | 413 |  | 1 Toby Box | October
D-HWP915 | Brothers | 2025-10-21 | 230 |  | 3 Toby Boxes / 1 Dap / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | October
Citrus Wood | J Garcia Underground | 2025-10-21 | 714 |  | 4 Toby Boxes / 2 Daps | October
D-HWP912 | Brothers | 2025-10-21 | 1007 |  | 3 Toby Boxes / 2 Daps / 8 Splices | October
D-HWP1307 | Brothers | 2025-10-21 | 1182 |  | 8 Toby Boxes / 7 Daps / 26 Splices | October
BHT-FOE-03 | Lightspeed | 2025-10-21 | 149 |  |  | October
D-HLR211 | GN Systems | 2025-10-21 | 1564 |  | 9 Toby Boxes / 9 Daps / 38 Splices | October
D-HLR207 | North Path | 2025-10-21 | 527 |  | 4 Toby Boxes / 4 Daps / 8 Splices | October
FB-HOE178 | GN Systems | 2025-10-21 |  |  | No Production--Gas Line Hit | October
FB-HNP104 | Lightspeed | 2025-10-22 | 168 |  |  | October
Lake Shore Park | Patriot Underground | 2025-10-22 | 190 |  |  | October
Citrus Wood | J Garcia Underground | 2025-10-22 | 2013 |  | 35 Toby Boxes / 18 Daps | October
D-HWP1307 | Brothers | 2025-10-22 | 1604 |  | 9 Toby Boxes / 7 Daps / 38 Splices | October
D-HWP912 | Brothers | 2025-10-22 | 1672 |  | 15 Toby Boxes / 10 Daps / 82 Splices | October
BHT-FOE-03 | Lightspeed | 2025-10-22 |  |  | Fiber Pulling | October
D-HLR211 | GN Systems | 2025-10-22 | 1012 |  | 5 Toby Boxes / 4 Daps / 26 Splices | October
D-HLR207 | North Path | 2025-10-22 | 553 |  |  | October
FB-HOE178 | GN Systems | 2025-10-22 | 1624 |  |  | October
D-HNP106 | Lightspeed | 2025-10-23 | 209 |  | 3 Toby Boxes / 3 Daps / 8 Splices | October
FB-HNP133 | Lightspeed | 2025-10-23 | 237 |  |  | October
Lake Shore Park | Patriot Underground | 2025-10-23 | 844 |  | 19 Toby Boxes / 3 Daps / 28 Splices | October
Lake Shore Park | APT Communications | 2025-10-23 | 350 |  |  | October
Citrus Wood | J Garcia Underground | 2025-10-23 | 1500 |  | 5 Toby Boxes / 3 Daps | October
D-HWP1307 | Brothers | 2025-10-23 | 1268 |  | 6 Toby Boxes / 5 Daps / 10 Splices | October
D-HWP912 | Brothers | 2025-10-23 | 1544 |  | 6 Toby Boxes / 6 Daps / 39 Splices | October
BHZD-FWP-08-W | Lightspeed | 2025-10-23 |  |  | No Production--Drill Breakdown | October
BHT-FOE-03 | Lightspeed | 2025-10-23 |  |  | No Production | October
D-HLR211 | GN Systems | 2025-10-23 | 588 |  | 4 Toby Boxes / 2 Daps / 6 Splices | October
FB-HOE178 | GN Systems | 2025-10-23 | 551 |  |  | October
D-HNP106 | Lightspeed | 2025-10-24 | 434 |  | 4 Toby Box / 4 Daps | October
FB-HNP104 | Lightspeed | 2025-10-24 | 34 |  |  | October
Lake Shore Park | Patriot Underground | 2025-10-24 | 142 |  | 1 Toby Box / 1 Dap / 12 Splices | October
Lake Shore Park | APT Communications | 2025-10-24 | 164 |  | 9 Toby Box / 2 Dap / 14 Splices | October
Citrus Wood | J Garcia Underground | 2025-10-24 | 1933 |  |  | October
BHT-FOE-03 | Lightspeed | 2025-10-24 |  |  | Pulling Fiber Cable | October
D-HLR210 | GN Systems | 2025-10-24 | 408 |  |  | October
D-HNP106 | Lightspeed | 2025-10-27 | 567 |  | 5 Toby Boxes / 1 Dap | October
FB-HNP104 | Lightspeed | 2025-10-27 | 188 |  |  | October
Lake Shore Park | Patriot Underground | 2025-10-27 |  |  | 1 Toby Box | October
Lake Shore Park | APT Communications | 2025-10-27 | 203 |  |  | October
Wilders Park | Kattle One | 2025-10-27 | 1224 |  | 12 Toby Boxes | October
Wilders Park | Maximo | 2025-10-27 |  |  | No Production | October
Citrus Wood | J Garcia Underground | 2025-10-27 | 820 |  | 28 Toby Boxes / 12 Daps | October
D-HWP912 | Brothers | 2025-10-27 | 587 |  | 12 Toby Boxes / 8 Daps / 131 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | October
D-HWP1307 | Brothers | 2025-10-27 | 1310 |  | 3 Toby Boxes / 3 Daps / 16 Splices / 1 HH / 1 Ground Rod | October
BHZD-FWP-08-W | Brothers | 2025-10-27 | 270 |  |  | October
FB-HLR201 | Lightspeed | 2025-10-27 |  |  | No Production--Crew Did Not Work This Location Today | October
D-HLR210 | GN Systems | 2025-10-27 | 1323 |  | 10 Toby Boxes / 10 Daps / 61 Splices | October
D-HLR207 | North Path | 2025-10-27 |  |  | No Production--Crew Did Not Work This Location Today | October
D-HNP106 | Lightspeed | 2025-10-28 |  |  | Placing FDH and Restoration | October
FB-HNP104 | Lightspeed | 2025-10-28 | 140 |  |  | October
Lake Shore Park | Patriot Underground | 2025-10-28 |  |  | No Production | October
Lake Shore Park | APT Communications | 2025-10-28 | 996 |  |  | October
Wilders Park | Kattle One | 2025-10-28 | 988 |  | 13 Toby Boxes | October
Wilders Park | Maximo | 2025-10-28 |  |  | No Production Crew Did Not Show Up Today | October
Citrus Wood | J Garcia Underground | 2025-10-28 | 2077 |  |  | October
D-HWP914 | Brothers | 2025-10-28 | 1509 |  | 13 Toby Boxes / 10 Daps / 70 Splices | October
D-HWP911 | Brothers | 2025-10-28 | 1678 |  | 9 Toby Boxes / 10 Daps / 47 Splices | October
D-HWP912 | Brothers | 2025-10-28 | 115 |  | 1 Dap / 2 Splices | October
BHZD-FWP-08-W | Lightspeed | 2025-10-28 | 60 | 886 | 2 HH / 886 Tracer Wire | October
D-HLR210 | GN Systems | 2025-10-28 | 1516 |  | 7 Toby Boxes / 12 Daps / 49 Splices | October
D-HLR207 | North Path | 2025-10-28 | 1224 |  |  | October
D-HLR207 | North Path | 2025-10-28 | 423 |  |  | October
FB-HNP111 | Lightspeed | 2025-10-29 | 171 |  |  | October
Lake Shore Park | Patriot Underground | 2025-10-29 |  |  | FDH Location | October
Lake Shore Park | Sosa Line | 2025-10-29 | 1147 |  | 17 Toby Boxes / 3 Daps / 14 Splices | October
Lake Shore Park | APT Communications | 2025-10-29 |  |  | 16 Toby Boxes / 3 Daps / 14 Splices | October
Wilders Park | Kattle One | 2025-10-29 | 1011 |  | 12 Toby Boxes | October
Wilders Park | APT Communications | 2025-10-29 | 1305 |  |  | October
Citrus Wood | J Garcia Underground | 2025-10-29 | 1096 |  | 28 Toby Boxes / 10 Daps | October
D-HWP914 | Brothers | 2025-10-29 | 1087 |  | 12 Toby Boxes / 10 Daps / 40 Splices | October
D-HLR210 | GN Systems | 2025-10-29 | 790 |  | 6 Toby Boxes / 5 Daps / 12 Splices | October
D-HLR207 | North Path | 2025-10-29 | 343 |  |  | October
D-HLR203 | North Path | 2025-10-29 | 3179 |  |  | October
BHT-FLX-01 | Lightspeed | 2025-10-29 |  |  | 30 Hand Trench / 2 HH / 2 Ground Rods / 2,850 Mule Tape | October
BHT-FOE-03 | Lightspeed | 2025-10-29 |  | 5475 | 4,875 Tracer Wire and Mule Tape | October
Lake Shore Park | Patriot Underground | 2025-10-30 |  |  | Placing FDH | October
Lake Shore Park | Sosa Line | 2025-10-30 | 1053 |  | 15 Toby Boxes / 4 Daps / 28 Splices | October
Wilders Park | Kattle One | 2025-10-30 | 1141 |  | 13 Toby Boxes / 1 Daps / 12 Splices | October
Wilders Park | APT Communications | 2025-10-30 | 925 |  | 24 Toby Boxes | October
Citrus Wood | J Garcia Underground | 2025-10-30 |  |  | 2 Toby Boxes / 2 HH / 2 FDH's / 2 Swing Arms / 2 Grounds | October
D-HWP914 | Brothers | 2025-10-30 | 777 |  | 3 Toby Boxes / 2 Flower Pots / 5 Daps / 68 Splices | October
D-HWP911 | Brothers | 2025-10-30 | 394 | 1275 | 6 Toby Boxes / 2 Daps / 15 Splices | October
FB-HWP901 | Brothers | 2025-10-30 | 978 |  |  | October
FB-HWP1377 | Lightspeed | 2025-10-30 | 502 |  | 1 HH / 1 Ground Rod | October
D-HWP912 | Lightspeed | 2025-10-30 |  | 669 |  | October
D-HWP913 | Brothers | 2025-10-30 |  |  | 3 Toby Boxes / 4 Daps | October
D-HLR207 | North Path | 2025-10-30 |  |  | Proofing Conduits | October
D-HLR210 | GN Systems | 2025-10-30 | 930 |  | 4 Toby Boxes / 4 Daps | October
D-HLR204 | Gold Gate Path | 2025-10-30 | 346 |  |  | October
BHT-FLX-01 | Lightspeed | 2025-10-30 |  |  | 1 HH / 736 Mule Tape | October
D-HNP106 | Lightspeed | 2025-10-31 |  |  | Proofing / Restoration | October
Lake Shore Park | Patriot Underground | 2025-10-31 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | October
Lake Shore Park | Sosa Line | 2025-10-31 | 955 |  | 13 Toby Boxes / 4 Daps / 22 Splices | October
Wilders Park | Kattle One | 2025-10-31 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | October
Wilders Park | APT Communications | 2025-10-31 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | October
Citrus Wood | J Garcia Underground | 2025-10-31 |  | 1428 |  | October
D-HWP914 | Brothers | 2025-10-31 |  |  | FDH / Proofing | October
D-HWP914 | Lightspeed | 2025-10-31 |  | 1862 | Stingray | October
FB-HOE301 | Lightspeed | 2025-10-31 | 60 |  |  | October
D-HLR210 | GN Systems | 2025-10-31 | 408 |  | 13 Toby Boxes / 4 Daps / 9 Splices | October
D-HLR204 | Gold Gate Path | 2025-10-31 |  |  | No Production | October
FB-HOE178 | GN Systems | 2025-10-31 | 168 |  |  | October
D-HNP106 | Lightspeed | 2025-11-03 |  |  | Proofing / Restoration | November
Lake Shore Park | Sosa Line | 2025-11-03 |  |  | FDH | November
FB-HWP901 | Brothers | 2025-11-03 | 1420 |  | 2 HH / 2 Ground Rods | November
D-HWP1307 | Brothers | 2025-11-03 | 701 |  | 1 Dap | November
D-HWP918 | Brothers | 2025-11-03 | 579 |  | 4 Toby Boxes / 3 Daps / 8 Splices | November
FB--HWP1377 | J Garcia Underground | 2025-11-03 | 365 |  |  | November
FB-HWP1377 | Lightspeed | 2025-11-03 | 259 |  |  | November
FB-HOE178 | GN Systems | 2025-11-03 | 463 |  |  | November
D-HLR203 | North Path | 2025-11-03 | 882 |  | 3 Toby Boxes / 3 Daps / 5 Splices | November
BHT-FLX-01 | Lightspeed | 2025-11-03 |  |  | 3 HH / 3 Ground Rods | November
BHT-FLX-01 | HYN Enterprise | 2025-11-03 |  | 3846 | 3,846 Tracer Wire / 2 Ground Rods | November
BHT-FLX-01 | Baseline | 2025-11-03 |  |  | 15 HH / 5 Ground Rods | November
FB-HOE675 | Lightspeed | 2025-11-03 | 207 |  |  | November
D-HSH222 | Brothers | 2025-11-03 | 3266 |  | 18 Toby Boxes / 19 Daps | November
D-HNP106 | Lightspeed | 2025-11-04 |  |  | Proofing / Restoration | November
Lake Shore Park | Sosa Line | 2025-11-04 |  |  | FDH | November
Sunset Palms MHP | Kattle One | 2025-11-04 | 363 |  |  | November
Sunset Palms MHP | GN Systems | 2025-11-04 | 778 |  |  | November
Sunset Palms MHP | Patriot Underground | 2025-11-04 | 550 |  |  | November
D-HWP918 | Brothers | 2025-11-04 | 1120 |  | 6 Toby Boxes / 6 Daps / 25 Splices | November
FB-HWP901 | Brothers | 2025-11-04 | 990 |  | 2 HH | November
FB-HWP1377 | J Garcia Underground | 2025-11-04 | 817 |  |  | November
FB-HWP1377 | Lightspeed | 2025-11-04 | 270 |  |  | November
FB-HOE178 | GN Systems | 2025-11-04 | 633 |  |  | November
D-HLR204 | Gold Gate Path | 2025-11-04 | 379 |  | 6 Toby Boxes / 2 Daps | November
D-HLR203 | North Path | 2025-11-04 | 1072 |  | 7 Toby Boxes / 5 Daps / 21 Splices | November
D-HLR211 | GN Systems | 2025-11-04 |  |  | 1 FDH / 1 HH / 1 Ground Rod | November
FB-HOE375 | Lightspeed | 2025-11-04 |  |  | 1 HH / 1 Ground Rod | November
D-HSH222 | Brothers | 2025-11-04 | 3910 |  | 25 Toby Boxes / 12 Daps | November
D-HSH224 | Brothers | 2025-11-04 | 372 |  |  | November
Sunset Palms MHP | Kattle One | 2025-11-05 | 1113 |  |  | November
Sunset Palms MHP | GN Systems | 2025-11-05 | 885 |  |  | November
D-HWP918 | Brothers | 2025-11-05 | 1488 |  | 9 Toby Boxes / 7 Daps / 30 Splices | November
FB-HWP901 | Brothers | 2025-11-05 | 549 |  | 3 HH | November
FB-HWP1377 | J Garcia Underground | 2025-11-05 | 1377 |  |  | November
FB-HWP1377 | Lightspeed | 2025-11-05 | 829 |  |  | November
FB-HWP1379 | Brothers | 2025-11-05 | 1031 |  |  | November
FB-HOE178 | GN Systems | 2025-11-05 | 625 |  |  | November
D-HLR204 | Gold Gate Path | 2025-11-05 | 208 |  | 2 Toby Boxes | November
D-HLR203 | North Path | 2025-11-05 | 1034 |  |  | November
BHU-FAL-01-W-2 | Lightspeed | 2025-11-05 | 150 |  |  | November
BHT-FLX-01 | HYN Enterprise | 2025-11-05 |  | 13112 | 13,112 Tracer Wire | November
D-HSH222 | Brothers | 2025-11-05 | 346 |  | 1 HH / 1 Ground Rod | November
D-HSH224 | Brothers | 2025-11-05 | 656 |  |  | November
D-HSH223 | Brothers | 2025-11-05 | 2985 |  | 24 Toby Boxes / 14 Daps | November
Sunset Palms MHP | Kattle One | 2025-11-06 |  |  | 6 Toby Boxes / 1 Dap / 4 Splices | November
Sunset Palms MHP | Legant Livings | 2025-11-06 | 760 |  |  | November
D-HWP918 | Brothers | 2025-11-06 | 954 |  | 8 Toby Boxes / 6 Daps / 31 Splices / 1 HH / 1 FDH / 1 Swing Arm / 1 Ground Rod | November
FB-HWP1377 | J Garcia Underground | 2025-11-06 | 183 |  |  | November
FB-HWP1377 | Lightspeed | 2025-11-06 | 270 |  |  | November
FB-HOE178 | HYN Enterprise | 2025-11-06 |  | 5200 | 5,200 Tracer Wire | November
D-HLR204 | Gold Gate Path | 2025-11-06 |  |  | No Production Crew Did Not Work This Location Today | November
D-HLR203 | North Path | 2025-11-06 | 209 |  |  | November
FB-HOE175 | GN Systems | 2025-11-06 | 1063 |  |  | November
D-HSH223 | Brothers | 2025-11-06 | 2373 |  | 13 Toby Boxes / 9 Daps | November
Sunset Palms MHP | Kattle One | 2025-11-07 | 923 |  |  | November
Sunset Palms MHP | Sosa Line | 2025-11-07 | 3052 |  |  | November
Wilders MHP | APT Communications | 2025-11-07 | 451 |  |  | November
FB-HWP1377 | J Garcia Underground | 2025-11-07 |  |  |  | November
FB-HOE175 | Lightspeed | 2025-11-07 | 350 |  |  | November
FB-HOE175 | GN Systems | 2025-11-07 | 913 |  | 3 HH | November
D-HLR204 | Gold Gate Path | 2025-11-07 |  |  | No Production Crew Did Not Work This Location Today | November
D-HLR210 | GN Systems | 2025-11-07 |  |  | FDH | November
D-HOE306 | North Path | 2025-11-07 | 569 |  |  | November
D-HSH240 | Brothers | 2025-11-07 | 2948 |  |  | November
Lake Shore Park | APT Communications | 2025-11-10 | 560 |  |  | November
FB-HWP1377 | Lightspeed | 2025-11-10 | 558 |  |  | November
FB-HWP1377 | J Garcia Underground | 2025-11-10 |  |  | 7 HH / 7 Ground Rods | November
FB-HWP1379 | Brothers | 2025-11-10 | 1351 |  |  | November
D-HWP1307 | Brothers | 2025-11-10 | 138 |  | 2 Daps / 6 Splices | November
FB-HWP901 | Brothers | 2025-11-10 | 632 |  | 3 HH / 3 Ground Rods | November
Sherwood Estates | H&H Underground | 2025-11-10 | 748 |  |  | November
D-HLR203 | North Path | 2025-11-10 | 96 |  |  | November
D-HLR204 | Gold Gate Path | 2025-11-10 | 562 |  |  | November
D-HLR205 | North Path | 2025-11-10 | 435 |  | 4 Daps / 8 Splices | November
D-HSH240 | Brothers | 2025-11-10 | 4084 |  |  | November
FB-HWP901 | Lightspeed | 2025-11-11 |  | 5569 | 4,569 Tracer Wire | November
Sherwood Estates | H&H Underground | 2025-11-11 | 1062 |  | 12 Toby Boxes / 12 Daps / 42 Splices | November
D-HLR211 | Lightspeed | 2025-11-11 |  |  | Could Not Complete Stingray Path | November
BHU-FAl-01-E | Lightspeed | 2025-11-11 |  |  | Mule Tape | November
FB-HNP138 | Lightspeed | 2025-11-12 |  |  | No Production--Drill Breakdown | November
FB-HWP1377 | Lightspeed | 2025-11-12 |  |  | 2 HH / 2 Ground Rods | November
D-HWP917 | Brothers | 2025-11-12 | 1580 |  | 9 Toby Boxes / 5 Daps | November
FB-HWP1379 | Brothers | 2025-11-12 | 890 |  |  | November
FB-HWP1379 | J Garcia Underground | 2025-11-12 |  |  | 1 HH / 1 Ground Rod | November
D-HWP916 | Brothers | 2025-11-12 | 877 |  | 4 Toby Boxes / 2 Daps / 7 Splices | November
Citrus Woods | Lightspeed | 2025-11-12 |  | 6640 |  | November
BHZD-FLX-04-W | Lightspeed | 2025-11-12 | 711 |  | 1 HH | November
D-HLR210 | GN Systems | 2025-11-12 |  |  | 2 HH / 1 FDH / 1 Swing Arm / 2 Ground Rods | November
D-HDF711 | GN Systems | 2025-11-12 | 1486 |  | 5 Toby Boxes / 4 Daps / 18 Splices | November
D-HLR204 | Gold Gate Path | 2025-11-12 | 474 |  |  | November
D-HSH240 | Brothers | 2025-11-12 | 242 |  |  | November
D-HSH237 | Brothers | 2025-11-12 | 1264 |  |  | November
D-HSH242 | Brothers | 2025-11-12 | 3678 |  |  | November
FB-HWP1377 | Lightspeed | 2025-11-13 |  |  | 5 HH | November
D-HWP917 | Brothers | 2025-11-13 | 1258 |  | 12 Toby Boxes / 7 Daps | November
D-HWP916 | Brothers | 2025-11-13 | 814 |  | 9 Toby Boxes / 6 Daps / 24 Splices | November
BHZD-FLX-04-W | Lightspeed | 2025-11-13 | 325 |  |  | November
BHZD-FLX-04-W | Lightspeed | 2025-11-13 |  |  | 3 HH | November
D-HLR204 | Gold Gate Path | 2025-11-13 | 606 |  |  | November
D-HLR205 | North Path | 2025-11-13 | 1123 |  | 6 Toby Boxes / 4 Daps / 10 Splices | November
D-HDF711 | GN Systems | 2025-11-13 | 2912 |  |  | November
BHU-FAL-01-E | Lightspeed | 2025-11-13 |  |  | 3 HH | November
D-HSH242 | Brothers | 2025-11-13 | 3382 |  |  | November
D-HSH237 | Brothers | 2025-11-13 | 1281 |  |  | November
FB-HSH241 | Brothers | 2025-11-13 | 424 |  |  | November
D-HSH243 | Brothers | 2025-11-13 | 598 |  |  | November
FB-HWP1377 | Lightspeed | 2025-11-14 |  | 5647 | 5,647 Tracer Wire | November
D-HWP1307 | Lightspeed | 2025-11-14 |  | 565 |  | November
Sherwood | H&H Underground | 2025-11-14 | 1505 |  | 22 Toby Boxes / 21 Daps / 61 Splices | November
BHZD-FLX-04-W | Lightspeed | 2025-11-14 | 430 |  |  | November
D-HLR204 | Gold Gate Path | 2025-11-14 | 322 |  |  | November
D-HDF711 | GN Systems | 2025-11-14 | 2125 |  |  | November
FB-HWP1377 | Lightspeed | 2025-11-17 | 127 |  |  | November
FB-HWP1377 | Lightspeed | 2025-11-17 |  | 300 | 300 Tracer Wire | November
Heatherwood MHP | J Garcia Underground | 2025-11-17 | 1505 |  |  | November
D-HWP1312 | Brothers | 2025-11-17 | 1471 |  | 5 Toby Boxes | November
Sherwood | H&H Underground | 2025-11-17 | 907 |  | 1 HH | November
D-HWP1311 | Brothers | 2025-11-17 | 762 |  |  | November
D-HWP916 | Brothers | 2025-11-17 | 956 |  | 14 Toby Boxes / 9 Daps | November
FB-HLR201 | Lightspeed | 2025-11-17 | 176 |  |  | November
FB-HLR201 | Lightspeed | 2025-11-17 | 270 |  |  | November
D-HLR204 | Gold Gate Path | 2025-11-17 | 420 |  |  | November
D-HDF711 | GN Systems | 2025-11-17 | 1449 |  |  | November
D-HSH241 | Brothers | 2025-11-17 | 5466 |  |  | November
D-HSH237 | Brothers | 2025-11-17 | 1662 |  |  | November
D-HSH243 | Brothers | 2025-11-17 | 1498 |  |  | November
Lake Shore Park | APT Communications | 2025-11-18 | 17 |  |  | November
Wilders | APT Communications | 2025-11-18 | 12 |  |  | November
FB-HWP1379 | Lightspeed | 2025-11-18 |  | 3272 | 3,2722 Tracer Wire | November
Heatherwood MHP | J Garcia Underground | 2025-11-18 | 1518 |  |  | November
D-HWP1313 | Brothers | 2025-11-18 | 1679 |  | 11 Toby Boxes / 10 Daps / 43 Splices | November
Sherwood | H&H Underground | 2025-11-18 |  |  | 5 Toby Boxes / 5 Daps / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | November
D-HWP1311 | Brothers | 2025-11-18 | 1530 |  | 11 Toby Boxes / 9 Daps / 29 Splices | November
BHUD-FOE-06-E-2 | Lightspeed | 2025-11-18 | 136 |  |  | November
FB-HLR201 | Lightspeed | 2025-11-18 | 120 |  |  | November
D-HLR205 | North Path | 2025-11-18 | 1917 |  |  | November
D-HDF713 | GN Systems | 2025-11-18 | 2351 |  |  | November
D-HSH237 | Brothers | 2025-11-18 | 2684 |  |  | November
D-HSH243 | Brothers | 2025-11-18 | 3613 |  |  | November
Sunset Palms | Kattle One | 2025-11-19 | 480 |  | 9 Flower Pots | November
D-HWP1307 | Lightspeed | 2025-11-19 |  | 2996 | 2,946 Tracer Wire | November
Heatherwood MHP | J Garcia Underground | 2025-11-19 | 1968 |  | 23 Toby Boxes / 23 Daps / 46 Splices | November
D-HWP1313 | Brothers | 2025-11-19 | 1429 |  | 11 Toby Boxes / 8 Daps / 44 Splices | November
Sherwood | H&H Underground | 2025-11-19 |  |  | FDH / Proofing | November
D-HWP1311 | Brothers | 2025-11-19 | 954 |  | 7 Toby Boxes / 5 Daps / 33 Splices | November
BHUD-FOE-06-E-2 | Lightspeed | 2025-11-19 | 170 |  |  | November
FB-HLR201 | Lightspeed | 2025-11-19 | 550 |  |  | November
D-HDF713 | GN Systems | 2025-11-19 | 1835 |  |  | November
FB-HNP138 | Lightspeed | 2025-11-20 | 170 |  |  | November
Sunset Palms | Kattle One | 2025-11-20 |  |  | 4 Flower Pots | November
D-HWP1311 | Brothers | 2025-11-20 | 1603 |  | 16 Toby Boxes / 11 Daps / 32 Splices | November
Heatherwood MHP | J Garcia Underground | 2025-11-20 | 345 |  | 10 Toby Boxes / 10 Daps / 20 Splices | November
D-HWP1313 | Brothers | 2025-11-20 | 1624 |  | 14 Toby Boxes / 8 Daps / 52 Splices | November
D-HWP1307 | Lightspeed | 2025-11-20 |  | 728 |  | November
BHZD-FLX-04-W | Lightspeed | 2025-11-20 | 195 |  | 1 HH / 2 Ground Rods | November
FB-HLR201 | Lightspeed | 2025-11-20 |  |  | 1 HH | November
D-HLR205 | North Path | 2025-11-20 | 272 |  |  | November
D-HDF711 | GN Systems | 2025-11-21 |  |  | 1 HH / 1 FDH / 1 Swing Arm / 1 Ground Rod | November
D-HDF713 | GN Systems | 2025-11-20 | 2139 |  |  | November
D-HSH241 | Brothers | 2025-11-20 | 2252 |  |  | November
D-HSH243 | Brothers | 2025-11-20 | 1027 |  |  | November
D-HSH244 | Brothers | 2025-11-20 | 1420 |  |  | November
D-HSH245 | Brothers | 2025-11-20 | 2376 |  |  | November
FB-HSH241 | Brothers | 2025-11-20 | 313 |  |  | November
FB-HNP138 | Lightspeed | 2025-11-21 | 271 |  |  | November
Sunset Palms | Kattle One | 2025-11-21 | 448 | 200 | 1 HH / 1 FDH / 1 Swing Arm / 2 Ground Rods / 250 Tracer Wire | November
Heatherwood MHP | J Garcia Underground | 2025-11-21 | 375 |  |  | November
BHUD-FOE-06-E-2 | Lightspeed | 2025-11-21 | 15 | 1159 | 1 HH / 1 Ground Rod / 849 Tracer Wire / 528 Mule Tape | November
D-HDF713 | GN Systems | 2025-11-21 | 789 |  | 9 Toby Boxes / 5 Daps / 30 Splices | November
D-HDF714 | GN Systems | 2025-11-21 | 1281 |  | 2 Daps / 10 Splices | November
D-HSH237 | Brothers | 2025-11-21 | 51 |  |  | November
FB-HSH241 | Brothers | 2025-11-21 | 3007 |  |  | November
D-HSH243 | Brothers | 2025-11-21 | 490 |  |  | November
D-HSH244 | Brothers | 2025-11-21 | 3043 |  |  | November
D-HSH245 | Brothers | 2025-11-21 | 1217 |  |  | November
D-HSH220 | Lightspeed | 2025-11-21 |  | 2257 | Stingray | November
D-HSH221 | Lightspeed | 2025-11-21 |  | 734 | Stingray | November
FB-HNP138 | Lightspeed | 2025-11-24 |  |  | No Production--Locate Issues | November
FB-HNP111 | Lightspeed | 2025-11-24 |  |  | No Production--Locate Issues | November
D-HNP108 | Lightspeed | 2025-11-24 |  |  | No Production--Locate Issues | November
Sunset Palms | Kattle One | 2025-11-24 | 1270 |  | 4 Flower Pots / 14 Splices | November
Sunset Palms | Legant Livings | 2025-11-24 | 448 |  |  | November
FX4-FWP-09 | Brothers | 2025-11-24 | 82 |  | 1 HH / 1 Concrete Pad | November
Heatherwood MHP | J Garcia Underground | 2025-11-24 | 2805 |  |  | November
D-HWP1311 | Brothers | 2025-11-24 | 805 |  | 11 Toby Boxes / 6 Daps / 25 Splices / 1 FDH/ 1 HH / 1 Swing Arm / 1 Ground Rod | November
D-HWP1312 | Brothers | 2025-11-24 | 665 |  |  | November
D-HWP1313 | Brothers | 2025-11-24 | 572 |  | 2 Toby Boxes / 3 Daps / 21 Splices | November
FB-HWP483 | Lightspeed | 2025-11-24 | 286 |  |  | November
D-HWP916 | Lightspeed | 2025-11-24 |  | 734 |  | November
D-HWP917 | Lightspeed | 2025-11-24 |  | 719 |  | November
D-HLR205 | North Path | 2025-11-24 | 900 |  | 3 Toby Boxes / 4 Daps / 17 Splices | November
FB-HOE178 | GN Systems | 2025-11-24 |  |  | 10 Ground Rod | November
FB-HOE175 | GN Systems | 2025-11-24 |  |  | 3 Ground Rod | November
D-HLR210 | GN Systems | 2025-11-24 |  |  | 1 Ground Rod | November
D-HDF704 | GN Systems | 2025-11-24 | 1655 |  | 7 Daps / 34 Splices | November
FB-HNP111 | Lightspeed | 2025-11-25 | 68 |  |  | November
Sunset Palms | Kattle One | 2025-11-25 | 500 |  | 7 Flower Pots / 25 Splices | November
Sunset Palms | Legant Livings | 2025-11-25 | 541 |  |  | November
Sunset Palms | Patriot Underground | 2025-11-25 | 1437 |  |  | November
FB-HWP483 | Lightspeed | 2025-11-25 | 357 |  | 1 HH | November
Heatherwood MHP | J Garcia Underground | 2025-11-25 | 1397 |  |  | November
D-HWP1314 | Brothers | 2025-11-25 | 1100 |  |  | November
D-HWP1312 | Brothers | 2025-11-25 | 1360 |  | 18 Toby Boxes / 17 Daps / 68 Splices | November
Fountain View | H&H Underground | 2025-11-25 | 486 |  |  | November
FB-HOE178 | GN Systems | 2025-11-25 |  |  | Restoration | November
FB-HOE175 | GN Systems | 2025-11-25 |  |  | Restoration | November
D-HLR210 | GN Systems | 2025-11-25 |  |  | Restoration | November
D-HDF714 | GN Systems | 2025-11-25 | 2568 |  |  | November
D-HDF704 | GN Systems | 2025-11-25 | 2537 |  |  | November
D-HSH238 | Brothers | 2025-11-25 | 2382 |  |  | November
D-HSH223 | Brothers | 2025-11-25 | 996 |  |  | November
D-HSH246 | Brothers | 2025-11-25 | 3634 |  |  | November
D-HSH245 | Brothers | 2025-11-25 | 3311 |  |  | November
D-HSH224 | Brothers | 2025-11-25 | 1175 |  |  | November
D-HSH244 | Brothers | 2025-11-25 | 3411 |  |  | November
Sunset Palms | Kattle One | 2025-11-26 |  |  | No Production | November
Sunset Palms | Legant Livings | 2025-11-26 | 179 |  |  | November
Sunset Palms | Patriot Underground | 2025-11-26 | 1388 |  |  | November
FB-HNP111 | Lightspeed | 2025-11-26 |  |  | No Production | November
FB-HWP483 | Lightspeed | 2025-11-26 | 331 | 1063 | 1 HH / 1 Ground Rod / 994 Tracer Wire | November
D-HWP1312 | Brothers | 2025-11-26 | 1024 |  | 9 Toby Boxes / 7 Daps / 40 Splices | November
D-HWP1314 | Brothers | 2025-11-26 | 855 |  | 9 Toby Boxes / 7 Daps / 28 Splices | November
Heatherwood Village | J Garcia Underground | 2025-11-26 | 955 |  | 17 Toby Boxes / 17 Daps / 34 Splices | November
Sherwood Mobile Manor | H&H Underground | 2025-11-26 |  |  | 2 FDH / 2 HH / 2 Ground Rods | November
FB-HOE178 | GN Systems | 2025-11-26 |  |  | Restoration | November
FB-HOE175 | GN Systems | 2025-11-26 |  |  | Restoration | November
D-HLR210 | GN Systems | 2025-11-26 |  |  | Restoration | November
D-HLR203 | North Path | 2025-11-26 |  |  | Restoration | November
D-HLR204 | Gold Gate Path | 2025-11-26 | 426 |  |  | November
D-HLR205 | North Path | 2025-11-26 |  |  | Restoration | November
BHU-FAL-01-E | HYN Enterprise | 2025-11-26 |  | 4668 | 4,218 Tracer Wire | November
D-HSH222 | Lightspeed | 2025-11-26 |  | 794 |  | November
D-HSH224 | Brothers | 2025-11-26 |  | 2338 | 2,088 Tracer Wire | November
D-HSH225 | Lightspeed | 2025-11-26 |  | 175 |  | November
D-HSH225 | Brothers | 2025-11-26 |  | 2455 | 2,205 Tracer Wire | November
D-HSH226 | Lightspeed | 2025-11-26 |  | 376 |  | November
D-HSH226 | Brothers | 2025-11-26 |  | 404 | 354 Tracer Wire | November
D-HSH227 | Lightspeed | 2025-11-26 |  | 1264 |  | November
D-HSH228 | Lightspeed | 2025-11-26 |  | 1520 |  | November
D-HSH229 | Lightspeed | 2025-11-26 |  | 1739 |  | November
D-HSH230 | Lightspeed | 2025-11-26 |  | 1584 |  | November
D-HSH231 | Lightspeed | 2025-11-26 |  | 1140 |  | November
D-HSH232 | Lightspeed | 2025-11-26 |  | 692 |  | November
|  | 2025-11-27 |  |  |  | November
D-HWP1311 | Lightspeed | 2025-11-28 |  | 160 | 60 Tracer Wire | November
D-HNP108 | Lightspeed | 2025-12-01 | 523 |  |  | December
Vantage Point | APT Communications | 2025-12-01 | 545 |  |  | December
Sunset Palms MHP | Kattle One | 2025-12-01 | 602 |  | 7 Flower Pots / 16 Splices | December
Sunset Palms MHP | Patriot Underground | 2025-12-01 |  |  | 4 Flower Pots / 1 Toby Box / 16 Splices | December
D-HWP1312 | Brothers | 2025-12-01 | 1610 |  | 13 Toby Boxes / 8 Daps / 13 Splices | December
D-HWP1314 | Brothers | 2025-12-01 | 1622 |  | 9 Toby Boxes / 8 Daps / 36 Splices | December
Heatherwood Village | J Garcia Underground | 2025-12-01 | 1765 |  |  | December
Fountain View | H&H Underground | 2025-12-01 | 600 |  |  | December
D-HDF704 | GN Systems | 2025-12-01 | 2113 |  | 10 Toby Boxes / 10 Daps / 30 Splices | December
D-HSH224 | Brothers | 2025-12-01 | 1515 |  | 3 HH / 3 Ground Rods | December
D-HSH246 | Brothers | 2025-12-01 | 3376 |  |  | December
D-HSH238 | Brothers | 2025-12-01 | 3084 |  |  | December
FB-HSH238 | Brothers | 2025-12-01 | 1829 |  |  | December
D-HSH239 | Brothers | 2025-12-01 | 1391 |  |  | December
Vantage Point | APT Communications | 2025-12-02 | 560 |  |  | December
Vantage Point | Lightspeed | 2025-12-02 | 612 |  | 12 Flower Pots / 54 Splices | December
Sunset Palms MHP | Kattle One | 2025-12-02 | 581 |  |  | December
Sunset Palms MHP | Patriot Underground | 2025-12-02 | 488 |  | 5 Flower Pots / 19 Splices | December
Fountain View | H&H Underground | 2025-12-02 | 610 |  | 5 Toby Boxes / 5 Daps / 5 Splices | December
D-HWP1314 | Brothers | 2025-12-02 | 1131 |  | 14 Toby Boxes / 5 Daps / 25 Splices | December
Heatherwood Village | J Garcia Underground | 2025-12-02 | 1153 |  | 14 Toby Boxes / 14 Daps / 28 Splices | December
D-HWP918 | Lightspeed | 2025-12-02 | 175 |  |  | December
D-HSH239 | Brothers | 2025-12-02 | 2916 |  |  | December
FB-HSH238 | Brothers | 2025-12-02 | 2302 |  |  | December
Vantage Point | APT Communications | 2025-12-03 | 721 |  | 11 Toby Boxes / 26 Splices | December
Vantage Point | Lightspeed | 2025-12-03 | 535 |  |  | December
Sunset Palms MHP | Kattle One | 2025-12-03 | 1029 |  | 4 Flower Pots / 12 Splices | December
Sunset Palms MHP | Patriot Underground | 2025-12-03 |  |  | 7 Flower Pots / 28 Splices | December
Sunset Palms MHP | Legant Livings | 2025-12-03 | 100 |  |  | December
Fountain View | H&H Underground | 2025-12-03 | 974 |  |  | December
D-HWP820 | Longo Underground | 2025-12-03 | 466 |  | 3 Flower Pots / 1 Toby Box / 1 Dap / 18 Splices | December
Heatherwood Village | J Garcia Underground | 2025-12-03 | 383 |  |  | December
D-HWP906 | Brothers | 2025-12-03 | 1379 |  | 6 Toby Boxes / 6 Daps / 17 Splices | December
D-HDF704 | GN Systems | 2025-12-03 | 1677 |  |  | December
D-HSH239 | Brothers | 2025-12-03 | 2430 |  |  | December
FB-HSH238 | Brothers | 2025-12-03 | 694 |  |  | December
D-HSH236 | Brothers | 2025-12-03 | 243 |  |  | December
Vantage Point | APT Communications | 2025-12-04 | 272 |  | 4 Toby Box / 2 Dap / 5 Splices | December
Sunset Palms MHP | APT Communications | 2025-12-04 | 285 |  |  | December
Sunset Palms MHP | Kattle One | 2025-12-04 | 756 |  |  | December
Sunset Palms MHP | Patriot Underground | 2025-12-04 |  |  | 3 Flower Pots / 12 Splices | December
D-HWP1315 | Brothers | 2025-12-04 | 1431 |  | 4 Toby Box / 3 Dap / 5 Splices | December
D-HWP820 | Longo Underground | 2025-12-04 | 195 |  | 3 Flower Pots / 1 Toby Box / 3 Dap / 30 Splices | December
Heatherwood Village | J Garcia Underground | 2025-12-04 | 490 |  | 14 Toby Box / 14 Dap / 28 Splices | December
D-HWP906 | Brothers | 2025-12-04 | 1154 |  | 9 Toby Box / 7 Dap / 35 Splices | December
D-HWP820 | Longo Underground | 2025-12-04 | 150 |  | 1 Flower Pot / 2 Toby Boxes / 1 Dap / 20 Splices | December
D-HDF704 | GN Systems | 2025-12-04 | 1316 |  |  | December
D-HDF714 | GN Systems | 2025-12-04 | 489 |  |  | December
D-HSH224 | Brothers | 2025-12-04 |  | 644 | 544 Tracer Wire | December
D-HSH241 | Lightspeed | 2025-12-04 | 64 |  | 36 Toby Boxes / 22 Daps / 1 HH / 1 Ground Rod | December
D-HSH244 | Brothers | 2025-12-04 | 52 |  | 5 Toby Box / 4 Dap | December
Vantage Point | APT Communications | 2025-12-05 | 86 |  | 44 Toby Boxes / 66 Splices | December
Sunset Palms MHP | APT Communications | 2025-12-05 | 710 |  |  | December
Sunset Palms MHP | Kattle One | 2025-12-05 | 1114 |  |  | December
D-HNP110 | Lightspeed | 2025-12-05 | 222 |  |  | December
Fountainview | H&H Underground | 2025-12-05 | 385 |  | 4 Toby Boxes / 4 Daps / 12 Splices | December
D-HWP1311 | Lightspeed | 2025-12-05 |  | 446 |  | December
D-HWP1314 | Lightspeed | 2025-12-05 |  | 422 |  | December
D-HWP1314 | Lightspeed | 2025-12-05 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
Heatherwood Village | J Garcia Underground | 2025-12-05 |  |  | 11 Toby Boxes / 12 Daps / 24 Splices / 3 FDH / 3 HH / 1 Swing Arm / 3 Ground Rods | December
D-HDF714 | GN Systems | 2025-12-05 | 2020 |  |  | December
D-HSH233 | Brothers | 2025-12-05 |  | 636 |  | December
D-HSH242 | Brothers | 2025-12-05 |  |  | 1 Toby Box / 32 Daps | December
Vantage Point | APT Communications | 2025-12-08 |  |  | No Production | December
Sunset Palms MHP | APT Communications | 2025-12-08 |  |  | No Production | December
Sunset Palms MHP | Kattle One | 2025-12-08 | 1283 |  |  | December
D-HNP110 | Lightspeed | 2025-12-08 | 237 |  | 2 Toby Boxes / 2 Daps / 4 Splices | December
Fountainview | H&H Underground | 2025-12-08 | 640 |  | 4 Toby Boxes / 4 Daps / 20 Splices | December
D-HWP1312 | Lightspeed | 2025-12-08 |  |  | Issues With Stingray Path | December
D-HWP820 | Longo Underground | 2025-12-08 | 1172 |  | 2 Flower Pots / 6 Toby Boxes / 4 Daps / 55 Splices | December
D-HWP1315 | Brothers | 2025-12-08 | 1583 |  | 11 Toby Boxes / 8 Daps / 11 Splices | December
D-HWP906 | Brothers | 2025-12-08 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
Heatherwood Village | Lightspeed | 2025-12-08 |  |  | 2 FDH / 2 HH / 2 Swing Arm / 2 Ground Rod | December
D-HDF714 | GN Systems | 2025-12-08 | 428 |  | 8 Toby Boxes / 5 Daps / 49 Splices | December
D-HSH250 | Brothers | 2025-12-08 | 2855 |  |  | December
Vantage Point | APT Communications | 2025-12-09 | 265 |  | 5 Flower Pots / 5 Daps / 2 FDH / 2 HH / 2 Swing Arms / 2 Ground Rods | December
Sunset Palms MHP | APT Communications | 2025-12-09 |  |  | No Production | December
Sunset Palms MHP | Kattle One | 2025-12-09 | 442 |  | 18 Flower Pots / 81 Splices | December
Sunset Palms MHP | Lightspeed | 2025-12-09 |  |  | 6 Flower Pots / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
D-HNP110 | Lightspeed | 2025-12-09 | 194 |  | 1 Toby Box / 1 Dap / 2 Splices | December
Fountainview | H&H Underground | 2025-12-09 | 541 |  | 5 Toby Boxes / 5 Daps / 10 Splices | December
D-HWP1315 | Brothers | 2025-12-09 | 1325 |  | 9 Toby Boxes / 7 Daps / 28 Splices | December
D-HWP906 | Lightspeed | 2025-12-09 |  | 540 |  | December
D-HWP819 | Longo Underground | 2025-12-09 | 1500 |  | 2 Flower Pots / 11 Toby Boxes / 11 Daps / 65 Splices | December
Heatherwood | Lightspeed | 2025-12-09 |  | 3493 |  | December
D-HDF702 | GN Systems | 2025-12-09 | 1640 |  | 6 Toby Boxes / 6 Daps / 14 Splices | December
D-HSH247 | Brothers | 2025-12-09 | 1980 |  | 1 Dap / 1 HH / Ground Rod / 6 Splices | December
D-HSH250 | Brothers | 2025-12-09 | 3343 |  |  | December
D-HSH223 | Brothers | 2025-12-09 | 2203 |  | 6 Toby Boxes | December
D-HSH249 | Brothers | 2025-12-09 | 1111 |  |  | December
D-HSH251 | Brothers | 2025-12-09 | 1743 |  |  | December
Vantage Point | APT Communications | 2025-12-10 | 542 |  | 7 Flower Pots / 6 Daps / 35 Splices | December
Sunset Palms MHP | APT Communications | 2025-12-10 |  |  | No Production | December
Sunset Palms MHP | Kattle One | 2025-12-10 |  |  | 12 Flower Pots / 48 Splices | December
D-HNP110 | Lightspeed | 2025-12-10 | 359 |  | 1 Toby Box / 1 Dap / 2 Splices | December
Fountainview | H&H Underground | 2025-12-10 | 330 |  | 4 Toby Boxes / 4 Daps / 8 Splices | December
D-HWP1315 | Brothers | 2025-12-10 | 621 |  | 5 Toby Boxes / 4 Daps / 10 Splices | December
D-HWP819 | Longo Underground | 2025-12-10 | 1084 |  | 10 Toby Box / 1 Flower Pot / 8 Dap / 52 Splices | December
D-HWP1312 | Lightspeed | 2025-12-10 |  | 1685 |  | December
D-HDF702 | GN Systems | 2025-12-10 | 1177 |  | 6 Toby Boxes / 10 Daps / 47 Splices | December
D-HDF703 | GN Systems | 2025-12-10 | 817 |  | 4 Toby Boxes / 3 Daps / 19 Splices | December
D-HSH247 | Brothers | 2025-12-10 | 1251 |  |  | December
D-HSH250 | Brothers | 2025-12-10 | 931 |  |  | December
D-HSH251 | Brothers | 2025-12-10 | 522 |  |  | December
FB-HSH238 | Brothers | 2025-12-10 | 91 |  |  | December
D-HSH223 | Brothers | 2025-12-10 |  | 3674 | 2,674 Tracer Wire | December
D-HSH249 | Brothers | 2025-12-10 | 1373 |  | 7 Toby Boxes / 9 Daps / 15 Splices | December
D-HNP110 | Lightspeed | 2025-12-11 | 255 |  | 2 Toby Boxes / 2 Daps / 4 Splices | December
Vantage Point | APT Communications | 2025-12-11 | 739 |  | 4 Flower Pots / 6 Daps / 24 Splices | December
Sunset Palms MHP | APT Communications | 2025-12-11 |  |  | No Production | December
Sunset Palms MHP | Kattle One | 2025-12-11 |  |  | 1 Flower Pot / 5 Splices | December
Sunset Palms MHP | Sosa Line | 2025-12-11 |  |  | 13 Flower Pots / 46 Splices | December
Fountainview | H&H Underground | 2025-12-11 | 520 |  |  | December
D-HWP817 | Longo Underground | 2025-12-11 | 1351 |  | 1 Flower Pot / 11 Toby Boxes / 9 Daps / 51 Splices | December
D-HDF703 | GN Systems | 2025-12-11 | 1820 |  | 12 Toby Boxes / 9 Daps / 19 Splices | December
D-HSH247 | Brothers | 2025-12-11 | 3172 |  |  | December
D-HSH243 | Brothers | 2025-12-11 | 242 |  | 13 Toby Boxes / 14 Daps | December
D-HSH251 | Brothers | 2025-12-11 | 1194 |  |  | December
D-HSH249 | Brothers | 2025-12-11 | 1090 |  |  | December
D-HNP110 | Lightspeed | 2025-12-12 | 253 |  | 1 Toby Box / 1 Dap / 2 Splices | December
Vantage Point | APT Communications | 2025-12-12 |  |  | Proofing Hub 1,2, and 3 | December
Sunset Palms MHP | APT Communications | 2025-12-12 | 706 |  |  | December
Sunset Palms MHP | Sosa Line | 2025-12-12 |  |  | 1 Flower Pot / 4 Splices | December
Sunset Palms MHP | Kattle One | 2025-12-12 |  |  | 2 FDH / 2 HH / 2 Swing Arms / 2 Ground Rods | December
Fountainview | H&H Underground | 2025-12-12 | 550 |  | 6 Toby Boxes / 6 Daps / 12 Splices | December
D-HDF707 | Lightspeed | 2025-12-12 | 1832 |  | 2 Toby Boxes / 2 Daps / 6 Splices | December
D-HSH243 | Brothers | 2025-12-12 |  |  | 32 Toby Boxes | December
D-HSH251 | Brothers | 2025-12-12 | 2811 |  |  | December
D-HSH249 | Brothers | 2025-12-12 | 1204 |  | 10 Toby Boxes | December
D-HNP110 | Lightspeed | 2025-12-15 | 365 |  | 4 Toby Boxes / 1 Dap / 8 Splices | December
Vantage Point | APT Communications | 2025-12-15 | 671 |  | 1 Flower Pot / 2 Toby Boxes / 2 Daps / 9 Splices | December
Sunset Palms MHP | APT Communications | 2025-12-15 | 735 |  |  | December
Sunset Palms MHP | Kattle One | 2025-12-15 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
Fountainview | H&H Underground | 2025-12-15 | 752 |  | 5 Toby Boxes / 5 Daps / 10 Splices | December
D-HWP817 | Longo Underground | 2025-12-15 | 689 |  | 4 Toby Boxes / 5 Daps / 31 Splices | December
D-HWP808-1 | Brothers | 2025-12-15 | 1095 |  |  | December
D-HWP901 | Brothers | 2025-12-15 | 1344 |  | 5 Toby Boxes / 1 Daps / 12 Splices | December
D-HWP1312 | Brothers | 2025-12-15 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
D-HDF715 | GN Systems | 2025-12-15 | 1511 |  | 10 Toby Boxes / 5 Daps / 27 Splices | December
D-HSH247 | Brothers | 2025-12-15 | 29 |  |  | December
D-HSH222 | Brothers | 2025-12-15 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
D-HSH245 | Brothers | 2025-12-15 | 87 |  | 34 Toby Boxes / 27 Daps / 118 Splices | December
D-HNP110 | Lightspeed | 2025-12-16 | 210 |  | 2 Toby Boxes / 2 Daps / 3 Splices / 1 FDH / 1 HH / 1 Swing Arm | December
Vantage Point | APT Communications | 2025-12-16 | 1204 |  |  | December
Sunset Palms MHP | APT Communications | 2025-12-16 |  |  | 4 Flower Pots / 16 Splices | December
Fountainview | H&H Underground | 2025-12-16 | 1249 |  | 3 Toby Boxes / 3 Daps / 6 Splices | December
D-HWP817 | Longo Underground | 2025-12-16 | 586 |  | 8 Toby Boxes / 2 Flower Pots / 6 Daps / 41 Splices | December
D-HWP808-1 | Brothers | 2025-12-16 | 1676 |  | 11 Toby Boxes / 7 Daps / 43 Splices | December
D-HWP901 | Brothers | 2025-12-16 | 1583 |  | 13 Toby Boxes / 7 Daps / 48 Splices | December
D-HOE501 | North Path | 2025-12-16 | 890 |  | 8 Toby Boxes / 7 Daps / 28 Splices | December
D-HDF707 | Lightspeed | 2025-12-16 | 1164 |  |  | December
D-HDF715 | GN Systems | 2025-12-16 | 1887 |  | 12 Toby Boxes / 9 Daps / 37 Splices | December
D-HSH247 | Brothers | 2025-12-16 |  |  | 2 Daps / 17 Splices | December
D-HSH248 | Brothers | 2025-12-16 | 1617 |  |  | December
Vantage Point | APT Communications | 2025-12-17 | 743 |  |  | December
Sunset Palms MHP | APT Communications | 2025-12-17 |  |  | 2 Flower Pot / 8 Splices | December
Vantage Point | Kattle One | 2025-12-17 | 467 |  |  | December
Sunset Palms MHP | Patriot Underground | 2025-12-17 |  |  | Proofing / Restoration | December
Sunset Palms MHP | Kattle One | 2025-12-17 |  |  | 1 Flower Pot / 4 Splices | December
Fountainview | H&H Underground | 2025-12-17 | 235 |  | 3 Toby Boxes / 3 Daps / 6 Splices | December
D-HWP817 | Longo Underground | 2025-12-17 | 199 |  | 3 Toby Boxes / 3 Daps / 1 HH / 1 Ground Rod / 12 Splices | December
D-HWP808-1 | Brothers | 2025-12-17 | 1139 |  | 1 Flower Pots / 25 Toby Boxes / 16 Daps / 92 Splices | December
D-HWP901 | Brothers | 2025-12-17 | 1027 |  | 11 Toby Boxes / 9 Daps / 38 Splices | December
D-HWP820 | Longo Underground | 2025-12-17 | 163 |  | 2 Flower Pots / 3 Toby Boxes / 3 Daps / 1 HH / 1 Ground Rod / 35 Splices | December
D-HOE501 | North Path | 2025-12-17 | 1810 |  | 12 Toby Boxes / 9 Daps / 42 Splices | December
D-HDF707 | Lightspeed | 2025-12-17 | 308 |  | 8 Toby Boxes / 6 Daps / 28 Splices | December
D-HDF715 | GN Systems | 2025-12-17 | 916 |  | 5 Toby Boxes / 4 Daps / 7 Splices | December
FB-HSH238 | Brothers | 2025-12-17 | 320 |  |  | December
D-HSH248 | Brothers | 2025-12-17 | 1083 |  |  | December
D-HSH243 | Brothers | 2025-12-17 |  |  | 11 Toby Boxes | December
D-HSH236 | Brothers | 2025-12-17 | 372 |  |  | December
D-HSH254 | Brothers | 2025-12-17 | 95 |  |  | December
D-HSH251 | Brothers | 2025-12-17 | 1049 |  |  | December
D-HSH242 | Brothers | 2025-12-17 |  | 870 |  | December
Vantage Point | APT Communications | 2025-12-18 | 292 |  | 14 Flower Pots / 37 Splices | December
Vantage Point | Kattle One | 2025-12-18 |  |  | 1 Flower Pot / 4 Splices | December
Vantage Point | Lightspeed | 2025-12-18 |  | 1506 |  | December
Sunset Palms MHP | Patriot Underground | 2025-12-18 |  |  | Restoration | December
Sunset Palms MHP | Kattle One | 2025-12-18 |  |  | Restoration | December
Sunset Palms MHP | APT Communications | 2025-12-18 |  |  | Restoration | December
Fountainview | H&H Underground | 2025-12-18 | 563 |  | 6 Toby Boxes / 6 Daps / 12 Splices | December
D-HWP817 | Longo Underground | 2025-12-18 |  |  | FDH / Proofing | December
D-HWP901 | Brothers | 2025-12-18 | 1596 |  | 12 Toby Boxes / 7 Daps / 40 Splices | December
D-HWP819 | Longo Underground | 2025-12-18 |  |  | FDH / Proofing | December
D-HWP820 | Longo Underground | 2025-12-18 |  |  | FDH / Proofing | December
FB-HWP880 | Brothers | 2025-12-18 | 1568 |  |  | December
D-HDF707 | Lightspeed | 2025-12-18 | 892 |  | 2 Toby Boxes / 1 Dap / 10 Splices | December
D-HDF715 | GN Systems | 2025-12-18 | 1704 |  | 10 Toby Boxes / 18 Dap / 60 Splices | December
D-HOE501 | Lightspeed | 2025-12-18 | 967 |  | 12 Toby Boxes / 11 Dap / 38 Splices
FB-HSH238 | Brothers | 2025-12-18 | 652 |  |  | December
FB-HSH241 | Brothers | 2025-12-18 | 396 |  |  | December
D-HSH248 | Brothers | 2025-12-18 | 1905 |  |  | December
D-HSH254 | Brothers | 2025-12-18 | 881 |  |  | December
D-HSH252 | Brothers | 2025-12-18 | 3028 |  | 6 Daps / 9 Splices | December
D-HSH242 | Brothers | 2025-12-18 |  |  | 1 HH / 1 FDH / 1 Swing Arm / 1 Ground Rod | December
D-HNP110 | Lightspeed | 2025-12-19 | 166 |  | 2 Toby Boxes / 2 Daps / 16 Splices | December
Vantage Point | APT Communications | 2025-12-19 |  |  | Proofing Conduits | December
Vantage Point | Kattle One | 2025-12-19 |  |  | 18 Flower Pots / 24 Daps / 78 Splices | December
Sunset Palms MHP | Patriot Underground | 2025-12-19 |  |  | Restoration | December
Sunset Palms MHP | Kattle One | 2025-12-19 |  |  | Restoration | December
Sunset Palms MHP | APT Communications | 2025-12-19 |  |  | Restoration | December
Fountainview | H&H Underground | 2025-12-19 | 483 |  |  | December
D-HWP817 | Longo Underground | 2025-12-19 |  | 765 |  | December
D-HWP808-1 | Brothers | 2025-12-19 |  | 883 | 2 Toby Boxes / 2 Daps / 8 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
D-HWP819 | Longo Underground | 2025-12-19 |  | 765 |  | December
D-HWP820 | Longo Underground | 2025-12-19 |  | 560 |  | December
D-HDF707 | Lightspeed | 2025-12-19 | 366 |  | 3 Toby Boxes / 3 Daps / 36 Splices | December
D-HDF715 | GN Systems | 2025-12-19 | 974 |  | 5 Toby Boxes / 5 Daps / 30 Splices | December
D-HSH236 | Brothers | 2025-12-19 | 582 |  |  | December
D-HSH248 | Brothers | 2025-12-19 | 2064 |  |  | December
D-HSH252 | Brothers | 2025-12-19 | 1683 |  |  | December
D-HSH249 | Brothers | 2025-12-19 | 1235 |  |  | December
D-HSH247 | Brothers | 2025-12-19 |  |  | 3 Daps / 9 Splices | December
FB-HSH238 | Brothers | 2025-12-19 | 780 |  |  | December
FB-HSH 241 | Brothers | 2025-12-19 |  | 5068 | 4,140 Tracer Wire | December
Vantage Point | APT Communications | 2025-12-22 |  |  | ABF Proofing | December
Vantage Point | Kattle One | 2025-12-22 |  |  | ABF Proofing | December
Fountainview | H&H Underground | 2025-12-22 |  |  | FDH / Proofing | December
FB-HWP880 | Brothers | 2025-12-22 | 380 |  |  | December
FB-HWP882 | Brothers | 2025-12-22 | 523 |  |  | December
D-HWP901 | Brothers | 2025-12-22 | 342 |  | 3 Toby Boxes / 1 Splice / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
D-HDF707 | Lightspeed | 2025-12-22 | 154 |  |  | December
D-HSH236 | Brothers | 2025-12-22 | 551 |  |  | December
D-HSH248 | Brothers | 2025-12-22 |  |  | 3 Daps / 10 Splices | December
D-HSH252 | Brothers | 2025-12-22 | 362 |  |  | December
D-HSH254 | Brothers | 2025-12-22 | 3523 |  |  | December
FB-HSH238 | Brothers | 2025-12-22 | 870 |  |  | December
D-HNP110 | Lightspeed | 2025-12-23 | 212 |  | 2 Toby Boxes | December
Fountainview | H&H Underground | 2025-12-23 |  |  | 3 FDH / 3 HH / 3 Swing Arms / 3 Ground Rods | December
FB-HWP880 | Brothers | 2025-12-23 |  |  | 4 HH / 4 Ground Rods | December
FB-HWP882 | Brothers | 2025-12-23 | 405 |  | 2 HH | December
D-HWP901 | Lightspeed | 2025-12-23 |  | 405 |  | December
FB-HSH238 | Brothers | 2025-12-23 |  | 14727 | Installing Fiber | December
D-HSH254 | Brothers | 2025-12-23 | 2384 |  |  | December
FB-HWP880 | Lightspeed | 2025-12-24 |  | 2448 | 1,948 Tracer Wire | December
FB-HWP882 | Lightspeed | 2025-12-24 |  | 1225 | 915 Tracer Wire | December
|  | 2025-12-25 |  |  |  | December
|  | 2025-12-26 |  |  |  | December
D-HNP110 | Lightspeed | 2025-12-29 | 108 |  | 1 Toby Box / 1 Splice | December
D-HWP1316 | Brothers | 2025-12-29 | 1188 |  | 13 Toby Boxes / 2 Flower Pots / 10 Daps / 71 Splices | December
D-HWP1317 | Brothers | 2025-12-29 | 900 |  | 10 Toby Boxes / 2 Flower Pots / 13 Daps / 96 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
FB-HWP880 | Lightspeed | 2025-12-29 | 100 |  |  | December
D-HSH236 | Brothers | 2025-12-29 | 738 |  |  | December
D-HSH252 | Brothers | 2025-12-29 | 1297 |  |  | December
D-HSH253 | Brothers | 2025-12-29 | 2583 |  |  | December
D-HSH237 | Brothers | 2025-12-29 | 0 |  | 94 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
D-HSH239 | Brothers | 2025-12-29 | 0 |  | 94 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
D-HSH251 | Brothers | 2025-12-29 | 0 |  | 94 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
D-HNP110 | Lightspeed | 2025-12-30 | 353 |  |  | December
D-HWP1315 | Lightspeed | 2025-12-30 |  | 766 |  | December
D-HWP1317 | Lightspeed | 2025-12-30 |  | 343 |  | December
D-HWP1316 | Brothers | 2025-12-30 | 0 |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
D-HSH236 | Brothers | 2025-12-30 | 466 |  |  | December
D-HSH253 | Brothers | 2025-12-30 | 3099 |  |  | December
D-HSH238 | Brothers | 2025-12-30 | 0 |  | 94 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | December
D-HDF707 | Lightspeed | 2025-12-31 | 173 |  |  | December
D-HSH239 | Lightspeed | 2025-12-31 |  | 2728 |  | December
D-HSH240 | Lightspeed | 2025-12-31 |  | 1231 |  | December
D-HSH251 | Lightspeed | 2025-12-31 |  | 1565 |  | December
|  | 2026-01-01 | 0 |  |  | January
|  | 2026-01-02 | 0 |  |  | January
FB-HWP484 | Brothers | 2026-01-05 | 1353 |  |  | January
D-HNP110 | Lightspeed | 2026-01-05 | 248 |  |  | January
FB-HLR202 | GN Systems | 2026-01-05 | 1105 |  |  | January
D-HSH236 | Brothers | 2026-01-05 | 3728 |  |  | January
D-HSH253 | Brothers | 2026-01-05 | 568 |  |  | January
D-HSH223 | Brothers | 2026-01-06 | 0 |  | FDH / 1 Swing Arm / 12 Ground Rods / / 12 HH / 2 Toby Boxes / 2 Daps | January
D-HSH236 | Brothers | 2026-01-06 | 1789 |  |  | January
D-HSH255 | Brothers | 2026-01-06 | 2362 |  |  | January
D-HWP907 | Brothers | 2026-01-06 | 1534 |  | 9 Toby Boxes / 7 Daps / 45 Splices | January
FB-HLR202 | GN Systems | 2026-01-06 | 942 |  |  | January
FB-HNP138 | Lightspeed | 2026-01-06 | 152 |  | 2 Splices | January
FB-HWP484 | Brothers | 2026-01-06 | 1153 |  |  | January
D-HNP110 | Lightspeed | 2026-01-07 | 366 |  | 1 Toby Box / 2 Splices | January
D-HSH248 | Brothers | 2026-01-07 | 0 |  | 94 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod / 43 Toby Boxes / 10 Daps / 83 Splices | January
D-HWP1003 | Brothers | 2026-01-07 | 1687 |  |  | January
D-HWP1004 | Brothers | 2026-01-07 | 1056 |  | 5 Toby Boxes / 5 Daps / 38 Splices | January
D-HWP907 | Brothers | 2026-01-07 | 180 |  | 2 Toby Boxes | January
FB-HLR202 | GN Systems | 2026-01-07 | 2151 |  |  | January
D-HSH255 | Brothers | 2026-01-07 | 3079 |  |  | January
D-HSH250 | Brothers | 2026-01-07 | 0 |  | 94 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | January
FB-HNP138 | Lightspeed | 2026-01-08 | 85 |  |  | January
D-HNP110 | Lightspeed | 2026-01-08 | 113 |  | 2 Toby Boxes / 1 Daps / 4 Splices | January
D-HWP1003 | Brothers | 2026-01-08 | 1053 |  | 26 Toby Boxes / 23 Daps / 168 Splices | January
FB-HLR202 | GN Systems | 2026-01-08 | 1926 |  |  | January
D-HSH256 | Brothers | 2026-01-08 | 2367 |  |  | January
FB-HOE175 | 1972 Fiber Core | 2026-01-08 |  | 2706 |  | January
FB-HOE175 | 1972 Fiber Core | 2026-01-09 | 0 |  | 4 Ground Rods | January
FB-HOE501 | 1972 Fiber Core | 2026-01-09 | 0 |  | 1 HH | January
FB-HLR202 | GN Systems | 2026-01-09 | 1000 |  |  | January
D-HSH248 | Brothers | 2026-01-09 | 104 |  |  | January
D-HSH249 | Brothers | 2026-01-09 |  | 1056 |  | January
D-HSH246 | Brothers | 2026-01-09 |  | 1090 |  | January
D-HSH256 | Brothers | 2026-01-09 | 447 |  |  | January
D-HDF705 | GN Systems | 2026-01-09 | 1319 |  | 6 Toby Boxes / 5 Daps / 26 Splices | January
D-HWP1003 | Brothers | 2026-01-12 | 0 |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | January
FB-HOE375 | 1972 Fiber Core | 2026-01-12 |  | 640 |  | January
FB-HOE675 | 1972 Fiber Core | 2026-01-12 |  | 428 | 1 HH | January
FB-HNP118 | Lightspeed | 2026-01-12 | 205 |  | 4 Daps / 8 Splices | January
D-HSH256 | Brothers | 2026-01-12 | 858 |  |  | January
D-HBK131 | Brothers | 2026-01-12 | 4915 |  |  | January
D-HBK130 | Brothers | 2026-01-12 | 813 |  |  | January
D-HWP1004 | Brothers | 2026-01-12 | 1356 |  | 12 Toby Boxes / 7 Daps / 32 Splices | January
Moss Creek | Kattle One | 2026-01-12 | 607 |  |  | January
FB-HLR202 | GN Systems | 2026-01-12 | 1812 |  |  | January
FB-HWP484 | Brothers | 2026-01-12 | 1314 |  | 6 HH / 6 Ground Rods | January
D-HDF705 | GN Systems | 2026-01-12 | 926 |  | 2 Toby Boxes / 2 Daps / 5 Splices | January
Fountain View Estates MHP | Lightspeed | 2026-01-13 |  | 2112 |  | January
FB-HWP377 | Brothers | 2026-01-13 |  | 1208 |  | January
D-HBK131 | Brothers | 2026-01-13 | 914 |  | 13 Toby Boxes / 11 Daps / 15 Splices | January
D-HBK132 | Brothers | 2026-01-13 | 6092 |  |  | January
D-HBK130 | Brothers | 2026-01-13 | 1491 |  |  | January
D-HBK133 | Brothers | 2026-01-13 | 822 |  |  | January
D-HWP1004 | Brothers | 2026-01-13 | 1435 |  | 13 Toby Boxes / 10 Daps / 79 Splices | January
FB-HNP138 | Lightspeed | 2026-01-13 | 312 |  | 4 Splices | January
FB-HLR202 | GN Systems | 2026-01-13 | 1838 |  |  | January
BHU-FAL-01-E | HYN Enterprise | 2026-01-13 |  | 5312 | 4,912 Tracer Wire | January
Moss Creek | Kattle One | 2026-01-13 | 662 |  |  | January
D-HDF705 | GN Systems | 2026-01-13 | 1128 |  | 8 Toby Boxes / 5 Daps / 24 Splices | January
D-HWP907 | Lightspeed | 2026-01-13 |  | 576 |  | January
D-HWP907 | Brothers | 2026-01-14 | 0 |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | January
D-HBK132 | Brothers | 2026-01-14 | 0 |  | 30 Toby Boxes / 19 Daps / 86 Splices | January
D-HBK130 | Brothers | 2026-01-14 | 1062 |  |  | January
D-HBK133 | Brothers | 2026-01-14 | 2611 |  |  | January
Moss Creek | Kattle One | 2026-01-14 | 877 |  | 10 Toby Boxes / 8 Daps / 20 Splices | January
FB-HLR201 | GN Systems | 2026-01-14 | 1200 |  |  | January
D-HDF705 | GN Systems | 2026-01-14 | 1082 |  | 5 Toby Boxes / 6 Daps / 25 Splices | January
D-HWP1004 | Brothers | 2026-01-14 | 1295 |  | 7 Toby Boxes / 3 Daps / 26 Splices | January
D-HBK135 | Brothers | 2026-01-14 | 544 |  | 4 Toby Boxes / 3 Daps / 7 Splices | January
D-HSH249 | Lightspeed | 2026-01-14 |  | 1562 |  | January
D-HBK131 | Brothers | 2026-01-14 | 0 |  | 18 Toby Boxes / 13 Daps / 36 Splices | January
D-HBK134 | Brothers | 2026-01-14 | 1728 |  | 9 Toby Boxes / 6 Daps | January
D-HBK130 | Brothers | 2026-01-15 | 527 |  | 2 Toby Boxes / 1 Daps | January
D-HBK136 | Brothers | 2026-01-15 | 1562 |  |  | January
D-HBK135 | Brothers | 2026-01-15 | 2832 |  |  | January
D-HBK132 | Brothers | 2026-01-15 | 0 |  | 8 Toby Boxes / 3 Daps / 8 Splices | January
FB-HBK104 | Brothers | 2026-01-15 | 1639 |  |  | January
FB-HLR201 | GN Systems | 2026-01-15 | 445 |  |  | January
Moss Creek | Kattle One | 2026-01-15 | 499 |  | 3 Toby Boxes / 2 Daps / 6 Splices | January
D-HDF705 | GN Systems | 2026-01-15 | 1325 |  | 13 Toby Boxes / 8 Daps / 22 Splices | January
D-HNP106 | Lightspeed | 2026-01-15 | 142 |  | 1 Toby Boxes / 2 Daps / 13 Splices | January
FB-HLR202 | GN Systems | 2026-01-15 | 0 |  | 16 HH | January
FB-HBK104 | Brothers | 2026-01-16 | 987 |  |  | January
D-HBK135 | Brothers | 2026-01-16 | 457 |  |  | January
D-HBK134 | Brothers | 2026-01-16 | 3082 |  |  | January
Moss Creek | Kattle One | 2026-01-16 | 186 |  | 4 Toby Boxes / 3 Daps / 7 Splices | January
FB-HLR201 | GN Systems | 2026-01-16 | 686 |  |  | January
D-HBK136 | Brothers | 2026-01-16 | 673 |  |  | January
D-HDH34 | Lightspeed | 2026-01-16 | 50 |  | 2 Daps / 48 Splices | January
FB-HNP118 | Lightspeed | 2026-01-16 | 107 |  |  | January
D-HDF705 | GN Systems | 2026-01-16 | 441 |  | 7 Toby Boxes / 5 Daps / 28 Splices | January
|  | 2026-01-19 | 0 |  |  | January
FB-HNP118 | Lightspeed | 2026-01-20 | 183 |  |  | January
D-HWP1004 | Brothers | 2026-01-20 | 0 |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | January
FB-HWP106 | Brothers | 2026-01-20 | 1344 |  | 1 HH / 1 Ground Rod | January
FB-HLR201 | GN Systems | 2026-01-20 | 0 |  | No Production Crew Did Not Work This Location Today | January
Moss Creek | Kattle One | 2026-01-20 | 660 |  | 6 Toby Boxes / 6 Daps / 10 Splices | January
Colonial Manor | APT Communications | 2026-01-20 | 1382 |  | 6 Toby Boxes / 6 Daps / 12 Splices | January
D-HDF708 | GN Systems | 2026-01-20 | 2719 |  | 10 Daps / 37 Splices | January
FB-HBK104 | Brothers | 2026-01-20 | 0 |  | No Production Crew Did Not Work This Location Today | January
FB-HBK130 | Brothers | 2026-01-20 | 1277 |  |  | January
D-HBK135 | Brothers | 2026-01-20 | 506 |  |  | January
D-HSH224 | Brothers | 2026-01-20 | 2209 |  | 1 FDH / 1 Swing Arm | January
FB-HNP118 | Lightspeed | 2026-01-21 | 182 |  |  | January
D-HNP108 | Kattle One | 2026-01-21 | 150 |  |  | January
D-HWP1006 | Longo Underground | 2026-01-21 | 686 |  | 6 Toby Boxes / 5 Daps / 26 Splices | January
D-HWP1005 | Brothers | 2026-01-21 | 867 |  | 7 Toby Boxes / 7 Daps / 32 Splices | January
FB-HWP484 | Lightspeed | 2026-01-21 |  | 3507 | 3,507 Tracer Wire | January
Moss Creek | Kattle One | 2026-01-21 | 754 |  | 8 Toby Boxes / 7 Daps / 15 Splices | January
Colonial Manor | APT Communications | 2026-01-21 | 993 |  | 12 Toby Boxes / 14 Daps / 28 Splices | January
D-HDF708 | GN Systems | 2026-01-21 | 408 |  |  | January
D-HDF740 | GN Systems | 2026-01-21 | 2000 |  |  | January
FB-HBK104 | Brothers | 2026-01-21 | 575 |  |  | January
D-HBK136 | Brothers | 2026-01-21 | 2265 |  |  | January
D-HSH256 | Brothers | 2026-01-21 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | January
FB-HNP118 | Lightspeed | 2026-01-22 | 186 |  | 2 HH | January
D-HNP108 | Kattle One | 2026-01-22 | 0 |  | No Production | January
D-HWP1006 | Longo Underground | 2026-01-22 | 736 |  | 3 Toby Boxes / 4 Daps / 16 Splices | January
D-HWP1005 | Brothers | 2026-01-22 | 1539 |  | 12 Toby Boxes / 9 Daps / 30 Splices | January
D-HWP1004 | Lightspeed | 2026-01-22 |  | 486 | 486 Tracer Wire | January
Moss Creek | Kattle One | 2026-01-22 | 520 |  | 3 Toby Boxes / 2 Daps / 6 Splices | January
Colonial Manor | APT Communications | 2026-01-22 | 1462 |  | 15 Toby Boxes / 13 Daps / 30 Splices | January
D-HLR208 | GN Systems | 2026-01-22 | 2031 |  | 20 Toby Boxes / 16 Daps / 35 Splices | January
D-HDF740 | GN Systems | 2026-01-22 | 970 |  | 2 HH / 2 Toby Boxes / 1 Dap / 2 Splices | January
D-HBK130 | Brothers | 2026-01-22 | 1776 |  | 33 Toby Boxes | January
D-HSH256 | Brothers | 2026-01-22 | 1940 |  | 22 Toby Boxes | January
D-HNP106 | Lightspeed | 2026-01-23 | 57 |  | 1 Dap / 4 Splices | January
D-HNP108 | Kattle One | 2026-01-23 | 274 |  |  | January
Moss Creek | Kattle One | 2026-01-23 | 0 |  | Restoration | January
Colonial Manor | APT Communications | 2026-01-23 | 1617 |  |  | January
D-HLR208 | GN Systems | 2026-01-23 | 845 |  | 4 Toby Boxes / 5 Daps / 14 Splices | January
D-HBK136 | Brothers | 2026-01-23 | 2651 |  | 9 Toby Boxes / 5 Daps / 20 Splices | January
FB-HBK104 | Brothers | 2026-01-23 | 818 |  |  | January
D-HSH248 | Lightspeed | 2026-01-23 |  | 1907 | Stingray | January
D-HNP108 | Kattle One | 2026-01-26 |  |  | No Production--MOT Did Show Until 10AM | January
D-HWP1005 | Brothers | 2026-01-26 | 1590 |  | 11 Toby Boxes / 9 Daps / 29 Splices | January
D-HWP1006 | Longo Underground | 2026-01-26 | 835 |  | 5 Toby Boxes / 3 Daps / 20 Splices | January
D-HWP1007 | Brothers | 2026-01-26 |  |  | No Production Crew Started Project Late | January
FB-HWP106 | Brothers | 2026-01-26 | 886 |  | 1 HH | January
FB-HWP484 | Lightspeed | 2026-01-26 |  | 313 | 313 Tracer Wire | January
Moss Creek | Kattle One | 2026-01-26 | 376 |  | 4 Toby Boxes / 4 Daps / 8 Splices | January
Colonial Manor | APT Communications | 2026-01-26 | 1642 |  | 13 Toby Boxes / 22 Daps / 44 Splices | January
D-HLR208 | GN Systems | 2026-01-26 | 1530 |  | 8 Toby Boxes / 8 Daps / 16 Splices | January
FB-HBK104 | Brothers | 2026-01-26 |  | 6116 | 4,019 Tracer Wire / 7 HH | January
D-HBK133 | Brothers | 2026-01-26 | 1908 |  | 15 Toby Boxes / 4 Daps / 14 Splices | January
D-HNP108 | Kattle One | 2026-01-27 | 343 |  |  | January
D-HLR208 | GN Systems | 2026-01-27 | 388 |  | 7 Toby Boxes / 8 Daps / 42 Splices | January
D-HWP1003 | Lightspeed | 2026-01-27 |  | 346 |  | January
D-HWP1005 | Brothers | 2026-01-27 | 1230 |  | 7 Toby Boxes / 5 Daps / 13 Splices | January
D-HWP1006 | Longo Underground | 2026-01-27 | 858 |  | 3 Toby Boxes / 3 Daps / 34 Splices | January
D-HWP1007 | Brothers | 2026-01-27 | 1758 |  | 11 Toby Boxes / 9 Daps / 43 Splices | January
Moss Creek | Kattle One | 2026-01-27 | 647 |  | 5 Toby Boxes / 4 Daps / 8 Splices | January
Colonial Manor | APT Communications | 2026-01-27 | 843 |  |  | January
FB-HLR201 | GN Systems | 2026-01-27 | 511 |  |  | January
FB-HBK130 | Brothers | 2026-01-27 |  | 2058 | 1,277' Tracer Wire / 4 HH | January
D-HBK130 | Brothers | 2026-01-27 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | January
D-HBK131 | Brothers | 2026-01-27 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | January
D-HBK134 | Brothers | 2026-01-27 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | January
D-HBK135 | Brothers | 2026-01-27 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | January
D-HBK136 | Brothers | 2026-01-27 |  |  | 9 Toby Boxes / 7 Daps / 21 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | January
D-HNP108 | Kattle One | 2026-01-28 | 62 |  |  | January
D-HWP1005 | Brothers | 2026-01-28 | 1015 |  | 7 Toby Boxes / 5 Daps / 12 Splices | January
D-HWP1006 | Longo Underground | 2026-01-28 | 976 |  | 6 Toby Boxes / 3 Daps / 16 Splices | January
D-HWP1007 | Brothers | 2026-01-28 | 1363 |  | 17 Toby Boxes / 14 Daps / 76 Splices | January
Moss Creek | Kattle One | 2026-01-28 | 565 |  | 5 Toby Boxes / 5 Daps / 10 Splices | January
Colonial Manor | APT Communications | 2026-01-28 |  |  | No Production Damage Hit | January
FB-HLR201 | GN Systems | 2026-01-28 | 324 |  | 4 HH / 4 Ground Rods | January
FB-HLR202 | GN Systems | 2026-01-28 | 149 |  |  | January
FB-HOE401-V2 | North Path | 2026-01-28 | 881 |  |  | January
D-HSH253 | Lightspeed | 2026-01-28 |  | 2071 |  | January
D-HSH254 | Brothers | 2026-01-28 |  | 1848 |  | January
D-HSH255 | Lightspeed | 2026-01-28 |  | 1139 |  | January
D-HSH256 | Lightspeed | 2026-01-28 |  | 901 |  | January
D-HBK130 | Lightspeed | 2026-01-28 |  | 899 |  | January
D-HBK132 | Lightspeed | 2026-01-28 |  | 751 |  | January
D-HNP108 | Kattle One | 2026-01-29 | 329 |  | 2 Toby Boxes / 1 Dap / 4 Splices | January
D-HWP1006 | Longo Underground | 2026-01-29 |  |  |  | January
Moss Creek | Kattle One | 2026-01-29 | 222 |  |  | January
Colonial Manor | APT Communications | 2026-01-29 | 410 |  | 14 Toby Boxes / 19 Daps / 35 Splices | January
FB-HLR201 | GN Systems | 2026-01-29 | 838 |  |  | January
FB-HOE401-V2 | North Path | 2026-01-29 | 1143 |  |  | January
D-HDF710 | GN Systems | 2026-01-29 | 1468 |  | 7 Toby Boxes / 7 Daps / 37 Splices | January
D-HLR208 | GN Systems | 2026-01-29 | 470 |  | 1 Dap / 2 Splices | January
D-HBK133 | Brothers | 2026-01-29 |  | 2048 |  | January
D-HBK134 | Lightspeed | 2026-01-29 |  | 404 |  | January
D-HBK136 | Lightspeed | 2026-01-29 |  | 1916 |  | January
D-HSH253 | Brothers | 2026-01-29 |  |  | 8 Toby Boxes / 2 Daps / 37 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | January
Moss Creek | Kattle One | 2026-01-30 |  |  | 1 Dap / 12 Splices | January
Colonial Manor | APT Communications | 2026-01-30 |  |  | No Production | January
FB-HOE401-V2 | North Path | 2026-01-30 |  |  | No Production Did Not Show | January
D-HDF710 | GN Systems | 2026-01-30 | 1637 |  | 4 Toby Boxes / 2 Daps / 8 Splices | January
FB-HLR201 | GN Systems | 2026-01-30 | 481 |  | 2 HH / 2 Ground Rod | January
D-HSH252 | Lightspeed | 2026-01-30 |  | 939 |  | January
D-HNP108 | Kattle One | 2026-02-02 | 251 |  | 2 Toby Boxes | February
FB-HNP118 | Lightspeed | 2026-02-02 |  |  | No Production | February
D-HWP1006 | Longo Underground | 2026-02-02 | 505 |  | 2 Toby Boxes / 1 Dap / 4 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | February
D-HWP1005 | Lightspeed | 2026-02-02 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | February
D-HWP1007 | Lightspeed | 2026-02-02 |  | 2004 | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | February
Moss Creek | Kattle One | 2026-02-02 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | February
Colonial Manor | APT Communications | 2026-02-02 |  |  | No Production Crew Did Not Show Up Today | February
FB-HOE401-V2 | North Path | 2026-02-02 |  |  | No Production Crew Did Not Show Up Today | February
FB-HLR202 | 1972 Fiber Core | 2026-02-02 |  | 13102 | 10,941 Tracer Wire / 16 Ground Rods | February
FB-HLR201 | GN Systems | 2026-02-02 | 859 |  |  | February
D-HWP1303 | Brothers | 2026-02-03 | 1250 |  | 13 Toby Boxes / 9 Daps / 67 Splices | February
D-H0306A-1 | Lightspeed | 2026-02-03 | 251 |  |  | February
Moss Creek | Kattle One | 2026-02-03 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | February
FB-HOE401-V2 | North Path | 2026-02-03 | 363 |  |  | February
D-HLR204 | Lightspeed | 2026-02-03 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | February
D-HDF710 | GN Systems | 2026-02-03 | 1646 |  | 9 Daps / 46 Splices | February
D-HWP1303 | Brothers | 2026-02-04 | 518 |  | 9 Toby Boxes / 5 Daps / 18 Splices | February
D-H0306A-1 | Lightspeed | 2026-02-04 |  |  | No Production Drill Breakdown | February
D-HWP109 | J Garcia Underground | 2026-02-04 | 330 |  |  | February
Colonial Manor | Kattle One | 2026-02-04 |  |  | 2 FDH / 2 HH / 2 Swing Arms | February
FB-HOE401-V2 | North Path | 2026-02-04 | 933 |  |  | February
D-HDF708 | GN Systems | 2026-02-04 | 1809 |  | 11 Toby Boxes / 9 Daps / 41 Splices | February
FB-HNP118 | Lightspeed | 2026-02-05 |  |  | No Production Crew Ran Into Issues With Conduit Path | February
D-HWP1303 | Brothers | 2026-02-05 | 990 |  | 12 Toby Boxes / 10 Daps / 53 Splices | February
D-H0306A-1 | Lightspeed | 2026-02-05 | 298 |  |  | February
D-HWP109 | J Garcia Underground | 2026-02-05 | 625 |  |  | February
FB-HLR201 | 1972 Fiber Core | 2026-02-05 |  | 9106 | 6,953 Tracer Wire / 13 Ground Rods | February
FB-HOE401-V2 | North Path | 2026-02-05 | 363 |  |  | February
D-HDF708 | GN Systems | 2026-02-05 | 696 |  | 9 Toby Boxes / 6 Daps / 51 Splices | February
D-HSH249 | Brothers | 2026-02-05 | 253 |  |  | February
D-HWP1303 | Brothers | 2026-02-06 |  |  | 2 HH / 2 Ground Rods | February
Colonial Manor | APT Communications | 2026-02-06 |  |  | 132 Micro Splices | February
D-HDF708 | GN Systems | 2026-02-06 | 3 |  | 3 Toby Boxes / 1 Dap / 2 Splices | February
D-HDF710 | GN Systems | 2026-02-06 | 6 |  | 4 Dap / 20 Splices | February
D-HNP108 | Lightspeed | 2026-02-09 | 389 |  |  | February
D-HWP1303 | Brothers | 2026-02-09 |  | 1049 | 1,049 Tracer Wire | February
D-HWP109 | J Garcia Underground | 2026-02-09 | 712 |  |  | February
FB-HLR201 | 1972 Fiber Core | 2026-02-09 |  | 0 | 695 Tracer Wire | February
D-HNP108 | Lightspeed | 2026-02-10 | 152 |  | 1 Toby Box / 2 Daps / 9 Splices | February
FB-HNP104 | Lightspeed | 2026-02-10 | 197 |  |  | February
D-HO306A-1 | Lightspeed | 2026-02-10 | 189 |  | 1 Dap | February
D-HWP109 | J Garcia Underground | 2026-02-10 | 1092 |  | 4 Toby Boxes / 2 Daps / 8 Splices | February
FB-HOE401-V2 | 1972 Fiber Core | 2026-02-10 |  | 2683 |  | February
FB-HAL175 | GN Systems | 2026-02-10 | 817 |  |  | February
FB-HLR202 | GN Systems | 2026-02-10 |  |  | 4 HH / 4 Ground Rods | February
D-HNP108 | Lightspeed | 2026-02-11 | 45 |  |  | February
FB-HNP104 | Lightspeed | 2026-02-11 | 338 |  |  | February
D-H0306A-1 | Lightspeed | 2026-02-11 | 150 |  | 4 Toby Boxes / 4 Daps / 20 Splices | February
D-HWP109 | J Garcia Underground | 2026-02-11 | 384 |  | 10 Toby Boxes / 8 Daps / 44 Splices | February
FB-HOE401-V2 | North Path | 2026-02-11 |  |  | 6 HH / 6 Ground Rods | February
FB-HOE401-V2 | 1972 Fiber Core | 2026-02-11 |  | 1781 | 3,864 Tracer Wire | February
FB-HOE401-V3 | North Path | 2026-02-11 | 753 |  |  | February
FB-HAL175 | GN Systems | 2026-02-11 |  |  | 3 HH / 3 Ground Rods | February
D-HDF712 | GN Systems | 2026-02-11 | 2073 |  | 11 Toby Boxes / 8 Daps / 40 Splices | February
D-H0306A-1 | Lightspeed | 2026-02-12 |  |  | Proofing Conduits | February
D-HWP109 | J Garcia Underground | 2026-02-12 | 397 |  | 4 Toby Boxes / 5 Daps / 8 Splices | February
D-HWP1303 | Lightspeed | 2026-02-12 |  | 711 |  | February
FB-HOE401-V2 | 1972 Fiber Core | 2026-02-12 | 30 |  |  | February
FB-HOE401-V3 | North Path | 2026-02-12 | 1289 |  |  | February
FB-HAL175 | 1972 Fiber Core | 2026-02-12 |  | 1230 | 830 Tracer Wire / 3 Ground Switches | February
D-HDF712 | GN Systems | 2026-02-12 | 1342 |  | 5 Toby Boxes / 3 Daps / 9 Splices | February
D-HWP1303 | Lightspeed | 2026-02-13 | 342 |  |  | February
D-HDF712 | GN Systems | 2026-02-13 | 1601 |  | 7 Toby Boxes / 4 Daps / 37 Splices | February
D-HWP109 | J Garcia Underground | 2026-02-16 | 669 |  |  | February
D-HWP106 | Brothers | 2026-02-16 | 1564 |  | 10 Toby Boxes / 7 Daps / 33 Splices | February
D-HNP114 | North Path | 2026-02-17 | 988 |  |  | February
D-HNP108 | Lightspeed | 2026-02-17 | 214 |  |  | February
FB-HNP104 | Lightspeed | 2026-02-17 | 214 |  |  | February
D-HWP109 | J Garcia Underground | 2026-02-17 | 467 |  |  | February
D-HWP106 | Brothers | 2026-02-17 | 1532 |  | 13 Toby Boxes / 9 Daps / 39 Splices | February
FB-HOE501 | GN Systems | 2026-02-17 | 1340 |  |  | February
Sabal Lakes | APT Communications | 2026-02-17 | 199 |  | 1 Dap / 2 Splices | February
D-HNP114 | North Path | 2026-02-18 | 712 |  |  | February
D-HNP108 | Lightspeed | 2026-02-18 |  |  | No Production | February
D-H0221F-Repair | Lightspeed | 2026-02-18 | 187 |  | Repair Request Work | February
D-HWP109 | J Garcia Underground | 2026-02-18 | 1133 |  | 4 Toby Boxes / 3 Daps / 21 Splices | February
D-HWP106 | Brothers | 2026-02-18 | 1447 |  | 10 Toby Boxes / 6 Daps / 36 Splices | February
FB-HOE501 | GN Systems | 2026-02-18 | 1529 |  |  | February
Sabal Lakes | APT Communications | 2026-02-18 | 361 |  |  | February
D-HNP114 | North Path | 2026-02-19 | 474 |  |  | February
D-H0221F-Repair | Lightspeed | 2026-02-19 | 300 |  | Repair Request Work | February
D-HWP109 | J Garcia Underground | 2026-02-19 | 448 |  |  | February
D-HWP106 | Brothers | 2026-02-19 | 864 |  | 8 Toby Boxes / 5 Daps / 6 Splices / 1 HH / 1 Ground Rod | February
D-HWP107 | Brothers | 2026-02-19 | 538 |  | 4 Toby Boxes / 3 Daps / 5 Splices | February
FB-HOE501 | GN Systems | 2026-02-19 | 1168 |  |  | February
Sabal Lakes | APT Communications | 2026-02-19 | 652 |  | 4 Toby Boxes / 4 Daps / 8 Splices | February
D-H0221F | Lightspeed | 2026-02-20 | 295 |  | Repair Request Work 1 Toby Box / 4 Daps / 6 Splices | February
D-HNP108 | Lightspeed | 2026-02-20 |  |  | FDH | February
FB-HOE501 | GN Systems | 2026-02-20 | 1008 |  |  | February
BHU-FAL-01-W | 1972 Fiber Core | 2026-02-20 | 45 | 5780 | 3 Daps / 7 HH / 7 Ground Rods | February
Sabal Lakes | APT Communications | 2026-02-20 | 379 |  | 4 Toby Boxes / 4 Daps / 8 Splices | February
D-H0221F-Repair | Lightspeed | 2026-02-23 | 201 |  | Repair Request Work 1 Toby Box / 1 Dap / 12 Splices | February
D-HNP114 | North Path | 2026-02-23 | 837 |  |  | February
D-HWP106 | Brothers | 2026-02-23 |  |  | FDH | February
D-HWP109 | J Garcia Underground | 2026-02-23 | 1044 |  | 13 Toby Boxes / 6 Daps / 29 Splices | February
FB-HOE501 | GN Systems | 2026-02-23 | 1274 |  |  | February
D-HDF712 | GN Systems | 2026-02-23 | 1099 |  |  | February
Sabal Lakes | APT Communications | 2026-02-23 | 534 |  | 8 Toby Boxes / 8 Daps / 16 Splices | February
D-HWP109 | J Garcia Underground | 2026-02-24 |  |  | 11 Toby Boxes / 10 Daps / 46 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | February
D-HWP107 | Brothers | 2026-02-24 | 1056 |  | 5 Toby Boxes / 5 Daps / 21 Splices | February
FB-HOE501 | GN Systems | 2026-02-24 | 1073 |  |  | February
FB-HOE401-V3 | North Path | 2026-02-24 | 1062 |  |  | February
D-H0221F-Repair | Lightspeed | 2026-02-25 | 200 |  | Repair Request Work | February
D-HWP107 | Brothers | 2026-02-25 | 2018 |  | 13 Toby Boxes / 10 Daps / 49 Splices | February
FB-HOE501 | GN Systems | 2026-02-25 | 271 |  |  | February
FB-HOE401-V3 | North Path | 2026-02-25 | 1318 |  |  | February
D-HDF712 | GN Systems | 2026-02-25 | 2025 |  |  | February
Sabal Lakes | APT Communications | 2026-02-25 | 223 |  | 2 Toby Boxes / 2 Daps / 4 Splices | February
D-HDF708 | GN Systems | 2026-02-25 | 667 |  |  | February
FB-HWP106 | Brothers | 2026-02-26 | 1033 |  | 2 HH / 2 Ground Rods | February
FB-HOE401-V3 | North Path | 2026-02-26 | 1165 |  |  | February
D-HDF712 | GN Systems | 2026-02-26 |  |  | No Production Crew Did Not Show Up Today | February
D-HNP114 | North Path | 2026-02-27 | 199 |  |  | February
FB-HWP106 | Lightspeed | 2026-02-27 |  | 3268 | 3,268 Tracer Wire | February
Sabal Lakes | APT Communications | 2026-02-27 | 1187 |  |  | February
D-HWP107 | Brothers | 2026-03-02 | 1016 |  | 9 Toby Boxes / 9 Daps / 34 Splices | March
D-HWP110 | Brothers | 2026-03-02 | 611 |  |  | March
FB-HOE401-V3 | North Path | 2026-03-02 | 1391 |  |  | March
Sabal Lakes | APT Communications | 2026-03-02 | 1287 |  |  | March
D-HWP110 | Brothers | 2026-03-03 | 1612 |  | 6 Toby Boxes / 2 Daps / 21 Splices | March
D-HOE501 | North Path | 2026-03-03 | 179 |  |  | March
Sabal Lakes | APT Communications | 2026-03-03 | 575 |  |  | March
D-HWP107 | Brothers | 2026-03-04 |  |  | FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | March
D-HWP110 | Brothers | 2026-03-04 |  |  | 10 Toby Boxes / 7 Daps / 34 Splices | March
D-HWP109 | Lightspeed | 2026-03-04 |  | 583 |  | March
D-HOE502 | North Path | 2026-03-04 | 480 |  | 2 Toby Boxes / 2 Daps / 4 Splices | March
FB-HOE501 | GN Systems | 2026-03-04 |  |  | 16 HH | March
FB-HOE501 | 1972 Fiber Core | 2026-03-04 |  | 9484 | 7,684 Tracer Wire / 17 Ground Switches / 17 Ground Rod Installed | March
Sabal Lakes | APT Communications | 2026-03-04 | 857 |  |  | March
D-HOE502 | North Path | 2026-03-05 | 774 |  |  | March
Sabal Lakes | APT Communications | 2026-03-05 | 668 |  |  | March
D-HOE502 | North Path | 2026-03-06 |  |  | 4 Toby Boxes / 5 Daps | March
Sabal Lakes | APT Communications | 2026-03-06 | 1392 |  | 11 Toby Boxes / 14 Daps / 28 Splices | March
D-HWP110 | Brothers | 2026-03-09 | 1561 |  | 11 Toby Boxes / 7 Daps / 41 Splices | March
D-HOE502 | North Path | 2026-03-09 | 570 |  | 8 Toby Boxes / 8 Daps / 16 Splices | March
FB-HLX401 | GN Systems | 2026-03-09 | 1146 |  |  | March
FB-HLX409 | Lightspeed | 2026-03-09 | 535 |  |  | March
Willow Walk | Kattle One | 2026-03-09 | 606 |  | 6 Toby Boxes / 5 Daps / 12 Splices | March
Sabal Lakes | APT Communications | 2026-03-09 | 167 |  |  | March
D-HWP108 | Brothers | 2026-03-10 | 1595 |  |  | March
FB-HLX401 | GN Systems | 2026-03-10 | 308 |  |  | March
Willow Walk | Kattle One | 2026-03-10 | 459 |  | 3 Toby Boxes / 3 Daps / 5 Splices | March
Sabal Lakes | APT Communications | 2026-03-10 | 487 |  | 33 Toby Boxes / 41 Daps / 82 Splices | March
D-HWP108 | Brothers | 2026-03-11 | 1704 |  | 14 Toby Boxes / 6 Daps / 43 Splices | March
FB-HLX401 | GN Systems | 2026-03-11 | 300 |  |  | March
FB-HLX409 | Lightspeed | 2026-03-11 | 342 |  |  | March
Willow Walk | Kattle One | 2026-03-11 | 243 |  | 1 Toby Box / 1 Dap / 2 Splices | March
Sabal Lakes | APT Communications | 2026-03-11 | 263 |  |  | March
FB-HLX401 | GN Systems | 2026-03-12 |  |  | No Production | March
FB-HLX409 | Lightspeed | 2026-03-12 | 103 |  | 2 HH / 2 Ground Rods / 2 Maclean Switches | March
Willow Walk | Kattle One | 2026-03-12 | 778 |  | 5 Toby Boxes / 6 Daps / 10 Splices | March
Sabal Lakes | APT Communications | 2026-03-12 | 399 |  |  | March
D-H0221F-Repair | Lightspeed | 2026-03-13 | 100 |  |  | March
FB-HLX401 | GN Systems | 2026-03-13 | 510 |  |  | March
FB-HLX409 | Lightspeed | 2026-03-13 |  | 618 |  | March
Willow Walk | Kattle One | 2026-03-13 | 664 |  | 7 Toby Boxes / 6 Daps / 14 Splices | March
Sabal Lakes | APT Communications | 2026-03-13 | 278 |  |  | March
D-H0221F-Repair | Lightspeed | 2026-03-16 | 314 |  |  | March
D-HWP108 | Brothers | 2026-03-16 | 1581 |  |  | March
FB-HLX401 | GN Systems | 2026-03-16 | 1297 |  |  | March
BHT-FLX-02 | GN Systems | 2026-03-16 | 1163 |  |  | March
D-HOE501 | North Path | 2026-03-16 | 326 |  | 4 Toby Boxes / 4 Daps / 8 Splices | March
D-HOE502 | North Path | 2026-03-16 | 307 |  |  | March
Willow Walk | Kattle One | 2026-03-16 | 534 |  | 4 Toby Boxes / 2 Daps / 4 Splices | March
Sabal Lakes | APT Communications | 2026-03-16 |  |  |  | March
D-H0221F-Repair | Lightspeed | 2026-03-17 | 240 |  | 3 Toby Boxes / 4 Daps / 68 Splices | March
D-HWP919 | J Garcia Underground | 2026-03-17 | 560 |  | 5 Toby Boxes / 4 Daps / 24 Splices | March
FB-HLX401 | GN Systems | 2026-03-17 | 1300 |  |  | March
D-HOE502 | North Path | 2026-03-17 | 872 |  | 4 Toby Boxes / 4 Daps / 8 Splices | March
Willow Walk | Kattle One | 2026-03-17 | 466 |  | 5 Toby Boxes / 4 Daps / 8 Splices | March
FB-HOE176 | Lightspeed | 2026-03-17 |  |  | No Production | March
FB-HOE180 | Lightspeed | 2026-03-17 | 130 |  | 1 HH / 1 Ground Rod / 1 Ground Switch | March
D-HNP151-Repair | Lightspeed | 2026-03-18 | 86 |  | 1 Toby Box / 1 Dap / 64 Splices | March
D-HWP919 | J Garcia Underground | 2026-03-18 | 367 |  | 5 Toby Boxes / 4 Daps / 36 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | March
D-HWP902-Repair | J Garcia Underground | 2026-03-18 | 157 |  |  | March
D-HOE502 | North Path | 2026-03-18 | 312 |  | 1 Toby Box / 2 Daps / 4 Splices | March
Willow Walk | Kattle One | 2026-03-18 | 483 |  | 3 Toby Boxes / 3 Daps / 6 Splices | March
BHCD-FSF-05-E | GN Systems | 2026-03-18 | 462 |  |  | March
FB-HNP111 | Lightspeed | 2026-03-19 | 140 |  | 2 Splices | March
D-HWP108 | Brothers | 2026-03-19 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod / 1 Toby Box / 1 Dap / 2 Splice | March
D-HWP108 | Lightspeed | 2026-03-19 |  | 412 |  | March
D-HWP110 | Brothers | 2026-03-19 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | March
D-HWP110 | Lightspeed | 2026-03-19 |  | 679 |  | March
Willow Walk North | Kattle One | 2026-03-19 | 646 |  |  | March
FB-HLX401 | GN Systems | 2026-03-19 | 1766 |  | 6 HH / 6 Ground Rods | March
D-HOE502 | North Path | 2026-03-19 | 287 |  | 6 Toby Boxes / 4 Dps / 12 Splices | March
BHCD-FSF-05-E | GN Systems | 2026-03-19 | 1412 |  |  | March
BHT-FLX-02 | 1972 Fiber Core | 2026-03-19 |  | 1678 | 1,328 Tracer Wire | March
FB-HOE180 | 1972 Fiber Core | 2026-03-19 |  | 318 | 118 Tracer Wire / 2 Ground Rod Switches | March
BHT-FLX-02 | GN Systems | 2026-03-19 |  |  | 1 HH / 1 Ground Rod / 4 Ground Rod Switches | March
Sabal Lakes | APT Communications | 2026-03-19 |  |  | No Production | March
FB-HLX401 | GN Systems | 2026-03-20 | 41 |  | 7 HH / 7 Ground Rods | March
Willow Walk North | Kattle One | 2026-03-20 | 212 |  |  | March
BHCD-FSF-05-E | GN Systems | 2026-03-20 | 1376 |  |  | March
Sabal Lakes | APT Communications | 2026-03-20 | 308 | 500 | 1 HH / 300 Tracer Wire | March
Willow Walk North | Kattle One | 2026-03-23 | 225 |  |  | March
D-HOE501 | North Path | 2026-03-23 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | March
D-HOE502 | North Path | 2026-03-23 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | March
D-HLR212 | North Path | 2026-03-23 | 735 |  |  | March
Willow Walk North | Kattle One | 2026-03-24 | 135 |  |  | March
FB-HSH404 | Lightspeed | 2026-03-24 | 513 |  |  | March
BHCD-FPW-03-W | Sunshine Drilling | 2026-03-24 |  |  | No Production | March
D-HLR212 | North Path | 2026-03-24 | 755 |  | 13 Toby Boxes / 7 Daps / 26 Splices | March
D-HNP114 | Lightspeed | 2026-03-25 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | March
FB-HWP478 | Brothers | 2026-03-25 | 918 |  | 3 HH / 3 Ground Rods | March
Willow Walk North | Kattle One | 2026-03-25 | 278 |  | 4 Toby Boxes / 6 Daps / 8 Splices | March
D-HLR212 | North Path | 2026-03-25 | 897 |  | 4 Toby Boxes / 4 Daps / 8 Splices | March
FB-HLX401 | 1972 Fiber Core | 2026-03-25 |  | 8226 | 6,826 Tracer Wire | March
Willow Walk North | Lightspeed | 2026-03-25 | 216 |  |  | March
BHCD-FSF-05-E | GN Systems | 2026-03-25 | 2020 |  |  | March
FB-HSF404 | Lightspeed | 2026-03-25 |  |  | No Production | March
BHCD-FSF-04-W | Lightspeed | 2026-03-25 | 7 |  | 1 HH | March
BHCD-FPW-03-W | Sunshine Drilling | 2026-03-25 | 172 |  |  | March
FB-HNP111 | Lightspeed | 2026-03-26 |  | 2676 |  | March
Willow Walk North | Kattle One | 2026-03-26 | 333 |  |  | March
D-HLR204 | North Path | 2026-03-26 | 438 |  |  | March
D-HLR212 | North Path | 2026-03-26 | 583 |  | 7 Toby Boxes / 7 Daps / 16 Splices | March
BHCD-FSF-05-E | GN Systems | 2026-03-26 | 1855 |  |  | March
FB-HSF477 | Lightspeed | 2026-03-26 | 265 |  |  | March
Willow Walk North | Kattle One | 2026-03-27 | 377 |  |  | March
BHCD-FSF-05-E | GN Systems | 2026-03-27 | 1609 |  |  | March
FB-HSF477 | Lightspeed | 2026-03-27 | 372 |  |  | March
Willow Walk North | Kattle One | 2026-03-30 | 526 |  |  | March
FB-HAL113 | North Path | 2026-03-30 | 978 |  |  | March
FB-HSF476 | Lightspeed | 2026-03-30 | 195 |  |  | March
FB-HSF477 | Lightspeed | 2026-03-30 | 396 |  |  | March
FB-HSF379 | GN Systems | 2026-03-30 | 788 |  |  | March
BHCD-FSF-05-E | GN Systems | 2026-03-30 |  |  | No Production | March
D-HDH57 Repair | Lightspeed | 2026-03-31 | 55 |  |  | March
Willow Walk North | Kattle One | 2026-03-31 | 36 |  | 12 Toby Boxes / 9 Daps / 24 Splices | March
FB-HAL113 | North Path | 2026-03-31 | 1555 |  |  | March
FB-HSF379 | GN Systems | 2026-03-31 | 1083 |  | 4 HH | March
BHCD-FSF-05-E | GN Systems | 2026-03-31 | 1420 |  |  | March
FB-HSF381 | GN Systems | 2026-03-31 | 551 |  | 2 HH | March
Willow Walk North | Kattle One | 2026-04-01 | 12 |  | 9 Toby Boxes / 5 Daps / 196 Splices / 2 FDH / 2 HH / 2 Ground Rods | April
FB-HAL113 | North Path | 2026-04-01 | 1095 |  |  | April
FB-HSF476 | Lightspeed | 2026-04-01 | 349 |  |  | April
BHCD-FSF-05-E | GN Systems | 2026-04-01 | 1208 |  |  | April
FB-HSF381 | GN Systems | 2026-04-01 | 1606 |  |  | April
Willow Walk North | Kattle One | 2026-04-02 |  |  | Proofing | April
Willow Walk North | Lightspeed | 2026-04-02 |  | 106 | 1 HH | April
FB-HAL113 | North Path | 2026-04-02 |  |  | 1 HH | April
FB-HSF477 | Lightspeed | 2026-04-02 | 145 |  |  | April
FB-HSF476 | GN Systems | 2026-04-02 | 790 |  |  | April
BHCD-FSF-05-E | GN Systems | 2026-04-02 | 596 |  |  | April
Sunset Palms | Lightspeed | 2026-04-03 |  |  | Restoration | April
FB-HSF475 | GN Systems | 2026-04-03 | 752 |  | 2 HH / 2 Ground Rods | April
FB-HSF476 | GN Systems | 2026-04-03 | 15 |  |  | April
FB-HSF477 | GN Systems | 2026-04-03 |  |  | 2 HH / 2 Ground Rods | April
Sunset Palms | Lightspeed | 2026-04-06 |  |  | Restoration | April
FB-HAL177 | North Path | 2026-04-06 | 1360 |  |  | April
D-HNP106 | Lightspeed | 2026-04-07 |  |  | Restoration | April
FB-HSF383 | GN Systems | 2026-04-07 | 102 |  | 1 HH / 1 Ground Rod | April
FB-HSF384 | GN Systems | 2026-04-07 | 417 |  | 2 HH | April
BHCD-FSF-05-E | GN Systems | 2026-04-07 |  |  | 25 HH | April
FB-HAL177 | North Path | 2026-04-07 |  |  | 3 HH | April
FB-HAL113 | North Path | 2026-04-07 | 400 |  | HH | April
BHCD-FSF-04-W | 1972 Fiber Core | 2026-04-07 |  | 244 | 12 Tracer Wire / 1 Ground Rod | April
FB-HSF379 | 1972 Fiber Core | 2026-04-07 |  | 2366 | 1,916 Tracer Wire / 5 Ground REods | April
FB-HSF381 | 1972 Fiber Core | 2026-04-07 |  | 2688 | 2,188 Tracer Wire / 5 Ground Rods | April
FB-HSF404 | 1972 Fiber Core | 2026-04-07 |  | 742 | 542 Tracer Wire / 1 Ground Rod | April
FB-HSF475 | 1972 Fiber Core | 2026-04-07 |  | 1048 | 848 Tracer Wire / 2 Ground Rods | April
FB-HSF476 | 1972 Fiber Core | 2026-04-07 |  | 1654 | 1,354 Tracer Wire / 3 Ground Rods | April
FB-HSF477 | 1972 Fiber Core | 2026-04-07 |  | 1456 | 1,156 Tracer Wire / 3 Ground Rods | April
FB-HLX417 | GN Systems | 2026-04-08 | 1036 |  |  | April
FB-HLX417 | GN Systems | 2026-04-09 |  |  | 2 HH / 2 Ground Rods | April
FB-HLX501 | North Path | 2026-04-10 | 891 |  |  | April
FB-HLX501 | North Path | 2026-04-13 | 2719 |  |  | April
FB-HLX501 | North Path | 2026-04-14 | 2206 |  |  | April
FB-HAL113 | HYN Enterprise | 2026-04-14 |  | 4672 | 3,749 Tracer Wire | April
FB-HAL177 | HYN Enterprise | 2026-04-14 |  | 1850 | 1,202 Tracer Wire | April
BHCD-FSF-05-E | 1972 Fiber Core | 2026-04-14 |  | 14650 | 12,150 Tracer Wire | April
FB-HLX501 | North Path | 2026-04-15 | 2612 |  |  | April
FB-HSF383 | Lightspeed | 2026-04-15 |  | 300 | 2 Ground Rods / 100 Tracer Wire | April
FB-HSF384 | Lightspeed | 2026-04-15 |  | 688 | 3 Ground Rods / 488 Tracer Wire | April
FB-HLX501 | North Path | 2026-04-16 | 1765 |  |  | April
FB-HAL113 | Lightspeed | 2026-04-16 |  |  | Mclean Switches | April
FB-HSF177 | Lightspeed | 2026-04-16 |  |  | Mclean Switches | April
BHUD-FLX-04-E | GN Systems | 2026-04-16 | 407 |  |  | April
FB-HLX501 | North Path | 2026-04-17 | 1356 |  |  | April
FB-HOE176 | Lightspeed | 2026-04-17 | 67 |  |  | April
BHUD-FLX-04-E | GN Systems | 2026-04-17 |  |  | No Production Crew Hit Rock | April
BHUD-FLX-04-E | GN Systems | 2026-04-20 | 940 |  |  | April
FB-HLX501 | North Path | 2026-04-20 | 1212 |  |  | April
FB-HLX417 | 1972 Fiber Core | 2026-04-20 |  | 1268 | 1,068 Tracer Wire | April
BHU-FLX-01-E | Lightspeed | 2026-04-20 |  |  | Locate Issue--Frontier Not Marked | April
BHCD-FPW-03-W | North Path | 2026-04-20 | 572 |  |  | April
FB-HSF377 | Lightspeed | 2026-04-20 | 288 |  |  | April
BHUD-FLX-04-E | GN Systems | 2026-04-21 | 1575 |  |  | April
FB-HLX501 | North Path | 2026-04-21 | 866 |  |  | April
BHU-FLX-01-E | Lightspeed | 2026-04-21 | 290 |  |  | April
BHU-FLX-01-E | Lightspeed | 2026-04-21 | 477 |  |  | April
BHCD-FPW-03-W | North Path | 2026-04-21 | 776 |  |  | April
FB-HSF377 | Lightspeed | 2026-04-21 |  |  | 1 HH | April
FB-HSF378 | Lightspeed | 2026-04-21 | 290 |  |  | April
D-HBR252 | Yosep | 2026-04-21 | 3749 |  |  | April
FB-HWP875 | J Garcia Underground | 2026-04-22 | 390 |  |  | April
FB-HWP879 | J Garcia Underground | 2026-04-22 | 454 |  |  | April
BHUD-FLX-04-E | GN Systems | 2026-04-22 | 507 |  |  | April
FB-HLX501 | North Path | 2026-04-22 | 969 |  |  | April
BHU-FLX-01-E | Lightspeed | 2026-04-22 | 183 |  |  | April
BHU-FLX-01-E | Lightspeed | 2026-04-22 | 596 |  |  | April
BHCD-FPW-03-W | North Path | 2026-04-22 | 1009 |  |  | April
D-HBR253 | Yosep | 2026-04-22 | 544 |  |  | April
FB-HWP875 | J Garcia Underground | 2026-04-23 |  |  | No Production--Crew Hit Rock | April
FB-HWP879 | J Garcia Underground | 2026-04-23 | 285 |  |  | April
BHUD-FLX-04-E | GN Systems | 2026-04-23 |  |  | No Production--Drill Breakdown | April
D-HLX416 | GN Systems | 2026-04-23 | 2434 |  |  | April
FB-HLX501 | North Path | 2026-04-23 | 262 |  |  | April
BHU-FLX-01-E | Lightspeed | 2026-04-23 | 130 |  | 2 HH | April
BHCD-FPW-03-W | North Path | 2026-04-23 | 770 |  |  | April
D-HBR253 | Yosep | 2026-04-23 | 723 |  |  | April
FB-HNP138 | Lightspeed | 2026-04-24 | 70 |  | 2 Daps / 48 Splices | April
FB-HWP875 | J Garcia Underground | 2026-04-24 | 8 |  | 2 HH / 2 Ground Rod | April
FB-HWP879 | J Garcia Underground | 2026-04-24 | 33 |  | 1 HH / 1 Ground Rods | April
D-HLX404 | North Path | 2026-04-24 | 1587 |  | 4 Toby Boxes / 5 Daps / 11 Splices | April
BHUD-FLX-04-E | GN Systems | 2026-04-24 | 354 |  |  | April
FB-HSF375 | Lightspeed | 2026-04-24 | 339 |  |  | April
FB-HSF377 | 1972 Fiber Core | 2026-04-24 |  | 488 | 388 Tracer Wire / 2 Ground Rods | April
FB-HSF378 | 1972 Fiber Core | 2026-04-24 |  | 400 | 300 Tracer Wire / 2 Ground Rods | April
BHCD-FPW-03-W | North Path | 2026-04-24 |  | 3306 | 2,556 Tracer Wire | April
D-HTG202 | Lopez Underground | 2026-04-24 | 1085 |  |  | April
D-HBR253 | Yosep | 2026-04-24 | 563 |  |  | April
FB-HNP138 | Lightspeed | 2026-04-27 | 380 | 1138 |  | April
FB-HWP875 | J Garcia Underground | 2026-04-27 | 615 |  |  | April
FB-HWP879 | J Garcia Underground | 2026-04-27 | 327 |  |  | April
D-HLX404 | North Path | 2026-04-27 | 1339 |  |  | April
BHUD-FLX-04-E | GN Systems | 2026-04-27 | 864 |  |  | April
FB-HOE176 | Lightspeed | 2026-04-27 | 245 |  |  | April
D-HTG202 | Lopez Underground | 2026-04-27 |  |  | Crew Did Not Show Up Today | April
D-HBR253 | Yosep | 2026-04-27 | 1246 |  |  | April
FB-HWP875 | J Garcia Underground | 2026-04-28 | 349 |  |  | April
FB-HWP879 | J Garcia Underground | 2026-04-28 | 269 |  |  | April
BHU-FLX-01-E | Lightspeed | 2026-04-28 | 276 |  |  | April
D-HLX404 | North Path | 2026-04-28 | 857 |  |  | April
BHUD-FLX-04-E | GN Systems | 2026-04-28 | 674 |  |  | April
BHU-FLX-01-W | North Path | 2026-04-28 | 2304 |  |  | April
FB-HOE176 | Lightspeed | 2026-04-28 |  | 315 | 1 HH / 1 Ground Rod | April
D-HBR254 | Yosep | 2026-04-28 | 540 |  |  | April
D-HBR254 | Yosep | 2026-04-28 | 168 |  |  | April
Heatherpoint Lake Estates | H&H Underground | 2026-04-29 | 440 |  |  | April
FB-HWP879 | J Garcia Underground | 2026-04-29 | 515 |  | 1 HH / 1 Ground Rod | April
BHUD-FLX-01-E | Lightspeed | 2026-04-29 | 258 |  |  | April
BHUD-FLX-01-E | Lightspeed | 2026-04-29 | 383 |  |  | April
D-HLX404 | North Path | 2026-04-29 | 32 |  | 16 Toby Boxes / 8 Daps / 156 Splices | April
D-HLX402 | North Path | 2026-04-29 | 947 |  |  | April
D-HLX416 | GN Systems | 2026-04-29 | 1012 |  |  | April
BHU-FLX-01-W | North Path | 2026-04-29 | 1216 |  |  | April
BHUD-FLX-04-E | GN Systems | 2026-04-29 | 724 |  |  | April
D-HBR254 | Yosep | 2026-04-29 | 697 |  |  | April
FB-HWP879 | J Garcia Underground | 2026-04-30 | 451 |  | 3 HH | April
FB-HWP879 | Kattle One | 2026-04-30 |  | 2984 | 2,334 Tracer Wire | April
FB-HWP875 | Kattle One | 2026-04-30 |  | 1662 | 1,362 Tracer Wire | April
Heatherpoint Lake Estates | H&H Underground | 2026-04-30 |  |  | 2 Toby Boxes | April
BHU-FLX-01-E | Lightspeed | 2026-04-30 | 285 |  |  | April
BHU-FLX-01-E | Lightspeed | 2026-04-30 | 140 |  | 1 HH | April
D-HLX402 | North Path | 2026-04-30 | 1381 |  |  | April
D-HTG202 | Lopez Underground | 2026-04-30 | 2018 |  |  | April
BHU-FLX-01-W | North Path | 2026-04-30 | 2932 |  |  | April
BHUD-FLX-04-E | GN Systems | 2026-04-30 | 165 |  |  | April
Heatherpoint Lake Estates | J Garcia Underground | 2026-05-01 | 549 |  |  | May
BHU-FLX-01-E | Lightspeed | 2026-05-01 |  |  | Drill Breakdown | May
D-HTG202 | Lopez Underground | 2026-05-01 | 1563 |  |  | May
Heatherpoint Lake Estates | J Garcia Underground | 2026-05-04 | 847 |  |  | May
BHU-FLX-01-W | North Path | 2026-05-04 | 350 |  |  | May
D-HLX402 | North Path | 2026-05-04 | 897 |  |  | May
D-HLX416 | GN Systems | 2026-05-04 | 757 |  |  | May
D-HTG202 | Lopez Underground | 2026-05-04 | 699 |  |  | May
Heatherpoint Lake Estates | J Garcia Underground | 2026-05-05 | 555 |  |  | May
BHU-FLX-01-E | Lightspeed | 2026-05-05 | 110 |  |  | May
D-HLX401 | North Path | 2026-05-05 | 473 |  |  | May
D-HLX402 | North Path | 2026-05-05 | 408 |  |  | May
D-HTG202 | Lopez Underground | 2026-05-05 | 463 |  |  | May
FB-HTG237 | North Path | 2026-05-05 | 1174 |  |  | May
FB-HSF304 | Lightspeed | 2026-05-05 | 521 |  |  | May
Heatherpoint Lake Estates | J Garcia Underground | 2026-05-06 | 831 |  |  | May
FB-HLX501 | 1972 Fiber Core | 2026-05-06 |  | 17400 | 15,150 Tracer Wire | May
FB-HLX501 | North Path | 2026-05-06 |  |  | 23 HH / 23 Ground Rods | May
D-HLX401 | North Path | 2026-05-06 | 1258 |  |  | May
D-HLX421 | GN Systems | 2026-05-06 | 873 |  |  | May
D-HTG202 | Lopez Underground | 2026-05-06 | 561 |  |  | May
FB-HTG237 | North Path | 2026-05-06 | 1060 |  |  | May
FB-HSF304 | Lightspeed | 2026-05-06 | 701 |  |  | May
D-HBR252 | Yosep | 2026-05-06 | 43 |  | 5 Locate Markers / 3 Daps / 6 Splices | May
D-HBR254 | Yosep | 2026-05-06 | 140 |  |  | May
Heatherpoint Lake Estates | J Garcia Underground | 2026-05-07 |  |  | 2 FDH / 2 HH / 2 Swing Arms / 2 Ground Rods | May
D-HLX401 | North Path | 2026-05-07 | 1494 |  |  | May
D-HLX421 | GN Systems | 2026-05-07 | 449 |  |  | May
D-HTG202 | Lopez Underground | 2026-05-07 | 129 |  |  | May
FB-HTG237 | North Path | 2026-05-07 | 818 |  |  | May
D-HTG208 | Lopez Underground | 2026-05-07 |  |  | No Production | May
FB-HSF304 | Lightspeed | 2026-05-07 | 707 |  | 1 HH | May
BHU-FLX-01-W | HYN Enterprise | 2026-05-07 |  | 7552 | 6,787 Tracer Wire | May
BHZD-FLX-04-W | GN Systems | 2026-05-07 | 513 |  |  | May
D-HBR252 | Yosep | 2026-05-07 | 8 |  | 2 Locate Markers Installed / 2 Daps / 4 Splice | May
BHU-FLX-01-E | HYN Enterprise | 2026-05-08 |  | 7946 | 7,346 Tracer Wire | May
FB-HTG237 | North Path | 2026-05-08 | 441 |  |  | May
D-HTG208 | Lopez Underground | 2026-05-08 | 1540 |  |  | May
FB-HSF304 | Lightspeed | 2026-05-08 | 512 |  |  | May
FB-HSF304 | HYN Enterprise | 2026-05-08 |  | 2142 | 1,641 Tracer Wire | May
D-HBR253 | Yosep | 2026-05-08 | 630 |  |  | May
Heatherpoint Lake Estates | J Garcia Underground | 2026-05-11 | 217 |  |  | May
D-HLX401 | North Path | 2026-05-11 | 1070 |  |  | May
D-HLX416 | GN Systems | 2026-05-11 | 1627 |  | 31 Toby Boxes / 24 Daps / 190 Splices | May
D-HLX501 | Power Connect | 2026-05-11 | 525 |  |  | May
D-HTG208 | Lopez Underground | 2026-05-11 | 483 |  |  | May
FB-HTG237 | North Path | 2026-05-11 |  |  | No Production | May
FB-HSF304 | Lightspeed | 2026-05-11 |  |  | No Production | May
D-HBR253 | Yosep | 2026-05-11 | 114 |  |  | May
D-HBR254 | Yosep | 2026-05-11 | 763 |  |  | May
D-HPP606 | Lightspeed | 2026-05-12 | 443 |  | 4 Toby Boxes / 1 Dap / 8 Splices | May
D-HLX401 | North Path | 2026-05-12 | 584 |  |  | May
D-HLX501 | Power Connect | 2026-05-12 |  |  | No Production | May
D-HLX402 | North Path | 2026-05-12 | 2700 |  | 31 Toby Boxes / 29 Daps / 108 Splices | May
FB-HTG237 | North Path | 2026-05-12 | 679 |  |  | May
D-HTG206 | Lopez Underground | 2026-05-12 | 1520 |  |  | May
D-HBR254 | Yosep | 2026-05-12 | 745 |  |  | May
D-HPP606 | Lightspeed | 2026-05-13 | 406 |  | 1 Toby Box / 1 Dap / 2 Splices | May
FB-HAL101 | North Path | 2026-05-13 | 675 |  |  | May
D-HLX406 | North Path | 2026-05-13 | 1245 |  |  | May
D-HLX501 | Power Connect | 2026-05-13 | 787 |  |  | May
FB-HTG237 | North Path | 2026-05-13 | 263 |  |  | May
D-HTG206 | Lopez Underground | 2026-05-13 | 413 |  |  | May
FB-HSF376 | Lightspeed | 2026-05-13 | 73 |  |  | May
BHZD-FLX-04-W | GN Systems | 2026-05-13 | 427 |  |  | May
FB-HLX409 | Lightspeed | 2026-05-13 | 258 |  |  | May
BHU-FAL-01-W | 1972 Fiber Core | 2026-05-13 |  | 6032 | 5,682 Tracer Wire | May
D-HBR254 | Yosep | 2026-05-13 | 673 |  |  | May
FB-HBR252 | Yosep | 2026-05-13 | 292 |  |  | May
D-HPP606 | Lightspeed | 2026-05-14 | 361 |  |  | May
FB-HTG237 | North Path | 2026-05-14 | 46 |  | 6 HH / 6 Ground Rods | May
D-HTG206 | Lopez Underground | 2026-05-14 | 1539 |  |  | May
FB-HSF375 | Lightspeed | 2026-05-14 | 110 |  |  | May
FB-HAL101 | North Path | 2026-05-14 | 1313 |  |  | May
D-HLX406 | North Path | 2026-05-14 | 1150 |  |  | May
D-HLX501 | Power Connect | 2026-05-14 |  |  | No Production--Drill Breakdown | May
FB-HAL176 | North Path | 2026-05-14 | 145 |  |  | May
BHU-FAL-01-W | 1972 Fiber Core | 2026-05-14 |  |  | 1 HH / 5 Daps | May
FB-HSF376 | 1972 Fiber Core | 2026-05-14 | 35 |  | 3 HH / 3 Ground Rods / 304 48CT Fiber Cable / 95 Tracer Wire | May
D-HPP606 | Lightspeed | 2026-05-15 | 345 |  | 9 Toby Boxes / 4 Daps / 18 Splices | May
D-HLX406 | North Path | 2026-05-15 | 1240 |  |  | May
D-HLX501 | Power Connect | 2026-05-15 | 540 |  |  | May
FB-HAL179 | Lightspeed | 2026-05-15 | 225 |  |  | May
D-HTG206 | Lopez Underground | 2026-05-15 | 770 |  |  | May
D-HTG208 | Lopez Underground | 2026-05-15 | 191 |  |  | May
FB-HTG237 | HYN Enterprise | 2026-05-15 |  | 5050 | 4,481 Tracer Wire | May
D-HBR254 | Yosep | 2026-05-15 | 931 |  |  | May
FB-HBR252 | Yosep | 2026-05-15 | 2380 |  |  | May
D-HPP606 | Lightspeed | 2026-05-18 | 766 |  |  | May
D-HLX406 | North Path | 2026-05-18 | 1210 |  |  | May
D-HLX501 | Power Connect | 2026-05-18 | 585 |  |  | May
FB-HAL179 | Lightspeed | 2026-05-18 | 280 |  |  | May
FB-HAL101 | North Path | 2026-05-18 |  |  | No Production--Drill Breakdown | May
D-HTG206 | Lopez Underground | 2026-05-18 | 1126 |  |  | May
D-HTG208 | Lopez Underground | 2026-05-18 | 587 |  |  | May
D-HPP606 | Lightspeed | 2026-05-19 | 566 |  | 8 Toby Boxes / 6 Daps / 28 Splices | May
D-HLX406 | North Path | 2026-05-19 | 1966 |  |  | May
D-HLX501 | Power Connect | 2026-05-19 | 464 |  |  | May
FB-HAL179 | Lightspeed | 2026-05-19 |  | 705 | 2 HH / 2 Ground Rods / 505 Tracer Wire | May
FB-HAL101 | North Path | 2026-05-19 | 1000 |  |  | May
BHU-FAL-01-W | 1972 Fiber Core | 2026-05-19 | 200 |  |  | May
BHU-FAL-01-W | Lightspeed | 2026-05-19 | 45 | 345 | 245 Tracer Wire | May
D-HTG206 | Lopez Underground | 2026-05-19 | 879 |  | 7 Toby Boxes / 3 Daps / 22 Splices | May
D-HTG208 | Lopez Underground | 2026-05-19 | 364 |  |  | May
D-HBR252 | Yosep | 2026-05-19 |  |  | 1 Locate Marker | May
FB-HBR252 | Yosep | 2026-05-19 | 766 |  |  | May
D-HPP606 | Lightspeed | 2026-05-20 | 488 |  | 1 Toby Box / 2 Daps / 4 Splices | May
D-HLX406 | North Path | 2026-05-20 | 189 |  | 2 Toby Boxes / 2 Daps / 7 Splices | May
D-HLX501 | Power Connect | 2026-05-20 | 579 |  |  | May
D-HLX403 | North Path | 2026-05-20 | 2164 |  |  | May
D-HTG206 | Lopez Underground | 2026-05-20 | 218 |  |  | May
D-HSF321 | GN Systems | 2026-05-20 | 1245 |  | 4 Toby Boxes / 4 Daps / 9 Splices | May
FB-HBR252 | Yosep | 2026-05-20 |  |  | 7 HH | May
D-HPP606 | Lightspeed | 2026-05-21 |  |  |  | May
FB-HWP478 | Lightspeed | 2026-05-21 |  | 1418 | 1,018 Tracer Wire | May
D-HLX401 | North Path | 2026-05-21 | 60 |  | 25 Toby Boxes / 18 Daps / 174 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | May
D-HLX403 | North Path | 2026-05-21 | 2748 |  |  | May
D-HLX501 | Power Connect | 2026-05-21 | 300 |  |  | May
D-HTG206 | Lopez Underground | 2026-05-21 | 71 |  |  | May
D-HTG208 | Lopez Underground | 2026-05-21 | 654 |  |  | May
D-HSF321 | GN Systems | 2026-05-21 | 1344 |  | 8 Toby Boxes / 3 Daps / 24 Splices | May
D-HBR252 | Yosep | 2026-05-21 |  |  | Restoration | May
D-HBR253 | Yosep | 2026-05-21 |  |  | Restoration | May
D-HPP606 | Lightspeed | 2026-05-22 | 225 |  |  | May
D-HLX403 | North Path | 2026-05-22 | 1060 |  |  | May
D-HLX501 | Power Connect | 2026-05-22 | 216 |  |  | May
D-HLX507 | Power Connect | 2026-05-22 | 351 |  |  | May
D-HTG208 | Lopez Underground | 2026-05-22 | 1381 |  |  | May
D-HSF321 | GN Systems | 2026-05-22 | 803 |  | 7 Toby Boxes / 3 Daps / 24 Splices | May
D-HBR252 | Yosep | 2026-05-22 |  |  | Restoration | May
D-HBR253 | Yosep | 2026-05-22 | 241 |  | Restoration | May
|  | 2026-05-25 |  |  |  | May
D-HPP606 | Lightspeed | 2026-05-26 | 465 |  | 4 Toby Boxes / 2 Daps / 8 Splices | May
D-HPP613 | APT Communications | 2026-05-26 | 1157 |  |  | May
D-HLX501 | Power Connect | 2026-05-26 | 65 |  |  | May
D-HLX507 | Power Connect | 2026-05-26 | 649 |  |  | May
D-HLX407 | North Path | 2026-05-26 | 2456 |  |  | May
D-HTG208 | Lopez Underground | 2026-05-26 |  |  | No Production--Crew Did Not Show Up Today | May
D-HBR255 | Yosep | 2026-05-26 | 591 |  |  | May
D-HPP606 | Lightspeed | 2026-05-27 | 193 |  | 2 Toby Boxes / 2 Daps / 2 Splices | May
D-HLX507 | Power Connect | 2026-05-27 | 130 |  |  | May
D-HLX407 | North Path | 2026-05-27 | 2095 |  |  | May
D-HLX405 | North Path | 2026-05-27 | 420 |  |  | May
FB-HAL176 | Lightspeed | 2026-05-27 |  | 254 | 150 Tracer Wire | May
D-HTG225 | Lopez Underground | 2026-05-27 | 1110 |  |  | May
D-HBR255 | Yosep | 2026-05-27 | 670 |  |  | May
D-HBR254 | Yosep | 2026-05-27 | 145 |  |  | May
D-HPP606 | Lightspeed | 2026-05-28 | 1067 |  | 14 Toby Box / 11 Daps / 24 Splices | May
D-HPP607 | Lightspeed | 2026-05-28 | 319 |  | 4 Toby Boxes / 3 Daps / 4 Splices | May
D-HPP612 | Power Connect | 2026-05-28 | 1251 |  |  | May
D-HLX507 | Power Connect | 2026-05-28 | 864 |  |  | May
D-HLX405 | North Path | 2026-05-28 | 690 |  |  | May
D-HLX518 | North Path | 2026-05-28 |  |  | No Production--Drill Breakdown | May
D-HTG225 | Lopez Underground | 2026-05-28 | 1904 |  |  | May
D-HTG208 | Lopez Underground | 2026-05-28 | 1196 |  |  | May
D-HSF321 | GN Systems | 2026-05-28 | 176 |  | 4 Toby Boxes / 2 Daps / 7 Splices | May
D-HBR255 | Yosep | 2026-05-28 | 622 |  |  | May
D-HPP606 | Lightspeed | 2026-05-29 | 339 |  |  | May
D-HPP607 | Lightspeed | 2026-05-29 | 446 |  | 4 Toby Boxes / 4 Daps / 6 Splices | May
D-HPP612 | Power Connect | 2026-05-29 | 2149 |  |  | May
D-HTG225 | Lopez Underground | 2026-05-29 | 836 |  |  | May
D-HSF321 | GN Systems | 2026-05-29 | 2202 |  | 8 Daps / 65 Splices | May
D-HBR255 | Yosep | 2026-05-29 | 664 |  |  | May
D-HPP607 | Lightspeed | 2026-06-01 | 693 |  | 2 Toby Boxes / 2 Daps / 2 Splices | June
D-HPP612 | Power Connect | 2026-06-01 | 1826 |  |  | June
D-HPP614 | Mid Florida Contractors | 2026-06-01 | 514 |  |  | June
D-HLX507 | Power Connect | 2026-06-01 | 500 |  | 2 Toby Boxes / 2 Daps / 4 Splices | June
D-HLX403 | North Path | 2026-06-01 | 883 |  |  | June
D-HLX405 | North Path | 2026-06-01 | 612 |  |  | June
D-HTG233 | Lopez Underground | 2026-06-01 | 1084 |  |  | June
D-HSF320 | GN Systems | 2026-06-01 | 1433 |  | 1 Toby Box / 3 Daps | June
D-HSF321 | GN Systems | 2026-06-01 | 587 |  | 6 Toby Boxes / 1 Dap | June
FB-HSF201 | Lightspeed | 2026-06-01 | 270 |  |  | June
FB-HSF301 | Lightspeed | 2026-06-01 | 500 |  |  | June
D-HBR254 | Yosep | 2026-06-01 | 54 |  | 6 Daps / 6 Locate Markers | June
D-HBR255 | Yosep | 2026-06-01 | 783 |  |  | June
FB-HBR252 | Yosep | 2026-06-01 |  | 4148 | 3,438 Tracer Wire | June
D-HPP606 | Lightspeed | 2026-06-02 | 411 |  |  | June
D-HPP607 | Lightspeed | 2026-06-02 | 596 |  | 2 Toby Boxes / 2 Daps / 2 Splices | June
D-HPP612 | Power Connect | 2026-06-02 | 882 |  |  | June
D-HPP614 | Mid Florida Contractors | 2026-06-02 | 457 |  |  | June
D-HLX507 | Power Connect | 2026-06-02 | 985 |  | 5 Toby Boxes / 4 Daps / 22 Splices | June
D-HLX518 | North Path | 2026-06-02 | 2110 |  |  | June
FB-HSF201 | Lightspeed | 2026-06-02 | 490 |  |  | June
FB-HSF301 | Lightspeed | 2026-06-02 | 260 |  | 3 HH / 3 Ground Rods / 3 McLean Switches | June
D-HSF320 | GN Systems | 2026-06-02 | 2630 |  | 3 Toby Boxes / 6 Daps / 42 Splices | June
D-HTG225 | Lopez Underground | 2026-06-02 | 1309 |  |  | June
D-HBR252 | Yosep | 2026-06-02 | 63 |  | 7 Locate Markers / 8 Daps | June
D-HBR253 | Yosep | 2026-06-02 | 18 |  | 1 Locate Markers / 1 Daps | June
D-HBR255 | Yosep | 2026-06-02 | 733 |  |  | June
D-HPP606 | Lightspeed | 2026-06-03 | 237 |  | 1 Toby Box / 1 Dap / 2 Splices | June
D-HPP607 | Lightspeed | 2026-06-03 | 240 |  | 4 Toby Boxes / 3 Daps / 4 Splices | June
D-HPP612 | Power Connect | 2026-06-03 | 1681 |  |  | June
D-HPP614 | Mid Florida Contractors | 2026-06-03 | 580 |  |  | June
D-HLX507 | Power Connect | 2026-06-03 | 860 |  | 8 Toby Boxes / 7 Daps / 16 Splices | June
D-HLX518 | North Path | 2026-06-03 | 218 |  |  | June
FB-HSF201 | Lightspeed | 2026-06-03 |  |  | No Production--Drill Breakdown | June
D-HSF320 | GN Systems | 2026-06-03 | 1848 |  | 25 Toby Boxes / 10 Daps / 52 Splices | June
D-HTG225 | Lopez Underground | 2026-06-03 | 427 |  |  | June
D-HTG233 | Lopez Underground | 2026-06-03 | 2699 |  |  | June
D-HBR252 | Yosep | 2026-06-03 |  |  | 1 Dap / 2 Splices | June
D-HBR253 | Yosep | 2026-06-03 | 57 |  | 4 Locate Markers / 6 Daps / 1 HH | June
D-HBR255 | Yosep | 2026-06-03 | 970 |  |  | June
D-HPP606 | Lightspeed | 2026-06-04 |  |  | Proofing | June
D-HPP607 | Lightspeed | 2026-06-04 | 180 |  |  | June
D-HPP612 | Power Connect | 2026-06-04 | 760 |  | 2 Toby Boxes / 3 Daps / 6 Splices | June
D-HPP614 | Mid Florida Contractors | 2026-06-04 | 590 |  |  | June
D-HLX405 | Lightspeed | 2026-06-04 |  | 544 |  | June
D-HLX507 | Power Connect | 2026-06-04 | 212 |  | 3 Toby Boxes / 3 Daps / 15 Splices | June
D-HLX518 | North Path | 2026-06-04 | 796 |  |  | June
D-HLX511 | Power Connect | 2026-06-04 | 590 |  |  | June
D-HTG225 | Lopez Underground | 2026-06-04 | 421 |  |  | June
D-HTG207 | Lopez Underground | 2026-06-04 | 2715 |  |  | June
D-HTG239 | Lopez Underground | 2026-06-04 | 804 |  |  | June
D-HBR253 | Yosep | 2026-06-04 | 248 |  | 13 Locate Markers / 14 Daps / 56 Splices | June
D-HBR255 | Yosep | 2026-06-04 | 917 |  |  | June
D-HPP606 | Lightspeed | 2026-06-05 | 26 |  | 1 FDH / 1 Swing Arm / 1 Ground Rod / 58 Splices Completed | June
D-HPP607 | Lightspeed | 2026-06-05 | 150 |  |  | June
D-HPP609 | Brothers | 2026-06-05 | 1404 |  |  | June
D-HPP612 | Power Connect | 2026-06-05 | 243 |  |  | June
D-HPP614 | Mid Florida Contractors | 2026-06-05 | 351 |  |  | June
D-HLX518 | North Path | 2026-06-05 | 800 |  |  | June
D-HLX511 | Power Connect | 2026-06-05 | 261 |  |  | June
D-HTG207 | Lopez Underground | 2026-06-05 | 1377 |  |  | June
D-HTG208 | Lopez Underground | 2026-06-05 | 241 |  |  | June
D-HTG239 | Lopez Underground | 2026-06-05 | 559 |  |  | June
FB-HSF201 | Lightspeed | 2026-06-05 | 270 |  |  | June
D-HBR255 | Yosep | 2026-06-05 | 589 |  |  | June
D-HPP606 | Lightspeed | 2026-06-08 |  |  | Restoration | June
D-HPP607 | Lightspeed | 2026-06-08 |  |  | No Production--Locate Issue | June
D-HPP609 | Brothers | 2026-06-08 | 1403 |  | 10 Toby Boxes / 10 Daps / 31 Splices | June
D-HPP612 | Power Connect | 2026-06-08 |  |  | No Production--Crew Did Not Show Up Today | June
D-HPP613 | APT Communications | 2026-06-08 | 1643 |  |  | June
D-HPP614 | Mid Florida Contractors | 2026-06-08 | 370 |  |  | June
D-HPP617 | Brothers | 2026-06-08 | 935 |  | 4 Toby Boxes / 4 Daps / 7 Splices | June
D-HPP301 | R&F Construction | 2026-06-08 | 557 |  |  | June
D-HLX507 | Power Connect | 2026-06-08 | 314 |  |  | June
D-HLX518 | North Path | 2026-06-08 | 363 |  |  | June
D-HLX511 | Power Connect | 2026-06-08 |  |  | No Production | June
FB-HSF201 | Lightspeed | 2026-06-08 | 100 |  |  | June
D-HTG207 | Lopez Underground | 2026-06-08 | 675 |  |  | June
D-HTG239 | Lopez Underground | 2026-06-08 | 1052 |  |  | June
D-HTG241 | Lightspeed | 2026-06-08 | 554 |  |  | June
D-HBR254 | Yosep | 2026-06-08 |  |  | 14 Locate Markers / 22 Daps / 136 Splices / 1 HH | June
D-HBR255 | Yosep | 2026-06-08 | 230 |  | 1 Toby Box / 2 Daps / 16 Splices | June
D-HPP609 | Brothers | 2026-06-09 | 1668 |  | 10 Toby Boxes / 11 Daps / 45 Splices | June
D-HPP612 | Power Connect | 2026-06-09 | 68 |  |  | June
D-HPP613 | APT Communications | 2026-06-09 | 1601 |  |  | June
D-HPP614 | Mid Florida Contractors | 2026-06-09 |  |  | No Production--No Clear Locates | June
D-HPP617 | Brothers | 2026-06-09 | 2201 |  |  | June
D-HPP301 | R&F Construction | 2026-06-09 | 788 |  |  | June
D-HLX518 | North Path | 2026-06-09 |  |  | Restoration | June
D-HTG207 | Lopez Underground | 2026-06-09 | 668 |  |  | June
D-HTG239 | Lopez Underground | 2026-06-09 | 1291 |  |  | June
D-HTG241 | Lightspeed | 2026-06-09 | 592 |  |  | June
D-HBR252 | Yosep | 2026-06-09 | 9 |  | 1 Locate Marker / 1 Dap / 2 Splices | June
D-HBR253 | Yosep | 2026-06-09 | 14 |  | 1 Locate Marker / 1 Dap / 2 Splices | June
D-HBR254 | Yosep | 2026-06-09 | 441 |  | 5 Locate Markers / 7 Daps / 44 Splices | June
D-HPP607 | Lightspeed | 2026-06-10 | 510 |  | 2 Toby Boxes / 4 Daps / 4 Splices | June
D-HPP609 | Brothers | 2026-06-10 | 1670 |  | 9 Toby Boxes / 10 Daps / 41 Splices | June
D-HPP612 | Power Connect | 2026-06-10 |  |  | No Production | June
D-HPP613 | APT Communications | 2026-06-10 | 764 |  |  | June
D-HPP614 | Mid Florida Contractors | 2026-06-10 |  |  | No Production--No Clear Locates | June
D-HPP617 | Brothers | 2026-06-10 | 2415 |  | 16 Toby Boxes / 15 Daps / 106 Splices | June
D-HPP301 | R&F Construction | 2026-06-10 | 911 |  | 5 Daps / 9 Splices | June
D-HLX519 | North Path | 2026-06-10 | 1095 |  |  | June
D-HTG207 | Lopez Underground | 2026-06-10 | 44 |  |  | June
D-HTG239 | Lopez Underground | 2026-06-10 | 781 |  |  | June
D-HTG241 | Lightspeed | 2026-06-10 |  |  | No Production--Drill Breakdown | June
D-HBR254 | Yosep | 2026-06-10 | 7 |  | 1 Locate Markers / 1 Dap / 2 Splices | June
D-HBR255 | Yosep | 2026-06-10 | 31 |  | 5 Locate Markers / 5 Dap / 21 Splices | June
D-HPP607 | Lightspeed | 2026-06-11 | 320 |  | 2 Toby Boxes / 2 Dap / 3 Splices | June
D-HPP609 | Brothers | 2026-06-11 | 1364 |  | 9 Toby Boxes / 10 Dap / 48 Splices | June
D-HPP612 | Power Connect | 2026-06-11 |  |  | No Production | June
D-HPP617 | Brothers | 2026-06-11 | 1484 |  |  | June
FB-HPP617 | Brothers | 2026-06-11 | 800 |  |  | June
D-HPP301 | R&F Construction | 2026-06-11 | 820 |  | 5 Toby Boxes / 5 Dap / 9 Splices | June
D-HLX516 | North Path | 2026-06-11 |  |  | No Production | June
D-HLX517 | North Path | 2026-06-11 | 981 |  |  | June
D-HLX519 | North Path | 2026-06-11 | 1806 |  |  | June
D-HTG201 | Lopez Underground | 2026-06-11 | 1809 |  |  | June
D-HTG207 | Lopez Underground | 2026-06-11 | 256 |  |  | June
D-HTG208 | Lopez Underground | 2026-06-11 | 525 |  |  | June
D-HTG225 | Lopez Underground | 2026-06-11 | 43 |  |  | June
D-HTG239 | Lopez Underground | 2026-06-11 | 294 |  |  | June
D-HBR254 | Yosep | 2026-06-11 | 36 |  | 4 Locate Markers / 4 Daps / 7 Splices | June
D-HBR255 | Yosep | 2026-06-11 | 24 |  | 3 Locate Markers / 3 Daps / 9 Splices | June
D-HBR256 | Yosep | 2026-06-11 | 682 |  |  | June
D-HPP607 | Lightspeed | 2026-06-12 | 155 |  | 2 Daps / 3 Splices | June
D-HPP612 | Power Connect | 2026-06-12 | 2404 |  |  | June
D-HPP617 | Brothers | 2026-06-12 | 792 |  | 13 Toby Boxes / 13 Daps / 37 Splices | June
D-HPP618 | Brothers | 2026-06-12 | 2663 |  |  | June
D-HPP632 | Power Connect | 2026-06-12 | 1192 |  |  | June
D-HPP301 | R&F Construction | 2026-06-12 |  |  | 4 Toby Boxes / 4 Daps / 7 Splices | June
D-HLX516 | North Path | 2026-06-12 | 1633 |  |  | June
D-HLX517 | North Path | 2026-06-12 | 1038 |  |  | June
D-HTG201 | Lopez Underground | 2026-06-12 | 1876 |  |  | June
D-HTG207 | Lopez Underground | 2026-06-12 | 42 |  |  | June
D-HTG239 | Lopez Underground | 2026-06-12 | 413 |  |  | June
D-HBR255 | Yosep | 2026-06-12 | 19 |  | 3 Locate Markers / 5 Daps / 54 Splices | June
D-HBR256 | Yosep | 2026-06-12 | 370 |  |  | June
D-HPP607 | Lightspeed | 2026-06-15 | 350 |  | 2 Toby Boxes / 2 Daps / 2 Splices | June
D-HPP609 | Brothers | 2026-06-15 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod / 9 Toby Boxes / 9 Daps / 105 Splices | June
D-HPP610 | NIA Underground | 2026-06-15 | 1161 |  |  | June
D-HPP611 | Brothers | 2026-06-15 | 1639 |  | 9 Toby Boxes / 9 Daps / 16 Splices | June
D-HPP613 | APT Communications | 2026-06-15 |  |  | 3 Toby Boxes / 2 Daps / 2 Splices | June
D-HPP617 | Brothers | 2026-06-15 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | June
D-HPP618 | Brothers | 2026-06-15 | 1830 |  | 16 Toby Boxes / 16 Daps / 73 Splices | June
D-HPP632 | Power Connect | 2026-06-15 | 889 |  |  | June
D-HPP638 | Lightspeed | 2026-06-15 | 300 |  | 1 Toby Box / 1 Dap | June
D-HPP301 | R&F Construction | 2026-06-15 | 572 |  | 3 Toby Boxes / 3 Daps / 7 Splices | June
D-HHP307 | Lightspeed | 2026-06-15 | 75 |  |  | June
D-HPP311 | Legant Livings | 2026-06-15 | 139 |  |  | June
D-HLX517 | North Path | 2026-06-15 | 806 |  |  | June
D-HTG201 | Lopez Underground | 2026-06-15 | 636 |  |  | June
D-HTG233 | Lopez Underground | 2026-06-15 | 1076 |  |  | June
D-HBR255 | Yosep | 2026-06-15 | 27 |  | 4 Locate Markers / 4 Daps / 7 Splices | June
D-HBR256 | Yosep | 2026-06-15 | 587 |  |  | June
D-HPP607 | Lightspeed | 2026-06-16 | 180 |  |  | June
D-HPP610 | NIA Underground | 2026-06-16 |  |  | No Production | June
D-HPP611 | Brothers | 2026-06-16 | 2989 |  | 13 Toby Box / 10 Dap / 44 Splices | June
D-HPP613 | APT Communications | 2026-06-16 | 1083 |  | 3 Daps / 6 Splices | June
D-HPP617 | Brothers | 2026-06-16 |  |  | No Production | June
D-HPP629 | Brothers | 2026-06-16 |  |  | No Production | June
D-HPP632 | Power Connect | 2026-06-16 | 1618 |  |  | June
D-HPP638 | Lightspeed | 2026-06-16 | 387 |  | 1 Toby / 2 Daps / 4 Splices | June
D-HPP301 | R&F Construction | 2026-06-16 | 236 |  | 2 Toby Boxes / 2 Daps / 3 Splices | June
D-HHP307 | Lightspeed | 2026-06-16 | 248 |  | 4 Toby Boxes /4 Daps / 6 Splices | June
D-HPP311 | Legant Livings | 2026-06-16 | 361 |  |  | June
D-HPP318 | NIA Underground | 2026-06-16 | 579 |  |  | June
D-HLX516 | North Path | 2026-06-16 |  |  | No Production | June
D-HLX517 | North Path | 2026-06-16 | 977 |  |  | June
FB-HAL179 | Lightspeed | 2026-06-16 | 120 |  |  | June
D-HTG229 | Lopez Underground | 2026-06-16 | 608 |  |  | June
D-HTG233 | Lopez Underground | 2026-06-16 | 999 |  |  | June
D-HTG237 | Lopez Underground | 2026-06-16 | 3059 |  |  | June
D-HBR255 | Yosep | 2026-06-16 | 32 |  | 8 Locate Markers / 9 Daps / 37 Splices | June
D-HBR256 | Yosep | 2026-06-16 | 708 |  |  | June
D-HPP607 | Lightspeed | 2026-06-17 | 529 |  | 3 Toby Box / 4 Dap / 5 Splice | June
D-HPP610 | NIA Underground | 2026-06-17 | 2191 |  |  | June
D-HPP611 | Brothers | 2026-06-17 | 1756 |  | 11 Toby Box / 11 Dap / 40 Splices | June
D-HPP613 | APT Communications | 2026-06-17 |  |  | No Production--No Clear Locate | June
D-HPP614 | Mid Florida Contractors | 2026-06-17 | 1008 |  |  | June
D-HPP617 | Brothers | 2026-06-17 | 289 |  | 2 Toby Boxes / 2 Daps / 4 Splices | June
D-HPP619 | Brothers | 2026-06-17 | 2590 |  | 16 Toby Box / 18 Daps / 40 Splices | June
D-HPP629 | Brothers | 2026-06-17 |  |  | No Production | June
D-HPP632 | Power Connect | 2026-06-17 | 597 |  |  | June
D-HPP638 | Lightspeed | 2026-06-17 | 245 |  | 4 Toby Boxes / 3 Daps / 30 Splices | June
D-HPP301 | R&F Construction | 2026-06-17 | 550 |  | 2 Toby Box / 2 Dap / 7 Splices | June
D-HPP307 | Lightspeed | 2026-06-17 | 179 |  | 1 Toby Box / 1 Dap / 2 Splices | June
D-HPP311 | Legant Livings | 2026-06-17 | 2000 |  |  | June
D-HPP318 | NIA Underground | 2026-06-17 |  |  | 5 Toby Box / 5 Daps / 7 Splices | June
D-HLX516 | North Path | 2026-06-17 | 1210 |  |  | June
D-HLX517 | North Path | 2026-06-17 | 621 |  |  | June
FB-HAL179 | Lightspeed | 2026-06-17 |  |  | No Production | June
D-HTG229 | Lopez Underground | 2026-06-17 | 784 |  |  | June
D-HTG235 | Lopez Underground | 2026-06-17 | 1611 |  |  | June
D-HTG237 | Lopez Underground | 2026-06-17 | 820 |  |  | June
D-HBR255 | Yosep | 2026-06-17 | 32 |  | 4 Locate Markers / 4 Daps / 21 Splices | June
D-HBR256 | Yosep | 2026-06-17 | 512 |  |  | June
D-HPP607 | Lightspeed | 2026-06-18 | 415 |  | 2 Toby Boxes / 2 Daps / 2 Splices | June
D-HPP610 | NIA Underground | 2026-06-18 | 520 |  |  | June
D-HPP611 | Brothers | 2026-06-18 | 1605 |  | 10 Toby Boxes / 10 Daps / 40 Splices | June
D-HPP614 | Mid Florida Contractors | 2026-06-18 | 653 |  |  | June
D-HPP619 | Brothers | 2026-06-18 | 1745 |  | 12 Toby Boxes / 15 Daps / 42 Splices | June
D-HPP621 | Brothers | 2026-06-18 | 724 |  |  | June
D-HPP627 | Brothers | 2026-06-18 |  |  | No production | June
D-HPP629 | Brothers | 2026-06-18 | 1289 |  | 5 Toby Boxes / 5 Daps / 8 Splices | June
D-HPP631 | Brothers | 2026-06-18 | 225 |  | 1 Toby Box / 1 Dap / 2 Splices | June
D-HPP632 | Power Connect | 2026-06-18 | 984 |  |  | June
D-HPP633 | Power Connect | 2026-06-18 |  |  | No Production--No Clear Locates | June
D-HPP638 | Lightspeed | 2026-06-18 | 245 |  | 1 Toby Box / 1 Dap / 2 Splices | June
D-HPP301 | R&F Construction | 2026-06-18 | 510 |  |  | June
D-HPP305 | HDD Underground | 2026-06-18 | 1218 |  |  | June
D-HPP307 | Lightspeed | 2026-06-18 |  |  | No Production--Water Table Issue | June
D-HPP311 | Legant Livings | 2026-06-18 | 2076 |  | 8 Toby Boxes / 8 Daps / 16 Splices | June
D-HPP318 | NIA Underground | 2026-06-18 | 2842 |  | 8 Toby Boxes / 8 Daps / 14 Splices | June
D-HLX516 | North Path | 2026-06-18 | 1249 |  |  | June
D-HLX522 | North Path | 2026-06-18 | 865 |  |  | June
FB-HAL179 | Lightspeed | 2026-06-18 | 40 | 1118 | 1 HH / 1 Ground Rod / 818 Tracer Wire | June
D-HTG229 | Lopez Underground | 2026-06-18 | 337 |  |  | June
D-HTG235 | Lopez Underground | 2026-06-18 | 2862 |  |  | June
D-HTG238 | Lopez Underground | 2026-06-18 | 382 |  |  | June
D-HTG241 | Lopez Underground | 2026-06-18 | 3 |  | 2 Toby Boxes / 1 Dap / 2 Splices | June
D-HBR255 | Yosep | 2026-06-18 | 65 |  |  | June
D-HBR256 | Yosep | 2026-06-18 | 661 |  | 7 Locate Markers / 8 Daps / 26 Splices | June
D-HLX512 | North Path | 2026-06-19 | 822 |  |  | June
D-HLX522 | North Path | 2026-06-19 |  |  | No Production--Drill Breakdown | June
D-HTG233 | Lopez Underground | 2026-06-19 | 309 |  |  | June
D-HTG235 | Lopez Underground | 2026-06-19 | 894 |  |  | June
D-HTG237 | Lopez Underground | 2026-06-19 | 553 |  |  | June
D-HTG238 | Lopez Underground | 2026-06-19 |  |  | No Production--Crew Shutdown | June
D-HTG241 | Lightspeed | 2026-06-19 | 402 |  |  | June
D-HBR255 | Yosep | 2026-06-19 | 31 |  | 5 Locate Markers / 5 Daps / 21 Splices | June
D-HBR256 | Yosep | 2026-06-19 | 303 |  |  | June
D-HPP607 | Lightspeed | 2026-06-22 | 171 |  |  | June
D-HPP610 | NIA Underground | 2026-06-22 |  |  | No Production--No Clear Locates | June
D-HPP614 | Mid Florida Contractors | 2026-06-22 | 214 |  |  | June
D-HPP619 | Brothers | 2026-06-22 | 825 |  | 5 Toby Boxes / 5 Daps / 9 Splices | June
D-HPP621 | Brothers | 2026-06-22 | 2294 |  | 5 Toby Boxes / 6 Daps / 9 Splices | June
D-HPP625 | Brothers | 2026-06-22 | 876 |  |  | June
D-HPP627 | Brothers | 2026-06-22 | 350 |  |  | June
D-HPP630 | Patriot Underground | 2026-06-22 | 335 |  |  | June
D-HPP632 | Power Connect | 2026-06-22 | 391 |  |  | June
D-HPP633 | Power Connect | 2026-06-22 | 1140 |  |  | June
D-HPP301 | R&F Construction | 2026-06-22 |  |  | 2 HH / 11 Toby Boxes / 11 Daps / 18 Splices | June
D-HPP301 | Lightspeed | 2026-06-22 | 87 |  | 1 Toby Box/ 2 Daps / 39 Splices | June
D-HPP303 | R&F Construction | 2026-06-22 | 500 |  |  | June
D-HPP305 | HDD Underground | 2026-06-22 |  |  | No Production--Crew Shutdown | June
D-HPP307 | Lightspeed | 2026-06-22 | 281 |  |  | June
D-HPP310 | Legant Livings | 2026-06-22 | 620 |  |  | June
D-HPP311 | Legant Livings | 2026-06-22 | 364 |  |  | June
D-HPP318 | NIA Underground | 2026-06-22 | 2283 |  |  | June
FB-HWP476 | J Garcia Underground | 2026-06-22 | 1115 |  |  | June
D-HLX512 | North Path | 2026-06-22 | 648 |  |  | June
D-HLX522 | North Path | 2026-06-22 | 859 |  |  | June
D-HTG233 | Lopez Underground | 2026-06-22 | 511 |  |  | June
D-HTG235 | Lopez Underground | 2026-06-22 |  |  | No Production--Crew Did Not Show Up Today | June
D-HTG238 | Lopez Underground | 2026-06-22 |  |  | No Production--Crew Did Not Show Up Today | June
D-HTG241 | Lightspeed | 2026-06-22 | 697 |  |  | June
D-HLX402 | Lightspeed | 2026-06-22 |  | 617 |  | June
D-HLX403 | Lightspeed | 2026-06-22 |  | 420 |  | June
D-HLX404 | Lightspeed | 2026-06-22 |  | 1563 |  | June
D-HLX406 | Lightspeed | 2026-06-22 |  | 387 |  | June
D-HBR256 | Yosep | 2026-06-22 | 672 |  | 1 Locate Marker / 1 Dap / 2 Splices | June
FB-HBR252 | Yosep | 2026-06-22 |  |  | 1 HH | June
D-HPP607 | Lightspeed | 2026-06-23 |  |  | No Production | June
D-HPP614 | Mid Florida Contractors | 2026-06-23 | 1276 |  |  | June
D-HPP618 | Brothers | 2026-06-23 |  |  | 1 FDH / 1 HH / 1 Ground Rod / 11 Toby Boxes / 12 Daps / 84 Splices | June
D-HPP619 | Brothers | 2026-06-23 | 950 |  | 6 Toby Boxes / 6 Daps / 23 Splices | June
D-HPP621 | Brothers | 2026-06-23 |  |  | 1 HH / 1 Ground Rod | June
D-HPP625 | Brothers | 2026-06-23 | 890 |  | 10 Toby Boxes / 10 Daps / 24 Splices | June
D-HPP630 | Patriot Underground | 2026-06-23 | 558 |  |  | June
D-HPP632 | Power Connect | 2026-06-23 |  |  | No Production | June
D-HPP633 | Power Connect | 2026-06-23 | 5027 |  |  | June
D-HPP303 | R&F Construction | 2026-06-23 | 559 |  |  | June
D-HPP307 | Lightspeed | 2026-06-23 | 115 |  |  | June
D-HPP310 | Legant Livings | 2026-06-23 |  |  | No Production--Crew Shutdown | June
D-HPP311 | Legant Livings | 2026-06-23 |  |  | 6 Toby Boxes / 6 Daps / 12 Splices | June
D-HPP318 | NIA Underground | 2026-06-23 | 1160 |  | 16 Toby Boxes / 16 Daps / 23 Splices | June
FB-HWP476 | J Garcia Underground | 2026-06-23 | 891 |  |  | June
D-HLX512 | North Path | 2026-06-23 | 1155 |  |  | June
D-HLX522 | North Path | 2026-06-23 | 971 |  |  | June
D-HTG229 | Lopez Underground | 2026-06-23 | 689 |  |  | June
D-HTG235 | Lopez Underground | 2026-06-23 | 210 |  |  | June
D-HTG237 | Lopez Underground | 2026-06-23 | 193 |  |  | June
D-HTG238 | Lopez Underground | 2026-06-23 | 949 |  |  | June
D-HBR256 | Yosep | 2026-06-23 | 710 |  | 1 HH / 2 Locate Markers / 4 Daps / 44 Splices | June
D-HPP607 | Lightspeed | 2026-06-24 | 93 |  |  | June
D-HPP610 | NIA Underground | 2026-06-24 | 2241 |  |  | June
D-HPP611 | Brothers | 2026-06-24 | 1179 |  | 6 Toby Boxes / 6 Daps / 23 Splices | June
D-HPP615 | Brothers | 2026-06-24 | 520 |  | 3 Toby Boxes / 3 Daps / 6 Splices | June
D-HPP619 | Brothers | 2026-06-24 | 502 |  | 5 Toby Boxes / 5 Daps / 10 Splices | June
D-HPP621 | Brothers | 2026-06-24 | 1974 |  | 2 Toby Boxes / 1 FDH / 1 Swing Arm / 1 Ground Rod / 107 Splices | June
D-HPP625 | Brothers | 2026-06-24 | 749 |  |  | June
D-HPP627 | Brothers | 2026-06-24 | 492 |  | 5 Toby Boxes / 5 Daps / 10 Splices | June
D-HPP629 | Brothers | 2026-06-24 | 2452 |  |  | June
D-HPP630 | Patriot Underground | 2026-06-24 | 815 |  |  | June
D-HPP633 | Power Connect | 2026-06-24 | 1021 |  |  | June
D-HPP303 | R&F Construction | 2026-06-24 | 1506 |  |  | June
D-HPP307 | Lightspeed | 2026-06-24 | 253 |  |  | June
D-HPP310 | Legant Livings | 2026-06-24 |  |  | No Production | June
D-HPP311 | Legant Livings | 2026-06-24 |  |  | No Production | June
D-HPP318 | NIA Underground | 2026-06-24 | 803 |  |  | June
FB-HWP476 | J Garcia Underground | 2026-06-24 | 1345 |  |  | June
D-HLX512 | North Path | 2026-06-24 | 778 |  | 34 Toby Boxes / 30 Daps / 227 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | June
D-HLX522 | North Path | 2026-06-24 | 667 |  |  | June
D-HTG228 | Lopez Underground | 2026-06-24 |  |  | No Production | June
D-HTG233 | Lopez Underground | 2026-06-24 | 84 |  |  | June
D-HTG238 | Lopez Underground | 2026-06-24 | 514 |  |  | June
D-HBR256 | Yosep | 2026-06-24 | 823 |  | 7 Locate Markers / 7 Daps / 44 Splices | June
D-HPP615 | Brothers | 2026-06-25 | 1599 |  | 8 Toby Boxes / 8 Daps / 24 Splices | June
D-HPP619 | Brothers | 2026-06-25 | 838 |  | 5 Toby Boxes / 8 Daps / 38 Splices | June
D-HPP620 | Brothers | 2026-06-25 | 575 |  |  | June
D-HPP625 | Brothers | 2026-06-25 | 346 |  | 9 Toby Boxes / 8 Daps / 16 Splices | June
D-HPP630 | Patriot Underground | 2026-06-25 |  |  | No Production--Crew Shutdown | June
D-HPP303 | R&F Construction | 2026-06-25 | 548 |  | 14 Toby Boxes / 14 Daps / 20 Splices | June
D-HPP307 | Lightspeed | 2026-06-25 |  |  | No Production | June
D-HPP318 | NIA Underground | 2026-06-25 |  |  | 3 Toby Boxes / 22 Daps / 32 Splices | June
FB-HWP476 | J Garcia Underground | 2026-06-25 | 1328 |  |  | June
D-HLX513 | North Path | 2026-06-25 | 1436 |  |  | June
D-HLX522 | North Path | 2026-06-25 | 1025 |  |  | June
D-HTG228 | Lopez Underground | 2026-06-25 | 951 |  |  | June
D-HTG233 | Lopez Underground | 2026-06-25 | 75 |  |  | June
D-HTG238 | Lopez Underground | 2026-06-25 | 790 |  |  | June
FB-HTG204 | Alpha Omega | 2026-06-25 | 492 |  |  | June
FB-HTG290 | HAS Global | 2026-06-25 | 343 |  |  | June
D-HBR256 | Yosep | 2026-06-25 | 601 |  | 3 Locate Markers / 4 Daps / 74 Splices | June
D-HPP615 | Brothers | 2026-06-26 | 1500 |  | 7 Toby Boxes / 6 Dap / 56 Splices | June
D-HPP620 | Brothers | 2026-06-26 | 2236 |  | 9 Toby Boxes / 15 Daps / 17 Splices | June
D-HPP633 | Power Connect | 2026-06-26 | 186 |  |  | June
D-HPP303 | R&F Construction | 2026-06-26 | 651 |  |  | June
D-HPP307 | Lightspeed | 2026-06-26 | 310 |  | 3 Toby Boxes / 3 Daps / 6 Splices | June
FB-HWP476 | J Garcia Underground | 2026-06-26 |  |  | 6 HH / 6 Ground Rods | June
D-HLX513 | North Path | 2026-06-26 | 877 |  |  | June
D-HLX522 | North Path | 2026-06-26 |  |  | No Production--Locate Issue | June
D-HTG235 | Lopez Underground | 2026-06-26 |  |  | 35 Toby Boxes | June
D-HTG241 | Lightspeed | 2026-06-26 | 3 |  | 9 Toby Boxes / 1 Dap / 2 Splices | June
FB-HTG204 | Alpha Omega | 2026-06-26 |  |  | No Production | June
FB-HTG290 | HAS Global | 2026-06-26 |  |  | No Production | June
D-HBR256 | Yosep | 2026-06-26 | 597 |  | 1 HH / 1 Locate Marker / 1 Dap / 2 Splice | June
D-HPP611 | Brothers | 2026-06-29 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | June
D-HPP615 | Brothers | 2026-06-29 | 1695 |  | 9 Toby Boxes / 9 Daps / 76 Splices | June
D-HPP619 | Brothers | 2026-06-29 | 55 |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | June
D-HPP620 | Brothers | 2026-06-29 | 905 |  |  | June
D-HPP625 | Brothers | 2026-06-29 | 1537 |  |  | June
D-HPP629 | Brothers | 2026-06-29 |  |  | No Production--MOT Did Not Show Up | June
D-HPP303 | R&F Construction | 2026-06-29 |  |  | No Production | June
D-HPP305 | R&F Construction | 2026-06-29 | 971 |  |  | June
D-HPP310 | Legant Livings | 2026-06-29 | 1299 |  | 5 Toby Boxes / 5 Daps / 10 Splices | June
D-HPP318 | Nia Underground | 2026-06-29 |  |  | 13 Toby Boxes / 3 Daps / 6 Splices | June
D-HLX513 | North Path | 2026-06-29 | 1027 |  |  | June
D-HLX522 | North Path | 2026-06-29 | 361 |  | 31 Toby Boxes / 30 Daps / 197 Splices / 1 FDH / 1 HH / 1 Swing Arm | June
D-HLX520 | North Path | 2026-06-29 |  |  | No Production--Drill Breakdown | June
D-HTG228 | Lopez Underground | 2026-06-29 | 1642 |  |  | June
D-HTG233 | Lopez Underground | 2026-06-29 | 123 |  |  | June
D-HTG229 | Lopez Underground | 2026-06-29 |  |  | No Production--Locate Issue | June
FB-HTG290 | HAS Global | 2026-06-29 | 594 |  |  | June
D-HBR256 | Yosep | 2026-06-29 | 344 |  | 1 HH / 2 Locate Markers / 2 Daps / 74 Splices | June
D-HPP307 | Lightspeed | 2026-06-29 | 215 |  | 3 Toby Boxes / 3 Daps / 6 Splices | June
D-HPP613 | APT Communications | 2026-06-30 | 395 |  |  | June
D-HPP615 | Brothers | 2026-06-30 | 1620 |  | 9 Toby Boxes / 9 Dap / 17 Splices | June
D-HPP620 | Brothers | 2026-06-30 | 3166 |  | 10 Toby Boxes / 4 Daps / 67 Splices | June
D-HPP621 | Brothers | 2026-06-30 | 1028 |  |  | June
D-HPP625 | Brothers | 2026-06-30 | 1097 |  | 12 Toby Boxes / 18 Daps / 10 Splices | June
D-HPP629 | Brothers | 2026-06-30 |  |  | No Production | June
D-HPP631 | Brothers | 2026-06-30 | 251 |  | 2 Toby Boxes / 2 Daps / 3 Splices | June
D-HPP301 | Lightspeed | 2026-06-30 | 121 |  | 1 Dap / 7 Splices | June
D-HPP303 | R&F Construction | 2026-06-30 | 767 |  |  | June
D-HPP305 | R&F Construction | 2026-06-30 |  |  | 5 Toby Boxes / 5 Daps / 9 Splices | June
D-HPP307 | Lightspeed | 2026-06-30 | 283 |  | 1 Toby Box / 2 Daps / 1 Splice | June
D-HPP310 | Legant Livings | 2026-06-30 | 918 |  |  | June
D-HPP311 | Legant Livings | 2026-06-30 |  |  | 10 Toby Boxes / 10 Daps / 20 Splices | June
FB-HWP976 | J Garcia Underground | 2026-06-30 | 960 |  | 1 HH / 1 Ground Rod | June
D-HLX520 | North Path | 2026-06-30 | 983 |  |  | June
D-HLX521 | North Path | 2026-06-30 | 1039 |  |  | June
D-HTG228 | Lopez Underground | 2026-06-30 | 1664 |  |  | June
FB-HTG204 | Alpha Omega | 2026-06-30 | 557 |  |  | June
FB-HTG290 | HAS Global | 2026-06-30 |  |  | 1 HH | June
D-HBR256 | Yosep | 2026-06-30 | 7 |  | 1 HH / 1 Locate Marker / 1 Dap / 16 Splices | June
D-HBR257 | Yosep | 2026-06-30 | 452 |  |  | June
D-HPP613 | APT Communications | 2026-07-01 |  |  | No Production--Crew Shutdown | July
D-HPP615 | Brothers | 2026-07-01 | 1295 |  | 10 Toby Boxes / 12 Daps / 44 Splices | July
D-HPP620 | Brothers | 2026-07-01 | 539 |  |  | July
D-HPP625 | Brothers | 2026-07-01 | 1846 |  |  | July
D-HPP629 | Brothers | 2026-07-01 | 1646 |  | 5 Toby Boxes / 10 Splices | July
D-HPP631 | Brothers | 2026-07-01 |  |  | No Production | July
D-HPP301 | Lightspeed | 2026-07-01 | 235 |  | 1 Toby Box/ 2 Daps / 36 Splices | July
D-HPP303 | R&F Construction | 2026-07-01 | 108 |  |  | July
D-HPP305 | R&F Construction | 2026-07-01 | 501 |  |  | July
D-HPP307 | Lightspeed | 2026-07-01 | 144 |  |  | July
D-HPP310 | Legant Livings | 2026-07-01 | 925 |  |  | July
D-HPP318 | Legant Livings | 2026-07-01 |  |  | 4 Toby Boxes / 6 Daps / 10 Splices | July
FB-HWP976 | J Garcia Underground | 2026-07-01 | 665 |  | 2 HH / 2 Ground Rods | July
D-HLX520 | North Path | 2026-07-01 |  |  | No Production | July
D-HLX521 | North Path | 2026-07-01 | 754 |  |  | July
D-HTG201 | Lopez Underground | 2026-07-01 | 339 |  |  | July
D-HTG228 | Lopez Underground | 2026-07-01 | 439 |  |  | July
D-HTG229 | Lopez Underground | 2026-07-01 | 544 |  |  | July
D-HTG238 | Lopez Underground | 2026-07-01 | 867 |  |  | July
FB-HTG204 | Alpha Omega | 2026-07-01 |  |  | 2 HH | July
FB-HTG290 | HAS Global | 2026-07-01 |  |  | 2 HH | July
D-HBR256 | Yosep | 2026-07-01 | 28 |  | 1 HH / 4 Locate Marker / 4 Daps / 84 Splices | July
D-HBR257 | Yosep | 2026-07-01 | 635 |  |  | July
D-HLX507 | Power Connect | 2026-07-01 |  |  | 4 Toby Boxes / 21 Daps / 1 HH / 1 Ground Rod | July
D-HPP615 | Brothers | 2026-07-02 | 905 |  | 1 HH / 1 FDH / 1 Swing Arm / 1 Ground Rod / 6 Toby Boxes / 6 Daps / 28 Splices | July
D-HPP627 | Brothers | 2026-07-02 | 1237 |  |  | July
D-HPP629 | Brothers | 2026-07-02 | 852 |  |  | July
D-HPP631 | Brothers | 2026-07-02 |  |  | No Production | July
D-HPP638 | Lightspeed | 2026-07-02 |  |  | No Production--Locate Issue | July
D-HPP301 | R&F Construction | 2026-07-02 |  |  | 1 HH | July
D-HPP305 | R&F Construction | 2026-07-02 | 492 |  | 3 Toby Boxes / 3 Daps / 6 Splices | July
FB-HWP476 | J Garcia Underground | 2026-07-02 | 300 |  | 1 HH / 1 Ground Rod | July
FB-HWP976 | J Garcia Underground | 2026-07-02 |  | 2025 | 1,625 Tracer Wire | July
D-HLX520 | North Path | 2026-07-02 | 841 |  |  | July
D-HLX521 | North Path | 2026-07-02 | 1000 |  |  | July
D-HTG229 | Lopez Underground | 2026-07-02 |  |  | No Production | July
D-HTG238 | Lopez Underground | 2026-07-02 | 206 |  |  | July
D-HTG241 | Lightspeed | 2026-07-02 | 18 |  | 24 Splices | July
D-HBR256 | Yosep | 2026-07-02 | 42 |  | 6 Locate Markers / 7 Daps / 55 Splices | July
D-HBR257 | Yosep | 2026-07-02 | 741 |  |  | July
D-HNP108 | Lightspeed | 2026-07-03 |  |  | Crew Shutdown By Tillman Expired Permit | July
D-HPP616 | Brothers | 2026-07-06 | 1613 |  | 8 Toby Boxes / 9 Daps / 30 Splices | July
D-HPP627 | Brothers | 2026-07-06 | 235 |  | 4 Toby Boxes / 2 Daps / 6 Splices | July
D-HPP639 | ASM Utilities | 2026-07-06 | 1050 |  |  | July
D-HPP305 | R&F Construction | 2026-07-06 | 646 |  | 2 Toby Boxes / 2 Daps / 4 Splices | July
D-HPP307 | Lightspeed | 2026-07-06 | 86 |  |  | July
D-HPP310 | R&F Construction | 2026-07-06 | 936 |  |  | July
FB-HWP476 | J Garcia Underground | 2026-07-06 | 1036 |  | 1 HH / 1 Ground Rod | July
D-HLX520 | North Path | 2026-07-06 | 1027 |  |  | July
D-HLX521 | North Path | 2026-07-06 | 973 |  |  | July
D-HTG228 | Lopez Underground | 2026-07-06 | 487 |  |  | July
D-HTG229 | Lopez Underground | 2026-07-06 | 845 |  |  | July
D-HTG238 | Lopez Underground | 2026-07-06 | 509 |  |  | July
FB-HTG290 | HAS Global | 2026-07-06 | 698 |  |  | July
D-HBR256 | Yosep | 2026-07-06 | 53 |  | 4 Locate Markers / 5 Daps / 61 Splices | July
D-HPP613 | APT Communications | 2026-07-07 | 37 |  | 1 Toby Box / 1 Dap / 2 Splices | July
D-HPP616 | Brothers | 2026-07-07 | 1647 |  | 11 Toby Boxes / 12 Daps / 32 Splices | July
D-HPP638 | Lightspeed | 2026-07-07 | 340 |  | 3 Toby Boxes / 3 Daps / 6 Splices | July
D-HPP639 | ASM Utilities | 2026-07-07 | 770 |  |  | July
D-HPP305 | R&F Construction | 2026-07-07 | 340 |  | 7 Toby Boxes / 7 Daps / 10 Splices | July
D-HPP310 | Lagent Livings | 2026-07-07 | 668 |  | 6 Toby Boxes / 6 Daps / 12 Splices | July
FB-HWP476 | J Garcia Underground | 2026-07-07 | 350 |  |  | July
D-HOE503 | North Path | 2026-07-07 | 449 |  |  | July
D-HLX521 | North Path | 2026-07-07 |  |  | No Production | July
FB-HLX375 | North Path | 2026-07-07 | 721 |  |  | July
D-HTG229 | Lopez Underground | 2026-07-07 | 206 |  |  | July
D-HTG238 | Lopez Underground | 2026-07-07 | 254 |  |  | July
FB-HTG290 | HAS Global | 2026-07-07 | 235 |  |  | July
FB-HTG288 | Alpha Omega | 2026-07-07 | 352 |  |  | July
BHCD-FPW-03-E | Lopez Underground | 2026-07-07 |  |  | No Production--Locate Issue | July
D-HPP307 | Lightspeed | 2026-07-07 | 322 |  | 3 Toby Boxes / 4 Daps / 6 Splices | July
D-HPP607 | Lightspeed | 2026-07-08 | 424 |  | 1 Toby Box / 2 Daps / 1 Splice / 1 FDH / 1 HH / 1 Swing Arm | July
D-HPP613 | APT Communications | 2026-07-08 | 1440 |  |  | July
D-HPP616 | Brothers | 2026-07-08 | 1647 |  | 10 Toby Boxes / 11 Daps / 44 Splices | July
D-HPP629 | Brothers | 2026-07-08 | 887 |  |  | July
D-HPP638 | Lightspeed | 2026-07-08 | 385 |  | 2 Toby Boxes / 3 Daps / 4 Splices | July
D-HPP639 | ASM Utilities | 2026-07-08 | 839 |  | 5 Toby Boxes / 10 Splices | July
D-HPP303 | R&F Construction | 2026-07-08 | 930 |  |  | July
D-HPP307 | Lightspeed | 2026-07-08 | 222 |  |  | July
D-HPP310 | Legant Livings | 2026-07-08 | 240 |  | 7 Toby Boxes / 7 Daps / 12 Splices | July
D-HOE503 | North Path | 2026-07-08 | 665 |  |  | July
D-HLX521 | North Path | 2026-07-08 | 87 |  | 38 Toby Boxes / 33 Daps / 152 Splices / 1 FDH / 1 HH / 1 Swing Arm// 1 Ground Rod | July
FB-HLX375 | North Path | 2026-07-08 | 1146 |  |  | July
FB-HOE401-V3 | 1972 Fiber Core | 2026-07-08 |  |  | 5,940 Tracer Wire | July
D-HTG229 | Lopez Underground | 2026-07-08 |  |  | No Production | July
D-HTG238 | Lopez Underground | 2026-07-08 | 187 |  |  | July
FB-HTG204 | Alpha Omega | 2026-07-08 |  |  | No Production--Drill Breakdown | July
FB-HTG290 | HAS Global | 2026-07-08 | 351 |  |  | July
BHCD-FPW-03-E | Lopez Underground | 2026-07-08 | 998 |  |  | July
D-HBR257 | Yosep | 2026-07-08 | 1774 |  |  | July
D-HPP616 | Brothers | 2026-07-09 | 495 |  | 4 Toby Boxes / 4 Daps / 6 Splices | July
D-HPP628 | Brothers | 2026-07-09 | 1169 |  |  | July
D-HPP631 | Brothers | 2026-07-09 | 525 |  |  | July
D-HPP638 | Lightspeed | 2026-07-09 | 255 |  | 2 Toby Boxes / 2 Daps / 16 Splices | July
D-HPP639 | ASM Utilities | 2026-07-09 | 874 |  |  | July
D-HPP303 | R&F Construction | 2026-07-09 |  |  | 11 Toby Boxes / 11 Daps / 18 Splices | July
D-HPP307 | Lightspeed | 2026-07-09 | 323 |  |  | July
D-HOE503 | North Path | 2026-07-09 | 782 |  |  | July
D-HLX501 | 1972 Fiber Core | 2026-07-09 |  | 550 | 450 Tracer Wire / 450 Mule Tape / 2 McLean Switches | July
D-HLX522 | 1972 Fiber Core | 2026-07-09 |  | 1300 | 1,150 Tracer Wire / 2 McLean Switches | July
FB-HLX375 | North Path | 2026-07-09 | 1085 |  |  | July
FB-HTG204 | Alpha Omega | 2026-07-09 | 934 |  |  | July
FB-HTG289 | HAS Global | 2026-07-09 | 536 |  |  | July
FB-HTG289 | Lightspeed | 2026-07-09 | 393 |  |  | July
D-HBR257 | Yosep | 2026-07-09 | 557 |  | 1 HH / 8 Locate Markers / 11 Daps / 212 Splices | July
D-HPP626 | Brothers | 2026-07-10 | 439 |  | 4 Toby Boxes / 4 Daps / 7 Splices | July
D-HPP628 | Brothers | 2026-07-10 | 1408 |  |  | July
D-HPP631 | Brothers | 2026-07-10 | 4486 |  | 17 Toby Boxes / 16 Daps / 30 Splices | July
D-HPP638 | Lightspeed | 2026-07-10 | 180 |  | 12 Splices | July
D-HPP639 | ASM utilities | 2026-07-10 | 781 |  |  | July
D-HPP307 | Lightspeed | 2026-07-10 | 340 |  | 3 Toby Boxes / 3 Daps / 6 Splices | July
D-HPP318 | NIA Underground | 2026-07-10 |  |  | 8 Toby Boxes / 2 Daps / 3 Splices / 1 HH / 1 FDH / 1 Swing Arm / 1 Ground Rod | July
D-HLX520 | North Path | 2026-07-10 | 1007 |  |  | July
FB-HLX375 | 1972 Fiber Core | 2026-07-10 |  |  | No Production | July
D-HTG238 | Lopez Underground | 2026-07-10 | 336 |  |  | July
FB-HTG204 | Alpha Omega | 2026-07-10 | 183 |  |  | July
FB-HTG289 | HAS Global | 2026-07-10 | 131 |  |  | July
FB-HTG289 | Lightspeed | 2026-07-10 |  |  | No Production | July
D-HBR257 | Yosep | 2026-07-10 | 678 |  | 4 Locate Markers / 5 Daps / 40 Splices | July
D-HPP616 | Brothers | 2026-07-13 |  |  | 1 Vault / 1 FDH / 1 Swing Arm / 1 Ground Rod / 79 Splices | July
D-HPP626 | Brothers | 2026-07-13 | 2286 |  |  | July
D-HPP627 | Brothers | 2026-07-13 | 694 |  |  | July
D-HPP628 | Brothers | 2026-07-13 | 2014 |  |  | July
D-HPP631 | Brothers | 2026-07-13 | 259 |  |  | July
D-HPP634 | NIA Underground | 2026-07-13 |  |  | No Production | July
D-HPP635 | NIA Underground | 2026-07-13 |  |  | No Production--Drill Breakdown | July
D-HPP639 | ASM Utilities | 2026-07-13 | 2842 |  | 9 Toby Boxes / 8 Daps / 16 Splices | July
D-HPP303 | R&F Construction | 2026-07-13 | 722 |  |  | July
D-HPP307 | Lightspeed | 2026-07-13 | 225 |  | 2 Toby Boxes / 2 Daps / 16 Splices | July
FB-HWP476 | J Garcia Underground | 2026-07-13 | 230 |  |  | July
D-HOE503 | North Path | 2026-07-13 | 685 |  |  | July
D-HLX511 | North Path | 2026-07-13 | 993 |  |  | July
FB-HLX375 | 1972 Fiber Core | 2026-07-13 |  | 3504 | 3,004 Tracer Wire / 4 MacLean Switch | July
FB-HTG204 | Alpha Omega | 2026-07-13 |  |  | 2 Vaults / 2 Ground Rods | July
FB-HTG289 | Lightspeed | 2026-07-13 | 458 |  |  | July
FB-HTG289 | HAS Global | 2026-07-13 | 578 |  |  | July
Colonial Pointe | APT Communications | 2026-07-13 | 1066 |  |  | July
D-HBR257 | Yosep | 2026-07-13 | 784 |  | 1 Locate Marker / 1 Dap / 130 Splices | July
D-HPP626 | Brothers | 2026-07-14 | 2056 |  |  | July
D-HPP628 | Brothers | 2026-07-14 | 1701 |  |  | July
D-HPP631 | Brothers | 2026-07-14 |  |  | No Production--Crew Shutdown | July
D-HPP635 | NIA Underground | 2026-07-14 | 1037 |  |  | July
D-HPP637 | Lightspeed | 2026-07-14 | 269 |  | 2 Toby Boxes / 2 Daps / 4 Splices | July
D-HPP639 | ASM Utilities | 2026-07-14 | 570 |  |  | July
D-HPP303 | R&F Construction | 2026-07-14 | 298 |  | 8 Toby Boxes / 8 Daps / 14 Splices | July
D-HPP305 | R&F Construction | 2026-07-14 | 224 |  | 3 Toby Boxes / 3 Daps / 5 Splices | July
D-HPP307 | Lightspeed | 2026-07-14 | 660 |  | 9 Toby Boxes / 9 Daps / 25 Splices | July
D-HOE503 | North Path | 2026-07-14 | 72 |  | 22 Daps / 155 Splices | July
D-HLX509 | North Path | 2026-07-14 | 1541 |  |  | July
D-HLX511 | North Path | 2026-07-14 | 1035 |  |  | July
FB-HTG288 | Alpha Omega | 2026-07-14 | 385 |  |  | July
FB-HTG289 | Lightspeed | 2026-07-14 |  |  | No Production--Sewer Main Hit | July
FB-HTG289 | HAS Global | 2026-07-14 |  |  | No Production--Sewer Main Hit | July
Colonial Pointe | APT Communications | 2026-07-14 | 431 |  |  | July
D-HBR257 | Yosep | 2026-07-14 | 756 |  | 7 Locate Markers / 7 Daps / 162 Splices | July
D-HPP626 | Brothers | 2026-07-15 | 1203 |  |  | July
D-HPP628 | Brothers | 2026-07-15 | 1696 |  | 10 Toby Boxes / 11 Daps | July
D-HPP635 | NIA Underground | 2026-07-15 | 1272 |  |  | July
D-HPP637 | Lightspeed | 2026-07-15 |  |  | No Production--Vehicle Breakdown | July
D-HPP303 | R&F Construction | 2026-07-15 | 232 |  | 3 Toby Boxes / 3 Daps / 5 Splices | July
D-HPP305 | R&F Construction | 2026-07-15 |  |  | 2 Toby Boxes / 2 Daps / 3 Splices | July
D-HPP307 | Lightspeed | 2026-07-15 | 38 |  | 2 Toby Boxes / 2 Daps / 2 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | July
D-HLX509 | North Path | 2026-07-15 | 948 |  |  | July
D-HLX511 | North Path | 2026-07-15 | 1130 |  |  | July
D-HOE117 | North Path | 2026-07-15 | 238 |  | Damage Repair | July
FB-HTG288 | Alpha Omega | 2026-07-15 |  |  | No Production | July
BHCD-FPW-03-E | Lopez Underground | 2026-07-15 | 756 |  |  | July
Colonial Pointe | APT Communications | 2026-07-15 | 676 |  |  | July
D-HBR256 | Yosep | 2026-07-15 | 32 |  | 5 Locate Markers / 8 Daps / 70 Splices | July
D-HBR257 | Yosep | 2026-07-15 | 926 |  | 4 Locate Markers / 5 Daps / 145 Splices | July
D-HPP630 | Brothers | 2026-07-16 |  |  | No Production--Crew Shutdown | July
D-HPP635 | NIA Underground | 2026-07-16 |  |  | No Production--Crew Shutdown | July
D-HPP636 | Brothers | 2026-07-16 | 1644 |  | 11 Toby Boxes / 12 Daps / 32 Splices | July
D-HPP637 | Lightspeed | 2026-07-16 | 188 |  |  | July
D-HLX506 | North Path | 2026-07-16 | 427 |  |  | July
D-HLX509 | North Path | 2026-07-16 | 540 |  |  | July
D-HLX511 | North Path | 2026-07-16 | 653 |  | 33 Toby Boxes / 30 Daps / 223 Splices | July
D-HTG229 | Lopez Underground | 2026-07-16 | 1084 |  |  | July
D-HTG238 | Lopez Underground | 2026-07-16 | 400 |  |  | July
Colonial Pointe | APT Communications | 2026-07-16 | 494 |  |  | July
D-HPP607 | Lightspeed | 2026-07-17 | 122
D-HPP635 | NIA Underground | 2026-07-17 | 912 |  |  | July
D-HPP636 | Brothers | 2026-07-17 | 1233 |  | 7 Toby Boxes / 7 Daps | July
D-HPP637 | Lightsped | 2026-07-17 | 186 |  | 2 Toby Boxes / 2 Daps | July
D-HPP638 | Lightspeed | 2026-07-17 | 110
D-HPP639 | ASM Utilities | 2026-07-17 |  |  | No Production--Locates Not Cleared | July
D-HPP303 | R&F Construction | 2026-07-17 |  |  | No Production--Locates Not Cleared | July
D-HTG241 | Lopez Underground | 2026-07-17 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod / 1 McLean Switch | July
FB-HTG288 | Alpha Omega | 2026-07-17 |  |  | 1 HH | July
D-HPP635 | NIA Underground | 2026-07-20 | 3372 |  |  | July
D-HPP636 | Brothers | 2026-07-20 | 1458 |  |  | July
D-HPP638 | Lightspeed | 2026-07-20 |  |  |  | July
D-HPP310 | Legant Livings | 2026-07-20 | 188 |  | 12 Toby Boxes / 12 Daps / 19 Splices | July
D-HLX506 | North Path | 2026-07-20 | 2233 |  |  | July
FB-HTG288 | Alpha Omega | 2026-07-20 |  |  | No Production | July
FB-HTG292 | Gulf Stream | 2026-07-20 |  |  | No Production | July
BHCD-FPW-03-E | Lopez Underground | 2026-07-20 |  |  | No Production | July
Colonial Pointe | APT Communications | 2026-07-20 |  |  | No Production | July
D-HSF308 | HD Cable | 2026-07-20 | 162 |  |  | July
D-HBR257 | Yosep | 2026-07-20 | 812 |  | 5 Locate Markers / 6 Daps / 67 Splices | July
D-HPP607 | Lightspeed | 2026-07-21 |  |  |  | July
D-HPP630 | Brothers | 2026-07-21 | 1158 |  |  | July
D-HPP634 | NIA Underground | 2026-07-21 | 1641 |  |  | July
D-HPP635 | NIA Underground | 2026-07-21 | 454 |  |  | July
D-HPP636 | Brothers | 2026-07-21 | 1610 |  | 15 Toby Boxes / 15 Daps | July
D-HPP310 | Legant Livings | 2026-07-21 | 115 |  |  | July
D-HLX506 | North Path | 2026-07-21 | 921 |  |  | July
D-HLX508 | North Path | 2026-07-21 | 979 |  |  | July
D-HSF308 | HD Cable | 2026-07-21 | 858 |  |  | July
FB-HTG289 | Lightspeed | 2026-07-21 |  |  | No Production | July
FB-HTG204 | Alpha Omega | 2026-07-21 | 478 |  |  | July
FB-HTG292 | Gulf Stream | 2026-07-21 | 745 |  |  | July
Colonial Pointe | APT Communications | 2026-07-21 | 721 |  |  | July
D-HPP630 | Brothers | 2026-07-22 | 1297 |  |  | July
D-HPP634 | NIA Underground | 2026-07-22 | 1662 |  |  | July
D-HPP636 | Brothers | 2026-07-22 | 1420 |  |  | July
D-HPP310 | Legant Livings | 2026-07-22 |  |  | No Production--Drill Breakdown | July
D-HPP311 | Legant Livings | 2026-07-22 |  |  | No Production--Drill Breakdown | July
D-HLX506 | North Path | 2026-07-22 | 397 |  |  | July
D-HLX508 | North Path | 2026-07-22 | 395 |  |  | July
D-HSF308 | HD Cable | 2026-07-22 | 1126 |  |  | July
FB-HTG289 | Lightspeed | 2026-07-22 | 325 |  |  | July
FB-HTG292 | GulfStream | 2026-07-22 | 358 |  |  | July
Colonial Pointe | APT Communications | 2026-07-22 | 1126 |  |  | July
D-HLX405 | North Path | 2026-07-22 | 21 |  | 8 Toby Boxes / 1 Dap / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | July
D-HBR257 | Yosep | 2026-07-22 | 242 |  | 3 Locate Markers / 4 Daps / 40 Splices | July
D-HPP617 | Brothers | 2026-07-23 |  |  | RESTORATION | July
D-HPP630 | Brothers | 2026-07-23 | 1849 |  |  | July
D-HPP634 | NIA Underground | 2026-07-23 | 661 |  |  | July
D-HPP635 | NIA Underground | 2026-07-23 |  |  | No Production | July
D-HPP636 | Brothers | 2026-07-23 |  |  | No Production | July
D-HPP637 | Lightspeed | 2026-07-23 | 428 |  | 3 Toby Box / 3 Daps / 6 Splices | July
D-HPP303 | R&F Construstion | 2026-07-23 | 410 |  |  | July
D-HPP310 | Legant Livings | 2026-07-23 | 35 |  |  | July
D-HPP311 | Legant Livings | 2026-07-23 | 150 |  |  | July
D-HLX506 | North Path | 2026-07-23 | 467 |  |  | July
D-HLX508 | North Path | 2026-07-23 | 1344 |  |  | July
D-HSF308 | HD Cable | 2026-07-23 | 1017 |  |  | July
FB-HTG204 | Alpha Omega | 2026-07-23 |  |  | 2 HH | July
FB-HTG289 | Lightspeed | 2026-07-23 |  |  | 6 HH | July
FB-HTG289 | 1972 Fiber Core | 2026-07-23 |  | 3872 |  | July
FB-HTG292 | GulfStream | 2026-07-23 | 10 |  |  | July
D-HTG218 | GulfStream | 2026-07-23 | 1144 |  |  | July
Colonial Pointe | APT Communications | 2026-07-23 | 556 |  |  | July
BHCD-FPW-03-E | Lopez Underground | 2026-07-23 | 2283 |  |  | July
D-HBR257 | Yoesp | 2026-07-23 | 26 |  | 4 Locate Markers / 7 Daps / 74 Splices | July
D-HBR258 | Yoesp | 2026-07-23 | 460 |  |  | July
D-HPP630 | Brothers | 2026-07-24 | 1158 |  |  | July
D-HPP634 | NIA Underground | 2026-07-24 | 717 |  |  | July
D-HPP637 | Lightspeed | 2026-07-24 | 141 |  |  | July
D-HPP303 | R&F Construstion | 2026-07-24 | 202 |  |  | July
D-HPP305 | R&F Construstion | 2026-07-24 |  |  | No Production | July
D-HPP310 | Legant Livings | 2026-07-24 |  |  | No Production | July
D-HPP311 | Legant Livings | 2026-07-24 |  |  | No Production | July
D-HLX503 | North Path | 2026-07-24 | 803 |  |  | July
D-HLX506 | North Path | 2026-07-24 | 111 |  | 42 Toby Boxes / 39 Daps / 235 Splices | July
D-HLX508 | North Path | 2026-07-24 | 679 |  |  | July
D-HSF308 | HD Cable | 2026-07-24 | 377 |  |  | July
Colonial Pointe | APT Communications | 2026-07-24 | 262 |  |  | July
BHCD-FPW-03-E | Lopez Underground | 2026-07-24 | 782 |  |  | July
D-HTG218 | GulfStream | 2026-07-24 | 508 |  |  | July
FB-HTG289 | Lightspeed | 2026-07-24 |  |  | 1 HH | July
D-HBR258 | Yoesp | 2026-07-24 | 629 |  |  | July
D-HPP617 | Brothers | 2026-07-27 |  |  | 14 Toby Boxes / 14 Daps / 39 Splices | July
D-HPP630 | Brothers | 2026-07-27 | 1171 |  |  | July
D-HPP634 | NIA Underground | 2026-07-27 | 202 |  |  | July
D-HPP635 | NIA Underground | 2026-07-27 |  |  | No Production | July
D-HPP637 | Lightspeed | 2026-07-27 | 203 |  | 1Toby Box / 1 Dap / 2 Splices | July
D-HPP638 | Lightspeed | 2026-07-27 |  |  | No Production | July
D-HPP639 | ASM Utilities | 2026-07-27 |  |  | FDH | July
D-HPP305 | Lightspeed | 2026-07-27 | 52 |  |  | July
D-HPP305 | R&F Construstion | 2026-07-27 | 893 |  |  | July
D-HLX503 | North Path | 2026-07-27 | 706 |  |  | July
D-HLX504 | North Path | 2026-07-27 |  |  | No Production--Drill Breakdown | July
D-HLX516 | North Path | 2026-07-27 | 120 |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod / 44 Toby Boxes / 41 Daps / 232 Splices | July
FB-HTG238 | Lopez Underground | 2026-07-27 | 2099 |  |  | July
D-HTG218 | GulfStream | 2026-07-27 | 763 |  |  | July
SFU-LEE-6 | APT Communications | 2026-07-27 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | July
D-HSF308 | HD Cable | 2026-07-27 | 1083 |  |  | July
D-HBR258 | Yoesp | 2026-07-27 | 375 |  |  | July
D-HPP614 | Mid Florida | 2026-07-28 | 2264 |  |  | July
D-HPP637 | Lightspeed | 2026-07-28 | 179 |  | 1 Toby Box / 1 Dap / 2 Splices | July
D-HPP638 | Lightspeed | 2026-07-28 | 215 |  |  | July
D-HPP639 | Lightspeed | 2026-07-28 | 861 |  |  | July
D-HPP303 | Lightspeed | 2026-07-28 | 65 |  |  | July
D-HPP305 | Lightspeed | 2026-07-28 | 64 |  |  | July
D-HLX503 | North Path | 2026-07-28 | 1159 |  |  | July
D-HLX504 | North Path | 2026-07-28 | 1635 |  |  | July
FB-HTG238 | Lopez Underground | 2026-07-28 | 2327 |  |  | July
FB-HTG288 | Alpha Omega | 2026-07-28 | 719 |  |  | July
FB-HTG292 | Gulfstream | 2026-07-28 | 200 |  |  | July
D-HTG201 | Lopez Underground | 2026-07-28 |  |  | No Production | July
D-HTG215 | Gulfstream | 2026-07-28 | 257 |  |  | July
D-HTG218 | GulfStream | 2026-07-28 | 214 |  |  | July
D-HTG228 | Lopez Underground | 2026-07-28 |  |  | No Production | July
D-HTG229 | Lopez Underground | 2026-07-28 |  |  | No Production | July
D-HTG230 | Restoring Pro | 2026-07-28 | 484 |  |  | July
D-HTG238 | Lopez Underground | 2026-07-28 | 232 |  |  | July
D-HSF308 | HD Cable | 2026-07-28 | 539 |  |  | July
D-HBR257 | Yoesp | 2026-07-28 | 10 |  | 2 Locate Markers / 6 Daps / 146 Splices | July
D-HBR258 | Yoesp | 2026-07-28 | 538 |  |  | July
D-HPP637 | Lightspeed | 2026-07-29 | 272 |  | 1 Toby Box / 1 Dap / 1 Splice | July
D-HPP638 | Lightspeed | 2026-07-29 | 105 |  | 2 Toby Boxes / 2 Daps / 3 Splices | July
D-HPP639 | ASM Utilities | 2026-07-29 | 334 |  |  | July
D-HPP303 | Lightspeed | 2026-07-29 | 160 |  | 1 Toby Box / 1 Dap / 14 Splices | July
D-HPP305 | R&F Construction | 2026-07-29 | 811 |  |  | July
D-HPP310 | Legant Livings | 2026-07-29 |  |  | PROOFING | July
D-HLX503 | North Path | 2026-07-29 | 1155 |  |  | July
D-HLX504 | North Path | 2026-07-29 | 694 |  |  | July
D-HTG201 | Lopez Underground | 2026-07-29 |  |  | No Production | July
D-HTG208 | Lopez Underground | 2026-07-29 | 436 |  |  | July
D-HTG218 | GulfStream | 2026-07-29 | 324 |  |  | July
D-HTG230 | Restoring Pro | 2026-07-29 | 955 |  |  | July
FB-HTG238 | Lopez Underground | 2026-07-29 |  |  | 7 HH | July
FB-HTG288 | Alpha Omega | 2026-07-29 | 534 |  |  | July
FB-HTG292 | Gulfstream | 2026-07-29 | 64 |  |  | July
D-HSF308 | HD Cable | 2026-07-29 | 700 |  |  | July
D-HBR257 | Yoesp | 2026-07-29 | 10 |  | 2 Locate Markers / 3 Daps / 62 Splices | July
D-HBR258 | Yoesp | 2026-07-29 | 621 |  |  | July
D-HPP614 | Lightspeed | 2026-07-30 |  |  | 13 Toby Boxes / 13 Daps / 40 Splices | July
D-HPP637 | Lightspeed | 2026-07-30 | 362 |  | 3 Toby Boxes / 3 Daps / 6 Splices | July
D-HPP638 | Lightspeed | 2026-07-30 | 445 |  | 2 Toby Boxes / 2 Daps / 4 Splices | July
D-HPP639 | ASM Utilities | 2026-07-30 |  |  | PROOFING | July
D-HPP305 | R&F Construction | 2026-07-30 | 449 |  |  | July
D-HLX503 | North Path | 2026-07-30 | 333 |  |  | July
D-HLX504 | North Path | 2026-07-30 | 1685 |  |  | July
D-HTG215 | GulfStream | 2026-07-30 |  |  | No Production | July
D-HTG218 | GulfStream | 2026-07-30 | 88 |  |  | July
FB-HTG288 | Alpha Omega | 2026-07-30 | 786 |  |  | July
D-HSF308 | HD Cable | 2026-07-30 | 202 |  | No Production | July
D-HBR258 | Yoesp | 2026-07-30 | 550 |  |  | July
D-HPP614 | Lightspeed | 2026-07-31 |  |  | 17 Toby Boxes / 17 Daps / 27 Splices | July
D-HPP637 | Lightspeed | 2026-07-31 | 297 |  | 2 Toby Boxes / 2 Daps / 4 Splices | July
D-HPP638 | Lightspeed | 2026-07-31 | 445 |  | 3 Toby Boxes / 3 Daps / 6 Splices | July
D-HPP639 | ASM Utilities | 2026-07-31 |  |  | PROOFING | July
D-HPP305 | R&F Construction | 2026-07-31 | 295 |  |  | July
D-HLX504 | North Path | 2026-07-31 | 724 |  |  | July
D-HLX513 | North Path | 2026-07-31 | 24 |  | 9 Toby Boxes / 9 Daps / 121 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | July
D-HTG215 | GulfStream | 2026-07-31 | 1036 |  |  | July
FB-HTG288 | Alpha Omega | 2026-07-31 |  |  | 3 HH | July
D-HSF308 | HD Cable | 2026-07-31 | 202 |  |  | July
D-HBR258 | Yoesp | 2026-07-31 | 893 |  |  | July
D-HPP614 | Lightspeed | 2026-08-03 |  |  | No Production--Weather | August
D-HPP634 | NIA Underground | 2026-08-03 |  |  | No Production--Weather | August
D-HPP635 | NIA Underground | 2026-08-03 |  |  | No Production--Weather | August
D-HPP637 | Lightspeed | 2026-08-03 |  |  | No Production--Weather | August
D-HPP638 | Lightspeed | 2026-08-03 |  |  | No Production--Weather | August
D-HPP303 | Lightspeed | 2026-08-03 | 58 |  |  | August
D-HPP314 | Power Connect | 2026-08-03 | 1053 |  |  | August
D-HLX505 | North Path | 2026-08-03 | 1304 |  |  | August
D-HLX506 | 1972 Fiber Core | 2026-08-03 |  | 1492 | 1,492' Stingray | August
D-HLX508 | 1972 Fiber Core | 2026-08-03 |  | 1501 | 1,501' Stingray | August
D-HLX511 | 1972 Fiber Core | 2026-08-03 |  | 3357 | 2,466' 96CT Fiber Cable / 891' Stingray / 2,366 Tracer Wire / 4 Daps Completed | August
D-HTG215 | GulfStream | 2026-08-03 | 1108 |  |  | August
FB-HTG288 | Alpha Omega | 2026-08-03 | 537 |  |  | August
D-HSF308 | HD Cable | 2026-08-03 | 54 |  | 8 Vaults / 30 Toby Boxes / 20 Daps / 105 Splices | August
D-HPP613 | Lightspeed | 2026-08-04 |  |  | 1 Ground Rod / 1 Swing Arm / 1 Maclean Switch | August
D-HPP614 | Lightspeed | 2026-08-04 |  |  | 9 Toby Boxes / 9 Daps / 17 Splices | August
D-HPP637 | Lightspeed | 2026-08-04 | 426 |  |  | August
D-HPP638 | Lightspeed | 2026-08-04 |  |  | No Production | August
D-HPP639 | ASM Utilities | 2026-08-04 |  |  | PROOFING | August
D-HPP305 | R&F Construction | 2026-08-04 |  |  | No Production | August
D-HPP310 | Legant Livings | 2026-08-04 |  |  | 13 Toby Boxes / 12 Daps / 22 Splices | August
D-HPP314 | Power Connect | 2026-08-04 | 1808 |  |  | August
D-HLX505 | North Path | 2026-08-04 | 1495 |  |  | August
D-HTG215 | GulfStream | 2026-08-04 | 1065 |  |  | August
FB-HTG288 | Alpha Omega | 2026-08-04 | 277 |  | 1 Vault | August
D-HSF308 | HD Cable | 2026-08-04 | 3 |  | 1 FDH / 3 Toby Boxes / 1 Dap / 2 Splices | August
FB-HTG292 | Gulfstream | 2026-08-04 | 269 |  |  | August
D-HPP613 | Lightspeed | 2026-08-05 |  |  | PROOFING | August
D-HPP634 | NIA Underground | 2026-08-05 | 3503 |  |  | August
D-HPP637 | Lightspeed | 2026-08-05 |  |  | 1 Toby Box / 1 Dap / 14 Splices | August
D-HPP638 | Lightspeed | 2026-08-05 | 330 |  |  | August
FB-HPP314 | Lightspeed | 2026-08-05 | 58 |  |  | August
FB-HLX175 | Lightspeed | 2026-08-05 | 217 |  |  | August
D-HPP637 | Lightspeed | 2026-08-06 | 233 |  | 1 Toby Box / 1 Dap / 2 Splices | August
D-HPP638 | Lightspeed | 2026-08-06 | 398 |  |  | August
D-HPP303 | Power Connect | 2026-08-06 | 308 |  |  | August
D-HPP314 | Power Connect | 2026-08-06 | 844 |  |  | August
D-HLX503 | Lightspeed | 2026-08-06 | 247 |  |  | August
D-HLX504 | North Path | 2026-08-06 | 126 |  | 45 Toby Boxes / 41 Daps / 238 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod / 1 McLean Switch Completed | August
D-HLX505 | North Path | 2026-08-06 | 1133 |  |  | August
FB-HLX175 | Lightspeed | 2026-08-06 | 280 |  |  | August
D-HTG201 | Lopez Underground | 2026-08-06 | 473 |  |  | August
D-HTG217 | Lopez Underground | 2026-08-06 |  |  | No Production | August
D-HTG230 | Restoring Pro | 2026-08-06 | 718 |  |  | August
FB-HTG288 | Alpha Omega | 2026-08-06 | 526 |  |  | August
D-HPP608 | Lightspeed | 2026-08-07 | 405 |  |  | August
D-HPP627 | Brothers | 2026-08-07 | 1667 |  |  | August
D-HPP638 | Lightspeed | 2026-08-07 |  |  | 2 Toby Boxes / 3 Daps / 27 Splices | August
D-HPP314 | Power Connect | 2026-08-07 | 944 |  |  | August
FB-HLXC512 | Brothers | 2026-08-07 | 745 |  |  | August
D-HLX505 | North Path | 2026-08-07 | 1375 |  |  | August
FB-HLX175 | Lightspeed | 2026-08-07 |  |  | 1 HH / 1 Ground Rod | August
D-HTG215 | Lopez Underground | 2026-08-07 | 287 |  |  | August
D-HTG216 | Lopez Underground | 2026-08-07 | 952 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-07 | 645 |  |  | August
FB-HTG288 | Alpha Omega | 2026-08-07 | 461 |  |  | August
D-HPP608 | Lightspeed | 2026-08-10 | 600 |  |  | August
D-HPP627 | Brothers | 2026-08-10 | 155 |  |  | August
D-HPP629 | Brothers | 2026-08-10 | 281 |  |  | August
D-HPP637 | Lightspeed | 2026-08-10 | 92 |  |  | August
D-HPP638 | Lightspeed | 2026-08-10 | 272 |  | 1 Toby Box / 1 Dap | August
D-HPP639 | ASM Utilities | 2026-08-10 |  |  | RESTORATION | August
D-HPP314 | Power Connect | 2026-08-10 | 1549 |  |  | August
D-HLX502 | Lightspeed | 2026-08-10 | 557 |  |  | August
FB-HLX175 | Lightspeed | 2026-08-10 | 184 |  |  | August
D-HTG215 | Gulfstream | 2026-08-10 | 586 |  |  | August
D-HTG216 | Lopez Underground | 2026-08-10 | 1289 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-10 | 244 |  |  | August
FB-HTG288 | Alpha Omega | 2026-08-10 | 599 |  |  | August
D-HBR258 | Yosep | 2026-08-10 |  |  | No Production | August
D-HPP608 | Lightspeed | 2026-08-11 | 500 |  |  | August
D-HPP614 | Lightspeed | 2026-08-11 |  |  | 6 Toby Boxes / 6 Daps / 59 Splices | August
D-HPP627 | Brothers | 2026-08-11 | 1156 |  |  | August
D-HPP637 | Lightspeed | 2026-08-11 | 295 |  |  | August
D-HPP638 | Lightspeed | 2026-08-11 | 247 |  |  | August
D-HLC518 | ASM Utilities | 2026-08-11 | 714 |  |  | August
D-HPP310 | Legant Livings | 2026-08-11 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 MacLean Switch / 1 Ground Rod / 77 Splices | August
D-HPP311 | Legant Livings | 2026-08-11 |  |  | 6 Toby Boxes / 6 Daps / 10 Splices | August
D-HPP314 | Power Connect | 2026-08-11 | 973 |  |  | August
D-HLX502 | North Path | 2026-08-11 | 733 |  |  | August
D-HLX510 | North Path | 2026-08-11 | 1080 |  |  | August
FB-HLX175 | Lightspeed | 2026-08-11 | 230 |  |  | August
D-HTG212 | Gulfstream | 2026-08-11 | 936 |  |  | August
D-HTG215 | Gulfstream | 2026-08-11 | 195 |  |  | August
D-HTG216 | Lopez Underground | 2026-08-11 | 1995 |  |  | August
D-HTG217 | Lopez Underground | 2026-08-11 | 2263 |  |  | August
D-HTG218 | Gulfstream | 2026-08-11 | 793 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-11 |  |  | No Production | August
FB-HTG288 | Alpha Omega | 2026-08-11 | 414 |  |  | August
D-HBR258 | Yosep | 2026-08-11 | 447 |  | 2 Locate Markers / 3 Daps / 72 Splices | August
D-HPP608 | Lightspeed | 2026-08-12 | 606 |  |  | August
D-HPP627 | Brothers | 2026-08-12 | 864 |  |  | August
D-HPP631 | Brothers | 2026-08-12 | 448 |  |  | August
D-HPP637 | Lightspeed | 2026-08-12 | 354 |  |  | August
D-HPP638 | Lightspeed | 2026-08-12 |  |  | No Production | August
D-HLC518 | ASM Utilities | 2026-08-12 | 1174 |  |  | August
D-HPP314 | Power Connect | 2026-08-12 | 883 |  |  | August
D-HLX502 | North Path | 2026-08-12 | 1379 |  |  | August
D-HLX504 | 1972 Fiber Core | 2026-08-12 |  | 1254 |  | August
D-HLX510 | North Path | 2026-08-12 | 1077 |  |  | August
FB-HLX175 | Lightspeed | 2026-08-12 | 260 |  |  | August
D-HTG212 | Gulfstream | 2026-08-12 | 1582 |  |  | August
D-HTG216 | Lopez Underground | 2026-08-12 | 2319 |  |  | August
D-HTG217 | Lopez Underground | 2026-08-12 | 1113 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-12 | 360 |  |  | August
D-HTG231 | Restoring Pro | 2026-08-12 | 180 |  | 1 Toby Box | August
FB-HTG288 | Alpha Omega | 2026-08-12 |  |  | 4 HH | August
D-HBR258 | Yosep | 2026-08-12 | 949 |  | 2 Locate Markers / 2 Daps / 24 Splices | August
D-HPP608 | Lightspeed | 2026-08-13 |  |  | 9 Toby Boxes / 9 Daps / 17 Splices | August
D-HPP635 | NIA Underground | 2026-08-13 | 1495 |  |  | August
D-HPP637 | Lightspeed | 2026-08-13 |  |  | No Production | August
D-HPP638 | Lightspeed | 2026-08-13 |  |  | No Production | August
FB-HPP631 | Brothers | 2026-08-13 | 1705 |  |  | August
D-HPP631 | Brothers | 2026-08-13 | 907 |  | 4 Toby Boxes / 4 Daps / 5 Splices | August
D-HLC512 | Brothers | 2026-08-13 | 1243 |  |  | August
D-HLC513 | Power Connect | 2026-08-13 | 566 |  |  | August
D-HLX502 | North Path | 2026-08-13 | 773 |  |  | August
D-HLX505 | 1972 Fiber Core | 2026-08-13 |  | 1324 |  | August
D-HLX510 | North Path | 2026-08-13 | 1445 |  |  | August
FB-HLX175 | Lightspeed | 2026-08-13 |  |  | No Production | August
D-HTG212 | Gulfstream | 2026-08-13 | 1036 |  |  | August
D-HTG213 | HD Cable | 2026-08-13 | 926 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-13 | 185 |  |  | August
D-HTG231 | Restoring Pro | 2026-08-13 |  |  | No Production | August
FB-HTG288 | Alpha Omega | 2026-08-13 |  |  | 4 HH | August
D-HSF322 | Lopez Underground | 2026-08-13 | 753 |  |  | August
FB-HBR252 | Yosep | 2026-08-13 | 292 |  |  | August
D-HPP627 | Brothers | 2026-08-14 |  |  | RESTORATION | August
D-HPP629 | Brothers | 2026-08-14 |  |  | RESTORATION | August
D-HPP631 | Brothers | 2026-08-14 | 369 |  |  | August
D-HPP636 | Brothers | 2026-08-14 | 1797 |  |  | August
D-HPP637 | Lightspeed | 2026-08-14 |  |  | No Production | August
D-HPP638 | Lightspeed | 2026-08-14 |  |  | No Production | August
FB-HPP631 | Brothers | 2026-08-14 | 973 |  |  | August
D-HLC513 | Power Connect | 2026-08-14 | 452 |  |  | August
D-HLX510 | North Path | 2026-08-14 | 877 |  |  | August
FB-HLX175 | Lightspeed | 2026-08-14 | 240 |  |  | August
FB-HLX175 | North Path | 2026-08-14 | 451 |  |  | August
D-HTG212 | Gulfstream | 2026-08-14 |  |  | No Production | August
D-HTG213 | HD Cable | 2026-08-14 | 457 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-14 |  |  | No Production | August
FB-HTG288 | Alpha Omega | 2026-08-14 | 147 |  |  | August
D-HSF322 | Lopez Underground | 2026-08-14 | 344 |  |  | August
D-HBR258 | Yosep | 2026-08-14 | 36 |  | 1 HH | August
D-HBR259 | Yosep | 2026-08-14 | 1273 |  |  | August
D-HPP608 | Lightspeed | 2026-08-17 | 220 |  |  | August
D-HPP627 | Brothers | 2026-08-17 | 669 |  |  | August
D-HPP637 | Lightspeed | 2026-08-17 | 294 |  | 2 Toby Boxes / 2 Daps | August
D-HPP638 | Lightspeed | 2026-08-17 | 189 |  |  | August
D-HPP314 | Lightspeed | 2026-08-17 |  |  | 1 FDH / 1 HH / 1 Swing ARM / 1 MacLean Switch / 1 Ground Rod | August
D-HLC517 | ASM Utilities | 2026-08-17 | 725 |  |  | August
D-HLC518 | ASM Utilities | 2026-08-17 | 358 |  |  | August
FB-HLC512 | Brothers | 2026-08-17 | 1608 |  |  | August
D-HLX408 | North Path | 2026-08-17 | 1044 |  |  | August
FB-HLX175 | Lightspeed | 2026-08-17 | 240 |  |  | August
FB-HLX175 | North Path | 2026-08-17 | 714 |  |  | August
FB-HOE401-V6 | Lightspeed | 2026-08-17 | 200 |  |  | August
D-HTG212 | Gulfstream | 2026-08-17 | 914 |  |  | August
D-HTG213 | HD Cable | 2026-08-17 | 969 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-17 | 361 |  |  | August
D-HTG231 | Restoring Pro | 2026-08-17 | 1039 |  |  | August
D-HPW348 | Alpha Omega | 2026-08-17 | 410 |  |  | August
D-HSF322 | Lopez Underground | 2026-08-17 | 641 |  |  | August
D-HBR259 | Yosep | 2026-08-17 | 896 |  |  | August
D-HPP608 | Lightspeed | 2026-08-18 | 289 |  |  | August
D-HPP637 | Lightspeed | 2026-08-18 | 174 |  | 3 Toby Boxes / 2 Daps / 60 Splices | August
D-HPP638 | Lightspeed | 2026-08-18 | 309 |  | 2 Toby Boxes / 2 Daps / 4 Splices | August
D-HLC517 | ASM Utilities | 2026-08-18 | 397 |  |  | August
D-HLC518 | ASM Utilities | 2026-08-18 | 198 |  |  | August
D-HLX408 | North Path | 2026-08-18 | 1374 |  |  | August
D-HLX520 | North Path | 2026-08-18 | 108 |  | 40 Toby Boxes / 20 Daps / 221 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | August
BHUD-FOE-401-W | North Path | 2026-08-18 | 410 |  |  | August
FB-HOE401-V4 | Lightspeed | 2026-08-18 | 190 |  | 1 HH | August
D-HTG212 | Gulfstream | 2026-08-18 | 213 |  |  | August
D-HTG213 | HD Cable | 2026-08-18 | 845 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-18 | 846 |  |  | August
D-HTG231 | Restoring Pro | 2026-08-18 |  |  | No Production | August
D-HPW348 | Alpha Omega | 2026-08-18 | 347 |  |  | August
FB-HPW331 | Gulfstream | 2026-08-18 | 1554 |  |  | August
D-HSF322 | Lopez Underground | 2026-08-18 | 719 |  |  | August
D-HBR258 | Yosep | 2026-08-18 | 66 |  | 7 Locate Markers / 8 Daps / 266 Splices | August
D-HBR259 | Yosep | 2026-08-18 | 830 |  |  | August
D-HPP608 | ITGCommunications | 2026-08-19 | 474 |  |  | August
D-HPP634 | NIA Underground | 2026-08-19 |  |  | No Production | August
D-HPP637 | ITGCommunications | 2026-08-19 | 334 |  | 3 Toby Boxes / 3 Daps / 4 Splices | August
D-HPP638 | ITGCommunications | 2026-08-19 | 558 |  |  | August
D-HLC512 | Brothers | 2026-08-19 | 1512 |  |  | August
FB-HLC512 | Brothers | 2026-08-19 | 934 |  |  | August
D-HLX408 | North Path | 2026-08-19 | 1098 |  |  | August
BHUD-FOE-401-W | North Path | 2026-08-19 | 996 |  |  | August
D-HTG210 | Gulfstream | 2026-08-19 | 691 |  |  | August
D-HTG213 | HD Cable | 2026-08-19 | 962 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-19 | 479 |  |  | August
D-HPW348 | Alpha Omega | 2026-08-19 | 650 |  |  | August
FB-HPW331 | Gulfstream | 2026-08-19 | 227 |  |  | August
FB-HTG279 | ITGCommunications | 2026-08-19 | 350 |  |  | August
D-HSF322 | Lopez Underground | 2026-08-19 | 1475 |  |  | August
D-HBR259 | Yosep | 2026-08-19 | 911 |  |  | August
D-HPP634 | NIA Underground | 2026-08-20 |  |  | PROOFING | August
D-HPP637 | ITGCommunications | 2026-08-20 | 501 |  |  | August
D-HPP638 | ITGCommunications | 2026-08-20 | 757 |  |  | August
D-HPP311 | ITGCommunications | 2026-08-20 | 50 |  | 1 HH / 1 FDH / 1 Ground Rod / 1 Swing Arm / 1 Maclean Switch / 77 Splices | August
D-HPP314 | ITGCommunications | 2026-08-20 |  |  | PROOFING | August
D-HLC512 | Brothers | 2026-08-20 | 1288 |  | 18 Toby Boxes / 17 Daps / 29 Splices | August
D-HLC513 | Power Connect | 2026-08-20 | 3917 |  |  | August
FB-HLC512 | Brothers | 2026-08-20 | 757 |  |  | August
D-HLX408 | North Path | 2026-08-20 | 999 |  |  | August
D-HLX502 | North Path | 2026-08-20 | 81 |  | 1 FDH / 1 Ground Rod / 1 Swing Arm / 32 Toby Boxes / 25 Daps / 182 Splices | August
FB-HLX175 | Lightspeed | 2026-08-20 | 240 |  |  | August
BHUD-FOE-401-W | North Path | 2026-08-20 |  |  | 4 HH | August
D-HTG210 | Gulfstream | 2026-08-20 | 1744 |  |  | August
D-HTG213 | HD Cable | 2026-08-20 |  |  | No Production | August
D-HTG230 | Restoring Pro | 2026-08-20 | 721 |  |  | August
D-HPW348 | Alpha Omega | 2026-08-20 | 125 |  |  | August
FB-HTG279 | ITGCommunications | 2026-08-20 |  |  | No Production | August
D-HSF322 | Lopez Underground | 2026-08-20 | 453 |  |  | August
BHCD-FPW-03-E | Lopez Underground | 2026-08-20 | 1218 |  |  | August
BHT-FSE-01 | BICOM | 2026-08-20 |  |  | No Production | August
D-HBR259 | Yosep | 2026-08-20 | 564 |  |  | August
D-HPP608 | ITGCommunications | 2026-08-21 |  |  | No Production | August
D-HPP637 | ITGCommunications | 2026-08-21 |  |  | No Production | August
D-HLC512 | Brothers | 2026-08-21 | 1558 |  |  | August
D-HLC513 | Power Connect | 2026-08-21 | 520 |  |  | August
FB-HLC512 | Brothers | 2026-08-21 | 280 |  |  | August
D-HLX408 | North Path | 2026-08-21 | 400 |  |  | August
D-HLX502 | ITGCommunications | 2026-08-21 |  | 1319 |  | August
D-HLX505 | North Path | 2026-08-21 | 114 |  | 40 Toby Boxes / 33 Daps / 241 Splices / 1 FDH / 1 HH / 1 Swing ARM / 1 Ground Rod
D-HLX510 | North Path | 2026-08-21 | 111 |  | 40 Toby Boxes / 38 Daps / 216 Splices / 1 FDH / 1 HH / 1 Swing ARM / 1 Ground Rod | August
D-HLX510 | ITGCommunications | 2026-08-21 |  | 1140 |  | August
D-HTG210 | Gulfstream | 2026-08-21 | 954 |  |  | August
D-HTG213 | HD Cable | 2026-08-21 |  |  | 6 Toby Boxes | August
D-HTG230 | Restoring Pro | 2026-08-21 | 696 |  |  | August
D-HPW348 | Alpha Omega | 2026-08-21 | 150 |  |  | August
FB-HTG279 | ITGCommunications | 2026-08-21 |  |  | No Production | August
BHCD-FPW-03-E | Lopez Underground | 2026-08-21 |  |  | No Production | August
D-HSF322 | Lopez Underground | 2026-08-21 | 1519 |  |  | August
BHT-FSE-01 | BICOM | 2026-08-21 |  |  | No Production | August
D-HBR258 | Yosep | 2026-08-21 |  |  | No Production | August
D-HBR259 | Yosep | 2026-08-21 | 764 |  |  | August
D-HPP637 | ITGCommunications | 2026-08-24 | 570 |  |  | August
D-HPP638 | ITGCommunications | 2026-08-24 |  |  | 7 Toby Boxes / 7 Daps / 14 Splices | August
D-HLC506 | Brothers | 2026-08-24 | 616 |  |  | August
D-HLC511 | ITGCommunications | 2026-08-24 | 319
D-HLC512 | Brothers | 2026-08-24 | 530 |  | 15 Toby Boxes / 15 Daps / 21 Splices | August
D-HLX408 | North Path | 2026-08-24 | 741 |  |  | August
FB-HLX175 | 1972 Fiber Core | 2026-08-24 |  | 3558 | 3,558 144ct Fiber / 3,073 Tracer Wire / 1,995 Mule Tape / 3,990 Wreck Out | August
BHUD-FOE-401-W | 1972 Fiber Core | 2026-08-24 |  | 2020 | 2,020 144ct Fiber / 1,520 Tracer Wire | August
D-HTG210 | Gulfstream | 2026-08-24 | 1269 |  |  | August
D-HTG217 | Lopez Underground | 2026-08-24 | 1428 |  |  | August
D-HPW348 | Alpha Omega | 2026-08-24 | 505 |  |  | August
D-HSF322 | Lopez Underground | 2026-08-24 | 837 |  |  | August
D-HBR258 | Yosep | 2026-08-24 | 38 |  | 6 Locate Markers / 7 Daps / 84 Splices | August
D-HBR259 | Yosep | 2026-08-24 | 102 |  |  | August
D-HPP608 | ITGCommunications | 2026-08-25 |  |  | No Production | August
D-HPP637 | ITGCommunications | 2026-08-25 |  |  | No Production--Weather | August
D-HPP638 | ITGCommunications | 2026-08-25 |  |  | No Production--Weather | August
D-HPP303 | ITGCommunications | 2026-08-25 | 119 |  |  | August
D-HPP311 | ITGCommunications | 2026-08-25 |  |  | Proofing | August
D-HPP314 | ITGCommunications | 2026-08-25 |  |  | 39 Toby Boxes / 39 Daps / 85 Splices | August
D-HLC506 | Brothers | 2026-08-25 |  |  | No Production--Weather | August
D-HLC511 | ITGCommunications | 2026-08-25 |  |  | No Production--Weather | August
D-HLC512 | Brothers | 2026-08-25 | 249 |  |  | August
D-HAL114 | North Path | 2026-08-25 | 1229 |  |  | August
D-HLX408 | North Path | 2026-08-25 | 63 |  | 32 Toby Boxes / 28 Daps | August
D-HTG210 | Gulfstream | 2026-08-25 | 319 |  |  | August
D-HTG217 | Lopez Underground | 2026-08-25 | 1277 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-25 |  |  | 1 FDH / HH | August
D-HPW348 | Alpha Omega | 2026-08-25 | 254 |  |  | August
BHCD-FPW-03-W | ITGCommunications | 2026-08-25 | 150 |  |  | August
BHC-FSW-04-E | BICOM | 2026-08-25 |  |  | No Production | August
D-HBR258 | Yosep | 2026-08-25 | 24 |  | 4 Locate Markers / 6 Daps / 52 Splices | August
D-HPP608 | ITGCommunications | 2026-08-26 | 292 |  |  | August
D-HPP631 | Brothers | 2026-08-26 | 135 |  |  | August
D-HPP637 | ITGCommunications | 2026-08-26 | 192 |  |  | August
D-HPP638 | ITGCommunications | 2026-08-26 |  |  | PROOFING | August
FB-HPP631 | Brothers | 2026-08-26 | 463 |  |  | August
D-HLC506 | Brothers | 2026-08-26 | 610 |  |  | August
D-HLC511 | ITGCommunications | 2026-08-26 | 150 |  | 2 Toby Boxes / 2 Daps / 4 Splices | August
D-HPP303 | ITGCommunications | 2026-08-26 | 100 |  |  | August
D-HAL114 | North Path | 2026-08-26 | 1266 |  |  | August
D-HLX408 | North Path | 2026-08-26 |  |  | 1 FDH / 1 Swing Arm / 1 Ground Rod / 209 Splices | August
D-HTG210 | Gulfstream | 2026-08-26 |  |  | RESTORATION | August
D-HPW348 | Alpha Omega | 2026-08-26 | 581 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-26 | 60 |  |  | August
D-HTG231 | Restoring Pro | 2026-08-26 | 326 |  |  | August
FB-HTG279 | ITG Comm | 2026-08-26 | 456 |  |  | August
BHC-FSW-04-E | BICOM | 2026-08-26 | 800 |  | 1 HH / 1 Ground Rod | August
D-HBR258 | Yosep | 2026-08-26 |  |  | No Production | August
D-HBR259 | Yosep | 2026-08-26 | 1144 |  |  | August
D-HPP608 | ITGCommunications | 2026-08-27 | 288 |  | 3 Toby Boxes / 3 Daps / 6 Splices | August
D-HPP631 | Brothers | 2026-08-27 | 206 |  |  | August
D-HPP637 | ITGCommunications | 2026-08-27 | 240 |  | 3 Toby Boxes / 3 Daps / 6 Splices | August
D-HPP638 | ITGCommunications | 2026-08-27 |  |  | 1 HH / 1 Ground Rod / 1 FDH / 1 MAclean Switch / 1 Swing Arm
D-HLC511 | ITGCommunications | 2026-08-27 |  |  | No Production | August
D-HLC519 | Brothers | 2026-08-27 |  |  | No Production | August
FB-HWP476 | J Garcia Underground | 2026-08-27 | 550 |  |  | August
D-HAL114 | North Path | 2026-08-27 | 704 |  |  | August
D-HPW330 | Lopez Underground | 2026-08-27 | 1312 |  |  | August
D-HPW348 | Alpha Omega | 2026-08-27 | 360 |  |  | August
D-HTG216 | Lopez Underground | 2026-08-27 | 43 |  |  | August
D-HTG230 | Restoring Pro | 2026-08-27 |  |  | No Production | August
D-HTG231 | Restoring Pro | 2026-08-27 | 1051 |  |  | August
FB-HTG279 | ITG Comm | 2026-08-27 |  |  | No Production | August
BHC-FSW-04-E | BICOM | 2026-08-27 | 185 |  | 1 HH / 1 Ground Rod | August
D-HSW405 | BICOM | 2026-08-27 | 185 |  |  | August
D-HBR258 | Yosep | 2026-08-27 |  |  | No Production | August
D-HPP637 | ITGCommunications | 2026-08-28 |  |  | No Production | August
D-HPP638 | ITGCommunications | 2026-08-28 |  |  | PROOFING | August
FB-HWP476 | J Garcia Underground | 2026-08-28 |  |  | 2 HH / 2 Ground Rods / 2 MacLean Switches | August
D-HPW348 | ITGCommunications | 2026-08-28 | 153 |  |  | August
D-HTG229 | Lopez Underground | 2026-08-28 | 288 |  |  | August
D-HTG233 | Lopez Underground | 2026-08-28 | 288 |  |  | August
D-HTG238 | Lopez Underground | 2026-08-28 | 89 |  |  | August
D-HTG305 | Alpha Omega | 2026-08-28 | 652 |  |  | August
D-HSF322 | Lopez Underground | 2026-08-28 |  |  | RESTORATION | August
BHU-FLX-01-W | North Path | 2026-08-28 |  |  | 10 HH / 10 Ground Rods | August
FB-HSF304 | ITGCommunications | 2026-08-28 | 1743 |  |  | August
BHC-FSW-04-E | BICOM | 2026-08-28 | 375 |  |  | August
D-HSW405 | BICOM | 2026-08-28 |  |  | No Production | August
D-HBR258 | Yosep | 2026-08-28 | 24 |  | 3 Locate Markers / 4 Daps / 26 Splices | August
D-HBR260 | Yosep | 2026-08-28 | 320 |  |  | August
D-HPP608 | ITGCommunications | 2026-08-31 | 215 |  |  | August
D-HPP637 | ITGCommunications | 2026-08-31 |  |  | No Production | August
D-HLC506 | Brothers | 2026-08-31 | 1512 |  |  | August
D-HLC511 | ITGCommunications | 2026-08-31 |  |  | No Production | August
D-HLC519 | Brothers | 2026-08-31 | 805 |  |  | August
D-HPP314 | Power Connect | 2026-08-31 |  |  | No Production | August
D-HAL115 | North Path | 2026-08-31 | 1173 |  |  | August
D-HTG305 | ITG Comm | 2026-08-31 |  |  | No Production | August
D-HPW348 | Alpha Omega | 2026-08-31 | 326 |  |  | August
D-HTG216 | Lopez Underground | 2026-08-31 |  |  | RESTORATION | August
D-HTG238 | Lopez Underground | 2026-08-31 |  |  | RESTORATION | August
D-HTG230 | Restoring Pro | 2026-08-31 |  |  | RESTORATION | August
BHC-FSW-04-E | BICOM | 2026-08-31 | 635 |  |  | August
D-HSW405 | BICOM | 2026-08-31 | 635 |  | 1 Toby Box | August
D-HBR259 | Yosep | 2026-08-31 | 25 |  | 5 Locate Markers / 5 Daps / 74 Splices | August
D-HBR260 | Yosep | 2026-08-31 | 840 |  |  | August
D-HPP608 | ITGCommunications | 2026-09-01 | 190 |  |  | September
D-HPP638 | ITGCommunications | 2026-09-01 |  |  | RESTORATION | September
D-HLC506 | Brothers | 2026-09-01 | 1497 |  |  | September
D-HLC511 | ITGCommunications | 2026-09-01 |  |  | No Production | September
D-HLC513 | ITGCommunications | 2026-09-01 | 250 |  |  | September
D-HLC519 | Brothers | 2026-09-01 | 1654 |  |  | September
FB-HPP314 | ITGCommunications | 2026-09-01 |  | 10625 |  | September
D-HAL115 | North Path | 2026-09-01 | 1126 |  |  | September
D-HLX408 | ITGCommunications | 2026-09-01 |  | 1500 | 1,250 Tracer Wire | September
D-HTG210 | Gulfstream | 2026-09-01 |  |  |  | September
D-HTG212 | Gulfstream | 2026-09-01 | 9 |  | 3 Daps / 8 Splices | September
D-HTG231 | Restoring Pro | 2026-09-01 | 746 |  |  | September
D-HTG305 | ITGCommunications | 2026-09-01 | 939 |  |  | September
D-HPW348 | Alpha Omega | 2026-09-01 | 565 |  |  | September
BHC-FSW-04-E | BICOM | 2026-09-01 | 431 |  |  | September
D-HSW405 | BICOM | 2026-09-01 | 246 |  | 2 Toby Boxes / 1 Dap / 2 Splices | September
FB-HSW419 | BICOM | 2026-09-01 | 185 |  |  | September
D-HBR256 | Yosep | 2026-09-01 |  | 3380 |  | September
D-HBR259 | Yosep | 2026-09-01 | 15 |  | 3 Locate Markers / 3 Daps / 5 Splices | September
D-HBR260 | Yosep | 2026-09-01 | 646 |  |  | September
D-HPP608 | ITGCommunications | 2026-09-02 | 367 |  |  | September
D-HPP638 | ITGCommunications | 2026-09-02 |  |  | PROOFING | September
FB-HPP631 | Brothers | 2026-09-02 |  |  | No Production | September
D-HLC506 | Brothers | 2026-09-02 | 1006 |  |  | September
D-HLC511 | ITGCommunications | 2026-09-02 | 165 |  |  | September
D-HLC513 | Power Connect | 2026-09-02 | 468 |  |  | September
D-HLC519 | Brothers | 2026-09-02 | 1252 |  | 6 Toby Boxes / 5 Daps / 11 Splices | September
D-HAL115 | North Path | 2026-09-02 |  |  | No Production | September
D-HPW348 | Alpha Omega | 2026-09-02 | 503 |  |  | September
D-HTG231 | Restoring Pro | 2026-09-02 | 1093 |  |  | September
D-HTG210 | Gulfstream | 2026-09-02 | 776 |  |  | September
D-HTG305 | ITGCommunications | 2026-09-02 | 883 |  |  | September
BHCD-FPW-03-E | Lopez Underground | 2026-09-02 | 1550 |  |  | September
BHC-FSW-04-E | BICOM | 2026-09-02 | 350 |  |  | September
FB-HSW419 | BICOM | 2026-09-02 | 350 |  |  | September
D-HBR259 | Yosep | 2026-09-02 | 20 |  | 4 Locate Markers / 4 Daps / 60 Splices | September
D-HBR260 | Yosep | 2026-09-02 | 851 |  |  | September
D-HPP608 | ITGCommunications | 2026-09-03 | 153 |  |  | September
D-HPP638 | ITGCommunications | 2026-09-03 |  |  | PROOFING | September
FB-HPP631 | Brothers | 2026-09-03 |  |  | 4 HH / 4 Ground Rods | September
D-HLC511 | ITGCommunications | 2026-09-03 |  |  | No Production | September
D-HLC513 | Power Connect | 2026-09-03 |  |  | No Production | September
D-HLC519 | Brothers | 2026-09-03 | 1003 |  |  | September
D-HAL115 | North Path | 2026-09-03 | 833 |  |  | September
D-HAL116 | North Path | 2026-09-03 | 306 |  |  | September
D-HPW330 | Lopez Underground | 2026-09-03 | 483 |  |  | September
D-HPW348 | Alpha Omega | 2026-09-03 | 115 |  |  | September
D-HPW349 | Gulfstream | 2026-09-03 |  |  | No Production | September
D-HTG210 | Gulfstream | 2026-09-03 |  |  | 5 Toby Boxes | September
D-HTG231 | Restoring Pro | 2026-09-03 | 751 |  |  | September
D-HTG305 | ITGCommunications | 2026-09-03 | 846 |  |  | September
BHCD-FPW-03-E | Lopez Underground | 2026-09-03 | 693 |  |  | September
BHC-FSW-04-E | BICOM | 2026-09-03 | 510 |  |  | September
D-HSW405 | BICOM | 2026-09-03 | 175 |  |  | September
FB-HSW419 | BICOM | 2026-09-03 | 335 |  |  | September
D-HBR259 | Yosep | 2026-09-03 |  |  | No Production | September
D-HBR260 | Yosep | 2026-09-03 | 499 |  | 3 Locate Markers / 3 Daps / 18 Splices | September
FB-HPP631 | Brothers | 2026-09-04 | 1010
D-HLC511 | ITGcommunications | 2026-09-04 |  |  | No Production | September
D-HLC519 | Brothers | 2026-09-04 | 617 |  |  | September
D-HAL115 | North Path | 2026-09-04 | 60 |  | 32 Toby Boxes / 23 Daps / 200 Splices | September
D-HAL116 | North Path | 2026-09-04 | 724 |  |  | September
D-HTG231 | Restoring Pro | 2026-09-04 | 255 |  |  | September
D-HTG305 | Lightspeed | 2026-09-04 |  |  | Restoration | September
D-HPW330 | Lopez Underground | 2026-09-04 | 639 |  |  | September
D-HPW348 | Alpha Omega | 2026-09-04 | 106 |  |  | September
BHC-FSW-04-E | BICOM | 2026-09-04 |  |  | No Production | September
FB-HSW419 | BICOM | 2026-09-04 |  |  | No Production | September
D-HBR259 | Yosep Aerial Star | 2026-09-04 | 5 |  | 1 HH / 2 Daps / 72 Splices | September
D-HBR260 | Yosep Aerial Star | 2026-09-04 | 747 |  |  | September
|  | 2026-09-07 |  |  |  | September
D-HLC511 | ITGcommunications | 2026-09-08 | 147 |  |  | September
D-HLC516 | Legant Livings | 2026-09-08 | 227 |  |  | September
FB-HLC519 | Power Connect | 2026-09-08 | 1264 |  |  | September
D-HLX503 | North Path | 2026-09-08 | 72 |  | 38 Toby Boxes / 25 Daps / 88 Splices
D-HAL116 | North Path | 2026-09-08 | 933 |  |  | September
North Oaks Estates | North Path | 2026-09-08 |  |  | No Production--Vehicle Breakdown | September
D-HTG218 | Gulfstream | 2026-09-08 |  |  | Restoration | September
D-HTG305 | Lightspeed | 2026-09-08 |  |  | No Production | September
FB-HTG279 | Lightspeed | 2026-09-08 | 146 |  |  | September
D-HPW348 | Alpha Omega | 2026-09-08 | 390 |  |  | September
BHC-FSW-04-E | BICOM | 2026-09-08 |  |  | No Production | September
FB-HSW419 | BICOM | 2026-09-08 |  |  | No Production | September
D-HSW419 | BICOM | 2026-09-08 |  |  | No Production | September
D-HBR260 | Yosep | 2026-09-08 | 615 |  |  | September
D-HPP608 | ITGCommunications | 2026-09-09 | 225 |  |  | September
FB-HPP631 | Brothers | 2026-09-09 |  |  | 2 Vaults / 2 Ground Rods / 2 Maclean Switch | September
D-HLC511 | ITG Comm | 2026-09-09 |  |  | No Production | September
D-HLC516 | Legant Livings | 2026-09-09 | 1010 |  |  | September
FB-HLC512 | Brothers | 2026-09-09 | 1375 |  |  | September
FB-HLC519 | PowerConnect | 2026-09-09 | 775 |  |  | September
D-HAL116 | North Path | 2026-09-09 | 1282 |  |  | September
North Oaks Estates | North Path | 2026-09-09 |  |  | No Production--Locate Issue | September
D-HPW361 | Alpha Omega | 2026-09-09 | 379 |  |  | September
D-HTG212 | Gulfstream | 2026-09-09 |  |  | Restoration | September
D-HTG215 | Gulfstream | 2026-09-09 |  |  | Restoration | September
D-HTG218 | Gulfstream | 2026-09-09 |  |  | Restoration | September
BHC-FSW-04-E | BICOM | 2026-09-09 | 530 |  |  | September
FB-HSW419 | BICOM | 2026-09-09 | 530 |  |  | September
D-HSW419 | BICOM | 2026-09-09 | 530 |  |  | September
D-HBR259 | Yosep | 2026-09-09 |  |  | No Production | September
D-HBR260 | Yosep | 2026-09-09 | 1037 |  |  | September
D-HPP608 | ITGcommunications | 2026-09-10 |  |  | No Production | September
D-HLC511 | ITGcommunications | 2026-09-10 | 408 |  | 3 Toby Boxes / 3 Daps / 6 Splices | September
D-HLC515 | Randy's Utilities | 2026-09-10 | 307 |  |  | September
D-HLC516 | Legant Livings | 2026-09-10 | 1086 |  |  | September
D-HLC519 | Brothers | 2026-09-10 | 1649 |  |  | September
FB-HLC512 | Brothers | 2026-09-10 |  |  | 7 Vaults / 7 Ground Rods | September
North Oaks | North Path | 2026-09-10 |  |  | No Production | September
D-HAL116 | North Path | 2026-09-10 | 123 |  |  | September
FB-HOE401-V5 | North Path | 2026-09-10 | 530 |  |  | September
Plantation Bay | APT Communications | 2026-09-10 | 362 |  |  | September
D-HPW346 | A1 Boardband | 2026-09-10 | 481 |  |  | September
D-HPW361 | Alpha Omega | 2026-09-10 | 168 |  |  | September
D-HTG212 | Gulfstream | 2026-09-10 |  |  | Restoration | September
FB-HTG238 | Lopez Underground | 2026-09-10 | 137 |  |  | September
FB-HTG290 | ITGcommunications | 2026-09-10 |  |  | No Production | September
BHT-FSE-01 | BICOM | 2026-09-10 | 430 |  |  | September
D-HSW419 | BICOM | 2026-09-10 | 430 |  |  | September
D-HBR259 | Yosep | 2026-09-10 | 45 | 1012 | 9 Locate Markers / 9 Daps / 111 Splices | September
D-HBR260 | Yosep | 2026-09-10 | 345 |  |  | September
D-HPP608 | ITGcommunications | 2026-09-11 | 504 |  |  | September
D-HLC507 | ASM Utilities | 2026-09-11 | 410 |  |  | September
D-HLC515 | Randy's Utilities | 2026-09-11 | 605 |  |  | September
D-HLC516 | Legant Livings | 2026-09-11 | 484 |  |  | September
FB-HLC512 | Brothers | 2026-09-11 |  |  | 1 HH / 1 Ground Rod | September
FB-HOE401-V5 | North Path | 2026-09-11 | 581 |  |  | September
North Oaks | North Path | 2026-09-11 |  |  | No Production | September
D-HPW346 | A1 Broadband | 2026-09-11 | 322 |  |  | September
D-HPW361 | Alpha Omega | 2026-09-11 |  |  | No Production | September
D-HTG212 | Gulfstream | 2026-09-11 |  |  | Restoration | September
FB-HTG238 | Lopez Underground | 2026-09-11 |  |  | No Production | September
BHT-FSE-01 | BICOM | 2026-09-11 | 755 |  |  | September
D-HSW419 | BICOM | 2026-09-11 | 755 |  |  | September
D-HBR261 | Yosep | 2026-09-11 | 806 |  |  | September
D-HPP608 | ITGcommunications | 2026-09-14 | 469 |  |  | September
D-HLC507 | ASM Utilities | 2026-09-14 | 324 |  |  | September
D-HLC511 | ITGcommunications | 2026-09-14 | 242 |  | 1 Toby Box / 1 Dap / 2 Splices | September
D-HLC515 | Randy's Utilities | 2026-09-14 |  |  | No Production | September
D-HLC516 | Legant Livings | 2026-09-14 | 1243 |  |  | September
D-HAL116 | North Path | 2026-09-14 | 249 |  |  | September
FB-HOE401-V5 | North Path | 2026-09-14 | 243 |  | 3 HH | September
North Okas | North Path | 2026-09-14 | 946 |  |  | September
Plantation Bay | APT Communications | 2026-09-14 |  |  | No Production | September
D-HPW348 | Alpha Omega | 2026-09-14 | 78 |  |  | September
D-HPW346 | A1 Broadband | 2026-09-14 | 712 |  |  | September
BHT-FSE-01 | BICOM | 2026-09-14 | 400 |  |  | September
D-HSW419 | BICOM | 2026-09-14 | 400 |  |  | September
D-HBR259 | Yosep | 2026-09-14 | 20 |  | 4 Locate Markers / 4 Daps / 48 Splices | September
D-HBR261 | Yosep | 2026-09-14 |  |  | No Production | September
D-HPP608 | ITGcommunications | 2026-09-15 | 331 |  |  | September
FB-HPP612 | Brothers | 2026-09-15 | 1045 |  |  | September
D-HLC507 | ASM Utilities | 2026-09-15 | 454 |  | 2 Toby Boxes / 2 Daps / 4 Splices | September
D-HLC511 | ITGcommunications | 2026-09-15 |  |  | No Production | September
D-HLC515 | Randy's Utilities | 2026-09-15 | 727 |  |  | September
D-HLC516 | Legant Livings | 2026-09-15 |  |  | No Production | September
D-HAL113 | North Path | 2026-09-15 | 716 |  |  | September
Plantation Bay | APT Communications | 2026-09-15 |  |  | No Production | September
FB-HOE401-V5 | 1972 Fiber Core | 2026-09-15 |  |  | No Production | September
North Oaks | North Path | 2026-09-15 | 988 |  |  | September
D-HPW346 | A1 Boardband | 2026-09-15 | 751 |  |  | September
D-HPW348 | Alpha Omega | 2026-09-15 |  |  | 1 Toby Box | September
D-HTG230 | Restoring Pro | 2026-09-15 | 661 |  |  | September
D-HTG231 | Restoring Pro | 2026-09-15 | 1387 |  |  | September
FB-HTG238 | Lopez Underground | 2026-09-15 | 857 |  |  | September
BHT-FSE-01 | BICOM | 2026-09-15 | 769 |  |  | September
D-HSW419 | BICOM | 2026-09-15 | 769 |  |  | September
D-HBR259 | Yosep | 2026-09-15 |  |  | No Production | September
D-HPP608 | ITGcommunications | 2026-09-16 | 845 |  |  | September
FB-HPP612 | Brothers | 2026-09-16 | 1311 |  |  | September
FB-HPP631 | Brothers | 2026-09-16 |  | 6092 | 5,318 Tracer Wire | September
D-HLC507 | ASM Utilities | 2026-09-16 | 891 |  |  | September
D-HLC508 | ASM Utilities | 2026-09-16 | 423 |  |  | September
D-HLC511 | ITGcommunications | 2026-09-16 | 205 |  | 1 Toby Box / 1 Dap / 2 Splices | September
D-HLC515 | Randy's Utilities | 2026-09-16 | 895 |  |  | September
D-HLC516 | Legant Livings | 2026-09-16 |  |  | No Production | September
FB-HOE401-V5 | 1972 Fiber Core | 2026-09-16 |  | 1958 | 1,538 Tracer Wire / 568 Mule Tape / 180 Wreckout | September
SFU-MNTE-3 | North Path | 2026-09-16 | 1144 |  | No Production--Locate Issue | September
SFU-MNTE-4 | 1972 Fiber Core | 2026-09-16 |  | 474 | 1 MacLean Switch | September
D-HAL116 | North Path | 2026-09-16 | 478 |  | 25 Daps | September
D-HPW346 | A1 Boardband | 2026-09-16 |  |  | No Production--Locate Issue | September
D-HTG305 | Lopez Underground | 2026-09-16 | 936 |  |  | September
D-HTG307 | Lopez Underground | 2026-09-16 | 86 |  | No Production--Drill Breakdown | September
FB-HTG238 | Lopez Underground | 2026-09-16 | 337 |  |  | September
FB-HTG290 | Alpha Omega | 2026-09-16 | 146 |  |  | September
BHT-FSE-01 | BICOM | 2026-09-16 | 400 |  |  | September
D-HSW419 | BICOM | 2026-09-16 | 400 |  |  | September
D-HBR259 | Yosep | 2026-09-16 | 20 |  | 4 Locate Markers / 5 Daps / 98 Splices | September
D-HBR261 | Yosep | 2026-09-16 | 1227 |  |  | September
D-HPP608 | ITGcommunications | 2026-09-17 |  |  | 3 Toby Boxes / 3 Daps / 51 Splices | September
D-HPP854 | Brothers | 2026-09-17 | 2096 |  |  | September
FB-HPP612 | Brothers | 2026-09-17 | 1408 |  |  | September
D-HLC507 | ASM Utilties | 2026-09-17 | 1451 |  |  | September
D-HLC511 | ITGcommunications | 2026-09-17 | 200 |  | 2 Toby Boxes / 2 Daps / 3 Splices | September
D-HLC515 | Randy's Utilities | 2026-09-17 |  |  | No Production--Drill Breakdown | September
D-HLC516 | Legant Livings | 2026-09-17 | 276 |  |  | September
D-HLC517 | ASM Utilties | 2026-09-17 |  |  | No Production--Drill Breakdown | September
FB-HLC512 | Brothers | 2026-09-17 |  |  | No Production | September
D-HAL113 | North Path | 2026-09-17 | 959 |  |  | September
D-HAL116 | ITGcommunications | 2026-09-17 |  | 378 | 228 Tracer Wire | September
SFU-MNTE-3 | North Path | 2026-09-17 | 1324 |  |  | September
D-HTG305 | Lopez Underground | 2026-09-17 | 124 |  |  | September
D-HTG307 | Lopez Underground | 2026-09-17 | 2001 |  |  | September
D-HPW361 | Alpha Omega | 2026-09-17 | 235 |  |  | September
BHC-FSW-04-E | BICOM | 2026-09-17 |  |  | 3 Vaults / 3 Ground Rods | September
BHT-FSE-01 | BICOM | 2026-09-17 |  |  | 3 Vaults / 3 Ground Rods | September
D-HBR261 | Yosep | 2026-09-17 | 1139 |  |  | September
FB-HPP612 | Brothers | 2026-09-18 | 1426 |  |  | September
D-HLC507 | ASM Utilities | 2026-09-18 | 498 |  |  | September
D-HLC510 | ITGcommunications | 2026-09-18 | 170 |  |  | September
D-HLC511 | ITGcommunications | 2026-09-18 | 110 |  |  | September
D-DLC516 | Legant Livings | 2026-09-18 | 465 |  |  | September
FB-HLC512 | Brothers | 2026-09-18 |  |  | No Production | September
D-HPP854 | Brothers | 2026-09-18 | 372 |  |  | September
SFU-MNTE-3 | North Path | 2026-09-18 | 840 |  |  | September
D-HAL113 | North Path | 2026-09-18 | 815 |  |  | September
D-HAL116 | North Path | 2026-09-18 | 72 |  | 1 Vault / 1 FDH / 1 Ground Rod / 43 Toby Boxes / 113 Splices | September
D-HTG305 | Lopez Underground | 2026-09-18 | 201 |  |  | September
D-HTG307 | Lopez Underground | 2026-09-18 | 379 |  |  | September
D-HPW328 | Lopez Underground | 2026-09-18 |  |  | No Production--Locate Issue | September
D-HPW329 | Lopez Underground | 2026-09-18 |  |  | No Production--Locate Issue | September
D-HPW330 | Lopez Underground | 2026-09-18 |  |  | No Production--Locate Issue | September
D-HPW361 | Alpha Omega | 2026-09-18 | 515 |  |  | September
FB-HOE401-V4 | ITGcommunications | 2026-09-18 | 25 |  | 1 Vault / 2 Maclean Switch / 2 Ground Rod | September
D-HBR261 | Yosep | 2026-09-18 | 995 |  |  | September
D-HLC507 | ASM Utilties | 2026-09-21 |  |  | No Production | September
D-HLC508 | ASM Utilties | 2026-09-21 | 1505 |  |  | September
D-HLC511 | ITG Communications | 2026-09-21 | 580 |  | 1 Toby Box / 1 Dap / 2 Splices | September
D-HLC514 | APT Communications | 2026-09-21 |  |  | No Production--Locate Issue | September
D-HLC515 | Randy's Utilities | 2026-09-21 | 553 |  |  | September
D-HLC516 | Legant Livings | 2026-09-21 | 461 |  |  | September
D-HLC517 | ASM Utilties | 2026-09-21 | 1157 |  |  | September
D-HPP854 | Brothers | 2026-09-21 | 452 |  |  | September
D-HPP858 | Brothers | 2026-09-21 | 1349 |  |  | September
SFU-MNTE-3 | North Path | 2026-09-21 | 1506 |  |  | September
SFU-MNTE-4 | APT Communications | 2026-09-21 | 739 |  |  | September
D-HAL113 | North Path | 2026-09-21 | 381 |  |  | September
D-HTG307 | Lopez Underground | 2026-09-21 | 764 |  |  | September
D-HPW348 | Alpha Omega | 2026-09-21 | 564 |  |  | September
D-HSF402 | GN Systems | 2026-09-21 |  |  | No Production | September
D-HSF419 | GN Systems | 2026-09-21 | 1933 |  |  | September
D-HSW419 | BICOM | 2026-09-21 | 647 |  |  | September
BHT-FSE-01 | BICOM | 2026-09-21 | 647 |  |  | September
D-HBR261 | Yosep | 2026-09-21 | 654 |  |  | September
D-HPP608 | ITG Communications | 2026-09-22 | 147 |  | 2 Toby Boxes / 1 Daps / 4 Splices
D-HLC507 | ASM Utilties | 2026-09-22 | 653 |  |  | September
D-HLC508 | ASM Utilties | 2026-09-22 | 1208 |  |  | September
D-HLC511 | ITG Communications | 2026-09-22 | 739 |  | 2 Toby Boxes / 2 Daps / 4 Splices | September
D-HLC514 | APT Communications | 2026-09-22 | 1300 |  |  | September
D-HLC515 | Randy's Utilities | 2026-09-22 | 303 |  |  | September
D-HLC516 | Legant Livings | 2026-09-22 | 380 |  |  | September
D-HLC517 | ASM Utilties | 2026-09-22 | 1729 |  |  | September
D-HLC518 | ASM Utilties | 2026-09-22 |  |  | No Production | September
D-HPP854 | Brothers | 2026-09-22 | 432 |  |  | September
D-HPP858 | Brothers | 2026-09-22 | 1694 |  |  | September
D-HHP883 | Power Connect | 2026-09-22 | 2088 |  |  | September
SFU-MNTE-3 | North Path | 2026-09-22 | 690 |  |  | September
SFU-MNTE-4 | APT Communications | 2026-09-22 | 223 |  |  | September
D-HTG213 | HD Cable | 2026-09-22 | 224 |  |  | September
D-HPW330 | Lopez Underground | 2026-09-22 |  |  | No Production | September
D-HPW348 | Alpha Omega | 2026-09-22 | 165 |  |  | September
D-HSF402 | GN Systems | 2026-09-22 |  |  | No Production | September
D-HSF419 | GN Systems | 2026-09-22 | 2929 |  |  | September
BHCD-FPW-03-E | Lopez Underground | 2026-09-22 | 183 |  |  | September
D-HSW403 | BICOM | 2026-09-22 | 716 |  |  | September
D-HSW404 | BICOM | 2026-09-22 | 48 |  |  | September
FB-HSW419 | BICOM | 2026-09-22 | 800 |  |  | September
BHT-FSE-01 | BICOM | 2026-09-22 |  |  | No Production | September
D-HBR259 | Yosep | 2026-09-22 |  |  | 1 HH / 1 FDH / 1 Swing Arm / 1 Ground Rod / 1 Maclean Switch | September
D-HBR260 | Yosep | 2026-09-22 | 27 |  | 2 Locate Markers / 4 Daps / 64 Splices | September
D-HBR261 | Yosep | 2026-09-22 | 760 |  |  | September
D-HLC507 | ASM Utilties | 2026-09-23 | 486 |  |  | September
D-HLC508 | ASM Utilties | 2026-09-23 | 1392 |  |  | September
D-HLC511 | ITG Communications | 2026-09-23 | 968 |  |  | September
D-HLC514 | APT Communications | 2026-09-23 | 1847 |  |  | September
D-HLC515 | Randy's Utilities | 2026-09-23 | 661 |  |  | September
D-HLC516 | Legant Livings | 2026-09-23 | 441 |  |  | September
D-HLC517 | ASM Utilties | 2026-09-23 | 369 |  |  | September
D-HLC518 | ASM Utilties | 2026-09-23 |  |  | No Production | September
D-HPP854 | Brothers | 2026-09-23 | 529 |  |  | September
D-HPP858 | Brothers | 2026-09-23 | 1580 |  |  | September
SFU-MNTE-3 | North Path | 2026-09-23 | 1248 |  |  | September
SFU-MNTE-4 | North Path | 2026-09-23 | 303 |  |  | September
D-HPW330 | Lopez Underground | 2026-09-23 | 521 |  |  | September
D-HPW346 | A1 Broadband | 2026-09-23 | 3368 |  |  | September
D-HTG213 | HD Cable | 2026-09-23 | 369 |  |  | September
D-HSF420 | GN Systems | 2026-09-23 | 2275 |  |  | September
FB-HSW419 | BICOM | 2026-09-23 | 1134 |  |  | September
D-HSW403 | BICOM | 2026-09-23 | 1134 |  |  | September
D-HPP608 | ITG Communications | 2026-09-24 | 165 |  |  | September
D-HPP637 | ITG Communications | 2026-09-24 |  |  | No Production | September
D-HPP854 | Brothers | 2026-09-24 | 340 |  |  | September
FB-HPP375 | Power Connect | 2026-09-24 | 387 |  |  | September
D-HLC507 | ASM Utilties | 2026-09-24 |  |  | No Production | September
D-HLC508 | ASM Utilties | 2026-09-24 |  |  | No Production | September
D-HLC511 | ITG Communications | 2026-09-24 | 860 |  |  | September
D-HLC514 | APT Communications | 2026-09-24 | 1371 |  |  | September
D-HLC515 | Randy's Utilities | 2026-09-24 | 204 |  |  | September
D-HLC516 | Legant Livings | 2026-09-24 | 445 |  |  | September
D-HLC517 | ASM Utilties | 2026-09-24 | 1679 |  |  | September
D-HLC518 | ASM Utilties | 2026-09-24 | 293 |  |  | September
SFU-MNTE-4 | North Path | 2026-09-24 | 1808 |  |  | September
SFU-MNTE-4 | APT Communications | 2026-09-24 | 383 |  |  | September
SFU-MNTE-3 | North Path | 2026-09-24 |  |  | No Production | September
SFU-MNTE-3 | 1972 Fiber Core | 2026-09-24 |  | 340 | 240 Tracer Wire | September
D-HAL113 | North Path | 2026-09-24 | 495 |  |  | September
D-HAL114 | 1972 Fiber Core | 2026-09-24 |  | 536 |  | September
D-HAL115 | 1972 Fiber Core | 2026-09-24 |  | 534 |  | September
D-HPW346 | A1 Broadband | 2026-09-24 | 843 |  |  | September
D-HSF401 | HD Cable | 2026-09-24 |  |  | No Production | September
D-HSF402 | GN System | 2026-09-24 | 1971 |  |  | September
D-HSW402 | BICOM | 2026-09-24 |  |  | No Production | September
FB-HSW419 | BICOM | 2026-09-24 | 349 |  |  | September
D-HBR260 | Yosep | 2026-09-24 | 19 |  | 3 Locate Markers / 5 Daps / 132 Splices | September
D-HBR261 | Yosep | 2026-09-24 | 809 |  |  | September
D-HPP608 | ITG Communications | 2026-09-25 | 100 |  | 1 Toby Box / 1 Dap / 2 Splices | September
D-HPP626 | Brothers | 2026-09-25 | 2339 |  | 22 Toby Boxes / 36 Daps | September
D-HPP637 | ITG Communications | 2026-09-25 | 124 |  |  | September
D-HPP854 | Brothers | 2026-09-25 |  |  | No Production | September
D-HPP858 | Brothers | 2026-09-25 | 948 |  |  | September
FB-HPP375 | Power Connect | 2026-09-25 |  |  | No Production | September
FB-HPP612 | Brothers | 2026-09-25 |  |  | 2 Vaults / 2 Ground Rods | September
D-HLC507 | ASM Utilties | 2026-09-25 |  |  | No Production | September
D-HLC508 | ASM Utilties | 2026-09-25 | 625 |  |  | September
D-HLC511 | ITG Communications | 2026-09-25 | 300 |  | 1 Toby Box / 1 Dap / 2 Splices | September
D-HLC512 | Brothers | 2026-09-25 | 660 |  |  | September
D-HLC514 | APT Communications | 2026-09-25 | 1776 |  |  | September
D-HLC516 | Legant Livings | 2026-09-25 | 487 |  |  | September
D-HLC517 | ASM Utilties | 2026-09-25 | 77 |  |  | September
D-HLC518 | ASM Utilties | 2026-09-25 | 1208 |  |  | September
SFU-MNTE-3 | North Path | 2026-09-25 | 141 |  | 54 Toby Boxes / 48 Daps / 315 Splices / 2 HH / 2 FDH / 2 Swing Arm / 2 MacLean Switch | September
D-HPW346 | A1 Broadband | 2026-09-25 | 232 |  |  | September
D-HSF401 | HD Cable | 2026-09-25 | 149 |  |  | September
D-HSW402 | BICOM | 2026-09-25 | 1212 |  |  | September
FB-HSW419 | BICOM | 2026-09-25 | 1212 |  |  | September
D-HBR260 | Yosep | 2026-09-25 | 14 |  | 4 Locate Markers / 6 Daps / 122 Splices | September
D-HBR261 | Yosep | 2026-09-25 | 712 |  |  | September
D-HPP608 | ITG Communications | 2026-09-28 | 288 |  |  | September
D-HPP637 | ITG Communications | 2026-09-28 |  |  | No Production | September
D-HLC507 | ASM Utilties | 2026-09-28 | 203 |  |  | September
D-HLC508 | ASM Utilties | 2026-09-28 |  |  | No Production | September
D-HLC511 | ITG Communications | 2026-09-28 | 542 |  | 5 Toby Boxes / 3 Daps / 6 Splices | September
D-HLC515 | Randy's Utilites | 2026-09-28 |  |  | No Production | September
D-HLC516 | Legant Livings | 2026-09-28 |  |  | No Production--Drill Breakdown | September
D-HLC518 | ASM Utilties | 2026-09-28 | 1251 |  |  | September
D-HPP839 | KattleOne | 2026-09-28 |  |  | No Production | September
D-HPP854 | Brothers | 2026-09-28 | 1327 |  |  | September
D-HPP858 | Brothers | 2026-09-28 | 55 |  |  | September
FB-HPP375 | Power Connect | 2026-09-28 | 1570 |  |  | September
FB-HPP612 | Brothers | 2026-09-28 |  |  | No Production | September
FB-HPP879 | Brothers | 2026-09-28 | 1527 |  |  | September
SFU-MNTE-4 | APT Communications | 2026-09-28 | 381 |  |  | September
SFU-MNTE-4 | NorthPath LLC | 2026-09-28 | 1538 |  |  | September
D-HAL113 | NorthPath LLC | 2026-09-28 | 126 |  | 44 Toby Boxes / 43 Daps / 231 Splices | September
FB-HLX175 | ITG Communications | 2026-09-28 |  |  | 3 HH | September
FB-HOE401-V6 | ITG Communications | 2026-09-28 |  |  | 1 HH | September
D-HPW330 | Lopez Underground | 2026-09-28 |  |  | No Production | September
D-HSF402 | GN Systems | 2026-09-28 | 314 |  |  | September
D-HSW402 | BICOM | 2026-09-28 | 125 |  |  | September
FB-HSW419 | BICOM | 2026-09-28 | 554 |  |  | September
D-HBR260 | Yosep | 2026-09-28 | 9 |  | 3 Locate Markers / 5 Daps / 72 Splices | September
D-HBR261 | Yosep | 2026-09-28 | 351 |  |  | September
D-HPP637 | ITG Communications | 2026-09-29 |  |  | No Production | September
D-HLC507 | ASM Utilties | 2026-09-29 |  |  | No Production | September
D-HLC508 | ASM Utilties | 2026-09-29 |  |  | No Production | September
D-HLC510 | ITG Communications | 2026-09-29 | 534 |  | 4 Toby Boxes / 4 Daps / 8 Splices | September
D-HLC511 | ITG Communications | 2026-09-29 |  |  | No Production | September
D-HLC514 | APT Communications | 2026-09-29 |  |  | No Production | September
D-HLC515 | Randy's Utilities | 2026-09-29 | 512 |  |  | September
D-HLC516 | Legant Livings | 2026-09-29 |  |  | No Production | September
D-HLC518 | ASM Utilties | 2026-09-29 |  |  | No Production | September
D-HLC539 | Sosa Line | 2026-09-29 | 1996 |  |  | September
D-HPP839 | Kattleone | 2026-09-29 | 1757 |  |  | September
D-HPP854 | Brothers | 2026-09-29 | 839 |  |  | September
FB-HLC512 | Brothers | 2026-09-29 |  | 6588 | 5,699 Tracer Wire | September
FB-HPP854 | Brothers | 2026-09-29 |  |  | No Production | September
FB-HPP879 | Brothers | 2026-09-29 | 1631 |  |  | September
SFU-MNTE-4 | APT Communications | 2026-09-29 | 552 |  |  | September
SFU-MNTE-4 | NorthPath LLC | 2026-09-29 | 712 |  |  | September
D-HPW330 | Lopez Underground | 2026-09-29 |  |  | No Production | September
BHCD-FPW-03-E | Lopez Undeground | 2026-09-29 |  |  | No Production | September
D-HSF401 | HD Cable | 2026-09-29 | 1013 |  |  | September
BHT-FSW-04-E | BICOM | 2026-09-29 | 199 |  |  | September
FB-HSW419 | BICOM | 2026-09-29 | 892 |  |  | September
D-HSW404 | BICOM | 2026-09-29 | 387 |  |  | September
D-HSW405 | BICOM | 2026-09-29 | 549 |  |  | September
D-HBR260 | Yosep | 2026-09-29 | 6 |  | 1 HH / 3 Locate Markers / 4 Daps / 48 Splices | September
D-HBR261 | Yosep | 2026-09-29 | 871 |  |  | September
D-HLC507 | ASM Communications | 2026-09-30 | 643 |  |  | September
D-HLC508 | ASM Communications | 2026-09-30 |  |  | No Production | September
D-HLC510 | ITG Communications | 2026-09-30 | 310 |  | 2 Toby Boxes / 2 Daps / 4 Splices | September
D-HLC514 | APT Communications | 2026-09-30 | 583 |  |  | September
D-HLC515 | Randy's Utilities | 2026-09-30 | 605 |  |  | September
D-HLC516 | Legant Livings | 2026-09-30 | 680 |  |  | September
D-HLC518 | ASM Utilties | 2026-09-30 |  |  | No Production | September
D-HLC539 | Sosa Line | 2026-09-30 | 1734 |  |  | September
D-HPP839 | Kattleone | 2026-09-30 | 1336 |  |  | September
FB-HPP879 | Brothers | 2026-09-30 | 1421 |  |  | September
SFU-MNTE-4 | APT Communications | 2026-09-30 | 532 |  |  | September
SFU-MNTE-4 | North Path | 2026-09-30 | 190 |  |  | September
BHCD-FPW-03-E | ITG Communications | 2026-09-30 |  |  | No Production | September
BHCD-FPW-03-E | Lopez Undeground | 2026-09-30 |  |  | No Production | September
D-HSF401 | HD Cable | 2026-09-30 |  |  | No Production | September
D-HSF402 | GN Systems | 2026-09-30 |  |  | No Production | September
FB-HSW419 | BICOM | 2026-09-30 | 320 |  |  | September
D-HSW404 | BICOM | 2026-09-30 | 70 |  |  | September
D-HSW405 | BICOM | 2026-09-30 | 250 |  |  | September
D-HBR260 | Yosep | 2026-09-30 | 21 |  | 5 Locate Markers / 8 Daps / 71 Splices | September
D-HBR261 | Yosep | 2026-09-30 | 366 |  |  | September
D-HLC508 | ASM Communications | 2026-10-01 | 76 |  |  | October
D-HLC510 | ITG Communications | 2026-10-01 | 275 |  | 1 Toby Box / 1 Dap / 2 Splices | October
D-HLC514 | APT Communications | 2026-10-01 |  |  | 1 FDH / 1 HH / 1 Swing Arm / 1 MacLean Switch | October
D-HLC515 | Randy's Utilities | 2026-10-01 | 388 |  |  | October
D-HLC516 | Legant Livings | 2026-10-01 | 218 |  |  | October
D-HLC518 | ASM Utilties | 2026-10-01 | 248 |  |  | October
D-HLC539 | Sosa Line | 2026-10-01 | 1741 |  |  | October
D-HPP839 | Kattleone | 2026-10-01 |  |  | No Production | October
FB-HPP879 | Brothers | 2026-10-01 | 1324 |  |  | October
D-HPP637 | ITG Communications | 2026-10-01 | 165 |  |  | October
SFU-MNTE-4 | APT Communications | 2026-10-01 | 596 |  |  | October
D-HPW346 | A1 Broadband | 2026-10-01 | 234 |  |  | October
D-HPW361 | Alpha Omega | 2026-10-01 |  |  | No Production | October
D-HSF401 | HD Cable | 2026-10-01 | 441 |  |  | October
D-HSF402 | GN Systems | 2026-10-01 | 1100 |  |  | October
BHCD-FPW-03-E | Lopez Underground | 2026-10-01 | 925 |  |  | October
FB-HSW419 | BICOM | 2026-10-01 | 126 |  |  | October
D-HSW402 | BICOM | 2026-10-01 | 126 |  |  | October
D-HBR260 | Yosep | 2026-10-01 |  |  | No Production | October
D-HBR261 | Yosep | 2026-10-01 | 10 |  | 1 Locate Marker / 5 Daps / 168 Splices | October
D-HBR262 | Yosep | 2026-10-01 | 742 |  |  | October
D-HLC507 | ITGcommunications | 2026-10-02 |  |  | No Production | October
D-HLC508 | ITGcommunications | 2026-10-02 |  |  | No Production | October
D-HLC514 | APT Communications | 2026-10-02 |  |  | No Production | October
D-HLC515 | Randy's Utilities | 2026-10-02 | 280 |  |  | October
D-HLC516 | Legant Livings | 2026-10-02 | 108 |  |  | October
D-HLC517 | ITGcommunications | 2026-10-02 |  |  | Proofing | October
D-HLC518 | ITGcommunications | 2026-10-02 |  |  | Proofing | October
D-HLC539 | Sosa Line | 2026-10-02 |  |  | No Production | October
D-HPP839 | Kattleone | 2026-10-02 |  |  | No Production | October
FB-HPP879 | Brothers | 2026-10-02 |  |  | No Production | October
D-HPW346 | A1 Broadband | 2026-10-02 | 269 |  |  | October
D-HPW361 | Alpha Omega | 2026-10-02 | 185 |  |  | October
D-HTG231 | 1972 Fiber Core | 2026-10-02 | 95 | 2300 | 1 Dap / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | October
D-HTG401 | HD Cable | 2026-10-02 |  |  | No Production | October
D-HSF402 | GN Systems | 2026-10-02 | 748 |  |  | October
BHC-FSW-04-E | BICOM | 2026-10-02 | 100 |  |  | October
D-HBR261 | Yosep | 2026-10-02 | 20 |  | 1 HH / 5 Daps / 204 Splices | October
D-HBR262 | Yosep | 2026-10-02 | 652 |  |  | October
D-HLC510 | ITGcommunications | 2026-10-05 | 525 |  |  | October
D-HLC514 | APT Communications | 2026-10-05 | 71 |  |  | October
D-HLC516 | Legant Livings | 2026-10-05 | 39 |  |  | October
D-HLC517 | ITGcommunications | 2026-10-05 |  |  | Proofing | October
D-HLC518 | ITGcommunications | 2026-10-05 |  |  | Proofing | October
D-HLC538 | APT Communications | 2026-10-05 |  |  | No Production--Locate Issue | October
D-HLC539 | Sosa Line | 2026-10-05 | 1508 |  |  | October
FB-HLC512 | ITGcommunications | 2026-10-05 |  | 14717 | Stingray Paths To Multiple Distros | October
FB-HLC519 | ITGcommunications | 2026-10-05 |  | 2895 | Stingray Paths To Multiple Distros | October
FB-HLC538 | Sosa Line | 2026-10-05 |  |  | No Production | October
D-HPP637 | ITGcommunications | 2026-10-05 | 400 |  | 3 Toby Boxes / 3 Daps / 6 Splices | October
FB-HPP612 | Brothers | 2026-10-05 |  | 6602 | 5,190 Tracer Wire | October
D-HPP839 | Kattleone | 2026-10-05 | 1779 |  |  | October
SFU-MNTE-4 | APT Communications | 2026-10-05 | 608 |  |  | October
D-HLX101 | North Path | 2026-10-05 | 428 |  |  | October
D-HPW350 | A1 Broadband | 2026-10-05 | 486 |  |  | October
D-HPW361 | Alpha Omega | 2026-10-05 | 182 |  |  | October
BHC-FSW-04-E | BICOM | 2026-10-05 | 100 |  |  | October
FB-HSW419 | BICOM | 2026-10-05 | 282 |  |  | October
D-HSW402 | BICOM | 2026-10-05 | 282 |  |  | October
D-HBR260 | Yosep | 2026-10-05 |  |  | 1 HH / 1 FDH | October
D-HBR261 | Yosep | 2026-10-05 | 70 |  | 8 Locate Markers / 10 Daps / 90 Splices | October
D-HBR262 | Yosep | 2026-10-05 | 571 |  |  | October
D-HPP637 | ITGcommunications | 2026-10-06 |  |  | No Production | October
D-HLC510 | ITGcommunications | 2026-10-06 | 488 |  | 4 Toby Boxes / 4 Daps / 8 Splices | October
D-HLC517 | ITGcommunications | 2026-10-06 |  |  | Proofing | October
D-HLC518 | ITGcommunications | 2026-10-06 |  |  | Proofing | October
D-HPP839 | Kattleone | 2026-10-06 | 324 |  |  | October
FB-HLC538 | Sosa Line | 2026-10-06 | 1739 |  |  | October
D-HAL113 | North Path | 2026-10-06 |  |  | 1 Vault / 1 FDH / 1 Ground Rod / 1 Maclean Switch | October
D-HLX101 | North Path | 2026-10-06 | 1278 |  |  | October
D-HPW350 | A1 Broadband | 2026-10-06 | 670 |  |  | October
D-HPW361 | Alpha Omega | 2026-10-06 | 483 |  |  | October
D-HSF402 | GN Systems | 2026-10-06 | 1602 |  |  | October
D-HSF419 | GN Systems | 2026-10-06 | 78 |  | 6 Toby Boxes / 22 Daps / 58 Splices | October
BHC-FSW-04-E | BICOM | 2026-10-06 | 204 |  |  | October
FB-HSW419 | BICOM | 2026-10-06 | 365 |  |  | October
D-HSW402 | BICOM | 2026-10-06 | 365 |  |  | October
D-HBR260 | Yosep | 2026-10-06 |  |  | No Production | October
D-HBR261 | Yosep | 2026-10-06 | 30 |  | 3 Locate Markers / 3 Daps / 36 Splices | October
D-HBR262 | Yosep | 2026-10-06 | 514 |  |  | October
D-HPW350 | A1 Broadband | 2026-10-07 | 731 |  |  | October
D-HPW361 | Alpha Omega | 2026-10-07 | 271 |  |  | October
D-HSF402 | GN Systems | 2026-10-07 | 190 |  |  | October
D-HSF419 | GN Systems | 2026-10-07 |  |  | 21 Toby Boxes | October
D-HSF420 | GN Systems | 2026-10-07 | 904 |  |  | October
BHC-FSW-04-E | BICOM | 2026-10-07 |  |  | 2 HH / 2 Ground Rods / 2 MacLean Switches | October
FB-HSW419 | BICOM | 2026-10-07 |  |  | No Production | October
D-HBR260 | Yosep | 2026-10-07 |  | 1324 |  | October
D-HBR261 | Yosep | 2026-10-07 |  | 1310 | 1 Vault / 1 FDH / 1 Swing Arm | October
D-HLC507 | ASM Utilities | 2026-10-08 | 749 |  |  | October
D-HLC508 | ASM Utilities | 2026-10-08 |  |  | No Production | October
D-HLC510 | ITG Communications | 2026-10-08 | 493 |  | 1 Toby Box / 1 Dap / 3 Splices | October
D-HLC517 | ASM Utilities | 2026-10-08 |  |  | 17 Toby Boxes / 17 Daps / 118 Splices | October
D-HLC517 | ITG Communications | 2026-10-08 | 36 |  | 12 Toby Boxes / 12 Daps / 20 Splices | October
D-HLC522 | Legant Livings | 2026-10-08 |  |  | No Production--Weather Issue | October
D-HPW350 | A1 Broadband | 2026-10-08 | 843 |  |  | October
D-HPW361 | Alpha Omega | 2026-10-08 | 360 |  |  | October
D-HSF420 | GN Systems | 2026-10-08 | 868 |  |  | October
D-HSW402 | BICOM | 2026-10-08 | 456 |  |  | October
FB-HSW419 | BICOM | 2026-10-08 |  |  | 4 HH / 4 Ground Rods / 4 MacLean Switches | October
D-HBR261 | Yosep | 2026-10-08 | 74 |  | 8 Locate Markers / 9 Daps / 112 Splices | October
D-HBR262 | Yosep | 2026-10-08 | 1291 |  |  | October
D-HLC508 | ASM Utilities | 2026-10-09 |  |  | No Production | October
D-HLC510 | ITG Communications | 2026-10-09 | 725 |  | 8 Toby Boxes / 8 Daps / 15 Splices | October
FB-HPP854 | Brothers | 2026-10-09 | 840 |  |  | October
D-HPP854 | Brothers | 2026-10-09 | 278 |  |  | October
D-HPP637 | ITG Communications | 2026-10-09 | 285 |  | 1 Toby Boxes / 1 Daps / 2 Splices | October
SFU-MNTE-4 | North Path | 2026-10-09 | 63 |  | 21 Toby Boxes / 21 Daps / 47 Splices | October
BHCD-FPW-03-E | Lopez Underground | 2026-10-09 | 844 |  |  | October
D-HPW361 | Alpha Omega | 2026-10-09 | 282 |  | 2 Toby Boxes / 2 Daps / 4 Splices | October
D-HSF420 | GN Systems | 2026-10-09 | 315 |  |  | October
D-HTG208 | Lopez Underground | 2026-10-09 | 504 |  |  | October
D-HTG215 | Gulfstream | 2026-10-09 | 62 |  |  | October
D-HSW402 | BICOM | 2026-10-09 | 374 |  |  | October
BHC-FSW-04-E | BICOM | 2026-10-09 |  |  | No Production | October
FB-HSW419 | BICOM | 2026-10-09 |  |  | 4 HH / 4 Ground Rods / 4 MacLean Switches | October
D-HBR261 | Yosep Aerial Star | 2026-10-09 |  |  | No Production | October
D-HBR262 | Yosep Aerial Star | 2026-10-09 | 969 |  |  | October
2026-10-12

## Tillman Projects Condensed
Market 1 NTP Number | AREA | SOW TSD Date | HHP | Permit Status | SOW Received | SOW Estimated Cost | NTP Received | Footage UG | Fiber Placement Footage
D-HPP630 | Clearwater | 2026-10-30 | 67 | Received | Yes | 100866 | Yes | 9021 | 0
D-HPP631 | Clearwater | 2026-10-30 | 93 | Received | Yes | 104934 | Yes | 8701 | 0
D-HPP637 | Clearwater | 2026-10-30 | 40 | Received | Yes | 91774 | Yes | 7530 | 0
FB-HPP612-2 | Clearwater | 2026-10-10 | 0 | Received | No | 649 | Yes | 0 | 0
D-HNP108/D-H0102E | St Petersburg | 2026-02-27 | 89 | Received | Yes | 72131.5 | Yes | 6182 | 0
Market 1 NTP Number Pinellas | AREA | SOW TSD Date | HHP | Permit Status | SOW Received | SOW Estimated Cost | NTP Received | Footage UG | Splicing Percentage Complete
D-HLC505 | Pinellas | 2026-10-30 | 41 | Received | Yes | 78963.5 | Yes | 5973 | 0
D-HLC508 | Pinellas | 2026-09-30 | 69 | Received | Yes | 84458.5 | Yes | 6831 | 1
D-HLC509 | Pinellas | 2026-10-30 | 72 | Received | No | 69525.5 | Yes | 5407 | 0
D-HLC510 | Pinellas | 2026-10-30 | 102 | Received | Yes | 59181 | Yes | 4718 | 0
D-HLC514 | Pinellas | 2026-09-30 | 83 | Received | Yes | 87651 | Yes | 7199 | 1
D-HLC515 | Pinellas | 2026-09-30 | 18 | Received | Yes | 80560 | Yes | 6416 | 1
D-HLC516 | Pinellas | 2026-09-30 | 90 | Received | Yes | 113855.5 | Yes | 8970 | 1
D-HLC520 | Pinellas | 2026-11-30 | 101 | Received | Yes | 72023 | Yes | 5644 | 0
D-HLC521 | Pinellas | 2026-10-30 | 108 | Received | Yes | 105904.5 | Yes | 8808 | 0
D-HLC522 | Pinellas | 2026-10-30 | 71 | Received | Yes | 79435.5 | Yes | 6374 | 0
D-HLC523 | Pinellas | 2026-11-30 | 92 | Received | Yes | 66908 | Yes | 5350 | 0
D-HLC524 | Pinellas | 2026-10-30 | 89 | Received | Yes | 86487 | Yes | 7078 | 0
D-HLC525 | Pinellas | 2026-11-30 | 77 | Received | Yes | 92514.5 | Yes | 7434 | 0
D-HLC527 | Pinellas | 2026-11-30 | 69 | Received | Yes | 41647.5 | Yes | 3170 | 0
D-HLC538 | Pinellas | 2026-11-30 | 37 | Received | Yes | 105048 | Yes | 8401 | 0
D-HLC540 | Pinellas | 2026-11-30 | 110 | Received | Yes | 54275 | Yes | 4386 | 0
D-HLC541 | Pinellas | 2026-11-30 | 50 | Received | Yes | 82194.5 | Yes | 6948 | 0
D-HLC547 | Pinellas | 2026-11-30 | 51 | Received | Yes | 53744.5 | Yes | 4212 | 0
D-HPP837 | Pinellas | 2026-10-30 | 23 | Received | Yes | 62033 | Yes | 4828 | 0
D-HPP838 | Pinellas | 2026-10-30 | 77 | Received | Yes | 64431 | Yes | 4931 | 0
D-HPP839 | Pinellas | 2026-10-30 | 65 | Received | Yes | 80031 | Yes | 6185 | 0
D-HPP852 | Pinellas | 2026-10-30 | 62 | Received | Yes | 95912 | Yes | 7541 | 0
D-HPP853 | Pinellas | 2026-10-30 | 44 | Received | Yes | 89669 | Yes | 7072 | 0
D-HPP855 | Pinellas | 2026-10-30 | 110 | Received | Yes | 96644.5 | Yes | 8090 | 0
D-HPP856 | Pinellas | 2026-10-30 | 45 | Received | Yes | 99698.5 | Yes | 8469 | 0
D-HPP857 | Pinellas | 2026-10-30 | 90 | Received | Yes | 111605.5 | Yes | 9260 | 0
D-HPP860 | Pinellas | 2026-10-30 | 95 | Received | Yes | 69986 | Yes | 5310 | 0
D-HPP882 | Pinellas | 2026-10-30 | 64 | Received | Yes | 69701 | Yes | 5357 | 0
D-HPP883 | Pinellas | 2026-10-30 | 90 | Received | Yes | 92174.5 | Yes | 7153 | 0
D-HPP884 | Pinellas | 2026-10-30 | 72 | Received | Yes | 105926.5 | Yes | 8767 | 0
FB-HLC521 | Pinellas | 2026-10-30 | 0 | Received | Yes | 2524 | Yes | 184 | 0
FB-HLC524 | Pinellas | 2026-10-30 | 0 | Received | Yes | 16946.9 | Yes | 1294 | 0
FB-HLC538 | Pinellas | 2026-11-27 | 0 | Received | Yes | 41225.6 | Yes | 3216 | 0
FB-HPP854 | Pinellas | 2026-10-30 | 0 | Received | Yes | 77452.2 | Yes | 6142 | 0
Market 2 NTP Number | AREA | SOW TSD Date | HHP | Permit Status | SOW Received | SOW Estimated Cost | NTP Received | Footage UG | Splicing Percentage Complete
FB-HWP376 | Lakeland | 2025-12-15 | 0 | Received | Yes | 54857.5 | Yes | 4104 | 0
FB-HWP881 | Lakeland | 2026-04-30 | 0 | Received | Yes | 255.05 | Yes | 3 | 0
Market 3 NTP Number | AREA | SOW TSD Date | HHP | Permit Status | SOW Received | SOW Estimated Cost | NTP Received | Footage UG | Splicing Percentage Complete
D-HLX101 | Bradenton | 2026-11-18 | 75 | Received | Yes | 73339.6 | Yes | 5791 | 0
D-HLX102 | Bradenton | 2026-11-18 | 75 | Received | No | 0 | Yes | 5465 | 0
D-HLX103 | Bradenton | 2026-11-18 | 86 | Received | No | 0 | Yes | 5520 | 0
D-HLX104 | Bradenton | 2026-11-18 | 83 | Received | No | 0 | Yes | 6204 | 0
D-HLX105 | Bradenton | 2026-11-18 | 36 | Received | No | 0 | Yes | 3700 | 0
D-HLX106 | Bradenton | 2026-11-18 | 67 | Received | No | 0 | Yes | 5013 | 0
D-HLX107 | Bradenton | 2026-11-18 | 47 | Received | No | 0 | Yes | 4414 | 0
D-HLX108 | Bradenton | 2026-11-18 | 69 | Received | Yes | 65485.9 | Yes | 4613 | 0
FB-HOE179 | Bradenton | 2026-01-18 | 0 | Received | Yes | 18171.6 | Yes | 1514 | 0
FB-HLX101 | Bradenton | 2026-11-18 | 0 | Received | Yes | 21152.35 | Yes | 1469 | 0
Plantation Bay - 4 | Bradenton | 2026-07-30 | 88 | Not Required | Yes | 101036.5 | Yes | 9133 | 1
BHCD-FPW-03-E | Fort Myers | 2026-07-30 | 0 | Received | Yes | 43061.3 | Yes | 11789 | 0
D-HDF708 | Fort Myers | 2026-02-28 | 88 | Pending | Yes | 79638 | Yes | 6613 | 0
D-HDF709 | Fort Myers | 2026-11-18 | 80 | Received | Yes | 71500 | Yes | 5625 | 0
D-HDF712 | Fort Myers | 2026-02-28 | 86 | Pending | Yes | 97494 | Yes | 8265 | 0
D-HDF717 | Fort Myers | 2026-10-30 | 86 | Received | Yes | 83702 | Yes | 6907 | 0
D-HDF740 | Fort Myers | 2026-05-29 | 26 | Pending | Yes | 35576 | Yes | 3150 | 0
D-HPW326 | Fort Myers | 2026-09-30 | 81 | Received | Yes | 77302 | Yes | 6384 | 0
D-HPW327 | Fort Myers | 2026-09-30 | 85 | Received | Yes | 78787 | Yes | 6242 | 0
D-HPW328 | Fort Myers | 2026-09-30 | 84 | Received | Yes | 45941.5 | Yes | 3794 | 0
D-HPW329 | Fort Myers | 2026-09-30 | 71 | Received | Yes | 71012.5 | Yes | 5739 | 0
D-HPW330 | Fort Myers | 2026-09-30 | 80 | Received | Yes | 78742 | Yes | 6179 | 0
D-HPW349 | Fort Myers | 2026-08-26 | 80 | Received | Yes | 77657.7 | Yes | 6243 | 0
D-HPW350 | Fort Myers | 2026-09-30 | 76 | Received | Yes | 88272 | Yes | 7206 | 0
D-HPW351 | Fort Myers | 2026-09-30 | 83 | Received | Yes | 57368 | Yes | 4517 | 0
D-HPW361 | Fort Myers | 2026-07-26 | 82 | Received | Yes | 85513 | Yes | 6678 | 0
D-HTG211 | Fort Myers | 2026-11-18 | 68 | Received | No | 76637.05 | Yes | 6224 | 0
D-HTG212 | Fort Myers | 2026-08-30 | 85 | Received | Yes | 64416.5 | Yes | 5445 | 0
D-HTG213 | Fort Myers | 2026-09-30 | 46 | Received | Yes | 54627.5 | Yes | 4834 | 0
D-HTG214 | Fort Myers | 2026-09-30 | 82 | Received | Yes | 77688.5 | Yes | 6136 | 0
D-HTG231 | Fort Myers | 2026-08-30 | 90 | Received | Yes | 90888 | Yes | 7881 | 0
D-HTG242 | Fort Myers | 2026-12-30 | 66 | Received | Yes | 38841 | Yes | 3106 | 0
D-HTG307 | Fort Myers | 2026-06-30 | 62 | Received | Yes | 48766 | Yes | 4009 | 0
FB-HTG285 | Fort Myers | 2026-10-30 | 0 | Received | Yes | 1721.7 | Yes | 79 | 0
FB-HTG288 | Fort Myers | 2026-06-30 | 0 | Received | Yes | 75219.2 | Yes | 5902 | 0
FB-HTG302 | Fort Myers | 2026-10-30 | 0 | Received | Yes | 1549.65 | Yes | 82 | 0
Promenades At The Forum | Fort Myers | 2026-05-30 | 402 | Not Required | Yes | 438978.5 | Yes | 30807 | 0
D-HSF401 | Port Charlotte | 2026-09-30 | 79 | Received | Yes | 75443.75 | Yes | 5953 | 0
D-HSF420 | Port Charlotte | 2026-09-30 | 49 | Received | Yes | 58273.5 | No | 4709 | 0
FB-HSF606 | Port Charlotte | 2026-03-30 | 0 | Pending | No | 0 | No | 0 | 0
FB-HSF675 | Port Charlotte | 2026-03-30 | 0 | Pending | No | 0 | No | 0 | 0
Market 4 NTP Number | AREA | SOW TSD Date | HHP | Permit Status | SOW Received | SOW Estimated Cost | NTP Received | Footage UG | Splicing Percentage Complete
D-HEF115 | Lee | 2026-11-18 | 74 | Received | No | 42924 | Yes | 3159 | 0
D-HEF116 | Lee | 2026-11-18 | 87 | Received | No | 73538 | Yes | 5678 | 0
D-HLP401 | Collier | 0 | 85 | Pending | No | 0 | No | 14927 | 0
D-HLP403 | Collier | 0 | 87 | Pending | No | 0 | No | 15088 | 0
D-HLP404 | Collier | 2026-09-18 | 87 | Received | Yes | 0 | Yes | 17114 | 0
D-HLP405 | Collier | 0 | 76 | Pending | No | 0 | No | 0 | 0
D-HLP406 | Collier | 0 | 86 | Pending | No | 0 | No | 14639 | 0
D-HLP601 | Collier | 0 | 83 | Pending | No | 0 | No | 5731 | 0
D-HLP603 | Collier | 0 | 84 | Pending | No | 0 | No | 6590 | 0
D-HLP604 | Collier | 0 | 87 | Pending | No | 0 | No | 6765 | 0
D-HLP605 | Collier | 0 | 79 | Pending | No | 0 | No | 5974 | 0
D-HLP606 | Collier | 0 | 82 | Pending | No | 0 | No | 5120 | 0
D-HLP607 | Collier | 2026-10-15 | 73 | Pending | Yes | 0 | Yes | 4585 | 0
D-HLP608 | Collier | 2026-10-15 | 66 | Received | Yes | 66448 | Yes | 5404 | 0
D-HLP609 | Collier | 0 | 80 | Pending | No | 0 | No | 5133 | 0
D-HPW301 | Lee | 2026-09-20 | 80 | Pending | Yes | 0 | Yes | 6429 | 0
D-HPW302 | Lee | 2026-10-27 | 77 | Pending | Yes | 0 | Yes | 6460 | 0
D-HPW324 | Lee | 2026-09-21 | 80 | Received | Yes | 0 | Yes | 6850 | 0
D-HPW339 | Lee | 2026-08-21 | 83 | Received | Yes | 0 | Yes | 6528 | 0
D-HPW341 | Lee | 2026-10-09 | 78 | Received | Yes | 0 | Yes | 6620 | 0
D-HPW342 | Lee | 0 | 0 | Pending | No | 0 | No | 7133 | 0
D-HPW344 | Lee | 2026-10-27 | 66 | Pending | Yes | 0 | Yes | 5191 | 0
D-HPW347 | Lee | 2026-10-27 | 70 | Received | Yes | 64762 | Yes | 5148 | 0
D-HTG220 | Lee | 2026-10-27 | 70 | Pending | Yes | 0 | Yes | 6468 | 0
D-HTG222 | Lee | 2026-10-09 | 78 | Pending | Yes | 0 | Yes | 6730 | 0
D-HTG223 | Lee | 2026-10-09 | 52 | Pending | Yes | 0 | Yes | 4785 | 0
D-HTG301 | Lee | 2026-10-15 | 81 | Received | Yes | 0 | Yes | 5811 | 0
D-HTG302 | Lee | 2026-10-27 | 72 | Pending | Yes | 0 | Yes | 5222 | 0
D-HTG303 | Lee | 0 | 0 | Pending | No | 0 | No | 6038 | 0
D-HTG304 | Lee | 2026-11-18 | 71 | Received | Yes | 83654 | Yes | 7094 | 0
D-HTG306 | Lee | 2026-10-15 | 29 | Received | Yes | 0 | Yes | 3727 | 0
D-HTG311 | Lee | 0 | 0 | Pending | No | 0 | No | 1750 | 0
D-HTG312 | Lee | 0 | 0 | Pending | No | 0 | No | 2069 | 0
D-HTG401 | Lee | 2026-09-21 | 72 | Received | Yes | 0 | Yes | 5521 | 0
D-HTG404 | Lee | 0 | 0 | Pending | No | 0 | No | 5990 | 0
D-HTG405 | Lee | 2026-10-27 | 25 | Pending | Yes | 0 | Yes | 3802 | 0
D-HTG406 | Lee | 2026-11-11 | 75 | Pending | Yes | 0 | Yes | 3452 | 0
D-HTG407 | Lee | 2026-10-27 | 77 | Pending | Yes | 0 | Yes | 6848 | 0
D-HTG408 | Lee | 0 | 0 | Pending | No | 0 | No | 1875 | 0
D-HTG409 | Lee | 0 | 0 | Pending | No | 0 | No | 2961 | 0
D-HTG410 | Lee | 0 | 0 | Pending | No | 0 | No | 1205 | 0
D-HTG411 | Lee | 0 | 0 | Pending | No | 0 | No | 3714 | 0
FB-HLP410 | Collier | 2026-10-15 | 0 | Pending | Yes | 0 | Yes | 15253 | 0
FB-HLP602 | Collier | 2026-09-25 | 0 | Pending | Yes | 0 | Yes | 3064 | 0
FB-HLP607 | Collier | 0 | 0 | Pending | No | 0 | No | 927 | 0
FB-HLP610 | Collier | 0 | 0 | Pending | No | 0 | No | 3803 | 0
FB-HPW303 | Lee | 0 | 0 | Pending | No | 0 | No | 5111 | 0
FB-HTG301 | Lee | 2026-10-27 | 0 | Pending | Yes | 0 | Yes | 773 | 0
FB-HTG309 | Lee | 2026-11-11 | 0 | Pending | Yes | 0 | Yes | 708 | 0
FB-HTG316 | Lee | 0 | 0 | Pending | Yes | 0 | Yes | 610 | 0
FB-HTG318 | Lee | 2026-10-20 | 0 | Pending | Yes | 0 | Yes | 1352 | 0
FB-HTG413 | Lee | 2026-10-15 | 0 | Pending | Yes | 0 | Yes | 1379 | 0
Market 7 NTP Number | AREA | SOW TSD Date | HHP | Permit Status | SOW Received | SOW Estimated Cost | NTP Received | Footage UG | Splicing Percentage Complete
BHT-FSE-01 | Kissimmee | 2026-10-31 | 0 | Received | Yes | 75444.55 | Yes | 5936 | 0
D-HSW401 | Kissimmee | 2026-10-23 | 60 | Received | Yes | 82732 | Yes | 7117 | 0
D-HSW402 | Kissimmee | 2026-10-23 | 83 | Received | Yes | 110980 | Yes | 9590 | 0
D-HSW403 | Kissimmee | 2026-10-23 | 84 | Received | Yes | 108948 | Yes | 9329 | 0
D-HSW404 | Kissimmee | 2026-10-23 | 89 | Received | Yes | 116114 | Yes | 9709 | 0
D-HSW405 | Kissimmee | 2026-10-23 | 79 | Received | Yes | 108665 | Yes | 9263 | 0
D-HSW406 | Kissimmee | 2026-10-23 | 87 | Received | Yes | 120731 | Yes | 10385 | 0
D-HSW407 | Kissimmee | 2026-11-25 | 86 | Received | Yes | 111864 | Yes | 9398 | 0
D-HSW408 | Kissimmee | 2026-11-25 | 63 | Pending | Yes | 88533.5 | Yes | 7517 | 0
D-HSW409 | Kissimmee | 2026-12-23 | 78 | Received | Yes | 75143.5 | Yes | 5920 | 0
D-HSW410 | Kissimmee | 2027-04-10 | 60 | Pending | Yes | 66890 | Yes | 5589 | 0
D-HSW411 | Kissimmee | 2026-10-15 | 60 | Pending | Yes | 65974 | Yes | 5515 | 0
D-HSW412 | Kissimmee | 2027-04-15 | 62 | Pending | Yes | 63989.5 | Yes | 5191 | 0
D-HSW413 | Kissimmee | 2027-04-10 | 60 | Pending | Yes | 67355.5 | Yes | 5620 | 0
D-HSW414 | Kissimmee | 2026-12-23 | 86 | Pending | Yes | 86438.5 | Yes | 6864 | 0
D-HSW415 | Kissimmee | 2027-04-10 | 89 | Pending | Yes | 88748.5 | Yes | 6461 | 0
D-HSW416 | Kissimmee | 2026-11-25 | 25 | Pending | Yes | 33288 | Yes | 2790 | 0
D-HSW417 | Kissimmee | 2026-11-25 | 79 | Pending | Yes | 89875.5 | Yes | 7368 | 0
D-HSW418 | Kissimmee | 2026-10-23 | 84 | Pending | Yes | 95052.5 | Yes | 7844 | 0
D-HSW419 | Kissimmee | 2026-10-23 | 88 | Received | Yes | 102476 | Yes | 8148 | 0
D-HSW420 | Kissimmee | 2026-10-23 | 60 | Received | Yes | 80344 | Yes | 6829 | 0
D-HSW421 | Kissimmee | 2026-10-23 | 61 | Pending | Yes | 73166 | Yes | 6157 | 0
D-HSW422 | Kissimmee | 2026-10-23 | 89 | Pending | Yes | 114642 | Yes | 9537 | 0
D-HSW423 | Kissimmee | 2027-01-28 | 87 | Pending | Yes | 85589.5 | Yes | 6796 | 0
D-HSW424 | Kissimmee | 2027-01-28 | 76 | Pending | Yes | 76640 | Yes | 6149 | 0
D-HSW425 | Kissimmee | 2026-12-11 | 89 | Pending | Yes | 80780 | Yes | 6284 | 0
D-HSW426 | Kissimmee | 2026-12-11 | 85 | Pending | Yes | 95244 | Yes | 7743 | 0
D-HSW427 | Kissimmee | 2027-01-28 | 87 | Pending | Yes | 86888 | Yes | 6932 | 0
D-HSW428 | Kissimmee | 2027-04-10 | 87 | Pending | Yes | 75700 | Yes | 6213 | 0
D-HSW429 | Kissimmee | 2027-04-10 | 52 | Pending | Yes | 53698 | Yes | 4339 | 0
D-HSW430 | Kissimmee | 2027-04-10 | 48 | Pending | Yes | 48883 | Yes | 3940 | 0
D-HSW431 | Kissimmee | 2026-12-23 | 88 | Pending | Yes | 83382 | Yes | 6855 | 0
D-HSW432 | Kissimmee | 2027-01-28 | 90 | Pending | Yes | 88834 | Yes | 7147 | 0
D-HSW433 | Kissimmee | 2027-04-10 | 83 | Pending | Yes | 81027.5 | Yes | 6376 | 0
D-HSW434 | Kissimmee | 2027-01-28 | 63 | Pending | Yes | 60264 | Yes | 4784 | 0
D-HSW435 | Kissimmee | 2026-12-11 | 86 | Pending | Yes | 81096 | Yes | 6387 | 0
D-HSW436 | Kissimmee | 2026-12-11 | 81 | Pending | Yes | 79796 | Yes | 6372 | 0
D-HSW437 | Kissimmee | 2026-12-23 | 77 | Pending | Yes | 69082 | Yes | 5363 | 0
D-HSW438 | Kissimmee | 2026-12-23 | 67 | Pending | Yes | 65448 | Yes | 5199 | 0
D-HSW439 | Kissimmee | 2026-12-23 | 90 | Pending | Yes | 116020.5 | Yes | 9771 | 0
D-HSW440 | Kissimmee | 2026-12-23 | 90 | Pending | Yes | 114306 | Yes | 9562 | 0
D-HSW441 | Kissimmee | 2026-11-25 | 87 | Pending | Yes | 80784 | Yes | 6309 | 0
D-HSW442 | Kissimmee | 2026-12-23 | 90 | Pending | Yes | 125540.85 | Yes | 10260 | 0
D-HSW443 | Kissimmee | 2027-04-10 | 89 | Pending | Yes | 119327 | Yes | 10080 | 0
D-HSW444 | Kissimmee | 2026-11-14 | 76 | Pending | Yes | 85720 | Yes | 6859 | 0
D-HSW445 | Kissimmee | 2026-11-14 | 84 | Pending | Yes | 75682 | Yes | 5873 | 0
D-HSW446 | Kissimmee | 2026-11-14 | 55 | Pending | Yes | 60784 | Yes | 4945 | 0
D-HSW447 | Kissimmee | 2026-12-11 | 54 | Pending | Yes | 52670 | Yes | 4275 | 0
D-HSW448 | Kissimmee | 2026-12-23 | 88 | Received | Yes | 86455.5 | No | 6378 | 0
FB-HSW406 | Kissimmee | 2026-10-23 | 0 | Received | Yes | 94474.5 | No | 7373 | 0
FB-HSW416 | Kissimmee | 2026-10-23 | 0 | Pending | Yes | 74145.85 | Yes | 5781 | 0
FB-HSW417 | Kissimmee | 2026-10-23 | 0 | Received | No | 0 | No | 9051 | 0
FB-HSW425 | Kissimmee | 2026-12-11 | 0 | Received | Yes | 126441.9 | Yes | 9638 | 0
FB-HSW443 | Kissimmee | 2026-10-23 | 0 | Received | Yes | 111398.8 | Yes | 8746 | 0
Market 10 NTP Number | AREA | SOW TSD Date | HHP | Permit Status | SOW Received | SOW Estimated Cost | NTP Received | Footage UG | Splicing Percentage Complete
D-HBR261 | Miami | 2026-12-31 | 81 | Received | Yes | 105892.05 | Yes | 8711 | 1
D-HBR262 | Miami | 2026-12-31 | 79 | Received | Yes | 88420 | Yes | 7502 | 0

## COP Pivot
Assigned Supervisor | NTP Number | Friday 09/25 updates | Max of Construction End Date | Sum of SOW Estimated Cost | 10/9/2026 Updates
Anthony Adum | D-HPP621 | QC Passed. working on this one | 2026-07-01 | 72668.5 | Pending pressure test from BP
| D-HPP629 | Bore logs sent. needs review. | 2026-08-17 | 91700 | Reconciling pics
| D-HLC506 | QC passed today. Working on this one | 2026-09-02 | 63582 | Reconciling pics
| FB-HLC512 | Passed QC. Working on COP | 2026-09-09 | 71505.7 | To be worked on as prior COPs are comp
| D-HLC519 | Gig list sent to contractor. | 2026-09-10 | 84001.5 | Chris Tingle to QC
| FB-HPP612 | Phase 1 vaults are being set | 2026-09-18 | 66431.7 | Not CX comp, pending vaults
| D-HLC512 | (blank) | 2026-09-25 | 86106.8 | To be worked on as prior COPs are comp
| D-HPP858 | (blank) | 2026-09-28 | 73595.5 | Chris Tingle to QC
| FB-HPP879 | (blank) | 2026-10-01 | 73440.1 | Not CX comp, pending vaults
| FB-HPP631 | (blank) | 2026-10-02 | 65477.3 | To be worked on as prior COPs are comp
| D-HPP854 | (blank) | 2026-10-09 | 78625.9
Anthony Adum Total |  |  | 2026-10-09 | 827135 | QC Complete, Pending production entry
Brenton Copelin | D-HAL114 | QC turned in and start COP & Change order needed | 2026-08-27 | 42744 | QC Complete, submitting Phase 1 and 2 10-9-2026
| D-HLX503 | Change order needed. Holding up billing | 2026-08-06 | 60062 | QC Complete, turning in last billing 10-9-2026 and then submitting Phase 1 and 2 10-12-2026
| D-HLX505 | Change order needed. Holding up billing | 2026-08-07 | 64040 | Phase 1 QC Complete, pending bore logs, scheduling Phase 2 QC 10-12-2026
| FB-HLX175 | Change order needed, fiber splicing complete. needs that added to SOW | 2026-08-20 | 36166.65 | Submitting Phase 1 and partial for Phase 2 10-9-2026
| FB-HOE401-V6 | QC complete phase 1 & Phase 2. Need change order | 2026-08-17 | 3232.9 | QC Complete, Pending production entry
| D-HAL116 | Needs change order. | 2026-09-16 | 52593.6 | QC Complete, Pending production entry
| D-HAL113 | Needs change order. | 2026-09-24 | 52728 | Not ready for QC. This still needs vault set, FDH, Swing Arm, and conduits proofed.
| D-HSF419 | Just started. Not ready for QC | 2026-09-22 | 62657
| D-HSF402 | (blank) | 2026-10-07 | 72242 | complete for phase 1 and 2. Waiting till cabinet is official hot before turning over phase 2 COP
Brenton Copelin Total |  |  | 2026-10-07 | 446466.15 | COP submit on 10/16
Cody | BHUD-FOE-401-W | Needs to be scheduled for QC | 2026-08-19 | 18856.2 | COP submit on 10/17
| D-HLX421 | GN Systems. Need bore logs. John has been in touch | 2026-05-07 | 23501
| FB-HLR201 | Still needed an in house inspector to complete bore logs | 2026-02-09 | 144972.5
Cody Total |  |  | 2026-08-19 | 187329.7 | Will be uploaded by Friday next week
Efrian | D-HBR252 | COP is ready | 2026-06-02 | 51528.05
| D-HBR256 | COP is ready | 2026-07-06 | 99925.7 | we are fixing what failed in the phase 1 QC
Efrian Total |  |  | 2026-07-06 | 151453.75 | Will be uploaded by Friday next week
Jose | FB-HBR252 | QC failed | 2026-08-13 | 50239.7 | QC will be scheduled next week
| D-HBR257 | Not started | 2026-07-29 | 108458.4 | QC failed we are working on getting it fixed asap
| D-HBR258 | Not started | 2026-08-28 | 70105.25 | Tillman let us know this week that we were using the wrong design maps after we had finished the project
| D-HBR260 | Not started | 2026-09-10 | 91411.65
| D-HBR259 | (blank) | 2026-09-30 | 78047.35 | By next friday
Jose Total |  |  | 2026-09-30 | 398262.35 | QC Fail
Joshua | FB-HPW331 | (blank) | 2026-10-09 | 25174.45 | QC Failed
Joshua Total |  |  | 2026-10-09 | 25174.45 | Missing Tobys then schedule for QC
Joshua Pacheco | D-HPP310 | Actualized. Will submit 10/2 | 2026-07-23 | 78994.5
| D-HPP311 | Actualized. Will submit 10/2 | 2026-08-20 | 62709 | This is Anthony Adum
| FB-HPP314 | Actualized. Will submit 10/2 | 2026-08-05 | 419 | Looking into final Footage walkout
| D-HPP303 | Actualized. Will submit 10/2 | 2026-08-28 | 98498 | Checking on Final Footage
Joshua Pacheco Total |  |  | 2026-08-28 | 240620.5 | Working on COP
Marcelo Zaldivar | D-HPP627 | Waiting on inspector to give final walk out footages | 2026-08-17 | 94688.5 | COP sent in
| D-HPP628 | 0 | 2026-07-15 | 97700
| D-HPP636 | 0 | 2026-08-14 | 97386.5
| D-HPP639 | Starting on the COP | 2026-07-30 | 106600
| D-HPP626 | (blank) | 2026-09-25 | 95477
Marcelo Zaldivar Total |  |  | 2026-09-25 | 491852
Matthew Nunes | D-HPP305 | Actualized. Will submit 10/2 | 2026-08-04 | 77365.5
| D-HPP314 | Actualized. Will submit 10/2 | 2026-08-12 | 99986.2
| FB-HLC519 | Actualized. Will submit 10/2 | 2026-09-09 | 25127.05
| D-HLC517 | (blank) | 2026-09-25 | 79947 | Finishing Hand Holes then working on COP
| D-HLC513 | (blank) | 2026-09-08 | 79458 | Finishing Hand Holes then working on COP
| D-HLC518 | (blank) | 2026-10-01 | 74446.5
Matthew Nunes Total |  |  | 2026-10-01 | 436330.25 | Still working on COP
Miguel | BHC-FSW-04-E | (blank) | 2026-10-06 | 68022.75 | Still working on COP
| FB-HSW419 | (blank) | 2026-10-06 | 9232.4 | Still working on COP
Miguel Total |  |  | 2026-10-06 | 77255.15 | Still working on COP
Treyvon Tillman | D-HPP607 | Passed QC. COP next week | 2026-07-08 | 71754.5
| D-HPP625 | Passed QC. COP next week | 2026-07-01 | 96607
| D-HPP638 | Pending QC | 2026-08-20 | 81059.5
| D-HLC511 | (blank) | 2026-09-28 | 72479.5 | Will be complete by end of day. Pending Verifacation
Treyvon Tillman Total |  |  | 2026-09-28 | 321900.5 | Will be complete by end of day. Pending Verifacation
Joshua Wheatcroft | BHCD-FPW-03-W | Not started | 2026-04-24 | 146065.95
| Colonial Pointe | Not started | 2026-07-24 | 60744.4
| D-HDF707 | Asbuilt done, needs BOM | 2025-12-31 | 65843.5 | Finished the Asbuilt. Still need bore logs
| D-HDF713 | Pictures of DAPS needed | 2025-11-21 | 90786
| D-HSF308 | working on change orders | 2026-07-31 | 62074
| D-HSF320 | Pending bore logs from lopez | 2026-06-03 | 73533
| D-HSF322 | Pending bore logs from lopez | 2026-08-24 | 81150
| D-HTG206 | Asbuilt complete. Pending phase 1 email | 2026-05-21 | 70666
| D-HTG207 | Started Asbuilt | 2026-06-12 | 72914
| D-HTG216 | Missing Bore logs Lopez | 2026-08-12 | 80274
| D-HTG225 | Not started | 2026-07-16 | 72896
| D-HTG228 | Missing Bore logs Lopez | 2026-07-16 | 70151.5
| D-HTG235 | Missing Bore logs Lopez | 2026-07-10 | 68762
| D-HTG237 | Not started | 2026-06-23 | 55504
| D-HTG239 | Missing Bore logs Lopez | 2026-06-12 | 64590 | As-Built Complete
| D-HTG241 | Not started | 2026-06-22 | 27694
| FB-HTG204 | Not started | 2026-07-21 | 35456.55
| FB-HTG289 | Not started | 2026-07-22 | 31327.7
| FB-HTG290 | Not started | 2026-07-08 | 27837.25 | As-Built Complete
| FB-HTG292 | Not started | 2026-08-05 | 21849.3
| D-HTG201 | Working On asbuilt | 2026-07-01 | 56455
| D-HTG218 | Waiting on Bore logs from Lopez | 2026-08-28 | 50669
| D-HTG229 | Pending Bore logs from Lopez & asbuilt | 2026-08-28 | 65362
| D-HTG233 | Walked out. Need to update asbuilt | 2026-08-28 | 91537.75 | As-Built Complete
| D-HTG238 | Pending asbuilt | 2026-08-28 | 70534.5
| FB-HSF304 | change orders needed | 2026-08-28 | 33518.7
| FB-HTG279 | Pending Phase 2. pulling fiber today | 2026-09-08 | 17689.15
| FB-HTG238 | Just completed. Need to pull fiber | 2026-09-16 | 72557.35
| D-HTG305 | Just completed | 2026-09-17 | 50042
| D-HPW348 | Just completed | 2026-09-21 | 78322 | 10.9 No Email will check SiteTracker
| D-HPW346 | (blank) | 2026-10-02 | 93910.15 | 10.9 Not Started
| D-HTG210 | (blank) | 2026-10-07 | 68598 | 10.9 Will actualize for Monday
Joshua Wheatcroft Total |  |  | 2026-10-07 | 2029314.75 | 10.9 Email send to sub, failed Internal
Johnnie Williams2 | BHU-FLX-01-E | Passed QC. Pending email | 2026-05-08 | 49846.95 | 10.9 Email send to sub, failed Internal
| D-HPP613 | Not started | 2026-07-08 | 100208 | 10.9 Will actualize for Tuesday
| D-HPP614 | Re walk has not been set | 2026-07-28 | 101920.5 | 10.9 In field today to get photos
| D-HPP633 | Internal QC 9/28 | 2026-07-31 | 99590 | 10.9 Hot Mess, still trying to get all photos / may need to visit site
| D-HPP634 | Internal QC 9/29 | 2026-08-05 | 103644.5 | 10.9 Confirmed today, project is not complete
| D-HPP635 | Internal QC 9/30 | 2026-08-12 | 106431.5 | 10.9 Just Complete / Not started COP
| FB-HNP133 | Missing Photos | 2025-11-07 | 23800.25
| Vantage Point Condominiums | In progress | 0 | 117414 | Treyvon
| FB-HPP375 | (blank) | 2026-09-28 | 24396.5
| D-HLC539 | (blank) | 2026-10-05 | 88399.4 | Pending QC
Johnnie Williams2 Total |  |  | 2026-10-05 | 815651.6
Robert Portee | D-HPP608 | (blank) | 2026-09-18 | 94021.5
Robert Portee Total |  |  | 2026-09-18 | 94021.5
Danny Combs | D-HLC507 | (blank) | 2026-10-02 | 78078
Danny Combs Total |  |  | 2026-10-02 | 78078
Grand Total |  |  | 2026-10-09 | 6620845.65

## EOS Tracker
DATE | SUB/TECH | SUPV | PROJECT NAME | FOOTAGE | STATUS | Ticket # | Ticket Status | Notes
2026-08-25 | Rocky Meek | Joshua Wheatcroft | BHCD-FPW-03-W | 150 | Pending Production |  | Not Created | 10/7 - sent email to John Kraus 9/30 Billing is not in Fuse. 10-6-26 No billiing for Rocky. Job was off the running line and had to be redone after quit. All Production to Lopez Underground.
2026-08-26 | Jordan Johnson | Joshua Wheatcroft | FB-HTG279 | 456 | Pending Production |  | Not Created | 10/7 not in Penguin not in Fuse - sent email to Josh W / John Kraus
2026-08-27 | NorthPath | Brenton Copelin | D-HAL114 | 704 | Pending Production |  | Not Created | 9/30 - No billing in Fuse
2026-08-28 | Lopez UG | Joshua Wheatcroft | D-HTG229 | 288 | Pending Production | 1629600 | Customer | 10/7 Pending bore log to approve 288' - Emailed Josh W
2026-08-28 | Lopez UG | Joshua Wheatcroft | D-HTG233 | 288 | Pending Production | 1629629 | Customer | 10/7 Pending bore log to approve 296' - Emailed Josh W
2026-08-28 | Lopez UG | Joshua Wheatcroft | D-HTG238 | 89 | Pending Production | 1629632 | Customer | 10/7 Pending bore log to approve 89' - Emailed Josh W
2026-08-28 | Rocky Meek | Joshua Wheatcroft | D-HTG238 | 503 | Pending Production |  | Not Created | 9/28 No billing in Fuse 9/24 sent email to Josh W
2026-08-28 | Jordan Johnson | Joshua Wheatcroft | D-HTG238 | 149 | Pending Production |  | Not Created | 9/28 No billing in Fuse 9/24 sent email to Josh W
2026-08-31 | Bicom | Yasmina Jerez | D-HBR260 | 840 | Pending Production |  | Not Created | 9/30 no billing in Fuse
2026-08-31 | Felipe | Robert Portee | D-HPP608 | 215 | Pending Production |  |  | 9/30 Felipe is not in Fuse for this amount or date
2026-08-31 | North Path | Cody Johns | D-HAL115 | 1173 | Pending Production | 1614192 | Closed | 9/28 Billing on redline adds up to 823. ALL FOOTAGE BILLED ON 1 INVOICE. COP PHASE 1 SUBMITTED
2026-08-31 | Yosep | Jose Espinosa | D-HBR259 | 25 | Pending Production |  |  | 9/28 no billing in Fuse will have to ask for a change order SOW covers what is in Penguin Sent to Jose
2026-08-31 | Yosep | Jose Espinosa | D-HBR260 | 840 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-01 | Felipe | Robert Portee | D-HPP608 | 38 | Pending Production |  |  | 9/30 Felipe is not in Fuse for this amount or date
2026-09-01 | Rocky Meek | Joshua Wheatcroft | D-HTG305 | 503 | Pending Production |  | Not Created | 9/28 No billing in Fuse 5164 is on SOW and there are 9 lines of this job # on this spreadsheet that total 6125 a change order will be needed Sent to Jose
2026-09-01 | Jordan Johnson | Joshua Wheatcroft | D-HTG305 | 149 | Pending Production |  | Not Created | 9/28 No billing in Fuse 5164 is on SOW and there are 9 lines of this job # on this spreadsheet that total 6125 a change order will be needed Sent to Jose
2026-09-01 | Restoring Pro | Joshua Wheatcroft | D-HTG231 | 746 | Pending Production | 1621652 | Closed | 10/7 4232' was billed to Restoring pro on 10/2
2026-09-01 | Yosep | Jose Espinosa | D-HBR256 | 3380 | Pending Production |  |  | 9/28 No billing in Fuse sent to Jose will need a change order - Jose responded he is working on
2026-09-01 | Yosep | Jose Espinosa | D-HBR259 | 15 | Pending Production |  |  | 9/28 no billing in Fuse will have to ask for a change order SOW covers what is in Penguin Sent to Jose
2026-09-02 | Power Connect | Johnnie Williams | D-HLC513 | 468 | Pending Production | 1636334 | Closed | 9/30 no billing for this date in Fuse on redline - johnnie is going back through the redline and get everything input in Fuse
2026-09-02 | Steve Wolfe | Treyvon Tillman | D-HPP638 | 165 | Pending Production |  |  | 9/30 no billiing in Fuse, no TCBDB2 to bill needs change order - Treyvon states this job has not been walked out yet
2026-09-02 | Yosep | Jose Espinosa | D-HBR260 | 851 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-02 | Rocky Meek | Joshua Wheatcroft | D-HTG305 | 433 | Pending Production |  | Not Created | 9/28 No billing in Fuse
2026-09-02 | Jordan Johnson | Joshua Wheatcroft | D-HTG305 | 450 | Pending Production |  | Not Created | 9/28 No billing in Fuse
2026-09-02 | Lopez | Joshua Wheatcroft | BHCD-FPW-03-E | 1550 | Pending Production | 1629637 | Customer | 10/7 Pending bore log to approve 1550' - Emailed Josh W
2026-09-02 | Gulfstream | Joshua Wheatcroft | D-HTG231 | 1093 | Pending Production | 1621652 | Closed | 10/7 4232' was billed to Restoring pro on 10/2
2026-09-02 | Yosep | Jose Espinosa | D-HBR259 | 20 | Pending Production |  |  | 9/28 no billing in Fuse will have to ask for a change order SOW covers what is in Penguin Sent to Jose
2026-09-02 | Gulfstream | Joshua Wheatcroft | D-HTG210 | 776 | Pending Production |  | Not Created | 9/28 No billing in Fuse
2026-09-03 | Felipe | Robert Portee | D-HPP608 | 153 | Pending Production |  |  | 09/28/26 143' reported in Fuse for Felipe
2026-09-03 | North Path | Brenton Copelin | D-HAL116 | 306 | Pending Production |  | Not Created | 9/30 No billing in Fuse for this date
2026-09-03 | Yosep | Yasmina Jerez | D-HBR260 | 499 | Pending Production | 1637242 | Closed | 10/7 - 1637' pending for Yosep on this sheet for D-HBR260, ticket 1637242 was completed for 6046 feet 9/27
2026-09-03 | Rocky Meek | Joshua Wheatcroft | D-HTG305 | 648 | Pending Production |  | Not Created | 9/28 No billing in Fuse
2026-09-03 | Jordan Johnson | Joshua Wheatcroft | D-HTG305 | 198 | Pending Production |  | Not Created | 9/28 No billing in Fuse
2026-09-03 | Restoring Pro | Joshua Wheatcroft | D-HTG231 | 751 | Pending Production | 1621652 | Closed | 10/7 4232' was billed to Restoring pro on 10/2
2026-09-03 | Lopez | Joshua Wheatcroft | D-HPW330 | 483 | Pending Production | 1629516 | Customer | 10/7 Pending bore log to approve 483' - Emailed Josh W
2026-09-03 | Lopez | Joshua Wheatcroft | BHCD-FPW-03-E | 693 | Pending Production | 1629637 | Customer | 10/7 Pending bore log to approve 693' - Emailed Josh W
2026-09-04 | Yosep | Yasmina Jerez | D-HBR260 | 747 | Pending Production | 1637242 | Closed | 10/7 - 1637' pending for Yosep on this sheet for D-HBR260, ticket 1637242 was completed for 6046 feet 9/27
2026-09-04 | North Path | Brenton Copelin | D-HAL116 | 724 | Pending Production |  | Not Created | 9/30 No billing in Fuse for this date
2026-09-04 | Yosep | Yasmina Jerez | D-HBR259 | 5 | Pending Production | 1639003 | Closed | 10/7 - i believe these were covered when 180' was approved for 9/27
2026-09-04 | Restoring Pro | Joshua Wheatcroft | D-HTG231 | 255 | Pending Production | 1621652 | Closed | 10/7 4232' was billed to Restoring pro on 10/2
2026-09-04 | Lopez | Joshua Wheatcroft | D-HPW330 | 639 | Pending Production | 1629516 | Customer | 10/7 Pending bore log to approve 639' - Emailed Josh W
2026-09-08 | North Path | Brenton Copelin | D-HAL116 | 933 | Pending Production |  | Not Created | 9/30 No billing in Fuse for this date
2026-09-08 | Rocky Meek | Joshua Wheatcroft | FB-HTG279 | 146 | Pending Production |  | Not Created | 10/7 No billing in Fuse sent email to Josh W
2026-09-08 | Jordan Johnson | Joshua Wheatcroft | FB-HTG279 | 146 | Pending Production |  | Not Created | 10/7 No billing in Fuse sent email to Josh W
2026-09-09 | Yosep | Jose Espinosa | D-HBR260 | 1037 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-10 | Yosep | Yasmina Jerez | D-HBR260 | 345 | Pending Production | 1637242 | Closed | 10/7 - 1637' pending for Yosep on this sheet for D-HBR260, ticket 1637242 was completed for 6046 feet 9/27
2026-09-10 | Lopez | Joshua Wheatcroft | FB-HTG238 | 137 | Pending Production | 1629642 | Customer | 10/7 Pending bore log to approve 1337' - Emailed Josh W
2026-09-10 | A1 Broadband | Joshua Wheatcroft | D-HPW346 | 481 | Pending Production |  | Not Created | 9/28 No billing in Fuse. 10-7-26 not in PC727 for billing being corrected
2026-09-10 | Yosep | Jose Espinosa | D-HBR259 | 45 | Pending Production |  |  | 9/28 no billing in Fuse will have to ask for a change order SOW covers what is in Penguin Sent to Jose
2026-09-10 | Randys Utliities | Joshua Pacheco | D-HLC515 | 307 | Pending Production |  |  | 10/6 NO BILLING IN FUSE
2026-09-10 | North Path | Brenton Copelin | D-HAL116 | 123 | Pending Production |  | Not Created | 9/30 No billing in Fuse for this date
2026-09-11 | Bicom | Miguel Herrero | D-HSW419 | 755 | Pending Production |  |  | 9/28 - 9/11 in fuse for 530 & 2754 ?
2026-09-11 | Randys Utliities | Joshua Pacheco | D-HLC515 | 605 | Pending Production |  |  | 10/6 NO BILLING IN FUSE
2026-09-11 | Yosep | Jose Espinosa | D-HBR261 | 806 | Pending Production |  |  | 9/30 no billing on this job in Fuse
2026-09-11 | A1 Broadband | Joshua Wheatcroft | D-HPW346 | 322 | Pending Production |  | Not Created | 9/28 No billing in Fuse. 10-7-26 not in PC727 for billing being corrected
2026-09-14 | A1 Broadband | Joshua Wheatcroft | D-HPW346 | 712 | Pending Production |  | Not Created | 9/28 No billing in Fuse. 10-7-26 not in PC727 for billing being corrected
2026-09-14 | North Path | Brenton Copelin | D-HAL116 | 249 | Pending Production |  | Not Created | 9/30 No billing in Fuse for this date
2026-09-14 | Yosep | Yasmina Jerez | D-HBR259 | 20 | Pending Production | 1639003 | Closed | 10/7 - i believe these were covered when 180' was approved for 9/27
2026-09-14 | ASM | Danny Combs | D-HPP507 | 324 | Pending Production |  |  | 9/28 job is not in Fuse
2026-09-14 | Bicom | Miguel Herrero | D-HSW419 | 400 | Pending Production |  |  | 9/28 - 9/11 in fuse for 530 & 2754 ?
2026-09-15 | North Path | Brenton Copelin | D-HAL113 | 716 | Pending Production |  | Not Created | 9/28 No biling in Fuse
2026-09-15 | Bicom | Miguel Herrero | D-HSW419 | 769 | Pending Production |  |  | 9/28 - 9/11 in fuse for 530 & 2754 ?
2026-09-15 | Restoring Pro | Joshua Wheatcroft | D-HTG230 | 661 | Pending Production | 1623028 | Customer | 10/7 Pending bore log to approve 661' (and backup for other codes) - Emailed Josh W
2026-09-15 | Randys Utliities | Joshua Pacheco | D-HLC515 | 727 | Pending Production |  |  | 10/6 NO BILLING IN FUSE
2026-09-15 | Lopez | Joshua Wheatcroft | FB-HTG238 | 857 | Pending Production | 1629642 | Customer | 10/7 Pending bore log to approve 857' - Emailed Josh W
2026-09-15 | A1 Broadband | Joshua Wheatcroft | D-HPW346 | 751 | Pending Production |  | Not Created | 9/28 No billing in Fuse. 10-7-26 not in PC727 for billing being corrected
2026-09-15 | Restoring Pro | Joshua Wheatcroft | D-HTG231 | 1387 | Pending Production | 1621652 | Closed | 10/7 4232' was billed to Restoring pro on 10/2
2026-09-15 | ASM | Danny Combs | D-HLC507 | 454 | Pending Production |  |  | 9/28 - 9/15 billing for 324
2026-09-16 | Bicom | Miguel Herrero | D-HSW419 | 400 | Pending Production |  |  | 9/28 - 9/11 in fuse for 530 & 2754 ?
2026-09-16 | North Path | Brenton Copelin | D-HAL116 | 478 | Pending Production |  | Not Created | 9/30 No billing in Fuse for this date
2026-09-16 | ASM | Danny Combs | D-HLC508 | 423 | Pending Production
2026-09-16 | Randys Utliities | Joshua Pacheco | D-HLC515 | 895 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-16 | Lopez | Joshua Wheatcroft | FB-HTG238 | 337 | Pending Production | 1629642 | Customer | 10/7 Pending bore log to approve 837' - Emailed Josh W
2026-09-16 | Lopez | Joshua Wheatcroft | D-HTG307 | 86 | Pending Production | 1629661 | Customer | 10/7 Pending bore log to approve 86' - Emailed Josh W
2026-09-16 | Lopez | Joshua Wheatcroft | D-HTG305 | 936 | Pending Production | 1629651 | Customer | 10/7 Pending bore log to approve 936' - Emailed Josh W
2026-09-16 | Alpha | Joshua Wheatcroft | FB-HTG290 | 146 | Pending Production | 1626675 | Customer | 10/7 Pending bore log to approve 146' (also need to know if this is TCBDB2 or B4) - Emailed Josh W
2026-09-16 | Yosep | Yasmina Jerez | D-HBR259 | 20 | Pending Production | 1639003 | Closed | 10/7 - i believe these were covered when 180' was approved for 9/27
2026-09-16 | Yosep | Yasmina Jerez | D-HBR261 | 1227 | Pending Production | 1641017 | Closed | Match
2026-09-16 | Jordan Johnson | Brenton Copelin | FB-HOE401-V4 | 218 | Pending Production |  |  | 9/28 no billing in Fuse - there is only qty of 34 left on TCBCB2 to bill ? DO NOT BILL. THIS EOS WAS INCORRECT, EMAIL SENT ON 9-17-26 BY TJ STATING TO DISREGARD EOS
2026-09-16 | Fiber Core | Brenton Copelin | SFU-MNTE-4 | 474 | Pending Production |  | Closed | 10/9 waiting on richard/TJ to answer my email. TJ has been fixing billing to subs on this project. This ticket it complete.
2026-09-17 | Lopez | Joshua Wheatcroft | D-HTG307 | 2001 | Pending Production | 1629661 | Customer | 10/7 Pending bore log to approve 2001' - Emailed Josh W
2026-09-17 | North Path | Brenton Copelin | D-HAL113 | 959 | Pending Production |  | Not Created | 9/28 No biling in Fuse
2026-09-17 | Lopez | Joshua Wheatcroft | D-HTG305 | 124 | Pending Production | 1629651 | Customer | 10/7 Pending bore log to approve 124' - Emailed Josh W
2026-09-17 | ASM | Danny Combs | D-HLC507 | 1451 | Pending Production |  |  | 9/28 - billing for 9/18 X 500, 9/18 X 410, 9/22 X 1747 - 9/16 x 891 I cleared off this sheet already
2026-09-17 | Yosep | Jose Espinosa | D-HBR261 | 1139 | Pending Production |  |  | 9/30 no billing on this job in Fuse
2026-09-17 | Brothers | Anthony Adum | D-HPP854 | 2096 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-18 | North Path | Cody Johns | SFU-MNTE-3 | 840 | Pending Production | 1632563 | Closed | 9/28 billing that is in Fuse has been removed from this spreadsheet
2026-09-18 | Brothers | Anthony Adum | D-HPP854 | 372 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-18 | Lopez | Joshua Wheatcroft | D-HTG305 | 201 | Pending Production | 1629651 | Customer | 10/7 Pending bore log to approve 201' - Emailed Josh W
2026-09-18 | North Path | Brenton Copelin | D-HAL113 | 815 | Pending Production |  | Not Created | 9/28 No biling in Fuse
2026-09-18 | Lopez | Joshua Wheatcroft | D-HTG307 | 379 | Pending Production | 1629661 | Customer | 10/7 Pending bore log to approve 397' - Emailed Josh W
2026-09-18 | ASM | Danny Combs | D-HLC507 | 498 | Pending Production |  |  | 9/28 - billing for 9/18 X 500, 9/18 X 500, 9/22 X 1747 - 9/16 x 891 I cleared off this sheet already
2026-09-18 | Yosep | Jose Espinosa | D-HBR261 | 995 | Pending Production |  |  | 9/30 no billing on this job in Fuse
2026-09-21 | Brothers | Anthony Adum | D-HPP854 | 452 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-21 | North Path | Brenton Copelin | D-HAL113 | 381 | Pending Production |  | Not Created | 9/28 No biling in Fuse
2026-09-21 | Brothers | Anthony Adum | D-HPP858 | 1349 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-21 | ASM | Danny Combs | D-HLC508 | 1550 | Pending Production |  | Closed | 10/7 9/21 x 1462 ?
2026-09-21 | North Path | Cody Johns | SFU-MNTE-3 | 1506 | Pending Production | 1632563 | Closed | 9/28 billing that is in Fuse has been removed from this spreadsheet
2026-09-21 | Lopez | Joshua Wheatcroft | D-HTG307 | 764 | Pending Production | 1629661 | Customer | 10/7 Pending bore log to approve 764' - Emailed Josh W
2026-09-21 | Randys Utilities | Joshua Pacheco | D-HLC515 | 553 | Pending Production |  |  | 10/6 NO BILLING IN FUSE
2026-09-21 | Yosep | Jose Espinosa | D-HBR258 | 365 | Pending Production |  |  | 9/28 Not in Fuse, and there is not TCBDB2 because there is billing in Penguin and it exceeds what was on the SOW.
2026-09-21 | APT | Brenton Copelin | SFU-MNTE-4 | 739 | Pending Production | 1639508 | Closed | 10/9 waiting on richard/TJ to answer my email. TJ has been fixing billing to subs on this project. This ticket it complete.
2026-09-21 | Yosep | Jose Espinosa | D-HBR261 | 654 | Pending Production |  |  | 9/30 no billing on this job in Fuse
2026-09-22 | Randys Utilities | Joshua Pacheco | D-HLC515 | 303 | Pending Production |  |  | 10/6 NO BILLING IN FUSE
2026-09-22 | Brothers | Anthony Adum | D-HPP854 | 432 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-22 | Brothers | Anthony Adum | D-HPP858 | 1694 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-22 | ASM | Danny Combs | D-HLC508 | 1208 | Pending Production |  |  | 9/28 - 9/16 X 896 in fuse ? No other billing in Fuse there are multiple lines on this spreadsheet for this job
2026-09-22 | Alpha Omega | Joshua Wheatcroft | D-HPW348 | 165 | Pending Production |  |  | 10/8 No billing for 9/22 in Fuse all others were cleared
2026-09-22 | Power Connect | Danny Combs | D-HLC507 | 653 | Pending Production |  |  | 10/07 no billing entered for Power Connect
2026-09-22 | Lopez | Joshua Wheatcroft | BHCD-FPW-09-e | 183 | Pending Production | 1629637 | Customer | 10/7 - BHCD-FPW-09-e does not pull up in Sitetracker. Pending bore log to approve 183' on project BHCD-FPW-03-E? Is that the correct project?
2026-09-22 | Yosep | Yasmina Jerez | D-HBR261 | 760 | Pending Production | 1641017 | Closed | Match
2026-09-22 | North Path | Cody Johns | SFU-MNTE-3 | 690 | Pending Production | 1632563 | Closed | 9/28 billing that is in Fuse has been removed from this spreadsheet
2026-09-23 | Brothers | Marcelo Zaldivar | D-HPP626 | 2339 | Pending Production |  |  | 9/28 No billing in Fuse
2026-09-23 | Brothers | Anthony Adum | D-HPP858 | 1580 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-23 | Brothers | Anthony Adum | D-HPP854 | 529 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-23 | ASM | Danny Combs | D-HLC507 | 486 | Pending Production |  |  | 9/29 - billing for 9/21 X 500, 9/18 X 500, 9/22 X 1747 - 9/16 x 891 I cleared off this sheet already
2026-09-23 | North Path | Cody Johns | SFU-MNTE-3 | 1248 | Pending Production | 1632563 | Closed | 9/28 billing that is in Fuse has been removed from this spreadsheet.ALL FOOTAGE BILLED ON 1 INVOICE COP PHASE 1 SUBMITTED Will need deductions
2026-09-23 | GNS | Brenton Copelin | D-HSF420 | 2275 | Pending Production |  | Not Created | 9/28 No billing in Fuse, waiting on bore logs
2026-09-23 | Randys Utilities | Joshua Pacheco | D-HLC515 | 661 | Pending Production |  |  | 10/6 NO BILLING IN FUSE
2026-09-23 | Lopez | Joshua Wheatcroft | D-HPW330 | 521 | Pending Production |  | Not Created | 9/28 No billing in Fuse
2026-09-23 | ASM | Danny Combs | D-HLC508 | 1392 | Pending Production |  | Closed | 10/7 - In Fuse 9/23 X 1501 ?
2026-09-23 | HD Cable | Joshua Wheatcroft | D-HTG213 | 369 | Pending Production |  | Not Created | 9/28 No billing in Fuse
2026-09-23 | A1 Broadband | Joshua Wheatcroft | D-HPW346 | 3368 | Pending Production |  | Not Created | 9/28 No billing in Fuse. 10-7-26 not in PC727 for billing being corrected
2026-09-24 | North Path | Brenton Copelin | D-HAL113 | 495 | Pending Production |  |  | 9/28 No billing in Fuse
2026-09-24 | GN Systems | Brenton Copelin | D-HSF402 | 1971 | Pending Production | 1645306 | Closed | Match. The billing is correct and covers all these EOS.
2026-09-24 | ASM | Matthew Nunes | D-HLC517 | 1679 | Pending Production |  |  | 9/28 No billing in Fuse for this day
2026-09-24 | Brothers | Anthony Adum | D-HPP854 | 340 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-24 | Steve Wolfe | Treyvon Tillman | D-HLC511 | 313 | Pending Production |  |  | 9/30 - 9/24 X 254 in Fuse
2026-09-24 | Power Connect | Johnnie Williams | FB-HPP375 | 387 | Pending Production | 1636287 | Closed
2026-09-24 | Yosep | Yasmina Jerez | D-HBR260 | 19 | Pending Production | 1637242 | Closed | 10/7 - 1637' pending for Yosep on this sheet for D-HBR260, ticket 1637242 was completed for 6046 feet 9/27
2026-09-24 | Yosep | Yasmina Jerez | D-HBR261 | 809 | Pending Production | 1641017 | Closed | Match
2026-09-24 | Bicom | Miguel Herrero | FB-HSW419 | 349 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-24 | A1 Broadband | Joshua Wheatcroft | D-HPW346 | 843 | Pending Production |  | Not Created | 9/28 No billing in Fuse. 10-7-26 not in PC727 for billing being corrected
2026-09-24 | North Path | Brenton Copelin | SFU-MNTE-4 | 1808 | Pending Production | 1640596 | Closed | 10/9 waiting on richard/TJ to answer my email. TJ has been fixing billing to subs on this project. This ticket it complete.
2026-09-24 | Randys Utilities | Joshua Pacheco | D-HLC515 | 204 | Pending Production |  |  | 10/6 NO BILLING IN FUSE
2026-09-25 | Brothers | Anthony Adum | D-HPP858 | 948 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-25 | A1 Broadband | Joshua Wheatcroft | D-HPW346 | 232 | Pending Production |  | Not Created | 9/28 No billing in Fuse. 10-7-26 not in PC727 for billing being corrected
2026-09-25 | ASM | Danny Combs | D-HLC508 | 625 | Pending Production |  |  | 9/28 - 9/16 X 896 in fuse ? No other billing in Fuse there are multiple lines on this spreadsheet for this job
2026-09-25 | ASM | Matthew Nunes | D-HLC517 | 77 | Pending Production |  |  | 9/28 No billing in Fuse for this day
2026-09-25 | Brothers | Anthony Adum | D-HPP854 | 376 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-25 | HD Cable | Carl Waters | D-HSF401 | 149 | Pending Production |  | Not Created | 9/30 No billing in Fuse..Waiting on Invoice from Sub-Contractor
2026-09-25 | Yosep | Jose Espinosa | D-HBR261 | 712 | Pending Production |  |  | 9/30 no billing on this job in Fuse
2026-09-25 | Yosep | Jose Espinosa | D-HBR260 | 14 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-25 | Bicom | Miguel Herrero | FB-HSW419 | 1212 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-25 | Bicom | Miguel Herrero | D-HSW402 | 1212 | Pending Production |  |  | 9/28 no billing for this date
2026-09-28 | Brothers | Anthony Adum | D-HPP858 | 55 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-28 | Brothers | Anthony Adum | FB-HPP879 | 1527 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-28 | Power Connect | Johnnie Williams | FB-HPP375 | 1570 | Pending Production | 1636287 | Closed
2026-09-28 | Brothers | Anthony Adum | D-HPP854 | 951 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-28 | Bicom | Miguel Herrero | D-HSW402 | 125 | Pending Production |  |  | 9/29 no billing in Fuse
2026-09-28 | Bicom | Miguel Herrero | FB-HSW419 | 554 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-28 | ASM | Danny Combs | D-HLC507 | 203 | Pending Production |  |  | 9/29 - billing for 9/21 X 500, 9/18 X 500, 9/22 X 1747 - 9/16 x 891 I cleared off this sheet already
2026-09-28 | Yosep | Jose Espinosa | D-HBR261 | 351 | Pending Production |  |  | 9/30 no billing on this job in Fuse
2026-09-28 | Yosep | Jose Espinosa | D-HBR260 | 9 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-28 | GN Systems | Brenton Copelin | D-HSF402 | 314 | Pending Production | 1645306 | Closed | Match. The billing is correct and covers all these EOS.
2026-09-28 | SAUL | Treyvon Tillman | D-HLC511 | 240 | Pending Production |  |  | 9/30 no billing in Fuse for this date
2026-09-28 | Joshua Ott | Treyvon Tillman | D-HLC511 | 151 | Pending Production |  |  | 9/30 no billing in Fuse for this date
2026-09-28 | Justin Greene | Treyvon Tillman | D-HLC511 | 151 | Pending Production |  |  | 9/30 no billing in Fuse for this date
2026-09-28 | North Path | Brenton Copelin | SFU-MNTE-4 | 1919 | Pending Production | 1640596 | Closed | 10/9 waiting on richard/TJ to answer my email. TJ has been fixing billing to subs on this project. This ticket it complete.
2026-09-29 | Brothers | Anthony Adum | FB-HPP879 | 1631 | Pending Production |  | Not Created | 10/9 Brothers not completed invoice with proper backup
2026-09-29 | Bicom | Miguel Herrero | D-HSW404 | 387 | Pending Production |  | Not Created | 9/30 no billing in fuse
2026-09-29 | Brothers | Anthony Adum | FB-HPP854 | 839 | Pending Production |  | Not Created | 10/9 Brothers not completed invoice with proper backup
2026-09-29 | Yosep | Yasmina Jerez | D-HBR260 | 6 | Pending Production | 1637242 | Closed | 10/7 - 1637' pending for Yosep on this sheet for D-HBR260, ticket 1637242 was completed for 6046 feet 9/27
2026-09-29 | Bicom | Miguel Herrero | D-HSW405 | 549 | Pending Production |  |  | 9/30 no billing in fuse
2026-09-29 | Bicom | Miguel Herrero | FB-HSW419 | 892 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-29 | Sosa | Matthew Nunes | D-HLC539 | 1996 | Pending Production |  |  | 9/30 no billing in fuse
2026-09-29 | Yosep | Yasmina Jerez | D-HBR261 | 871 | Pending Production | 1641017 | Closed | Match
2026-09-29 | North Path | Brenton Copelin | SFU-MNTE-4 | 712 | Pending Production | 1640596 | Closed | 10/9 waiting on richard/TJ to answer my email. TJ has been fixing billing to subs on this project. This ticket it complete.
2026-09-29 | APT | Brenton Copelin | SFU-MNTE-4 | 552 | Pending Production | 1639508 | Closed | 10/9 waiting on richard/TJ to answer my email. TJ has been fixing billing to subs on this project. This ticket it complete.
2026-09-29 | Randys Utilities | Joshua Pacheco | D-HLC515 | 512 | Pending Production |  |  | 10/6 NO BILLING IN FUSE
2026-09-29 | K-One | Danny Combs | D-HPP839 | 1757 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-29 | HD Cable | Carl Waters | D-HSF401 | 1013 | Pending Production |  | Not Created | 9/30 no billing in Fuse..Waiting on Invoice from Sub-Contractor
2026-09-29 | Legant Livings | Joshua Pacheco | D-HLC516 | 680 | Pending Production |  |  | 10/09 8517' total billed in Fuse
2026-09-30 | Yosep | Yasmina Jerez | D-HBR261 | 366 | Pending Production | 1641017 | Closed | Match
2026-09-30 | Brothers | Anthony Adum | FB-HPP879 | 1421 | Pending Production |  |  | 10/9 Brothers not completed invoice with proper backup
2026-09-30 | Yosep | Yasmina Jerez | D-HBR260 | 21 | Pending Production | 1637242 | Closed | 10/7 - 1637' pending for Yosep on this sheet for D-HBR260, ticket 1637242 was completed for 6046 feet 9/27
2026-09-30 | Sosa | Matthew Nunes | D-HLC539 | 1734 | Pending Production |  |  | 9/30 no billing in Fuse
2026-09-30 | Bicom | Miguel Herrero | D-HSW405 | 250 | Pending Production
2026-09-30 | Bicom | Miguel Herrero | D-HSW404 | 70 | Pending Production
2026-09-30 | Bicom | Miguel Herrero | FB-HSW419 | 320 | Pending Production
2026-09-30 | K-One | Danny Combs | D-HPP639 | 1336 | Pending Production |  |  | 9/30 no billing in Fuse for this date
2026-09-30 | APT | Brenton Copelin | SFU-MNTE-4 | 532 | Pending Production | 1639508 | Closed | 10/9 waiting on richard/TJ to answer my email. TJ has been fixing billing to subs on this project. This ticket it complete.
2026-09-30 | North Path | Brenton Copelin | SFU-MNTE-4 | 190 | Pending Production | 1640596 | Closed | 10/9 waiting on richard/TJ to answer my email. TJ has been fixing billing to subs on this project. This ticket it complete.
2026-09-30 | Randys Utilities | Joshua Pacheco | D-HLC515 | 605 | Pending Production |  |  | 10/6 NO BILLING IN FUSE
2026-09-30 | APT | Joshua Pacheco | D-HLC514 | 583 | Pending Production |  |  | 10/08 811' approved in Fuse
2026-09-30 | ASM | Danny Combs | D-HLC508 | 76 | Pending Production
2026-09-30 | ASM | Danny Combs | D-HLC507 | 643 | Pending Production |  |  | 09/29 billing entered for 733'
9/30 or 10/1 | Lopez | Joshua Wheatcroft | BHCD-FPW-03-E | 925 | Pending Production |  | Not Created
2026-10-01 | Randys Utilities | Joshua Pacheco | D-HLC515 | 388 | Pending Production |  | Not Created | 10/6 NO BILLING IN FUSE
2026-10-01 | Legant Livings | Joshua Pacheco | D-HLC516 | 218 | Pending Production |  | Not Created | 10/09 8517' total billed in Fuse
2026-10-01 | HD Cable | Carl Waters | D-HSF401 | 441 | Pending Production |  | Not Created | 10/7 NO BILLING IN FUSE..Waiting on Invoice from Sub-Contractor
2026-10-01 | Yosep | Jose Espinosa | D-HBR261 | 10 | Pending Production |  | Customer
2026-10-01 | A1 Broadband | Joshua Wheatcroft | D-HPW346 | 234 | Pending Production |  | Not Created | 10/7 NO BILLING IN FUSE.10-7-26 not in PC727 for billing being corrected
2026-10-01 | GN Systems | Brenton Copelin | D-HSF402 | 1100 | Pending Production | 1645306 | Closed | Match. The billing is correct and covers all these EOS.
2026-10-01 | Yosep | Jose Espinosa | D-HBR262 | 742 | Pending Production |  | Not Created | 10/7 NO BILLING IN FUSE
2026-10-01 | Sosa | Johnnie Williams | D-HLC539 | 1741 | Pending Production | 1644050 | Not Created | 10.8 Pending Sosa Line added to PC728 ticket 1644379
2026-10-01 | APT | Brenton Copelin | SFU-MNTE-4 | 596 | Pending Production | 1639508 | Closed | 10/9 waiting on richard/TJ to answer my email. TJ has been fixing billing to subs on this project. This ticket it complete.
2026-10-01 | Bicom | Miguel Herrero | FB-HSW419 | 252 | Pending Production | 1643584 | Closed | match - correct footage for TCBDB2 is 126'
2026-10-01 | Bicom | Miguel Herrero | D-HSW402 | 126 | Pending Production | 1643585 | Closed
2026-10-01 | Brothers | Anthony Adum | FB-HPP879 | 1324 | Pending Production |  | Not Created | 10/9 Brothers not completed invoice with proper backup
2026-10-02 | GN Systems | Brenton Copelin | D-HSF402 | 748 | Pending Production | 1645306 | Closed | Match. The billing is correct and covers all these EOS.
2026-10-02 | Alpha Omega | Carl Waters | D-HPW361 | 185 | Pending Production |  | Not Created | 10/7 NO BILLING IN FUSE..Waiting on Invoice from customer once this shot is complete
2026-10-02 | A1 Broadband | Joshua Wheatcroft | D-HPW346 | 269 | Pending Production |  | Not Created | 10/7 NO BILLING IN FUSE.10-7-26 not in PC727 for billing being corrected
2026-10-02 | APT | Brenton Copelin | SFU-MNTE-4 | 748 | Pending Production | 1639508 | Closed | 10/9 waiting on richard/TJ to answer my email. TJ has been fixing billing to subs on this project. This ticket it complete.
2026-10-02 | 1972 FiberCore | Joshua Wheatcroft | D-HTG231 | 95 | Pending Production |  | Not Created
2026-10-02 | AMB | Joseph Aiello | D-HTG301 | 286 | Pending Production
2026-10-02 | Yosep | Yasmina Jerez | D-HBR261 | 20 | Pending Production | 1641017 | Closed | Match
2026-10-02 | Yosep | Yasmina Jerez | D-HBR262 | 652 | Pending Production |  | Not Created
2026-10-02 | Randys Utilities | Joshua Pacheco | D-HLC515 | 280 | Pending Production
2026-10-02 | Legant Livings | Joshua Pacheco | D-HLC516 | 108 | Pending Production |  | Not Created | 10/09 8517' total billed in Fuse
2026-10-05 | APT | Brenton Copelin | SFU-MNTE-4 | 608 | Pending Production | 1639508 | Closed | 10/9 waiting on richard/TJ to answer my email. TJ has been fixing billing to subs on this project. This ticket it complete.
2026-10-05 | Sosa | Johnnie Williams | D-HLC539 | 1508 | Pending Production | 1644050 | Not Created | 10.8 Pending Sosa Line added to PC728 ticket 1644379
2026-10-05 | Bicom | Miguel Herrero | D-HSW402 | 282 | Pending Production | 1643585 | Closed
2026-10-05 | RDA | Randy Emmett | D-HTG222 | 700 | Pending Production
2026-10-05 | AMB | Joseph Aiello | D-HTG301 | 466 | Pending Production
2026-10-05 | K-One | Danny Combs | D-HLC508 | 1779 | Pending Production
2026-10-05 | North Path | Cody Johns | D-HLX101 | 428 | Pending Production |  | Not Created | 10/7 NO BILLING IN FUSE. NO BORE LOGS
2026-10-05 | Alpha Omega | Carl Waters | D-HPW361 | 182 | Pending Production | 1645602 | Biz Ops | 10/7 NO BILLING IN FUSE
2026-10-05 | Legant Livings | Joshua Pacheco | D-HLC516 | 39 | Pending Production |  | Not Created | 10/09 8517' total billed in Fuse
2026-10-05 | A1 Broadband | Carl Waters | D-HPW350 | 486 | Pending Production |  | Not Created | Waiting on Invoice from Sub-Contractor
2026-10-05 | Yosep | Jose Espinosa | D-HBR262 | 571 | Pending Production
2026-10-05 | APT | Joshua Pacheco | D-HLC514 | 71 | Pending Production |  |  | 10/08 811' approved in Fuse
2026-10-06 | Sosa | Johnnie Williams | FB-HLC538 | 1739 | Pending Production |  | Customer | 10.8 Waiting on Billing Package from Sosa Line
2026-10-06 | BICOM | Miguel Herrero | D-HSW402 | 365 | Pending Production | 1643585 | Closed
2026-10-06 | North Path | Cody Johns | D-HLX101 | 1278 | Pending Production |  | Not Created | 10/7 NO BILLING IN FUSE. NO BORE LOGS
2026-10-06 | K-One | Danny Combs | D-HPP839 | 324 | Pending Production
2026-10-06 | Saul | Treyvon Tillman | D-HLC510 | 308 | Pending Production |  | Not Created | 10/7 325' in Fuse for Saul
2026-10-06 | Felipe | Treyvon Tillman | D-HLC510 | 180 | Pending Production |  | Not Created | 10/7 200' in Fuse for Felipe
2026-10-06 | Yosep | Yasmina Jerez | D-HBR261 | 30 | Pending Production |  | Not Created
2026-10-06 | Yosep | Yasmina Jerez | D-HBR262 | 514 | Pending Production |  | Not Created
2026-10-06 | GN Systems | Brenton Copelin | D-HSF402 | 1602 | Pending Production | 1645306 | Closed | Match. The billing is correct and covers all these EOS.
2026-10-06 | Alpha Omega | Carl Waters | D-HPW361 | 483 | Pending Production | 1645602 | Biz Ops | 10/7 NO BILLING IN FUSE
2026-10-06 | A1 Broadband | Carl Waters | D-HPW350 | 670 | Pending Production |  | Not Created | 10/7 NO BILLING IN FUSE
2026-10-07 | GN Systems | Brenton Copelin | D-HSF402 | 190 | Pending Production | 1645306 | Closed | Match. The billing is correct and covers all these EOS.
2026-10-07 | A1 Broadband | Carl Waters | D-HPW350 | 731 | Pending Production |  |  | Waiting on Invoice from Sub-Contractor
2026-10-07 | Alpha Omega | Carl Waters | D-HPW361 | 271 | Pending Production | 1645602
2026-10-07 | Yosep | Jose Espinosa | D-HBR261 | 1310 | Pending Production
2026-10-07 | Yosep | Jose Espinosa | D-HBR260 | 1324 | Pending Production
2026-10-07 | GN Systems | Brenton Copelin | D-HSF420 | 904 | Pending Production |  | Not Created | waiting on bore logs
2026-10-08 | ITG | Matthew Nunes | D-HLC517 | 36 | Pending Production
2026-10-08 | ASM | Danny Combs | D-HLC507 | 749 | Pending Production
2026-10-08 | Felipe | Treyvon Tillman | D-HLC510 | 160 | Pending Production
2026-10-08 | Yosep | Yasmina Jerez | D-HBR261 | 74 | Pending Production
2026-10-08 | Bicom | Miguel Herrero | D-HSW402 | 456 | Pending Production
2026-10-08 | GN Systems | Brenton Copelin | D-HSF420 | 868 | Pending Production |  | Not Created | waiting on bore logs
2026-10-08 | Yosep | Yasmina Jerez | D-HBR262 | 1291 | Pending Production
2026-10-08 | Alpha Omega | Carl Waters | D-HPW361 | 360 | Pending Production | 1645602
2026-10-08 | A1 Broadband | Carl Waters | D-HPW350 | 843 | Pending Production |  |  | Waiting on Invoice from Sub-Contractor