## Raw Data (hidden)
| YTD | JAN | FEB | MARCH | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC
Total Completed | YTD: 23; JAN: 23
Total Goal | YTD: 13721; JAN: 921; FEB: 11888; MARCH: 753; APR: 159
DOY | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% to Year End | 5.976% | 68.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Achieved % to Goal | 0.1676% | 2.497% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total % | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| 251 | 22 | 20 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22

## Tillman UG Footage
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | QC Requested Date | QC Walkout Date | Passed QC Walkout | QC Received From Tillman | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | Fiber Placement and Splice Only Footage | UG Percentage Complete | Construction Start Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Construction Total Percent Complete | Notes
BHUD-FCW-01-W-2 | St Petersburg | 2026-01-31 | Splice Only | TBD | Eric | PPM99354 | 0 | On Track | Not Required |  |  | Yes | 388 | Yes | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0% |  | 0% | 0% | 0%
D-HST11 | St Petersburg | 2025-10-30 |  |  |  |  | 86 | On Track | Received |  | 2025-09-17 | Yes | 45500 | Yes | Locates Called | 2025-09-17 |  |  |  |  | 3242 |  | 3242 | 0 | 0% |  | 0% | 0% | 0%
D-HNP106/D-H0102C | St Petersburg | 2025-11-30 | Power Connect | 2025-03-27 | Robert | PPM93922 | 69 | On Track | Received |  | 2025-03-25 | Yes | 67734.5 | Yes | In Process | 2025-03-28 |  |  |  |  | 4822 | 1914 | 2908 | 0 | 40% | 2025-05-07 | 0% | 0% | 0%
D-HNP107 | St Petersburg | 2025-11-30 | Power Connect | 2025-03-18 | Robert | PPM90859 | 85 | On Track | Received |  | 2025-03-19 | Yes | 72382.5 | Yes | Locates Called | 2025-03-27 |  |  |  |  | 6041 |  | 6041 | 0 | 0% |  | 0% | 0% | 0%
D-HNP108/D-H0102E | St Petersburg | 2025-11-30 | Longo Underground | 2025-03-27 | Tim | PPM91941 | 89 | On Track | Received |  | 2025-03-25 | Yes | 72131.5 | Yes | Locates Called | 2025-04-01 |  |  |  |  | 6182 | 3167 | 3015 | 0 | 51% | 2025-08-22 | 0% | 0% | 0%
D-HNP110/D-H0102G | St Petersburg | 2025-11-30 | Power Connect | 2025-03-27 | Robert | PPM94012 | 54 | On Track | Received |  | 2025-03-25 | Yes | 48215.5 | Yes | Locates Called | 2025-03-28 |  |  |  |  | 3796 |  | 3796 | 0 | 0% |  | 0% | 0% | 0%
D-HNP111/D-H0103A | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-03-27 | Betsy | PPM92084 | 85 | On Track | Received |  | 2025-03-25 | Yes | 84226.5 | Yes | Locates Called | 2025-04-02 |  |  |  |  | 7020 | 386 | 6634 | 0 | 5% | 2025-08-19 | 0% | 0% | 0% | 6.27.25 switched to telecom fiber.
D-HNP114_H0103D | St Petersburg | 2025-11-30 | FCA/Lightspeed In-House | 2025-02-12 | Betsy | PLK88966 | 81 | On Track | Received |  | 2025-02-14 | Yes | 70635 | Yes | In Process | 2025-02-08 |  |  |  |  | 6092 | 4227 | 1865 | 0 | 69% | 2025-03-31 | 0% | 0% | 0% | Print Received From Tillman--Pending Permit, and NTP Package/rec dot, need city/county
D-HNP115/D-H0103E | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-03-27 | Johnnie | PPM94017 | 87 | On Track | Received |  | 2025-03-25 | Yes | 75191.5 | Yes | Locates Called | 2025-04-01 |  |  |  |  | 6387 |  | 6387 | 0 | 0% |  | 0% | 0% | 0% | 04-15-25 Switched to MTX ,HDD Being off boarded. 4-29-25 reassigned to BFI
D-HNP135/D-H0106G | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-03-27 | Johnnie | PPM94426 | 70 | On Track | Received |  | 2025-03-25 | Yes | 67735.5 | Yes | In Process | 2025-05-02 |  |  |  |  | 6152 | 4796 | 1356 | 0 | 78% | 2025-05-15 | 0% | 0% | 0% | 6/17/2025 JW ¦ WORK STARTED TODAY
D-HNP144 | St Petersburg | 2025-11-30 | FCA/Lightspeed In-House | 2025-03-19 | Betsy | PPM90863 | 79 | On Track | Received |  | 2025-03-19 | Yes | 67925 | Yes | In Process | 2025-03-20 |  |  |  |  | 5825 | 1257 | 4568 | 0 | 20% | 5/52025 | 0% | 0% | 0%
FB-H0205A | St Petersburg | 2025-09-30 | Splice Only | TBD | Eric | PPM90591 | 0 | On Track | Received |  | 2025-02-28 | Yes | 582 | Yes | In Process | Not Required |  |  |  |  | 0 | 0 | 0 | 3 | 100% |  | 0% | 0% | 0%
FB-HNP104 | St Petersburg | 2025-11-30 | Longo Underground | 2025-04-01 | Tim | PPM90880 | 0 | On Track | Received |  | 2025-03-25 | Yes | 29634.15 | Yes | In Process | 2025-03-27 |  |  |  |  | 1831 | 625 | 1206 | 0 | 34% | 2025-05-13 | 0% | 0% | 0% | 5/14/2025 JW ¦ LOCATES SENT TO LAUREN TO BE CALLED IN 5/15/2025
FB-HNP111 | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-04-01 | Betsy | PPM92372 | 0 | On Track | Received |  | 2025-03-25 | Yes | 17203.45 | Yes | In Process | 2025-03-26 |  |  |  |  | 1157 | 175 | 982 | 0 | 15% | 2025-09-25 | 0% | 0% | 0% | 04-15-25 Switched to MTX. HDD Being off boarded.
FB-HNP118 | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-04-01 | Johnnie | PPM92375 | 0 | On Track | Received |  | 2025-03-26 | Yes | 13442.35 | Yes | Locates Called | 2025-03-26 |  |  |  |  | 831 |  | 831 | 0 | 0% |  | 0% | 0% | 0% | 5/14/2025 PENDING LOCATES / WORK BEGIN TDB
FB-HNP133 | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-05-02 | Johnnie | PPM92370 | 0 | On Track | Received |  | 2025-03-26 | Yes | 23800.25 | Yes | In Process | 2025-03-27 |  |  |  |  | 1697 | 250 | 1447 | 0 | 15% | 2025-05-14 | 0% | 0% | 0% | 5/14/2025 PENDING LOCATES / WORK BEGIN TDB
FB-HNP138 | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-02-12 | Betsy | PPM89817 | 0 | On Track | Received |  | 2025-02-12 | Yes | 19745.25 | Yes | In Process | 2025-02-08 |  |  |  |  | 1534 | 353 | 1181 | 0 | 23% | 2025-03-20 | 0% | 0% | 0%
FB-HNP144 | St Petersburg | 2025-11-30 | Lightspeed In-House | 2025-04-01 | Johnnie | PPM90914 | 0 | On Track | Received |  | 2025-03-25 | Yes | 31186.25 | Yes | In Process | 2025-03-27 |  |  |  |  | 2003 | 225 | 1778 | 0 | 11% | 2025-05-08 | 0% | 0% | 0% | 5/14/2025 CAUGHT UP TO LOCATES
FX4-FBB-01 | St Petersburg | 2025-10-30 |  |  |  |  | 0 | On Track | Received |  |  | No |  | No | Not Started | [5 empty] | 11 |  | 11 | 0 | 0% |  | 0% | 0% | 0%
Lake Shore Park | St Petersburg | 2025-12-17 |  |  |  |  | 80 | On Track | Not Required |  |  | Yes | 86136 | Yes | Not Started | [5 empty] | 7655 |  | 7655 | 0 | 0% |  | 0% | 0% | 0%
Wilders MHP | St Petersburg | 2025-12-17 |  |  |  |  | 139 | On Track | Not Required |  |  | Yes | 42766.5 | Yes | Not Started | [5 empty] | 3853 |  | 3853 | 0 | 0% |  | 0% | 0% | 0%
Sunset Palms MHP | St Petersburg | 2025-12-17 |  |  |  |  | 517 | On Track | Not Required |  |  | Yes | 215088 | Yes | Not Started | [5 empty] | 22387 |  | 22387 | 0 | 0% |  | 0% | 0% | 0%
BHU-FWP-08-E | Lakeland | 2025-09-30 | Lightspeed In-House | 2025-09-18 | Travis |  | 0 | On Track | Pending |  | 2025-09-18 | Yes | 10840.25 | Yes | Not Started | 2025-09-12 |  |  |  |  | 865 | 744 | 121 | 0 | 86% | 2025-09-24 | 0% | 0% | 0% | CL 9-12/CX START 9-24/
BHZD-FWP-08-W | Lakeland | 2025-09-30 | Lightspeed In-House | 2025-09-18 | Travis |  | 0 | On Track | Received |  | 2025-09-18 | Yes | 9611.95 | Yes | Not Started | 2025-09-18 |  |  |  |  | 807 |  | 807 | 0 | 0% |  | 0% | 0% | 0% | 9/15 FDOT Permit Received With NTP Package. / 9/19- CL9.18 WL 9.19
D-HWP813 | Lakeland | 2025-09-30 | Brothers | 2025-09-10 | Travis | PLK97686 | 87 | On Track | Received |  |  | Yes | 60115.95 | Yes | Locates Called | 2025-09-08 |  |  |  |  | 4774 |  | 4774 | 0 | 0% |  | 0% | 0% | 0% | Have NTP, No permit. Permit Received 9/11
D-HWP816 | Lakeland | 2025-09-30 | Brothers | 2025-09-10 | Travis | PLK98762 | 80 | On Track | Received |  | 2025-09-03 | Yes | 59116.7 | Yes | In Process | 2025-09-03 |  |  |  |  | 4833 | 4146 | 687 | 0 | 86% | 2025-09-23 | 0% | 0% | 0% | Have NTP, No permit. Permit Received 9/11
D-HWP818 | Lakeland | 2025-09-30 | Brothers | 2025-09-10 | Travis | PLK99387 | 67 | On Track | Received |  | 2025-09-03 | Yes | 40406 | Yes | In Process | 2025-09-03 |  |  |  |  | 3895 | 2205 | 1690 | 0 | 56% | 2025-09-24 | 0% | 0% | 0% | Have NTP, No permit. Permit Received 9/11 / start cx 9.24
D-HWP817 | Lakeland | 2025-10-15 |  |  |  |  | 67 | On Track | Pending | Permits |  | Yes | 38192 | Yes | Not Started | [5 empty] | 2845 |  | 2845 | 0 | 0% |  | 0% | 0% | 0% | 8/28 Pending Permit.
D-HWP819 | Lakeland | 2025-10-15 |  |  |  |  | 68 | On Track | Pending | Permits |  | Yes | 37755.6 | Yes | Not Started | [5 empty] | 2783 |  | 2783 | 0 | 0% |  | 0% | 0% | 0% | 8/26 Pending Permit.
D-HWP820 | Lakeland | 2025-10-15 |  |  |  |  | 28 | On Track | Pending | Permits |  | Yes | 27615.5 | Yes | Not Started | [5 empty] | 2027 |  | 2027 | 0 | 0% |  | 0% | 0% | 0% | 9/4 Pending Permit.
D-HWP901 | Lakeland | 2025-10-15 |  |  |  |  | 87 | On Track | Pending | Permits |  | Yes | 74384 | Yes | Not Started | [5 empty] | 6130 |  | 6130 | 0 | 0% |  | 0% | 0% | 0% | 8/26 Pending Permit.
D-HWP906 | Lakeland | 2025-10-15 |  |  |  |  | 28 | On Track | Pending | Permits |  | Yes | 29683 | Yes | Not Started | [5 empty] | 2414 |  | 2414 | 0 | 0% |  | 0% | 0% | 0% | 9/22 Pending Permit.
D-HWP907 | Lakeland | 2025-10-15 |  |  |  |  | 21 | On Track | Pending | Permits |  | Yes | 20891 | Yes | Not Started | [5 empty] | 1820 |  | 1820 | 0 | 0% |  | 0% | 0% | 0% | 8/20 Pending Permit.
D-HWP908 | Lakeland | 2025-09-30 | Longo Underground | 2025-09-15 | Anthony |  | 53 | On Track | Received |  | 2025-09-12 | Yes | 47676 | Yes | Locates Called | 2025-09-12 |  |  |  |  | 4022 |  | 4022 | 0 | 0% |  | 0% | 0% | 0% | 8/20/Pending Permit.Permit Received 9/11. 9/12 - cl wl dt complete. / 9/18- still pending water
D-HWP909 | Lakeland | 2025-10-15 |  |  |  |  | 59 | On Track | Pending | Permits |  | Yes | 44697.6 | Yes | Not Started | [5 empty] | 3495 |  | 3495 | 0 | 0% |  | 0% | 0% | 0% | 9/8 Pending Permit.
D-HWP910 | Lakeland | 2025-09-30 | Longo Underground | 2025-09-15 | Anthony |  | 82 | On Track | Received |  | 2025-09-12 | Yes | 82621.15 | Yes | Locates Called | 2025-09-12 |  |  |  |  | 6691 |  | 6691 | 0 | 0% |  | 0% | 0% | 0% | 8/25 Pending Permit.Permit Received 9/11. 9/12 - cl wl dt complete. / 9/18- still pending water
D-HWP911 | Lakeland | 2025-10-15 |  |  |  |  | 35 | On Track | Pending | Permits |  | Yes | 26026 | Yes | Not Started | [5 empty] | 2071 |  | 2071 | 0 | 0% |  | 0% | 0% | 0% | 8/26 Pending Permit.
D-HWP912 | Lakeland | 2025-10-15 |  |  |  |  | 82 | On Track | Pending | Permits |  | Yes | 58864 | Yes | Not Started | [5 empty] | 4747 |  | 4747 | 0 | 0% |  | 0% | 0% | 0% | 9/3 Pending Permit.
D-HWP913 | Lakeland | 2025-10-15 |  |  |  |  | 34 | On Track | Pending | Permits |  | Yes | 29646 | Yes | Not Started | [5 empty] | 2188 |  | 2188 | 0 | 0% |  | 0% | 0% | 0% | 9/26Pending Permit.
D-HWP914 | Lakeland | 2025-10-30 |  |  |  |  | 79 | On Track | Pending | Permits |  | Yes | 45014 | Yes | Not Started | [5 empty] | 3378 |  | 3378 | 0 | 0% |  | 0% | 0% | 0% | 9/3 Pending Permit.
D-HWP915 | Lakeland | 2025-10-30 |  |  |  |  | 75 | On Track | Pending | Permits |  | Yes | 38796 | Yes | Not Started | [5 empty] | 2874 |  | 2874 | 0 | 0% |  | 0% | 0% | 0% | 8/28 Pending Permit.
D-HWP916 | Lakeland | 2025-10-15 |  |  |  |  | 61 | On Track | Pending | Permits |  | Yes | 35050 | Yes | Not Started | [5 empty] | 2527 |  | 2527 | 0 | 0% |  | 0% | 0% | 0% | 8/25 Pending Permit.
D-HWP917 | Lakeland | 2025-10-15 |  |  |  |  | 69 | On Track | Pending | Permits |  | Yes | 37418 | Yes | Not Started | [5 empty] | 2851 |  | 2851 | 0 | 0% |  | 0% | 0% | 0% | 9/3 Pending Permit.
D-HWP918 | Lakeland | 2025-10-15 |  |  |  |  | 48 | On Track | Pending | Permits |  | Yes | 54228.7 | Yes | Not Started | [5 empty] | 4342 |  | 4342 | 0 | 0% |  | 0% | 0% | 0% | 9/10 Pending Permit.
D-HWP1003 | Lakeland | 2025-11-30 |  |  |  |  | 85 | On Track | Pending | Permits |  | Yes | 38323.55 | Yes | Not Started | [5 empty] | 2691 |  | 2691 | 0 | 0% |  | 0% | 0% | 0% | 9/3 Pending Permit.
D-HWP1004 | Lakeland | 2025-11-30 |  |  |  |  | 87 | On Track | Pending | Permits |  | Yes | 63322.45 | Yes | Not Started | [5 empty] | 5030 |  | 5030 | 0 | 0% |  | 0% | 0% | 0% | 8/26 Pending Permit.
D-HWP1005 | Lakeland | 2025-11-30 |  |  |  |  | 88 | On Track | Pending | Permits |  | Yes | 77109.5 | Yes | Not Started | [5 empty] | 6325 |  | 6325 | 0 | 0% |  | 0% | 0% | 0% | 9/10 Pending Permit.
D-HWP1006 | Lakeland | 2025-11-30 |  |  |  |  | 58 | On Track | Pending | Permits |  | Yes | 58952.88 | Yes | Not Started | [5 empty] | 4731 |  | 4731 | 0 | 0% |  | 0% | 0% | 0% | 9/3 Pending Permit.
D-HWP1007 | Lakeland | 2025-11-30 |  |  |  |  | 69 | On Track | Pending | Permits |  | Yes | 41834.75 | Yes | Not Started | [5 empty] | 3183 |  | 3183 | 0 | 0% |  | 0% | 0% | 0% | 9/3 Pending Permit.
D-HWP1307 | Lakeland | 2025-10-30 |  |  |  |  | 83 | On Track | Pending | Permits |  | Yes | 96748 | Yes | Not Started | [5 empty] | 7529 |  | 7529 | 0 | 0% |  | 0% | 0% | 0% | 8/18 Pending Permit.
D-HWP1313 | Lakeland | 2025-11-30 |  |  |  |  | 83 | On Track | Pending | Permits |  | Yes | 66402 | Yes | Not Started | [5 empty] | 5324 |  | 5324 | 0 | 0% |  | 0% | 0% | 0% | 8/26 Pending Permit.
D-HWP1312 | Lakeland | 2025-11-30 |  |  |  |  | 88 | On Track | Pending | Permits |  | Yes | 76565.85 | Yes | Not Started | [5 empty] | 6025 |  | 6025 | 0 | 0% |  | 0% | 0% | 0% | 9/15 Pending Permit.
D-HWP1314 | Lakeland | 2025-11-30 |  |  |  |  | 75 | On Track | Pending | Permits |  | Yes | 60620 | Yes | Not Started | [5 empty] | 4814 |  | 4814 | 0 | 0% |  | 0% | 0% | 0% | 8/28 Pending Permit.
D-HWP1315 | Lakeland | 2025-11-30 |  |  |  |  | 77 | On Track | Pending | Permits |  | Yes | 63997.35 | Yes | Not Started | [5 empty] | 5053 |  | 5053 | 0 | 0% |  | 0% | 0% | 0% | 9/10 Pending Permit.
D-HWP1316 | Lakeland | 2025-11-30 |  |  |  |  | 48 | On Track | Pending | Permits |  | Yes | 18021.7 | Yes | Not Started | [5 empty] | 1111 |  | 1111 | 0 | 0% |  | 0% | 0% | 0% | 8/20 Pending Permit.
D-HWP1317 | Lakeland | 2025-11-30 |  |  |  |  | 56 | On Track | Pending | Permits |  | Yes | 20705 | Yes | Not Started | [5 empty] | 1547 |  | 1547 | 0 | 0% |  | 0% | 0% | 0% | 8/20 Pending Permit.
FB-HWP478 | Lakeland | 2025-09-30 |  |  |  |  | 0 | On Track | Pending | Permits |  | Yes | 13022.05 | Yes | Not Started | [5 empty] | 923 |  | 923 | 0 | 0% |  | 0% | 0% | 0% | 8/20 Pending Permit.
FB-HWP479 | Lakeland | 2025-12-30 |  |  |  |  | 0 | On Track | Pending | Permits |  | Yes | 17139.4 | Yes | Not Started | [5 empty] | 1347 |  | 1347 | 0 | 0% |  | 0% | 0% | 0% | 69
FB-HWP481 | Lakeland | 2025-09-30 |  |  | Anthony | PLK97440 | 0 | On Track | Pending | Permits |  | Yes | 3410.1 | Yes | Not Started | [5 empty] | 226 |  | 226 | 0 | 0% |  | 0% | 0% | 0% | Needs City Permit, Just Email
FB-HWP483 | Lakeland | 2025-11-30 |  |  |  |  | 0 | On Track | Pending | Permits |  | Yes | 12840.7 | Yes | Not Started | [5 empty] | 911 |  | 911 | 0 | 0% |  | 0% | 0% | 0% | 9/22 Pending Permit.
FB-HWP875 | Lakeland | 2025-08-30 |  |  | Travis | PLK98757 | 0 | On Track | Pending | Permits |  | Yes | 17916.55 | Yes | Not Started | [5 empty] | 1433 |  | 1433 | 0 | 0% |  | 0% | 0% | 0% | Need City, FDOT permit
FB-HWP876 | Lakeland | 2025-08-30 |  | 2025-07-28 | Travis | PLK98825 | 0 | On Track | Pending | Permits | 2025-07-28 | Yes | 18401.05 | Yes | Locates Called | 2025-07-28 |  |  |  |  | 1403 |  | 1403 | 0 | 0% |  | 0% | 0% | 0% | Need city, App only. 7/28- Assigned to Brothers LOC/DT requested.
FB-HWP877 | Lakeland | 2025-11-30 |  |  |  |  | 0 | On Track | Pending | Permits |  | Yes | 7666.75 | Yes | Not Started | [5 empty] | 465 |  | 465 | 0 | 0% |  | 0% | 0% | 0% | 9/4 Pending Permit.
FB-HWP879 | Lakeland | 2025-10-30 |  |  |  |  | 0 | On Track | Pending | Permits |  | Yes | 34863 | Yes | Not Started | [5 empty] | 2710 |  | 2710 | 0 | 0% |  | 0% | 0% | 0% | 9/8 Pending Permit.
FB-HWP901 | Lakeland | 2025-08-30 |  |  | Travis | PLK97705 | 0 | On Track | Pending | Permits |  | Yes | 51970 | Yes | Not Started | [5 empty] | 4544 |  | 4544 | 0 | 0% |  | 0% | 0% | 0% | Needs City, App only
FB-HWP904 | Lakeland | 2025-08-30 | Splice Only |  |  |  | 0 | On Track | Not Required |  |  | Yes | 388 | Yes | Not Started | [5 empty] | 0 |  | 0 | 0 | 0% |  | 0% | 0% | 0% | 8/27 Splice Only Project.
Mas Verde MHP | Lakeland | 2025-10-30 | BASELINE/JUAN G UG/ | 2025-09-15 | Travis |  | 384 | On Track | Not Required |  | 2025-09-05 | Yes | 145985.5 | Yes | In Process | 2025-09-06 |  |  |  |  | 14150 | 4135 | 10015 | 0 | 29% | 2025-09-26 | 0% | 0% | 0% | dispatched 8-5/locatge scalled 9-5/CX START 9-25-25/
Oakhill MHP | Lakeland | 2025-09-30 | HH UG | 2025-09-16 | Travis |  | 84 | Completed on Track | Not Required |  |  | Yes | 30892 | Yes | Completed | 2025-09-11 |  |  |  |  | 2811 | 2732 | 79 | 0 | 69% | 2025-09-22 | 0% | 0% | 0% | 9/10 Pending SOW From Tillman/ locates called 9-11. 9/16 SOW Received. / 9/19- HH scheduled to start 9.22
BHUD-FOE-06-E | Bradenton | 2025-11-30 |  | 2025-02-28 | Joshua | MAN92243 | 0 | On Track | Received | Pending Re-Design | 2025-02-28 | Yes | 14013.5 | Yes | Locates Called | 2025-03-05 |  |  |  |  | 150 |  | 150 | 0 | 0% |  | 0% | 0% | 0% | 7-28-25 waiting on FDOT Permits. Removed Sub and Supervisor from tracker.
BHT-FOE-03 | Bradenton | 2025-10-30 | North Path | 2025-07-14 | Joshua | MAN97574 | 0 | On Track | Received |  | 2025-07-14 | Yes | 42837.2 | Yes | In Process | 2025-07-14 |  |  |  |  | 3432 | 1495 | 1937 | 0 | 43% | 2025-07-28 | 0% | 0% | 0%
D-HOE302 | Bradenton | 2025-11-30 | North Path | 2025-08-11 | Joshua | MAN98158 | 57 | On Track | Received |  | 2025-07-25 | Yes | 49223.7 | Yes | In Process | 2025-07-25 |  |  |  |  | 3737 | 1890 | 1847 | 0 | 50% | 2025-09-16 | 0% | 0% | 0%
FB-HLR201 | Bradenton | 2025-10-30 | Lightspeed In-House | 2025-07-29 | Joshua | MAN98152 | 0 | On Track | Received |  |  | Yes | 144972.5 | Yes | In Process | 2025-07-29 |  |  |  |  | 12735 | 2563 | 10172 | 0 | 20% | 2025-08-15 | 0% | 0% | 0%
D-HOE306 | Bradenton | 2025-11-30 | North Path | 2025-08-11 | Joshua | MAN99374 | 75 | On Track | Received |  |  | Yes | 68151.75 | Yes | Locates Called | 2025-08-12 |  |  |  |  | 5362 | 551 | 4811 | 0 | 10% | 2025-09-26 | 0% | 0% | 0%
BHT-FLX-01 | Bradenton | 2025-10-30 | Baseline | 2025-08-28 | Joshua |  | 0 | On Track | Received |  | 2025-08-22 | Yes | 184994.5 | Yes | In Process | 2025-08-22 |  |  |  |  | 14790 | 7455 | 7335 | 0 | 50% | 2025-09-10 | 0% | 0% | 0% | 8/20 Project Received.
D-HLR211 | Bradenton | 2025-10-30 |  |  |  |  | 82 | On Track | Received |  |  | Yes | 93666.75 | Yes | Locates Called | 2025-08-28 |  |  |  |  | 7778 |  | 7778 | 0 | 0% |  | 0% | 0% | 0% | 8/26 Permit Received With NTP Package.
D-HLR203 | Bradenton | 2025-10-30 |  |  |  |  | 82 | On Track | Received |  |  | Yes | 87830 | Yes | Locates Called | 2025-08-29 |  |  |  |  | 7022 |  | 7022 | 0 | 0% |  | 0% | 0% | 0% | 8/27 Permit Received With NTP Package.
D-HLR207 | Bradenton | 2025-10-30 | MC Underground | 2025-08-29 | Betsy |  | 80 | On Track | Received |  |  | Yes | 90173 | Yes | Locates Called | 2025-08-29 |  |  |  |  | 7009 |  | 7009 | 0 | 0% |  | 0% | 0% | 0% | 8/27 Permit Received With NTP Package.
BHU-FAL-01-E | Bradenton | 2025-10-30 | HAS Global | 2025-09-09 | Betsy |  | 0 | On Track | Received |  | 2025-09-05 | Yes | 98170.1 | Yes | In Process | 2025-09-08 |  |  |  |  | 9086 | 1461 | 7625 | 0 | 16% | 2025-09-22 | 0% | 0% | 0% | 8/28 Permit Received With NTP Package. Assigned to HAS Global. 9.24 new design recieved and whitelined. Pending locates
BHU-FAL-01-W-2 | Bradenton | 2025-10-30 | Lightspeed In-House | 2025-09-05 | Joshua |  | 0 | On Track | Received |  |  | Yes | 2167.3 | Yes | Locates Called | 2025-09-08 |  |  |  |  | 158 |  | 158 | 0 | 0% |  | 0% | 0% | 0% | 8/22 Project Received With Permit. 9-18-25 on hold per tillman needs redesign. 9/22 Package 10 Permit Received. 9.24 new design recieved and whitelined. Pending locates
FB-HLR202 | Bradenton | 2025-10-30 | HAS Global | 2025-09-23 | Betsy |  | 0 | On Track | Received |  |  | Yes | 139581.6 | Yes | Not Started | 2025-09-18 |  |  |  |  | 11150 |  | 11150 | 0 | 0% |  | 0% | 0% | 0% | 9/15 FDOT Permit Received With NTP Package
D-HLR210 | Bradenton | 2025-10-30 |  |  |  |  | 80 | On Track | Received |  | 2025-09-05 | Yes | 66674.3 | Yes | Locates Called | 2025-09-22 |  |  |  |  | 4672 |  | 4672 | 0 | 0% |  | 0% | 0% | 0% | 8/28 Permit Received With NTP Package.
FB-HOE175 | Bradenton | 2025-10-30 |  |  |  |  | 0 | On Track | Received |  |  | Yes | 29960 | Yes | Not Started | 2025-09-22 |  |  |  |  | 2372 |  | 2372 | 0 | 0% |  | 0% | 0% | 0% | 9/15 FDOT Permit Received With NTP Package
D-HLR204 | Bradenton | 2025-11-30 |  |  |  |  | 69 | On Track | Received |  |  | Yes | 51632 | Yes | Not Started | [5 empty] | 3997 |  | 3997 | 0 | 0% |  | 0% | 0% | 0% | 9/15 Pending Permit. 9/22 Package 10 Permit Received.
D-HLR205 | Bradenton | 2025-11-30 |  |  |  |  | 74 | On Track | Received |  |  | Yes | 47064 | Yes | Not Started | [5 empty] | 4366 |  | 4366 | 0 | 0% |  | 0% | 0% | 0% | 9/15 Pending Permit. 9/22 Package 10 Permit Received.
D-HLR208 | Bradenton | 2025-11-30 |  |  |  |  | 81 | On Track | Received |  |  | Yes | 68962 | Yes | Not Started | [5 empty] | 5333 |  | 5333 | 0 | 0% |  | 0% | 0% | 0% | 9/15 Pending Permit. 9/22 Package 10 Permit Received.
D-HLR212 | Bradenton | 2025-11-30 |  |  |  |  | 48 | On Track | Pending | Permits |  | Yes | 39064 | Yes | Not Started | [5 empty] | 2982 |  | 2982 | 0 | 0% |  | 0% | 0% | 0% | 9/15 Pending Permit.
D-HLX403 | Bradenton | 2026-05-30 |  |  |  |  | 70 | On Track | Received |  |  | Yes | 80624 | Yes | Not Started | [5 empty] | 6762 |  | 6762 | 0 | 0% |  | 0% | 0% | 0% | 9/26 Permit Received.
D-HLX406 | Bradenton | 2026-05-30 |  |  |  |  | 48 | On Track | Received | On Hold Per Tillman |  | Yes | 54814 | Yes | Not Started | [5 empty] | 4515 |  | 4515 | 0 | 0% |  | 0% | 0% | 0% | 9/24 Package 10 Permit Received With NTP. 9/25 on hold per tillman
D-HLX407 | Bradenton | 2026-05-30 |  |  |  |  | 60 | On Track | Received | On Hold Per Tillman |  | Yes | 76865.5 | Yes | Not Started | [5 empty] | 5795 |  | 5795 | 0 | 0% |  | 0% | 0% | 0% | 9/24 Package 10 Permit Received With NTP. 9/25 on hold per tillman
D-HLX416 | Bradenton | 2026-05-30 |  |  |  |  | 72 | On Track | Received | On Hold Per Tillman |  | Yes | 85035 | Yes | Not Started | [5 empty] | 7140 |  | 7140 | 0 | 0% |  | 0% | 0% | 0% | 9/24 Package 10 Permit Received With NTP. 9/25 on hold per tillman
FB-HOE178 | Bradenton | 2025-12-30 |  |  |  |  | 0 | On Track | Received |  |  | Yes | 50539.6 | Yes | Not Started | [5 empty] | 4084 |  | 4084 | 0 | 0% |  | 0% | 0% | 0% | Pending Splice Detail File.
FB-HAL175 | Bradenton | 2026-03-30 |  |  |  |  | 0 | On Track | Pending | Permits |  | Yes | 11518.95 | Yes | Not Started | [5 empty] | 881 |  | 881 | 0 | 0% |  | 0% | 0% | 0% | 9/16 Pending Permit.
FX4-FAL-01 | Bradenton | 2025-10-25 | Brothers | 2025-09-19 | TBD | MAN93941 | 0 | On Track | Received |  | TBD | Yes | 4646.75 | No | Not Started | [5 empty] | 238 |  | 238 | 0 | 0% |  | 0% | 0% | 0%
Completed Projects Pending Paperwork
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | QC Requested Date | QC Walkout Date | Passed QC Walkout | QC Received From Tillman | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | Fiber Placement and Splice Only Footage | UG Percentage Complete | Construction Start Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Construction Total Percent Complete | Notes
BHUD-FOE-02-W | Bradenton | 2025-07-30 | Power Connect | 2025-02-28 | Joshua | MAN92070 | 0 | Completed on Track | Received |  | 2025-02-28 | Yes | 64932.55 | Yes | Completed | 2025-03-05 |  |  |  |  | 5151 | 5127 | 24 | 0 | 100% | 2025-04-01 | 100% | 100% | 100%
BHZD-FOE-03-W | Bradenton | 2025-11-30 | Raven | 2025-02-19 | Joshua | PPM89496 | 0 | Completed on Track | Received |  | 2025-02-20 | Yes | 87944.4 | Yes | Completed | 2025-02-21 |  |  |  |  | 7008 | 7258 | -250 | 0 | 103% | 2025-03-31 | 100% | 100% | 100% | Needs soft dig to finish. Locates expired and re-called
D-HOE206 | Bradenton | 2025-11-30 | Power Connect - In-House | 2025-02-28 | Betsy | PPM92353 | 31 | Completed on Track | Received |  | 2025-02-28 | Yes | 28777 | Yes | Completed | 2025-02-28 |  |  |  |  | 2315 | 2509 | -194 | 0 | 108% | 2025-07-24 | 100% | 100% | 100%
D-HOE215 | Bradenton | 2025-11-30 | Raven | 2025-02-28 | Joshua | MAN91697 | 44 | Completed on Track | Received |  | 2025-02-28 | Yes | 57973.5 | Yes | Completed | 2025-02-28 |  |  |  |  | 4885 | 4554 | 331 | 0 | 93% | 2025-03-25 | 100% | 100% | 100%
FB-HOE201 | Bradenton | 2025-11-30 | Brothers / Power Connect | 2025-03-19 | Joshua | MAN91981 | 0 | Completed on Track | Received |  | 2025-03-02 | Yes | 200394.1 | Yes | Completed | 2025-02-28 |  |  |  | 2025-09-26 | 15386 | 15339 | 47 | 0 | 100% | 2025-03-31 | 100% | 100% | 100%
FB-HOE301 | Bradenton | 2025-11-30 | Raven | 2025-07-28 | Joshua | MAN98180 | 0 | Completed on Track | Received |  | 2025-07-25 | Yes | 143407.25 | Yes | Completed | 2025-07-25 |  |  |  |  | 11987 | 12047 | -60 | 0 | 101% | 2025-07-31 | 100% | 100% | 100%
FB-HOE375 | Bradenton | 2025-11-30 | Lightspeed In-House | 2025-08-11 | Betsy | MAN99383 | 0 | Completed on Track | Received |  | 2025-08-12 | Yes | 4815.65 | Yes | Completed | 2025-08-12 |  |  |  |  | 321 | 367 | -46 | 0 | 114% | 2025-09-05 | 0% | 0% | 0%
BHT-FWP-09 | Lakeland | 2025-07-30 | Brothers | 2025-05-09 | Travis | PLK95075 | 0 | Completed on Track | Received |  | 2025-05-09 | Yes | 133172.15 | Yes | Completed | 2025-05-12 | 2025-06-18 | 2025-06-20 | 2025-06-20 | 2025-09-17 | 13306 | 13332 | -26 | 0 | 100% | 2025-06-02 | 100% | 100% | 100% | Piping complete 6-17/do we need a change order for greyed out area? Brothers sch 7-21/need cop needs uploaded
BHUD-FWP-13-W | Lakeland | 2025-07-30 | Brothers | 2025-06-20 | Anthony | PLK95092 | 0 | Completed on Track | Received |  | 2025-06-18 | Yes | 144886 | Yes | Completed | 2025-07-02 |  |  |  | 2025-09-17 | 11054 | 11100 | -46 | 0 | 100% | 2025-07-07 | 100% | 100% | 100% | Needs City Permit, Just Email. 6/18 COL permit rec'd, WL/DT 7.1. Still need County permit/greyed out on city portion ,need other jobs to build (1312+1310+1307bh-13w002) 7/3- need county permit
BHZD-FWP-11-W | Lakeland | 2025-08-30 | Brothers | 2025-07-15 | Travis | PLK97102 | 0 | Completed on Track | Received |  | 2025-07-15 | Yes | 60849.9 | Yes | Completed | 2025-07-15 |  |  |  | 2025-09-16 | 5276 | 5016 | 260 | 0 | 95% | 2025-08-05 | 100% | 100% | 100% | Sch 8-7 DOT Bore Brothers/need bore logs ,splicing docs + change order for cop 8-20
BHZD-FWP-13-E | Lakeland | 2025-07-30 | Lightspeed In-House | 2025-05-16 | Anthony | PLK95389 | 0 | Completed on Track | Received |  | 2025-05-16 | Yes | 53589.8 | Yes | Completed | 2025-05-16 | In Progress |  |  | 2025-09-17 | 8305 | 8818 | -513 | 0 | 106% | 2025-06-02 | 100% | 100% | 100% | Locates called in 5/16, doortags 5/16 and 5/19. Only have city of Lakeland Permit, still need APPROVED FDOT and County permits. 5/22 Jeff in market doing GPR. / 5/27- IH drill broke down, failed to pull back. / 6/2- IH drilling for 275', becket broke during 2nd pullback. / 6/4 - IH Drilling, 310' bad weather. / 6/5-IH drilling lost pullback, crew got dispatched to a different Tillman escalation. / 6/12- IH had flat tired on vac, had to move job sites after starting because FTR needed to work damaged fiber, ground was hard and drill head could not come up, incliment weather set it and was not able to complete any shots. / 7/3- Change order request sent to Tillman for more bore footage needed to continue. 7/3- need fdot permit
D-HWP802 | Lakeland | 2025-08-30 | Longo Underground | 2025-08-20 | Anthony |  | 76 | Completed on Track | Received |  | 2025-08-19 | Yes | 53902 | Yes | Completed | 2025-08-18 |  |  |  |  | 3566 | 3704 | -138 | 0 | 104% | 2025-09-04 | 100% | 100% | 100% | waiting on locates 9-3/In Progress 45% complete 9-8/90% 9-16/ug cx com 9-17/sr placed 9-18/wo 9-23 *passed inspection/permiit closed 9-25
D-HWP803 | Lakeland | 2025-09-30 | Brothers | 2025-08-11 | Anthony | PLK97105 | 62 | Completed on Track | Received |  | 2025-08-11 | Yes | 56807.95 | Yes | Completed | 2025-08-11 |  |  |  | 2025-09-17 | 3787 | 4670 | -883 | 0 | 123% | 2025-08-19 | 100% | 100% | 100% | Needs City Permit, Just Email/start 8-21/8-25 complete/walkout scheduled for 9-9
D-HWP805 | Lakeland | 2025-09-30 | Brothers | 2025-08-13 | Anthony | PLK97109 | 85 | Completed on Track | Received |  | 2025-08-13 | Yes | 59869.5 | Yes | Completed | 2025-08-13 |  |  |  | 2025-09-17 | 4537 | 4660 | -123 | 0 | 102% | 2025-08-25 | 100% | 100% | 100% | permit receved 8-13/dispatched 8-13/cx started 8-25/moved to 826 for priorities/cx in progress 9-3(stingray spl 9-3)/ walk out schedule 9-9/permit closed 9-25
D-HWP809 | Lakeland | 2025-09-30 | Brothers | 2025-08-27 | Anthony | PLK97122 | 72 | Completed on Track | Received |  | 2025-08-28 | Yes | 50874.95 | Yes | Completed | 2025-08-28 |  |  |  |  | 3012 | 3012 | 0 | 0 | 100% | 2025-09-16 | 100% | 100% | 100% | Needs City Permit, Just Email. 8/29 Permit Received./cx start 9-16/cx sch completion 9-18 / 9/19-resto/proofing/fdh scheduled to comp 9.23/permit closed 9-25
D-HWP811 | Lakeland | 2025-09-30 | Brothers | 2025-08-27 | Anthony | PLK97116 | 66 | Completed on Track | Received |  | 2025-08-28 | Yes | 44896.1 | Yes | Completed | 2025-08-28 |  |  |  |  | 2385 | 2385 | 0 | 0 | 100% | 2025-09-18 | 100% | 100% | 100% | Needs City Permit, Just Email. 8/29 Permit Received./cx start sch 9-18 / 9/19-cx IP ECD 9.23/permit closed 9-25
D-HWP823 | Lakeland | 2025-09-30 | Brothers | 2025-09-10 | Travis |  | 54 | Completed on Track | Received |  | 2025-09-03 | Yes | 27186 | Yes | Completed | 2025-09-03 |  |  |  |  | 2084 | 2039 | 45 | 0 | 97% | 2025-09-18 | 100% | 100% | 100% | 8/20 Pending Permit. Permit Received 9/11/cx sch start 9-18
D-HWP824 | Lakeland | 2025-08-30 | Brothers | 2025-08-18 | Anthony | PLK100224 | 73 | Completed on Track | Received |  | 2025-08-18 | Yes | 37930 | Yes | Completed | 2025-08-18 |  |  |  | 2025-09-17 | 2649 | 2678 | -29 | 0 | 100% | 2025-08-26 | 100% | 100% | 100% | construction start 8-26/cx complete/walkout with tillman complete 9-2
D-HWP825 | Lakeland | 2025-08-30 | Longo Underground | 2025-08-18 | Anthony | PLK100282 | 70 | Completed on Track | Received |  | 2025-08-18 | Yes | 69889 | Yes | Completed | 2025-08-18 |  |  |  | 2025-09-17 | 3836 | 3836 | 0 | 0 | 100% | 2025-08-27 | 100% | 100% | 100% | 8/20 Project Received./waiting on locates 8-26/cx in progress 9-2/cx complete 9-4/ Walkout schedule 9-9/permit closed 9-25
D-HWP826 | Lakeland | 2025-08-30 | Brothers | 2025-08-18 | Travis | PLK100281 | 84 | Completed on Track | Received |  | 2025-08-18 | Yes | 52110 | Yes | Completed | 2025-08-18 |  |  |  | 2025-09-17 | 4071 | 4043 | 28 | 0 | 100% | 2025-08-26 | 100% | 100% | 100% | construction start 8-26/ Construction Complete 9-2
D-HWP827 | Lakeland | 2025-09-30 | Brothers | 2025-08-27 | Anthony |  | 87 | Completed on Track | Received |  | 2025-08-28 | Yes | 52204 | Yes | Completed | 2025-08-27 |  |  |  |  | 4048 | 5120 | -1072 | 0 | 126% | 2025-09-10 | 100% | 100% | 100% | 8/20 Pending Permit. 8/29 Permit Received. 9-10 CX started/ cx sch completion 9-18 / 9/24- cx comp, tillman walk comp, SR rts/permit closed 9-25
D-HWP1310 | Lakeland | 2025-09-30 | Brothers | 2025-08-15 | Anthony |  | 69 | Completed on Track | Received |  | 2025-08-15 | Yes | 67441 | Yes | Completed | 2025-08-15 |  |  |  | 2025-09-17 | 4348 | 4348 | 0 | 0 | 100% | 2025-08-26 | 100% | 100% | 100% | Disp. 8/15- Locates called 8-15/pass through completed, spl sch 8-29/cx in progress 9-3/ cx complete 9-8/ Stingray Blown 9-10/permit closed 9-25
FB-HWP480 | Lakeland | 2025-09-30 | Lightspeed In-House | 2025-09-02 | Travis |  | 0 | Completed on Track | Received |  | 2025-09-02 | Yes | 5604.6 | Yes | Completed | 2025-09-02 |  |  |  |  | 328 | 335 | -7 | 0 | 100% | 2025-09-22 | 100% | 100% | 100% | 9-2 permit received/locates called 9-2/Locates clear 9-9
FB-HWP801 | Lakeland | 2025-06-30 | Brothers | 2025-05-09 | Anthony | PLK94839 | 0 | Completed on Track | Received |  | 2025-05-13 | Yes | 63283 | Yes | Completed | 2025-05-13 | 2025-06-05 | 2025-06-06 | 2025-06-20 | 2025-07-08 | 5776 | 5776 | 0 | 0 | 125% | 2025-05-19 | 100% | 100% | 100% | Dispatched 5-9/Door Tag 5-14 & whitelned 5-13 / 5/19 Both permits received, requested ticket info from Brothers. 5/19 Brothers 644', return tmrw/ 5/20 Brothers drilling 1430' 3 HH., return on 5/21. Brother drilling 970', DOT Xing sched 5/27 9am. / 5/27 DOT Xing comp. Brothers 948' 3 HH. / 6/2- 1957' 8 HH. Will QC on 6.3 and brothers is getting back to LS on fiber sched. / 6/5- fiber placed, scheduling Tillman walkout for 6-6 /
Skyview Estates MHP | Lakeland | 2025-09-30 | Brothers | 2025-08-05 | Anthony |  | 208 | Completed on Track | Not Required |  | 2025-08-07 | Yes | 124980 | Yes | Completed | 2025-08-07 |  |  |  | 2025-09-26 | 11700 | 12084 | -384 | 0 | 103% | 2025-08-21 | 0% | 0% | 0% | in progress 8-27/moved to priorities/dilling complete 9-10 / 9-15- Proofing in progress
D-H0222A | St Petersburg | 2025-04-25 | Power Connect | 2025-02-05 | Robert | PPM89513 | 86 | Completed on Track | Received |  | 2025-02-26 | Yes | 94170.5 | Yes | Completed | 2025-02-05 | 2025-07-31 | 2025-09-03 |  |  | 7980 | 7457 | 523 | 0 | 93% | 2025-02-25 | 100% | 100% | 100% | Reassinged to Longo . -- Waiting on redesign from tillman--2-26-25. 8-18-25 rescheuled rewalk for 9-3-25
D-H0222C | St Petersburg | 2025-04-25 | Power Connect | 2025-02-10 | Robert | PPM89539 | 89 | Completed on Track | Received |  | 2025-02-07 | Yes | 89698.5 | Yes | Completed | 2025-02-06 | 2025-09-17 | 2025-10-06 |  |  | 7562 | 6528 | 1034 | 0 | 80% | 2025-02-21 | 100% | 100% | 100% | Confirmed With Tillman Project Date Changed To 3/31/2025. Tentative Start Date 2/18/2025.
D-HDH04 | St Petersburg | 2025-01-31 | J Garcia | 2025-01-28 | David | PPM88371 | 86 | Completed -Missed TSD | Received |  | 2025-01-20 | Yes | 78075.5 | Yes | Completed | 2025-01-18 | 2025-08-01 | 2025-08-18 |  | 2025-08-25 | 6526 | 6217 | 309 | 0 | 95% | 2025-01-28 | 100% | 100% | 100%
D-HDH84 | St Petersburg | 2025-03-26 | Reycamp | 2025-01-23 | Tim | PPM88311 | 79 | Completed -Missed TSD | Received |  | Completed | Yes | 64790.5 | Yes | Completed | 2025-01-18 | 2025-09-17 | 2025-10-01 |  |  | 4975 | 4794 | 181 | 0 | 96% | 2025-01-23 | 0% | 0% | 0% | Stingray from 81 to 84, Waiting for Redesign and permits for the redesign. Will possibly feed from 66
D-HNP113 | St Petersburg | 2025-11-30 | BFI / Longo Underground | 2025-03-19 | Tim | PPM90871 | 70 | Completed on Track | Received |  | 2025-02-28 | Yes | 56262.5 | Yes | Completed | 2025-03-28 | 2025-09-17 | 2025-09-30 |  |  | 4870 | 5044 | -174 | 0 | 103% | 2025-04-07 | 0% | 0% | 0% | 5.5 JW ¦ WAITING ON CLEAR LOCATES..5-7-25 switched to BFI
FB-H0223A | St Petersburg | 2025-02-23 | Power Connect | 2025-02-06 | Robert | PPM89789 | 0 | Completed -Missed TSD | Received |  | 2025-01-29 | Yes | 22755.7 | Yes | Completed | 2025-02-05 | 2025-07-15 | 2025-07-23 | 2025-07-23 | 2025-08-26 | 1735 | 1718 | 17 | 0 | 100% | 2025-03-13 | 100% | 100% | 100% | 2-14/need to get tied ins together*
FB-HDH02A | St Petersburg | 2025-06-25 | Multiple | TBD | EVERYONE | PPM87852 | 0 | Completed on Track | Received |  | Completed | Yes | 289634.75 | Yes | Completed | 2025-02-05 | 2025-07-11 | 2025-08-05 | 2025-08-13 | 2025-08-13 | 22725 | 19837 | 2888 | 0 | 87.29% | 2025-01-17 | 100% | 100% | 100% | 5/14/2025 JW ¦ LOCATES SENT TO LAUREN TO BE CALLED IN 5/15/2025. 7-18-25 finishing gig list.
Pending QC Form From Tillman
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | QC Requested Date | QC Walkout Date | Passed QC Walkout | QC Received From Tillman | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | Fiber Placement and Splice Only Footage | UG Percentage Complete | Construction Start Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Construction Total Percent Complete | Notes
D-HOE116 | Bradenton | 2025-05-30 | Power Connect | TBD | David | MAN90788 | 84 | Completed on Track | Received |  | 2025-02-28 | Yes | 2812.95 | Yes | Completed | 2025-05-15 |  |  |  | Pending Tillman QC Form | 285 | 285 | 0 | 3451 | 0% | 2025-05-21 | 100% | 100% | 100%
D-H0221C | St Petersburg | 2025-06-30 | Bartlett Fiber | 2025-03-11 | Caten | PPM91690 | 71 | Completed on Track | Received |  | 2025-03-12 | Yes | 60843.5 | Yes | Completed | 2025-03-06 | 2025-09-17 | 2025-09-29 |  | Pending Tillman QC Form | 4979 | 5020 | -41 | 0 | 101% | 2025-03-25 | 100% | 100% | 100% | 9-24 - JW - Tillman Walkout scheduled for 9-29-25
D-H0223A | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-01-29 | Caten | PPM89575 | 77 | Completed on Track | Received |  | 2025-01-29 | Yes | 61924 | Yes | Completed | 2025-02-04 | 2025-07-09 | 2025-07-14 |  | Pending Tillman QC Form | 5005 | 4996 | 9 | 0 | 100% | 2025-02-20 | 100% | 100% | 100% | 9-25-25 - JW- Working on gig list, will schedule once complete and ready for Tillman - Tentative Start Date 2/18/2025.
D-H0223E | St Petersburg | 2025-04-25 | US Builders | 2025-02-06 | Caten | PPM89581 | 84 | Completed on Track | Received |  | 2025-02-10 | Yes | 63402.5 | Yes | Completed | 2025-02-07 | 2025-07-09 | 2025-07-14 |  | Pending Tillman QC Form | 4979 | 4984 | -5 | 0 | 100% | 2025-02-26 | 100% | 100% | 100% | 9-25-25 - JW- Working on gig list, will schedule once complete and ready for Tillman - 2-24-25 sent to borecom will be on site thursday. reassigned to Keys Underground 2-26-25--GPR Requested on 2/25/2025. 2-28-25 Reassigned to US Builders.
D-HDH32 | St Petersburg | 2025-01-31 | Power Connect | 2025-02-07 | Robert | PPM89595 | 88 | Completed -Missed TSD | Received |  | Completed | Yes | 43130 | Yes | Completed | 2025-02-03 | 2025-08-01 | 2025-09-08 |  | Pending Tillman QC Form | 2931 | 2931 | 0 | 0 | 100% | 2025-04-03 | 100% | 100% | 100% | 9-25-25 - JW- Working on gig list, will schedule once complete and ready for Tillman - 2-18-25 Pipe is all in need feeding route verified and proofed
D-HDH34 | St Petersburg | 2025-01-31 | Lightspeed In-House | 2025-01-29 | Johnnie | PPM88372 | 88 | Completed -Missed TSD | Received |  | 2025-02-18 | Yes | 69212.5 | Yes | Completed | 2025-01-22 | 2025-09-17 | 2025-09-18 |  | Pending Tillman QC Form | 5661 | 5813 | -152 | 0 | 103% | 2025-01-24 | 100% | 100% | 100% | 9-25-25 - JW- Tillman Walkout scheduled for 10-2-2025 - 6/17/2025 JW ¦ PENDING RESTORATION BY IN HOUSE CREWS
D-HDH41 | St Petersburg | 2025-04-25 | MTX | 2025-03-27 | Allen / Sean | PPM91655 | 85 | Completed on Track | Received |  | 2025-03-25 | Yes | 74508.5 | Yes | Completed | 2025-04-02 | 2025-09-17 | 2025-09-25 |  | Pending Tillman QC Form | 5795 | 5411 | 384 | 0 | 94% | 2025-04-16 | 100% | 100% | 100% | 9-25-25 - JW- Tillman Walkout scheduled for 10-8-2025 -
D-HDH43 | St Petersburg | 2025-04-25 | US Builders | 2025-03-27 | Caten | PPM92271 | 57 | Completed on Track | Received |  | 2025-03-25 | Yes | 49071 | Yes | Completed | 2025-03-29 | 2025-06-24 | 2025-07-01 |  | Pending Tillman QC Form | 3967 | 3936 | 31 | 0 | 100% | 2025-04-09 | 100% | 100% | 100% | 9-25-25 - JW- Working on gig list, will schedule once complete and ready for Tillman -
D-HNP117/D-H0103G | St Petersburg | 2025-11-30 | FCA/Lightspeed In-House | 2025-03-27 | Betsy | PPM93990 | 60 | Completed on Track | Received |  | 2025-03-25 | Yes | 47849 | Yes | Completed | 2025-03-28 | 2025-09-15 | 2025-09-22 | 2025-09-25 | Pending Tillman QC Form | 4194 | 4448 | -254 | 0 | 106% | 2025-05-07 | 0% | 0% | 0% | 9-25 - 25 JW Passed Tillman Insecption, pending QAQC Form from Brian DiLillo
BHU-FDH-01-W | St Petersburg | 2025-02-28 | Lightspeed In-House | 2025-02-13 | Johnnie | PPM89496 | 0 | Completed | Received |  | 2025-02-17 | Yes | 1295 | Yes | Completed | 2025-02-18 | 2025-06-18 |  |  | Pending Tillman QC Form | 153 | 153 | 0 | 0 | 100% | 2025-04-07 | 100% | 100% | 100% | 9-25-25 JW - On my list for restoration, will schedule TIllman Wallk out once complete and ready - Crossing Assigned to Key Underground. Betsy door tagged--Tentative Start Date 2/24/2025. 2-28-25 reassigned to US Builders
FX4-FML-05 | St Petersburg | 2025-09-24 | Brothers | 2025-04-25 | Johnnie | PPM93377 | 0 | Completed on Track | Received |  | TBD | Yes | 4397.65 | Yes | Completed | 2025-07-14 |  |  |  | Pending Tillman QC Form | 129 | 129 | 0 | 0 | 100% | 2025-07-18 | 0% | 0% | 0% | 9-25-25 JW - On my list for restoration, will schedule TIllman Wallk out once complete and ready
FB-HWP1075 | Lakeland | 2025-09-30 | Lightspeed In-House | 2025-09-02 | Travis |  | 0 | Completed on Track | Received |  | 2025-09-02 | Yes | 12695 | Yes | Completed | 2025-09-02 |  |  |  | Pending Tillman QC Form | 1010 | 978 | 32 | 0 | 99% | 2025-09-11 | 100% | 100% | 100% | 9-2 permit received/locates called 9-2/Locates clear 9-9/CX started 9-11
Splicing Projects
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | QC Requested Date | QC Walkout Date | Passed QC Walkout | QC Received From Tillman | Footage UG | Actual Redline Completed Footage UG | Footage Remaining | Fiber Placement and Splice Only Footage | UG Percentage Complete | Construction Start Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Construction Total Percent Complete | Notes
D-HOE111 | Bradenton | 2025-05-30 | Splice Only | TBD | David | PPM92353 | 60 | Completed on Track | Not Required |  | 2025-02-28 | Yes | 2075.7 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 2266 | 100% | 2025-03-28 | 100% | 100% | 100%
D-HOE117 | Bradenton | 2025-05-30 | Splice Only | TBD | David | MAN90778 | 79 | Completed on Track | Not Required |  | 2025-02-28 | Yes | 2947.5 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 3830 | 100% | 2025-03-28 | 100% | 100% | 100%
D-HOE120 | Bradenton | 2025-05-30 | Splice Only | TBD | David | MAN90857 | 83 | Completed on Track | Not Required |  | 2025-02-28 | Yes | 2908.95 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 3371 | 100% | 2025-03-28 | 100% | 100% | 100%
D-H0220D | St Petersburg | 2025-05-30 | Splice Only | TBD | Eric | PPM90335 | 68 | Completed | Not Required |  | 2025-02-28 | Yes | 1134 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 5569 | 0% |  | 100% | 100% | 100%
D-H0221E | St Petersburg | 2025-04-25 | Splice Only | TBD | Eric | PPM90342 | 38 | Completed | Not Required |  | 2025-02-28 | Yes | 870 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 145 | 0% | 2025-03-26 | 100% | 100% | 100%
D-HDH13 | St Petersburg | 2025-02-17 | Splice Only | TBD | Eric | PPM92251 |  | Completed | Not Required |  | TBD | Yes | 3283.2 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 4696 | 0% |  | 100% | 100% | 100%
D-HDH64 | St Petersburg | 2025-02-17 | Splice Only | TBD | Eric | PPM92289 | 75 | Completed | Not Required |  | TBD | Yes | 3150.75 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 4215 | 100% | 2025-02-28 | 100% | 100% | 100%
D-HDH65 | St Petersburg | 2025-02-17 | Splice Only | TBD | Eric | PPM91553 | 80 | Completed | Not Required |  | TBD | Yes | 3391.5 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 5030 | 100% | 2025-02-28 | 100% | 100% | 100%
D-HDH72 | St Petersburg | 2025-04-25 | Power Connect | 2025-02-10 | Robert | PPM89624 | 82 | Completed on Track | Received |  | 2025-02-28 | Yes | 2025.6 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 1408 | 0% | 2025-02-28 | 100% | 100% | 100% | This was already completed when assigned.
D-HDH77 | St Petersburg | 2025-03-26 | Splice Only | 2025-02-27 | Eric | PPM92290 | 84 | Completed | Not Required |  | 2025-02-27 | Yes | 3801.75 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 5915 | 0% | 2025-02-28 | 100% | 100% | 100%
D-HDH79 | St Petersburg | 2025-03-26 | Splice Only | TBD | Eric | PPM90331 | 87 | Completed | Not Required |  | 2025-02-28 | Yes | 4021.5 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 5750 | 0% | 2025-02-28 | 100% | 100% | 100%
D-HDH81 | St Petersburg | 2025-02-17 | Splice Only | TBD | Eric | PPM91558 | 90 | Completed | Not Required |  | Completed | Yes | 4490.25 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 6485 | 100% | 2025-02-28 | 100% | 100% | 100%
D-HDH83 | St Petersburg | 2025-03-26 | Splice Only | TBD | Eric | PPM90333 | 87 | Completed | Not Required |  | 2025-02-28 | Yes | 4056.9 | Yes | Completed | Not Required | Not Required | Not Required | Not Required | Not Required | 0 | 0 | 0 | 5842 | 0% | 2025-02-28 | 100% | 100% | 100%
Vault Move EMMA / N FLA | Lakeland |  | Lightspeed In-House | 2025-04-21 | Anthony |  | 0 | Completed | Not Required |  | Not Required | No | 0 | No | Completed | Not Required | N/A | N/A | N/A |  | 3 | 3 | 0 | 0 | 100% | 2025-04-21 | 0% | 0% | 100% | completed 4-21*need to bill BAU Work
Vault Move FDH302B | Lakeland |  | Lightspeed In-House | 2025-04-21 | Anthony |  | 0 | Completed | Not Required |  | Not Required | No | 0 | No | Completed | Not Required | N/A | N/A | N/A |  | 3 | 3 | 0 | 0 | 100% | 2025-04-21 | 0% | 0% | 100% | completed, need t o bill BAU Work
Note on A13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on J25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-15-2025 FDOT Permit Received.
Note on W110: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-17-2025 673' Was Removed From The Project As Per Travis.
Note on W113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-18-2025 446' Was Removed From The Project On Sheets 15 and 16 As Per Anthony. Also Part Of The Remaining Footage Was Captured On Project D-HWP812(Stingray Portion).
Note on V114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-24-2025 Design Change--Part of The Footage On Project D-HWP811 Was Removed And Changed To Project D-HWP808. Approx 1000' As Per Anthony.
Note on W114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-24-2025 Design Change--Part of The Footage On Project D-HWP811 Was Removed And Changed To Project D-HWP808. Approx 1000' As Per Anthony.
Note on W117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-11-2025 As Per Anthony Part Of The Project Was Removed By Tillman--Approved By Jessie.
Note on W119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-18-2025 Additional Conduit Placement Has Been Added Due To Existing Utility Conflicts, This Additional Conduit Placement Has Been Approved By Tillman As Per Anthony.
Note on W120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-17-2025 Footage Changed Due To Adding Additional Conduit To Project BHZD-FWP-13-W.
Note on W122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-2-2025 Change Order Submitted For Addition Conduit Placement---New Total Is 5,776'.
Note on W123: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-25-2025 All Rear Easement Toby Boxes Were Changed To Front Yard As Per Tillman And Skyview Management As Per Anthony.
Note on P129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on A135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on W135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-23-2025 Completed Missing Bore Connection To Feed. Reply: Change Order Approved By Joe Cutright On 7-18-2025.
Note on W136: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-20-2025 Confirmed Actual Completed Footage.
Note on Z136: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-20-2025 Conduit Placement Confirmed Completed.
Note on P137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on W137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-2-2025 Confirmed Actual Completed Footage.
Note on Z137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-2-2025 Conduit Placement Confirmed Completed.
Note on W138: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-2-2025 Confirmed Actual Completed Footage.
Note on Z138: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-2-2025 Conduit Placement Confirmed Completed.
Note on W139: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per Tillman On 2-10-2025 SOW Footage/Work Is Only For The County Permit That Is Pending Approval, All The City Work Is Already Completed.
Note on Z139: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-21-2025 Conduit Placement Confirmed Completed.
Note on P140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per David On 1/29/2025
Note on W140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-12-2025 Confirmed Actual Completed Footage.
Note on Z140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-12-2025 Conduit Placement Confirmed Completed.
Note on W141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-25-2025 Confirmed Actual Completed Footage.
Note on Z141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-25-2025 Conduit Placement Confirmed Completed.
Note on W142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-27-2025 Confirmed Actual Completed Footage.
Note on Z142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-27-2025 Conduit Placement Confirmed Completed.
Note on W143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-19-2025 Confirmed Actual Completed Footage.
Note on Z143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-19-2025 Conduit Placement Confirmed Completed.
Note on J144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-26-2025 FDOT Permit Activated As Per Dustin From Tillman.
Note on W144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-7-2025 Design Change Per Tillman. Reply: 6-10-2025 Confirmed Actual Completed Footage.
Note on Z144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-10-2025 Conduit Placement Confirmed Completed.
Note on W145: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-3-2025 Confirmed Actual Completed Footage.
Note on Z145: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-3-2025 Conduit Placement Confirmed Completed.
Note on W146: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-25-2025 Confirmed Actual Completed Footage.
Note on Z146: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-25-2025 Conduit Placement Confirmed Completed.
Note on A151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on P151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on A152: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on P152: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on A153: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on P153: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on A154: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A156: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on AC156: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Splicing Completed by Utilities One as Per Tillman.
Note on A157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on P157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-14-2025 Splicing Completed by Utilities One as Per Tillman.
Note on A158: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on P158: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-14-2025 Splicing Completed by Utilities One as Per Tillman.
Note on AC158: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-14-2025 Splicing Completed by Utilities One as Per Tillman.
Note on A159: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Splice Only Project.
Note on A160: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A161: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A162: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on P162: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-14-2025 Splicing Completed by Utilities One as Per Tillman.
Note on AC162: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-14-2025 Splicing Completed by Utilities One as Per Tillman.
Note on A163: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.

## Comp Projects Invoiced-Paid Out
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Door Tag Date | SOW Received | SOW Estimated Cost | Invoice Amount Paid | NTP Received | Constuction Status | Locate Date | Footage UG | Actual Redline Completed Footage UG | Fiber Placement and Splice Only Footage | UG Percentage Complete | Construction Start Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Construction Total Percent Complete | QC Received From Tillman | Column1
BHT-FWP-06 | Lakeland | 2025-04-25 | Lightspeed In-House | 2025-02-03 | Travis | PLK89457 | 0 | Completed on Track | Received | 2025-02-20 | Yes | 62460.45 | 61491.05 | Yes | Completed | 2025-02-21 | 4949 | 5089 | 0 | 103% | 2025-03-04 | 100% | 100% | 100% | 2025-06-13
BHT-FWP-07 | Lakeland | 2025-04-25 | LSCG | 2025-03-19 | Travis | PLK91807 | 0 | Completed on Track | Received | 2025-03-19 | Yes | 15690.1 | 16153.75 | Yes | Completed | 2025-03-19 | 1242 | 1243 | 0 | 100% | 2025-03-27 | 100% | 100% | 100% | 2025-06-27 | locates updated 3-21/SOW REC 3-21/ about 600' left 3-31,ecd 4-4/need to confirm 144 cut at carol vault- / Job Complete. Need Walkout/ Closeout sent/ Walkout cleared by paul, turn over to tanner 4-23
BHT-FWP-10 | Lakeland | 2025-05-30 | Brothers | 2025-05-01 | Travis | PLK94470 | 0 | Completed on Track | Received | 2025-05-05 | Yes | 119135.3 | 121256.65 | Yes | Completed | 2025-05-05 | 9356 | 9202 | 0 | 98% | 2025-05-15 | 100% | 100% | 100% | 2025-08-28 | Dispatched 5-1/ Locates expedited 5/8. / 5/14 Brothers to start 5.15 w 1 drill. LS Jeff to GPR 5.15/ 1580' 5-15/270' 5-19/5-20 waiting on city locates/ 948' 5-22/ 954' 5-27/ 2,973' 5-28/ DOT crossing sch 6-5/ 2,248' 5-29. Fiber Pulled 6-17/COP Sent 6-18/needs jobs next to it completed for fs to take place
BHUD-FWP-08-E | Lakeland | 2025-05-10 | Brothers | 2025-02-27 | Travis | PLK91306 | 0 | Completed on Track | Received | Completed | Yes | 12601.45 | 13008.1 | Yes | Completed | 2025-02-28 | 939 | 928 | 0 | 99% | 2025-03-17 | 100% | 100% | 100% | 2025-06-16
D-HWP102 | Lakeland | 2025-02-23 | Power Connect /SB | 2025-02-05 | Anthony | PLK88966 | 54 | Completed -Missed TSD | Received | Completed | Yes | 47461.5 | 45340 | Yes | Completed | 2025-02-04 | 3775 | 3734 | 0 | 99% | 2025-02-20 | 100% | 100% | 100% | 2025-03-27
D-HWP103 | Lakeland | 2025-02-23 | Brothers | 2025-02-24 | Travis | PLK88967 | 49 | Completed -Missed TSD | Received | 2025-02-25 | Yes | 43064 | 44346 | Yes | Completed | 2025-02-04 | 3422 | 3519 | 0 | 103% | 2025-03-11 | 100% | 100% | 100% | 2025-03-27
D-HWP105 | Lakeland | 2025-02-28 | Brothers | 2025-02-18 | Anthony | PLK90239 | 56 | Completed -Missed TSD | Received | 2025-02-19 | Yes | 62522.54 | 56001 | Yes | Completed | 2025-02-19 | 4063 | 4097 | 0 | 100% | 2025-03-03 | 100% | 100% | 100% | 2025-06-27
D-HWP1304 | Lakeland | 2025-09-25 | Brothers | 2025-04-08 | Anthony | PLK93497 | 82 | Completed on Track | Received | 2025-04-09 | Yes | 67171.5 | 64739 | Yes | Completed | 2025-04-09 | 5373 | 5300 | 0 | 99% | 2025-04-28 | 100% | 100% | 100% | 2025-06-10
D-HWP1306 | Lakeland | 2025-09-25 | LSCG | 2025-04-02 | Anthony | PLK92368 | 79 | Completed on Track | Received | 2025-04-02 | Yes | 72492 | 73087.5 | Yes | Completed | 2025-04-02 | 5941 | 5972 | 0 | 100% | 2025-04-14 | 0% | 0% | 0% | 2025-06-26
D-HWP1309 | Lakeland | 2025-09-25 | Brothers | 2025-04-02 | Travis | PLK92363 | 59 | Completed on Track | Received | 2025-04-03 | Yes | 51295 | 51485.5 | Yes | Completed | 2025-04-03 | 4122 | 4138 | 0 | 100% | 2025-04-17 | 100% | 100% | 100% | 2025-06-10
D-HWP412 | Lakeland | 2025-01-31 | SB Martinez | 2025-01-09 | Travis | PLK87663 | 23 | Completed on Track | Received | Completed | Yes | 26617 | 25405 | Yes | Completed | 2025-01-02 | 2121 | 2106 | 0 | 100% | 2025-01-13 | 100% | 100% | 100% | 2025-02-14
D-HWP415 | Lakeland | 2025-01-31 | Lightspeed In-House | 2025-01-22 | Travis | PLK88133 | 70 | Completed -Missed TSD | Received | Completed | Yes | 72118 | 70778 | Yes | Completed | 2025-01-02 | 5987 | 5879 | 0 | 98% | 2025-01-22 | 100% | 100% | 100% | 2025-06-13
D-HWP425 | Lakeland | 2025-01-31 | Brothers | 2025-01-28 | Travis | PLK88584 | 75 | Completed -Missed TSD | Received | Completed | Yes | 69288 | 70664 | Yes | Completed | 2025-01-15 | 5690 | 5759 | 0 | 101% | 2025-01-28 | 100% | 100% | 100% | 2025-03-28
D-HWP436 | Lakeland | 2025-01-31 | HH/LS | 2025-02-05 | Anthony | PLK88375 | 65 | Completed -Missed TSD | Received | 2025-01-16 | Yes | 69555 | 70432 | Yes | Completed | 2025-01-16 | 5661 | 5633 | 0 | 100% | 2025-02-05 | 100% | 100% | 100% | 2025-06-13
D-HWP441 | Lakeland | 2025-01-31 | Brothers | 2025-01-28 | Travis | PLK88853 | 81 | Completed -Missed TSD | Received | Completed | Yes | 83754 | 80572.5 | Yes | Completed | 2025-01-15 | 7140 | 6854 | 0 | 96% | 2025-01-28 | 100% | 100% | 100% | 2025-02-14
D-HWP701 | Lakeland | 2025-03-26 | Brothers | 2025-02-20 | Anthony | PLK89401 | 50 | Completed -Missed TSD | Received | 2025-02-17 | Yes | 43895.5 | 44479.5 | Yes | Completed | 2025-02-18 | 3581 | 3634 | 0 | 101% | 2025-03-12 | 100% | 100% | 100% | 2025-03-27
D-HWP702 | Lakeland | 2025-03-26 | Brothers | 2025-03-13 | Anthony | PLK92108 | 52 | Completed on Track | Received | 2025-03-17 | Yes | 50824.5 | 50928.5 | Yes | Completed | 2025-03-13 | 4030 | 4064 | 0 | 100% | 2025-04-02 | 100% | 100% | 100% | 2025-05-12
D-HWP703 | Lakeland | 2025-04-25 | Brothers | 2025-03-19 | Travis | PLK92329 | 86 | Completed on Track | Received | 2025-03-21 | Yes | 83462 | 83033 | Yes | Completed | 2025-03-19 | 6723 | 6757 | 0 | 100% | 2025-04-07 | 100% | 100% | 100% | 2025-05-12
D-HWP705 | Lakeland | 2025-02-28 | Brothers | 2025-02-24 | Anthony | PLK91019 | 51 | Completed -Missed TSD | Received | Completed | Yes | 47414 | 45744 | Yes | Completed | 2025-02-28 | 3597 | 3636 | 0 | 101% | 2025-03-11 | 100% | 100% | 100% | 2025-03-27
D-HWP706 | Lakeland | 2025-04-25 | Brothers | 2025-03-19 | Anthony | PLK91963 | 59 | Completed on Track | Received | 2025-03-20 | Yes | 59562.5 | 52525.5 | Yes | Completed | 2025-03-19 | 4123 | 4094 | 0 | 100% | 2025-03-31 | 100% | 100% | 100% | 2025-05-12
D-HWP707 | Lakeland | 2025-04-25 | Brothers | 2025-03-19 | Travis | PLK92185 | 35 | Completed on Track | Received | 2025-03-19 | Yes | 41187 | 39597.5 | Yes | Completed | 2025-03-19 | 3235 | 3240 | 0 | 100% | 2025-04-03 | 100% | 100% | 100% | 2025-05-12
D-HWP713 | Lakeland | 2025-02-23 | Brothers | 2025-02-07 | Anthony | PLK89267 | 22 | Completed on Track | Received | Completed | Yes | 14497.5 | 14042 | Yes | Completed | 2025-02-07 | 1073 | 1091 | 0 | 100% | 2025-02-18 | 100% | 100% | 100% | 2025-03-05
D-HWP902 | Lakeland | 2025-07-24 | Brothers | 2025-04-11 | Travis | PLK93385 | 62 | Completed on Track | Received | 2025-04-15 | Yes | 62502 | 59129.5 | Yes | Completed | 2025-04-15 | 5008 | 4791 | 0 | 96% | 2025-05-06 | 100% | 100% | 100% | 2025-06-23
D-HWP903 | Lakeland | 2025-07-24 | Brothers | 2025-04-11 | Travis | PLK93393 | 89 | Completed on Track | Received | 2025-04-15 | Yes | 70705.5 | 67666 | Yes | Completed | 2025-04-15 | 5203 | 5333 | 0 | 102% | 2025-04-29 | 100% | 100% | 100% | 2025-06-10
D-HWP904 | Lakeland | 2025-07-24 | Brothers | 2025-04-11 | Travis | PLK93379 | 87 | Completed on Track | Received | 2025-04-15 | Yes | 66004.5 | 64943.5 | Yes | Completed | 2025-04-15 | 5120 | 5340 | 0 | 105% | 2025-05-05 | 100% | 100% | 100% | 2025-06-10
D-HWP905 | Lakeland | 2025-07-30 | Brothers | 2025-05-09 | Travis | PLK94794 | 60 | Completed on Track | Received | 2025-05-13 | Yes | 57237 | 55777 | Yes | Completed | 2025-05-13 | 4508 | 4426 | 0 | 99% | 2025-06-04 | 100% | 100% | 100% |  | DISPATCHED 5-9/ Locates called 5-12/Tillman Walkout completed 6-13/need other jobs done to pull fiber and splice in
FB-HWP101 | Lakeland | 2025-01-31 | Power Connect /SB/LS | 2025-01-27 | Anthony | PLK88377 | 0 | Completed | Received | 2025-01-16 | Yes | 24886.5 | 7262 | Yes | Completed | 2025-01-16 | 330 | 330 | 0 | 100% | 2025-01-27 | 100% | 100% | 100% | 2025-06-13
FB-HWP701 | Lakeland | 2025-05-28 | Brothers | 2025-02-07 | Anthony | PLK89265 | 0 | Completed on Track | Received | 2025-02-17 | Yes | 88491.8 | 85791.25 | Yes | Completed | 2025-02-17 | 7207 | 6778 | 0 | 94% | 2025-03-05 | 100% | 100% | 100% | 2025-08-29 | gave to power connect 2-17-25/START 2-26/exp 811 2-26/not clear 3-4@730am/3-4 3rd notice called into to 811 8am/ partial locates work sch 3-5 tin in to 713 locates not complete 3-4 @3pm/ Expedited 4pm 3-4/*do not build peice ro 703(ada x-ing)/ Expedited locates 4pm 3-5/pending zayo marks 3-7/talked to state manager for zayo, he is dending them asap to locate/Zayo marked. 3-10 Power connect drilling, Returning 3-11 to connect Griffin Rd to N Florida and pull 48f. 3/12-IP, 100' left to bore on Kalt Dr. to tie in D-HWP713, 48f pull. 3/13- x-ing at Martha call locates 3-13 for ls to complete/. 3/13- locs called/whitelined, IH crew to dig up 144 and place 48f so D701,D705 and D702 can be heated up. 3/17- still pending clear loc for Martha(will expedite tmrw), Tillman aprvd a bore to get a 48f from FB to D701 loc called 3.14./504' 4-10/dot sch for 5-13 9am/ 5/7- DOT Xing scheduled for Tuesday 5/13. Expedited tickets 5-8*fs sch 5-22/ DOT crossing sch 5-20. 5/14 1190' today, will return on 5/20 to complete remaining path. / 5/19 Brothers said they were doing this bore on 5.20 and made a mistake with the date, it is scheduled for 5.21 and the fiber to be pulled in on the same day. / 6/5- Tillman walking today
FX4-FWP-08 | Lakeland | 2025-05-15 | Brothers | 2025-02-07 | Travis | PLK89273 | 0 | Completed | Received | Completed | Yes | 3425.55 | 7741.4 | Yes | Completed | 2025-02-01 | 73 | 73 | 0 | 100% | 2025-02-10 | 100% | 100% | 100% | 2025-06-27
Golden Wings MDU | Lakeland | 2025-01-31 | SB Martinez | 2025-01-25 | Travis | PLK88370 | 48 | Completed -Missed TSD | Not Required | Completed | Yes | 21648.75 | 35235 | Yes | Completed | 2025-01-21 | 2264 | 2163 | 0 | 96% | 2025-01-24 | 100% | 100% | 100% | 2025-06-10
D-H0220C | St Petersburg | 2025-05-30 | Power Connect | 2025-03-11 | Robert | PPM91630 | 80 | Completed | Received | 2025-03-12 | Yes | 88033.5 | 88045.5 | Yes | Completed | 2025-03-11 | 7442 | 7447 | 0 | 100% | 2025-03-24 | 100% | 100% | 100% | 2025-05-14
D-H0221D | St Petersburg | 2025-03-26 | Bartlett Fiber | 2025-02-28 | Caten | PPM91321 | 87 | Completed | Received | 2025-02-28 | Yes | 74446 | 73894 | Yes | Completed | 2025-03-07 | 6149 | 6362 | 0 | 104% | 2025-03-17 | 100% | 100% | 100% | 2025-07-21
D-H0221F | St Petersburg | 2025-04-25 | Brothers | 2025-02-28 | Johnnie | PPM91656 | 83 | Completed | Received | 2025-02-28 | Yes | 84935.5 | 81445 | Yes | Completed | 2025-03-10 | 7049 | 7081 | 0 | 100% | 2025-03-24 | 100% | 100% | 100% | 2025-04-23
D-H0222B | St Petersburg | 2025-04-25 | Brothers | 2025-01-28 | Johnnie | PPM89528 | 76 | Completed on Track | Received | 2025-02-04 | Yes | 90302 | 98764.5 | Yes | Completed | 2025-02-06 | 8420 | 8553 | 0 | 102% | 2025-02-21 | 100% | 100% | 100% | 2025-07-29 | 6/17/2025 JW ¦ PENDING RESTORATION BY IN HOUSE CREWS
D-H0222D | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-02-07 | Caten | PPM89539 | 86 | Completed on Track | Received | 2025-02-10 | Yes | 71361 | 72125 | Yes | Completed | 2025-01-31 | 6214 | 6214 | 0 | 100% | 2025-02-20 | 100% | 100% | 100% | 2025-05-14
D-H0223C | St Petersburg | 2025-04-25 | Longo Underground | 2025-01-29 | Tim | PPM89447 | 81 | Completed on Track | Received | 2025-02-12 | Yes | 76139.5 | 79581.5 | Yes | Completed | 2025-02-04 | 6303 | 6761 | 0 | 106% | 2025-02-12 | 100% | 100% | 100% | 2025-07-21 | Tentative Start Date 2/18/2025. 2-20-25 need GPR on sheet 6 crossing 51st ave.
D-HDH03 | St Petersburg | 2025-01-31 | Power Connect | 2025-02-04 | Robert | PPM89589 | 90 | Completed -Missed TSD | Received | Completed | Yes | 51958 | 20330.26 | Yes | Completed | 2025-02-06 | 760 | 708 | 0 | 95% | 2025-03-13 | 100% | 100% | 100% | 2025-05-15 | 2-10-2025 David Barrett To Fill Out An MOT Trooper Request 2-18-25 Pipe is all in need feeding route verified and proofed. PowerConnect addressing today.
D-HDH31 | St Petersburg | 2025-01-31 | Reycamp | 2025-02-04 | Betsy | PPM89043 | 86 | Completed -Missed TSD | Received | Completed | Yes | 82480.5 | 77870.5 | Yes | Completed | 2025-01-18 | 6390 | 6114 | 0 | 96% | 2025-01-30 | 100% | 100% | 100% | 2025-08-13 | Partial Completed--SOW / Footage Work Is For The County Permit That Is Pending Approval, All The City Work Has Been Completed.
D-HDH42 | St Petersburg | 2025-04-25 | FCA Fiber | 2025-03-27 | Betsy | PPM92270 | 88 | Completed on Track | Received | 2025-03-25 | Yes | 73070.5 | 72678 | Yes | Completed | 2025-04-02 | 6028 | 6070 | 0 | 100% | 2025-04-22 | 100% | 100% | 100% | 2025-06-16
D-HDH45 | St Petersburg | 2025-02-23 | Reycamp | 2025-02-03 | Betsy | PPM89601 | 73 | Completed -Missed TSD | Received | 2025-02-10 | Yes | 60575.5 | 59352 | Yes | Completed | 2025-02-03 | 4614 | 4614 | 0 | 100% | 2025-02-18 | 100% | 100% | 100% | 2025-08-19 | Tentative Start Date 2/18/2025. GPR Requested on 2/25/2025.
D-HDH46 | St Petersburg | 2025-02-23 | FCA Fiber | 2025-02-19 | Betsy | PPM89610 | 65 | Completed -Missed TSD | Received | 2025-02-10 | Yes | 65001 | 68269 | Yes | Completed | 2025-02-20 | 5284 | 5458 | 0 | 103% | 2025-03-06 | 100% | 100% | 100% | 2025-04-17
D-HDH47 | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-03-27 | Caten | PPM92273 | 70 | Completed on Track | Received | 2025-03-25 | Yes | 62104 | 64186 | Yes | Completed | 2025-03-28 | 5210 | 5139 | 0 | 100% | 2025-04-09 | 100% | 100% | 100% | 2025-05-12
D-HDH48 | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-03-27 | Caten | PPM92278 | 84 | Completed on Track | Received | 2025-03-25 | Yes | 63756.5 | 64902.5 | Yes | Completed | 2025-04-08 | 5237 | 5439 | 0 | 104% | 2025-04-18 | 100% | 100% | 100% | 2025-05-13
D-HDH49 | St Petersburg | 2025-04-25 | Brothers | 2025-03-27 | Johnnie | PPM92276 | 75 | Completed on Track | Received | 2025-03-25 | Yes | 67840.5 | 66607.5 | Yes | Completed | 2025-03-31 | 5601 | 5628 | 0 | 100% | 2025-04-14 | 100% | 100% | 100% | 2025-06-23
D-HDH50 | St Petersburg | 2025-06-23 | FCA Fiber | 2025-04-14 | Betsy | PPM93107 | 69 | Completed on Track | Received | 2025-04-10 | Yes | 53906.75 | 54578.5 | Yes | Completed | 2025-04-10 | 4615 | 4588 | 0 | 100% | 2025-04-25 | 100% | 100% | 100% | 2025-06-16
D-HDH52 | St Petersburg | 2025-06-23 | In House | 2025-05-30 | Johnnie | PPM93114 | 50 | Completed on Track | Received | 2025-04-10 | Yes | 47432.5 | 54385.09 | Yes | Completed | 2025-04-10 | 3932 | 4034 | 0 | 102% | 2025-04-24 | 0% | 0% | 0% | 2025-07-11 | 6/17/2025 JW ¦ RESTORATION ON GOING, SODZILLA WILL BE WRAPPING UP, PENDING TILLMAN WALKOUT
D-HDH53 | St Petersburg | 2025-06-23 | Longo Underground | 2025-04-14 | Tim | PPM93118 | 76 | Completed | Received | 2025-04-10 | Yes | 62383 | 61939 | Yes | Completed | 2025-04-10 | 5164 | 5164 | 0 | 100% | 2025-04-25 | 100% | 100% | 100% | 2025-06-30
D-HDH54 | St Petersburg | 2025-06-23 | HAS Global | 2025-04-14 | Johnnie | PPM93122 | 88 | Completed | Received | 2025-04-10 | Yes | 80443.5 | 81941 | Yes | Completed | 2025-04-10 | 6617 | 6743 | 0 | 102% | 2025-04-24 | 0% | 0% | 0% | 2025-07-11 | 6/17/2025 JW ¦ RESTORATION COMPLETE \\ PENDING TILLMAN WALKOUT
D-HDH55 | St Petersburg | 2025-06-23 | In House | 2025-05-30 | Johnnie | PPM93069 | 86 | Completed on Track | Received | 2025-04-10 | Yes | 68736.5 | 68249 | Yes | Completed | 2025-04-09 | 5939 | 5791 | 0 | 97% | 2025-04-21 | 0% | 0% | 0% | 2025-07-11 | 6/17/2025 JW ¦ RESTORATION COMPLETE \\ PENDING TILLMAN WALKOUT
D-HDH56 | St Petersburg | 2025-04-25 | Longo Underground | 2025-03-27 | Tim | PPM92087 | 84 | Completed on Track | Received | 2025-03-25 | Yes | 73491.5 | 202651 | Yes | Completed | 2025-04-01 | 5390 | 5327 | 0 | 100% | 2025-04-21 | 0% | 0% | 0% | 2025-07-21
D-HDH60 | St Petersburg | 2025-04-25 | Longo Underground | 2025-03-27 | Tim | PPM92088 | 80 | Completed on Track | Received | 2025-03-25 | Yes | 70235 | 134171.5 | Yes | Completed | 2025-03-29 | 5585 | 5566 | 0 | 100% | 2025-04-10 | 100% | 100% | 100% | 2025-07-21
D-HDH66 | St Petersburg | 2025-01-31 | Bartlett Fiber | 2025-01-27 | Caten | PPM88373 | 90 | Completed -Missed TSD | Received | Completed | Yes | 60625.5 | 59084 | Yes | Completed | 2025-01-22 | 5038 | 4909 | 0 | 98% | 2025-01-27 | 100% | 100% | 100% | 2025-06-23
D-HDH67 | St Petersburg | 2025-04-25 | Power Connect | 2025-02-28 | Robert | PPM91122 | 86 | Completed on Track | Received | 2025-03-05 | Yes | 79507 | 86709.5 | Yes | Completed | 2025-03-04 | 6756 | 6667 | 0 | 99% | 2025-03-12 | 100% | 100% | 100% | 2025-05-14
D-HDH70 | St Petersburg | 2025-04-25 | Longo Underground | 2025-02-28 | Tim | PPM91121 | 82 | Completed on Track | Received | 2025-02-28 | Yes | 64609 | 76965 | Yes | Completed | 2025-03-04 | 5327 | 5450 | 0 | 102% | 2025-03-12 | 100% | 100% | 100% | 2025-07-21
D-HDH73 | St Petersburg | 2025-04-25 | Power Connect | 2025-02-04 | Robert | PPM89626 | 59 | Completed on Track | Received | 2025-02-10 | Yes | 52222 | 51838 | Yes | Completed | 2025-02-03 | 4772 | 4329 | 0 | 91% | 2025-02-19 | 100% | 100% | 100% | 2025-05-14
D-HDH75 | St Petersburg | 2025-04-25 | Longo Underground | 2025-02-28 | Tim | PPM91431 | 88 | Completed | Received | 2025-02-28 | Yes | 67463 | 69992 | Yes | Completed | 2025-03-04 | 5491 | 5605 | 0 | 102% | 2025-03-19 | 100% | 100% | 100% | 2025-06-23
D-HDH76 | St Petersburg | 2025-02-23 | J Garcia / US Builders | 2025-02-04 | David | PPM89553 | 86 | Completed -Missed TSD | Received | 2025-02-10 | Yes | 66638 | 65072 | Yes | Completed | 2025-02-03 | 5428 | 5399 | 0 | 100% | 2025-02-12 | 100% | 100% | 100%
D-HDH78 | St Petersburg | 2025-02-23 | FCA Fiber | 2025-02-18 | Betsy | PPM90248 | 85 | Completed on Track | Received | 2025-02-19 | Yes | 67,657,50 | 67080 | Yes | Completed | 2025-02-19 | 5564 | 5576 | 0 | 100% | 2025-03-11 | 100% | 100% | 100% | 2025-04-10
D-HDH80 | St Petersburg | 2025-04-25 | MTX | 2025-03-27 | Sean | PPM92262 | 91 | Completed on Track | Received | 2025-03-25 | Yes | 79069.5 | 73300 | Yes | Completed | 2025-03-28 | 6330 | 6180 | 0 | 97% | 2025-04-04 | 100% | 100% | 100% | 2025-07-21
D-HDH82 | St Petersburg | 2025-04-25 | MTX | 2025-03-27 | Sean | PPM92198 | 20 | Completed on Track | Received | 2025-03-25 | Yes | 16398 | 15664 | Yes | Completed | 2025-03-28 | 1265 | 1257 | 0 | 100% | 2025-04-03 | 100% | 100% | 100% | 2025-07-11
D-HNP137 | St Petersburg | 2025-04-30 | FCA Fiber | 2025-02-12 | Betsy | PPM89749 | 78 | Completed | Received | 2025-02-20 | Yes | 56854 | 62254 | Yes | Completed | 2025-02-08 | 5239 | 5205 | 0 | 100% | 2025-02-28 | 100% | 100% | 100% | 2025-05-14
D-HNP138 | St Petersburg | 2025-03-26 | FCA Fiber | 2025-02-06 | Betsy | PPM89683 | 87 | Completed | Received | 2025-02-20 | Yes | 73639 | 73025 | Yes | Completed | 2025-02-08 | 5868 | 5979 | 0 | 102% | 2025-02-26 | 100% | 100% | 100% | 2025-04-11
D-HNP141 | St Petersburg | 2025-03-31 | Power Connect | 2025-02-12 | Robert | PPM89690 | 60 | Completed | Received | 2025-02-10 | Yes | 54861 | 55197 | Yes | Completed | 2025-02-10 | 4552 | 4552 | 0 | 100% | 2025-03-11 | 100% | 100% | 100% | 2025-06-03
D-HNP151 | St Petersburg | 2025-06-30 | Longo Underground | 2025-03-20 | Tim | PPM90865 | 50 | Completed on Track | Received | 2025-03-19 | Yes | 41285 | 40484 | Yes | Completed | 2025-03-20 | 3415 | 3445 | 0 | 100% | 2025-04-02 | 100% | 100% | 100% | 2025-07-21
FB-H0221A | St Petersburg | 2025-03-26 | HAS Global | 2025-02-19 | Johnnie | PPM89791 | 0 | Completed -Missed TSD | Received | 2025-02-28 | Yes | 21944.6 | 26564 | Yes | Completed | 2025-02-28 | 1695 | 1634 | 0 | 96% | 2025-03-18 | 100% | 100% | 100% | 2025-07-11 | 5/14/2025 PENDING RESTO / TILLMAN / LIGHT LEVELS
FB-H0222A | St Petersburg | 2025-02-23 | Bartlett Fiber | 2025-02-07 | Caten | PPM88374 | 0 | Completed -Missed TSD | Received | 2025-02-07 | Yes | 20939.75 | 13575.75 | Yes | Completed | 2025-02-05 | 1235 | 1160 | 0 | 95% | 2025-03-11 | 100% | 100% | 100% | 2025-08-19
[12 empty] | 3835658.54 | 4061426.3
Repairs | [12 empty] | 31333
4092759.3
Pending Invoiced
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Door Tag Date | SOW Received | SOW Estimated Cost | Invoice Amount Paid | NTP Received | Constuction Status | Locate Date | Footage UG | Actual Redline Completed Footage UG | Fiber Placement and Splice Only Footage | UG Percentage Complete | Construction Start Date | Fiber Placement Percentage Complete | Splicing Percentage Complete | Construction Total Percent Complete | QC Received From Tillman | Comments
FB-HOE117 | Bradenton | 2025-02-23 | Brothers | 2025-02-19 | Allen | MAN89824 | 0 | Completed on Track | Received | 2025-02-13 | Yes | 111163 |  | Yes | Completed | 2025-03-02 | 7805 | 7969 | 0 | 102% | 2025-03-24 | 100% | 100% | 100% | 2025-07-16
D-HOE102 | Bradenton | 2025-05-30 | MTX | 2025-02-18 | Joshua | MAN89819 | 56 | Completed on Track | Received | 2025-02-13 | Yes | 55089 |  | Yes | Completed | 2025-02-21 | 4836 | 5095 | 0 | 105% | 2025-03-25 | 100% | 100% | 100% | 2025-09-26 | 4-29-25 Was MTX need to reassign.
BHT-FWP-08 | Lakeland | 2025-07-30 | Brothers | 2025-06-05 | Anthony | PLK96231 | 0 | Completed on Track | Received | 2025-05-16 | Yes | 104070.8 |  | Yes | Completed | 2025-05-16 | 7848 | 7859 | 0 | 100% | 2025-06-17 | 100% | 100% | 100% | 2025-08-28 | 1465 drilled 6-17/ 6/23 Drilling 1269'/ 6/24 - DOT Xing scheduled for 6/26. 6/30- All path complete, Dave Simmon is getting a date to place fiber. Cozmin to work on restoration 7/1. 7/7- placing and restoration complete, only thing pending is splicing. Construction CO sent to Garrison
D-HWP801 | Lakeland | 2025-07-30 | Brothers | 2025-05-19 | Anthony | PLK95087 | 58 | Completed on Track | Received | 2025-05-20 | Yes | 43097.65 |  | Yes | Completed | 2025-06-02 | 3309 | 3194 | 0 | 96% | 2025-06-24 | 100% | 100% | 100% | 2025-08-29 | NEED NTP per James. City of Lakeland Permit Received/dis for doortag and locates 5-19. 5/27-I asked Brothers to call in locates/doortags b/c they have not done so yet. / 6/9 doortagged 6/6 and loc called in 6/2 / 6/24- Brothers drilling 1044' / 1100' 6-25/ 1050' Path complete 6-26/pending qc form 7-1/needs change order
D-HWP812 | Lakeland | 2025-07-30 | Brothers | 2025-07-01 | Travis | PLK97117 | 77 | Completed on Track | Received | 2025-07-02 | Yes | 10430.55 |  | Yes | Completed | 2025-07-02 | 2773 | 2659 | 0 | 96% | 2025-07-21 | 100% | 100% | 100% | 2025-08-06 | Needs City Permit, Just Email
D-HWP814 | Lakeland | 2025-07-30 | Brothers | 2025-07-02 | Travis | PLK97122 | 81 | Completed on Track | Received | 2025-07-09 | Yes | 71310.9 |  | Yes | Completed | 2025-07-09 | 4940 | 4818 | 0 | 97% | 2025-07-16 | 100% | 100% | 100% | 2025-08-06 | need bore logs to finish cop
D-HWP815 | Lakeland | 2025-07-30 | Brothers | 2025-07-01 | Travis | PLK97093 | 86 | Completed on Track | Received | 2025-07-02 | Yes | 53605.2 |  | Yes | Completed | 2025-07-02 | 4009 | 4039 | 0 | 101% | 2025-07-24 | 100% | 100% | 100% | 2025-08-06 | Tickets expedited 7-14
D-HWP821 | Lakeland | 2025-07-30 | Brothers | 2025-06-25 | Anthony | PLK96634 | 66 | Completed on Track | Received | 2025-06-25 | Yes | 32940.45 |  | Yes | Completed | 2025-06-25 | 2067 | 2937 | 0 | 144% | 2025-07-02 | 100% | 100% | 100% | 2025-08-28 | dispatched 6-25,start eta 7.3 / 7/2 Brothers drilled 355' and drill broke down, will resume next week.
D-HWP822 | Lakeland | 2025-07-30 | Brothers | 2025-07-01 | Travis | PLK97098 | 43 | Completed on Track | Received | 2025-07-02 | Yes | 23404.75 |  | Yes | Completed | 2025-07-02 | 1667 | 1661 | 0 | 100% | 2025-07-15 | 100% | 100% | 100% | 2025-09-16 | Needs City Permit, Just Email/ Assigned to Brothers 7-1/ 7/3- need city permit / 7/9- Pending clear locates, ESD 7/14-15/need light levels to complete cop/
FB-HWP1302 | Lakeland | 2025-07-30 | Lightspeed In-House | 2025-07-11 | Travis | PLK97344 | 0 | Completed on Track | Received | 2025-07-10 | Yes | 1206 |  | Yes | Completed | 2025-07-10 | 90 | 90 | 0 | 100% | 2025-07-16 | 100% | 100% | 100% | 2025-08-29 | SCH 7/16
FB-HWP175 | Lakeland | 2025-06-30 | Brothers | 2025-06-09 | Travis | PLK96355 | 0 | Completed on Track | Received | 2025-06-13 | Yes | 23436.55 |  | Yes | Completed | 2025-06-09 | 1769 | 1044 | 0 | 60% | 2025-06-23 | 100% | 100% | 100% | 2025-08-28 | portion on 10th st is built previously,needs proffed and tie piont on mlk with 144/6-17 tentative con date. 6/18- Brothers driller not working today, ESD 6/23/ring cut to hand off to mdu project/952' 6-23/fiber to pull 6-26
FB-HWP477 | Lakeland | 2025-08-30 | In House | 2025-08-07 | Anthony |  | 0 | Project Cancelled | Received | TBD | Yes | 1343 |  | Yes | Project Cancelled | Not Required | 74 | 0 | 0 | 0% | Not Required | 0% | 0% | 0% | Not Required | 6/24 Pending Permit.
FB-HWP804 | Lakeland | 2025-07-30 | Lightspeed In-House | 2025-07-15 | Travis | PLK97717 | 0 | Completed on Track | Received | 2025-07-15 | Yes | 68216.5 |  | Yes | Completed | 2025-07-15 | 581 | 581 | 0 | 100% | 2025-07-30 | 100% | 100% | 100% | 2025-09-16 | Sch 7-21 with Telecom/ih drilling 7-28/complete
FB-HWP902 | Lakeland | 2025-07-30 | Lightspeed In-House | 2025-07-01 | Travis | PLK97335 | 0 | Completed on Track | Received | 2025-06-30 | Yes | 72566 |  | Yes | Completed | 2025-06-30 | 765 | 786 | 0 | 103% | 2025-07-07 | 100% | 100% | 100% | 2025-09-16 | Restoration 7-14/passed tillman qc
FB-HWP375 | Lakeland | 2025-08-30 | Lightspeed In-House | 2025-08-07 | Travis |  | 0 | Completed on Track | Received | 2025-08-07 | Yes | 1462.85 |  | Yes | Completed | 2025-08-07 | 116 | 130 | 0 | 100% | 2025-08-27 | 100% | 100% | 100% | 2025-09-26 | white lined + call loc 8-7/startred 8-25/need soft dig/spl sch for 8-28 pm
FB-HWP776 | Lakeland | 2025-08-30 | Brothers | 2025-08-13 | Anthony |  | 0 | Completed on Track | Received | 2025-08-13 | Yes | 13056.5 |  | Yes | Completed | 2025-08-13 | 1100 | 1110 | 0 | 100% | 2025-08-18 | 100% | 100% | 100% | 2025-09-26 | permit received 8-13/dispatched 8-13 / 8-21 placing complete, ready to splice. Tillman's MDU portion may not be placed./spl sch 8-28pm
FB-HWP802 | Lakeland | 2025-09-30 | Lightspeed In-House | 2025-07-30 | Travis | PLK98828 | 0 | Completed on Track | Received | 2025-07-30 | Yes | 14179.65 |  | Yes | Completed | 2025-07-30 | 973 | 1060 | 0 | 109% | 2025-08-11 | 100% | 100% | 100% | 2025-09-26 | white lined + Loc called 7-30/sch to start 8-11/
FB-HWP1375 | Lakeland | 2025-08-30 | Lightspeed In-House | 2025-08-13 | Travis | PLK97346 | 0 | Completed on Track | Received | TBD | Yes | 18903.7 |  | Yes | Completed | 2025-08-13 | 575 | 575 | 0 | 100% | 2025-08-18 | 100% | 100% | 100% | 2025-09-26 | 6/16- need city and county permit/ White lined/loc 8-13/cx start 8-26/spl sch for 8-29/splicing needs complete
FB-HWP1376 | Lakeland | 2025-08-30 | Lightspeed In-House | 2025-05-29 | Travis | PLK96627 | 0 | Completed on Track | Received | 6/16/25 County | Yes | 21888.65 |  | Yes | Completed | 2025-06-16 | 1669 | 1701 | 0 | 100% | 2025-06-25 | 100% | 100% | 100% | 2025-09-26 | 6/16- whitelines/locates/doortags/County permit activation req sent all on 6/16. 6/18- County permit is active and Xing scheduled for 6/24 11am. Still need city permit for final completion.. 6/24- County permit rescheduled for 7/2 11am./ Drilled 335' 6-25/ 7/3- need city permit. / 8/1- called in LS locates for city portion
12 Oaks MHP | Lakeland | 2025-08-30 | Brothers | 2025-08-04 | Anthony |  | 50 | Completed on Track | Not Required | 2025-08-05 | Yes | 11894.25 |  | Yes | Completed | 2025-08-04 | 1471 | 1437 | 0 | 98% | 2025-08-12 | 100% | 100% | 100% | 2025-09-26
FX4-FWP-13 | Lakeland | 2025-05-10 | Brothers | 2025-04-16 | Anthony | PLK93160 | 0 | Completed on Track | Received | Completed | Yes | 3707.3 |  | Yes | Completed | 2025-04-16 | 143 | 143 | 0 | 100% | 2025-04-21 | 0% | 0% | 100% | 2025-09-26 | gave to power connect 2-17-25/START 2-26/exp 811 2-26/not clear 3-4@730am/3-4 3rd notice called into to 811 8am/ partial locates work sch 3-5 tin in to 713 locates not complete 3-4 @3pm/ Expedited 4pm 3-4/*do not build peice ro 703(ada x-ing)/ Expedited locates 4pm 3-5/pending zayo marks 3-7/talked to state manager for zayo, he is dending them asap to locate/Zayo marked. 3-10 Power connect drilling, Returning 3-11 to connect Griffin Rd to N Florida and pull 48f. 3/12-IP, 100' left to bore on Kalt Dr. to tie in D-HWP713, 48f pull. 3/13- x-ing at Martha call locates 3-13 for ls to complete/. 3/13- locs called/whitelined, IH crew to dig up 144 and place 48f so D701,D705 and D702 can be heated up. 3/17- still pending clear loc for Martha(will expedite tmrw), Tillman aprvd a bore to get a 48f from FB to D701 loc called 3.14./504' 4-10/dot sch for 5-13 9am/ 5/7- DOT Xing scheduled for Tuesday 5/13. Expedited tickets 5-8*fs sch 5-22/ DOT crossing sch 5-20. 5/14 1190' today, will return on 5/20 to complete remaining path. / 5/19 Brothers said they were doing this bore on 5.20 and made a mistake with the date, it is scheduled for 5.21 and the fiber to be pulled in on the same day. / 6/5- Tillman walking today
FB-HWP975 | Lakeland | 2025-09-30 | Lightspeed In-House | 2025-09-02 | Travis |  | 0 | Completed on Track | Received | 2025-09-02 | Yes | 3067.9 |  | Yes | Completed | 2025-09-02 | 662 | 662 | 0 | 100% | 2025-09-09 | 100% | 100% | 100% | 2025-09-26 | 8/28 Pending permit/received permit 9-4/CL 9-2/ cx started 9-9/CX complete 9-11
D-H0220A | St Petersburg | 2025-06-30 | Longo Underground | 2025-06-10 | Tim | PPM95827 | 56 | Completed on Track | Received | 2025-06-09 | Yes | 75953 |  | Yes | Completed | 2025-06-09 | 6005 | 6044 | 0 | 100% | 2025-06-16 | 100% | 100% | 100% | 2025-07-30
D-H0220B | St Petersburg | 2025-07-30 | US Builders / Longo Underground | 2025-03-03 | Tim | PPM91680 | 60 | Completed on Track | Received | 2025-02-28 | Yes | 64727 |  | Yes | Completed | 2025-03-03 | 5853 | 5975 | 0 | 102% | 2025-03-25 | 100% | 100% | 100% | 2025-07-30
D-H0221A | St Petersburg | 2025-05-30 | Brothers | 2025-03-11 | Johnnie | PPM91357 | 90 | Completed | Received | 2025-03-12 | Yes | 82979.5 |  | Yes | Completed | 2025-03-12 | 6524 | 6492 | 0 | 100% | 2025-03-24 | 100% | 100% | 100% | 2025-09-16 | 6/17/2025 JW ¦ TILLMAN WALKOUT SET FOR 6/18/2025 (0830) 4/28 JW ¦ PLEASE SEE COMMENT
D-H0221B | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-02-28 | Caten | PPM91351 | 56 | Completed on Track | Received | 2025-02-28 | Yes | 45321.5 |  | Yes | Completed | 2025-03-06 | 3642 | 3666 | 0 | 100% | 2025-03-18 | 100% | 100% | 100% | 2025-09-17
D-H0223D | St Petersburg | 2025-04-25 | Brothers | 2025-01-28 | Johnnie | PPM89579 | 81 | Completed on Track | Received | 2025-02-11 | Yes | 73583.5 |  | Yes | Completed | 2025-02-03 | 6205 | 6180 | 0 | 100% | 2025-02-11 | 100% | 100% | 100% | 2025-09-16 | 6/17/2025 JW ¦ PENDING TILLMAN WALKOUT RESTORATION COMPLETE \\ 5/14/2025 FINAL COP IN PROGRESS PENDING TILLMAN QAQC AND LIGHT LEVELS. 8-27-25 rewalk scheduled for -9-10-25
D-HDH57 | St Petersburg | 2025-06-23 | Bartlett Fiber | 2025-05-30 | Caten | PPM92588 | 87 | Completed on Track | Received | 2025-04-10 | Yes | 78331 |  | Yes | Completed | 2025-04-10 | 6334 | 6228 | 0 | 98% | 2025-04-22 | 0% | 0% | 0% | 2025-09-17 | 4-29-25 Was MTX need to reassign.
D-HDH58 | St Petersburg | 2025-04-25 | Brothers | 2025-03-27 | Johnnie | PPM92280 | 81 | Completed on Track | Received | 2025-03-25 | Yes | 74961 |  | Yes | Completed | 2025-03-31 | 6327 | 6414 | 0 | 101% | 2025-04-14 | 100% | 100% | 100% | 2025-08-25 | 6/17/2025 JW ¦ RESTORATION COMPLETE \\ PENDING TILLMAN WALKOUT
D-HDH62 | St Petersburg | 2025-04-25 | US Builders | 2025-03-27 | Caten | PPM92283 | 63 | Completed on Track | Received | 2025-03-25 | Yes | 41813 |  | Yes | Completed | 2025-03-29 | 3243 | 3290 | 0 | 100% | 2025-04-14 | 100% | 100% | 100% | 2025-09-17 | original walkout was on 6-20-25 no qc recieved. reissued walkout for 8-26-25
D-HDH68 | St Petersburg | 2025-02-23 | Longo Underground | 2025-01-29 | Tim | PPM89616 | 90 | Completed -Missed TSD | Received | 2025-02-12 | Yes | 77320 |  | Yes | Completed | 2025-02-18 | 6041 | 6024 | 0 | 100% | 2025-02-26 | 100% | 100% | 100% | 2025-08-25 | -2-24-25 sent info to us building they will be subbing in for longo on this project starting 02-26-25..2-27-25 longo on site
D-HDH69 | St Petersburg | 2025-04-25 | Longo Underground | 2025-02-20 | Tim | PPM89618 | 82 | Completed on Track | Received | 2025-02-10 | Yes | 71979 |  | Yes | Completed | 2025-02-06 | 5628 | 3692 | 0 | 70% | 2025-03-26 | 100% | 100% | 100% | 2025-08-25
D-HDH71 | St Petersburg | 2025-04-25 | HDD Underground | 2025-02-06 | Betsy | PPM89623 | 64 | Completed on Track | Received | 2025-02-13 | Yes | 48609 |  | Yes | Completed | 2025-02-10 | 4035 | 4045 | 0 | 100% | 2025-02-21 | 100% | 100% | 100% | 2025-08-25 | Notified Chris Tillman of the crew going off run line a bit due to gas / water. sent him pics/video, spoke with chris and said to stay as close as safley possible. 2/17 340pm SL .
D-HDH74 | St Petersburg | 2025-04-25 | Bartlett Fiber | 2025-01-29 | Caten | PPM89643 | 85 | Completed on Track | Received | 2025-02-10 | Yes | 67892.5 |  | Yes | Completed | 2025-02-21 | 5494 | 5431 | 0 | 99% | 2025-03-06 | 100% | 100% | 100% | 2025-09-17 | Locates called in 02-20-25
D-HNP104/D-H0102A | St Petersburg | 2025-07-24 | Longo Underground | 2025-03-27 | Tim | PPM93993 | 88 | Completed on Track | Received | 2025-03-25 | Yes | 75396.5 |  | Yes | Completed | 2025-04-02 | 6061 | 6217 | 0 | 103% | 2025-05-08 | 0% | 0% | 0% | 2025-08-18
D-HNP123 | St Petersburg | 2025-07-24 | HDD Underground | 2025-02-06 | Betsy | PPM89671 | 90 | Completed on Track | Received | 2025-02-10 | Yes | 68216.5 |  | Yes | Completed | 2025-02-10 | 5410 | 5337 | 0 | 99% | 2025-03-03 | 100% | 100% | 100% | 2025-09-17 | reassigned to MTX. 4-29-25 needs new reassignment.
D-HNP143 | St Petersburg | 2025-03-31 | Brothers | 2025-02-10 | Johnnie | PPM89772 | 87 | Completed | Received | 2025-02-11 | Yes | 72566 |  | Yes | Completed | 2025-02-11 | 6133 | 6133 | 0 | 100% | 2025-03-05 | 100% | 100% | 100% | 2025-09-17 | 6/17/2025 JW ¦ RESTORATION COMPLETE \\ PENDING TILLMAN WALKOUT. 8-18-25 rescheduled walkout for 9-4-25
FB-H0220A | St Petersburg | 2025-03-26 | Longo Underground | 2025-02-20 | Tim | PPM89778 | 0 | Completed | Received | 2025-02-24 | Yes | 14262 |  | Yes | Completed | 2025-02-24 | 826 | 810 | 0 | 100% | 2025-03-25 | 100% | 100% | 100% | 2025-07-29
FB-HDH01A-2A | St Petersburg | 2025-06-30 | In House | 2025-06-16 | Johnnie | PPM96333 | 0 | Completed on Track | Received | TBD | Yes | 1594 |  | Yes | Completed | 2025-06-10 | 65 | 65 | 0 | 100% | 2025-06-23 | 100% | 100% | 100% | 2025-07-21 | Partial Completed--SOW Shows The Whole Project, But This Is To Complete 4100' Left On The Project.
FB-HDH275 | St Petersburg | 2025-03-26 | HDD Underground | 2025-02-20 | Betsy | PPM89801 | 0 | Completed on Track | Received | 2025-02-26 | Yes | 93462.85 |  | Yes | Completed | 2025-02-21 | 7497 | 7251 | 0 | 96% | 2025-03-12 | 100% | 100% | 100% | 2025-09-16
FB-HWP482 | Lakeland | 2025-08-30 | Brothers | 2025-08-01 | Anthony | PLK97720 | 0 | Completed on Track | Received | 2025-08-01 | Yes | 49307.5 |  | Yes | Completed | 2025-08-01 | 3914 | 3675 | 0 | 94% | 2025-08-04 | 100% | 100% | 100% | 2025-09-16 | Have County, Need City./ 7-23 Assigned county work to Brothers. Need LOCs so we can activate cnty permit/ Conuty sch 8-4, 8/1- city locates called by Brothers
FB-HWP775 | Lakeland | 2025-08-30 | Brothers | 2025-08-01 | Anthony | PLK98767 | 0 | Completed on Track | Received | 2025-08-01 | Yes | 12886.4 |  | Yes | Completed | 2025-08-01 | 884 | 797 | 0 | 90% | 2025-08-07 | 100% | 100% | 100% | 2025-09-16 | Need city, App only. 8/1- Had Brothers call in locates for this and 12 Oaks MHP.
Note on S2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Approx. 100' Added For Tie In To D-HWP701.
Note on U2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Conduit Placement Confirmed Completed. Reply: 6-3-2025 Approx. 100' Added For Tie In To D-HWP701.
Note on S4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-18-2025 Confirmed Actual Completed Footage.
Note on U4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-18-2025 Conduit Placement Confirmed Completed.
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2-20-2025 Only the FDOT Permit Has Been Received--City Permit to Follow. Reply: 3-11-2025 City of Lakeland Permit Added to the Folder. Reply: 3-11-2025 City of Lakeland Permit Is Only the Cover Page.
Note on S5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-31-2025 Drill Footage Changed. Project Completed Reply: 4-9-2025 Confirmed Actual Completed Footage.
Note on U5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on P6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To FDC On 2-5-2025.
Note on S6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on U6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on P7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on S7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Confirmed Actual Completed Footage.
Note on U7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Conduit Placement Confirmed Completed.
Note on S8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2025 Confirmed Actual Completed Footage.
Note on U8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2025 Conduit Placement Confirmed Completed.
Note on S9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-15-2025 Confirmed Actual Completed Footage.
Note on U9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-15-2025 Conduit Placement Confirmed Completed.
Note on S10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-4-2025 Confirmed Actual Completed Footage.
Note on U10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-4-2025 Conduit Placement Confirmed Completed.
Note on S11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-5-2025 Confirmed Actual Completed Footage.
Note on U11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-5-2025 Conduit Placement Confirmed Completed.
Note on S12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2025 Confirmed Actual Completed Footage.
Note on U12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-14-2025 Conduit Placement Confirmed Completed.
Note on S13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Confirmed Actual Completed Footage.
Note on U13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Conduit Placement Confirmed Completed.
Note on P14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project Completed As Per Brothers On 2-3-2025.
Note on S14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Confirmed Actual Completed Footage.
Note on U14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Conduit Placement Confirmed Completed.
Note on S15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2025 Confirmed Actual Completed Footage.
Note on U15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2025 Conduit Placement Confirmed Completed.
Note on S16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Confirmed Actual Completed Footage.
Note on U16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Conduit Placement Confirmed Completed.
Note on P17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Brothers As Per Tom On 2-3-2025. Locates To Be Called In On 2-6-2025.
Note on S17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on U17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on S18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Confirmed Actual Completed Footage.
Note on U18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Conduit Placement Confirmed Completed.
Note on S19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-23-2025 Confirmed Actual Completed Footage.
Note on U19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-23-2025 Conduit Placement Confirmed Completed.
Note on S20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Confirmed Actual Completed Footage.
Note on U20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Conduit Placement Confirmed Completed.
Note on R21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2025 SiteTracker Footage Has 4,123'.
Note on S21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2025 Confirmed Actual Completed Footage.
Note on U21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2025 Conduit Placement Confirmed Completed.
Note on S22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on U22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on P23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Brothers As Per Tom On 2-3-2025. Locates To Be Called In On 2-6-2025.
Note on S23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on U23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on S24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-5-2025 Confirmed Actual Completed Footage.
Note on U24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-5-2025 Conduit Placement Confirmed Completed.
Note on S25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-19-2025 Confirmed Actual Completed Footage.
Note on U25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-19-2025 Conduit Placement Confirmed Completed.
Note on P26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Brothers As Per Tom On 2-3-2025. Locates To Be Called In On 2-6-2025.
Note on S26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-16-2025 Confirmed Actual Completed Footage.
Note on U26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-16-2025 Conduit Placement Confirmed Completed.
Note on R28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Partial Project, Most Of The Drilling Was Completed By Circet Prior To Lightspeed Receiving The Project.
Note on S28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Confirmed Actual Completed Footage.
Note on U28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-11-2025 Conduit Placement Confirmed Completed.
Note on S29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-20-2025 Confirmed Actual Completed Footage.
Note on U29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-20-2025 Conduit Placement Confirmed Completed.
Note on S30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on U30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on S31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Confirmed Actual Completed Footage.
Note on U31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-9-2025 Conduit Placement Confirmed Completed.
Note on P32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on S32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-13-2025 Confirmed Actual Completed Footage.
Note on U32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-13-2025 Conduit Placement Confirmed Completed.
Note on R34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Design Change Approved By Tillman.
Note on S34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on U34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on S35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on U35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on S36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on U36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on P38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Partial Build Project Per Tillman On 2-10-2025.
Note on R38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-19-2025 Drill Footage Based Off SiteTracker--5,325 Total
Note on S38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per Tillman on 2-10-2025 Job Is Completed Except 6 Crossings On 6th Ave. SOW Shows Total For The Entire Project. Reply: 6-27-2025 Confirmed Actual Completed Footage.
Note on U38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-27-2025 Conduit Placement Confirmed Completed.
Note on S39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-13-2025 Confirmed Actual Completed Footage.
Note on U39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-13-2025 Conduit Placement Confirmed Completed.
Note on S40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-21-2025 Confirmed Actual Completed Footage.
Note on U40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-21-2025 Conduit Placement Confirmed Completed.
Note on S41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-22-2025 Confirmed Actual Completed Footage.
Note on U41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-22-2025 Conduit Placement Confirmed Completed.
Note on P42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on S42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-16-2025 Confirmed Actual Completed Footage.
Note on U42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-16-2025 Conduit Placement Confirmed Completed.
Note on S43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-14-2025 Confirmed Actual Completed Footage.
Note on U43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-14-2025 Conduit Placement Confirmed Completed.
Note on S44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-14-2025 Confirmed Actual Completed Footage.
Note on U44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-14-2025 Conduit Placement Confirmed Completed.
Note on S45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-23-2025 Confirmed Actual Completed Footage.
Note on U45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-23-2025 Conduit Placement Confirmed Completed.
Note on S46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on U46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on S48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Confirmed Actual Completed Footage.
Note on U48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 Conduit Placement Confirmed Completed.
Note on S53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on U53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on X53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-14-2025 Splicing Completed by Utilities One as Per Tillman.
Note on S54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-11-2025 Confirmed Actual Completed Footage.
Note on U54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-11-2025 Conduit Placement Confirmed Completed.
Note on P56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Power Connect as Per Curtis on 2-4-2025.
Note on S56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-12-2025 Confirmed Actual Completed Footage.
Note on U56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-12-2025 Conduit Placement Confirmed Completed.
Note on S57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Confirmed Actual Completed Footage.
Note on U57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 Conduit Placement Confirmed Completed.
Note on S58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-16-2025 Confirmed Actual Completed Footage.
Note on U58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-16-2025 Conduit Placement Confirmed Completed.
Note on S59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-17-2025 Confirmed Actual Completed Footage.
Note on U59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-16-2025 Conduit Placement Confirmed Completed.
Note on R62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-19-2025 Project Completed-Re-Design on Project Changed the Footage.
Note on S62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-29-2025 Confirmed Actual Completed Footage.
Note on U62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-29-2025 Conduit Placement Confirmed Completed.
Note on A63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-3-2025 As Per Theresa Only Construction Has Been Invoiced--Fiber To Follow.
Note on P63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FCA
Note on S63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-13-2025 Confirmed Actual Completed Footage.
Note on U63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-13-2025 Conduit Placement Confirmed Completed.
Note on S64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-11-2025 Confirmed Actual Completed Footage.
Note on U64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-11-2025 Conduit Placement Confirmed Completed.
Note on R66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-6-2025 222' Of Additional 1 1/2 Conduit Was Placed On This Project.
Note on S67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-30-2025 Confirmed Actual Completed Footage.
Note on U67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-30-2025 Conduit Placement Confirmed Completed.
Note on S75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-18-2025 Confirmed Actual Completed Footage.
Note on U75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-18-2025 Conduit Placement Confirmed Completed.
Note on P76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on S76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-9-2025 Confirmed Actual Completed Footage.
Note on U76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-9-2025 Conduit Placement Confirmed Completed. Reply: 7-10-2025 Change Order Approved By Tillman(Chad Plummer).
Note on S77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Confirmed Actual Completed Footage.
Note on U77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Conduit Placement Confirmed Completed.
Note on A78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-20-2025 Pending SiteTracker Change By Tillman.
Note on S78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-9-2025 Confirmed Actual Completed Footage.
Note on U78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-9-2025 Conduit Placement Confirmed Completed.
Note on S79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-8-2025 Confirmed Actual Completed Footage.
Note on U79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-8-2025 Conduit Placement Confirmed Completed.
Note on S80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-26-2025 Confirmed Actual Completed Footage.
Note on U80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-26-2025 Conduit Placement Confirmed Completed.
Note on S81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-8-2025 Confirmed Actual Completed Footage.
Note on U81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-8-2025 Conduit Placement Confirmed Completed.
Note on S82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Confirmed Actual Completed Footage. Reply: 7-11-2025 Design Change In Footage(909') As Some Of This Project Was Original On Project FB-HWP801.
Note on U82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Conduit Placement Confirmed Completed.
Note on S83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2025 Confirmed Actual Completed Footage.
Note on U83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-16-2025 Conduit Placement Confirmed Completed.
Note on S84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Confirmed Actual Completed Footage.
Note on U84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Conduit Placement Confirmed Completed.
Note on S85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-24-2025 As Per Tom M Project Has Pre-Existing Piping On Part Of The Project. Reply: 8-7-2025 Confirmed Actual Completed Footage.
Note on U85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-24-2025 As Per Tom M Project Has Pre-Existing Piping On Part Of The Project. Reply: 8-7-2025 Confirmed Actual Completed Footage.
Note on A86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-5-2025 Project Cancelled By Tillman After Lightspeed GPR Location. Lightspeed To Submit Invoice For GPR.
Note on S87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-4-2025 Confirmed Actual Completed Footage.
Note on U87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-4-2025 Conduit Placement Confirmed Completed.
Note on S88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-26-2025 Confirmed Actual Completed Footage.
Note on U88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-26-2025 Conduit Placement Confirmed Completed.
Note on A89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-29-2025 Fiber Splicing Completed.
Note on S89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-4-2025 Confirmed Actual Completed Footage.
Note on U89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-4-2025 Conduit Placement Confirmed Completed.
Note on S90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-8-2025 Confirmed Actual Completed Footage.
Note on U90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-8-2025 Conduit Placement Confirmed Completed.
Note on S91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2025 Confirmed Actual Completed Footage.
Note on U91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2025 Conduit Placement Confirmed Completed.
Note on R92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-8-2025 SOW Had 1,442' But A Portion Of The Project Was Built By The MDU Crew As Per Travis.
Note on S92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-8-2025 SOW Had 1,442' But A Portion Of The Project Was Built By The MDU Crew As Per Travis. Reply: 9-8-2025 Confirmed Actual Completed Footage.
Note on U92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-8-2025 Conduit Placement Confirmed Completed.
Note on S93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2025 Confirmed Actual Completed Footage.
Note on U93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-9-2025 Conduit Placement Confirmed Completed.
Note on S94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-11-2025 Confirmed Actual Completed Footage.
Note on U94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-11-2025 Conduit Placement Confirmed Completed.
Note on S95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Confirmed Actual Completed Footage. This Project Called For A Design Change--Approved By Tillman.
Note on U95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Conduit Placement Confirmed Completed. This Project Called For A Design Change--Approved By Tillman.
Note on S96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-11-2025 Travis To Submit Change Order For The Additional Conduit Placement Required On This Project. Reply: 9-23-2025 Confirmed Actual Completed Footage.
Note on U96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-23-2025 Conduit Placement Confirmed Completed.
Note on S97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Confirmed Actual Completed Footage.
Note on U97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Conduit Placement Confirmed Completed.
Note on S98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Confirmed Actual Completed Footage.
Note on U98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-7-2025 Conduit Placement Confirmed Completed.
Note on S99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Confirmed Actual Completed Footage.
Note on U99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-10-2025 Conduit Placement Confirmed Completed.
Note on AA99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4/28 CREW WILL NO COME BACK TO RESTRO THIS JOB, SPOKE WITH CURTIS AND WILL NEED TO HAVE A LANDSCAPE CREW TO REST. HAS NOT PASSED TILLMAN WO Reply: SUBMITTED RESTORATION AS BUILT TO CURTIS 4/27/2025
Note on S100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2025 Confirmed Actual Completed Footage.
Note on U100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2025 Conduit Placement Confirmed Completed.
Note on S101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2025 Confirmed Actual Completed Footage.
Note on U101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-15-2025 Conduit Placement Confirmed Completed.
Note on S102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-30-2025 Confirmed Actual Completed Footage.
Note on U102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-30-2025 Conduit Placement Confirmed Completed.
Note on S103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-25-2025 Confirmed Actual Completed Footage.
Note on U103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-25-2025 Conduit Placement Confirmed Completed.
Note on S104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-24-2025 Confirmed Actual Completed Footage.
Note on U104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-24-2025 Conduit Placement Confirmed Completed.
Note on P105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Longo Underground Construction Inc Per Curtis On 1/29/2025.
Note on S105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-4-2025 Confirmed Actual Completed Footage.
Note on U105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-4-2025 Conduit Placement Confirmed Completed.
Note on Y105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3-14-2025 Splicing Completed by Utilities One as Per Tillman.
Note on A106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-14-2025 Partial Build Project As Per Tillman Email On 2-10-2025.
Note on P106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025. Reply: Partial Build Project Per Tillman On 2-10-2025.
Note on S106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per Tillman On 2-10-2025 SOW Shows The Whole Project, But This Is To Complete The 4100ft Left On The Project. Partial Build Project. Reply: 8-14-2025 Confirmed Actual Completed Footage.
Note on U106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-14-2025 Partial Build Project--Conduit Placement Confirmed Completed.
Note on P107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HDD 2-6
Note on S107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Confirmed Actual Completed Footage.
Note on U107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-10-2025 Conduit Placement Confirmed Completed.
Note on S108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2025 Confirmed Actual Completed Footage.
Note on U108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-17-2025 Conduit Placement Confirmed Completed.
Note on S109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-19-2025 Confirmed Actual Completed Footage.
Note on U109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-19-2025 Conduit Placement Confirmed Completed.
Note on S110: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-10-2025 Confirmed Actual Completed Footage.
Note on U110: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6-10-2025 Conduit Placement Confirmed Completed.
Note on S111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-21-2025 Confirmed Actual Completed Footage.
Note on U111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-21-2025 Conduit Placement Confirmed Completed.
Note on P112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on S112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2025 Confirmed Actual Completed Footage.
Note on U112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2025 Conduit Placement Confirmed Completed.
Note on P113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigned To Barlett Fiber Per Curtis On 1/29/2025.
Note on S113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-16-2025 Confirmed Actual Completed Footage.
Note on U113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7-16-2025 Conduit Placement Confirmed Completed.
Note on S114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-27-2025 Confirmed Actual Completed Footage.
Note on U114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-27-2025 Conduit Placement Confirmed Completed.
Note on A115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2025 Fiber Splicing Completed.
Note on S115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-26-2025 Confirmed Actual Completed Footage.
Note on U115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-26-2025 Conduit Placement Confirmed Completed.
Note on A116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-28-2025 Fiber Splicing Completed.
Note on S116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-26-2025 Confirmed Actual Completed Footage.
Note on U116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9-26-2025 Conduit Placement Confirmed Completed.

## Production Summary
[7 empty] | Schedule Date | (Multiple Items)
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | Grand Total | Sum of UG FOOTAGE COMPLETED |  | Sum of UG FOOTAGE COMPLETED | Production Month
D-H0223C |  |  |  |  | 1049 | 1049 | CONTRACTOR | Total | CONTRACTOR | February | March | April | Grand Total
D-H0223D |  |  | 1426 | 1190 | 23 | 2639 | Bartlett Fiber | 6147 | Bartlett Fiber | 7120 | 22896 | 7447 | 37463
D-HDH04 |  | 202 |  |  |  | 202 | Brothers | 22274 | Brothers | 11735 | 42799 | 33743 | 88277
D-HDH31 | 2677 |  |  |  |  | 2677 | EHL | 0 | FCA Fiber | 3158 | 21322 | 3629 | 28109
D-HDH34 |  | 241 | 366 | 202 | 120 | 929 | FCA Fiber | 3629 | HAS Global |  | 4135 | 7641 | 11776
D-HWP415 |  |  |  | 106 |  | 106 | HAS Global | 0 | In-House |  | 2546 | 627 | 3173
D-HWP436 |  | 534 | 460 | 886 | 202 | 2082 | HDD Underground | 933 | Lightspeed | 3226 | 17340 | 7593 | 28159
FB-HDH02A |  | 1990 | 1045 |  |  | 3035 | In-House | 627 | Longo Underground | 6056 | 14625 | 17060 | 37741
Grand Total | 2677 | 2967 | 3297 | 2384 | 1394 | 12719 | Lightspeed | 3502 | MTX |  | 5968 | 20002 | 25970
[7 empty] | Longo Underground | 7128 | US Builders | 2073 | 6882 | 7027 | 15982
[7 empty] | MC Logistics | 2298 | Grand Total | 33368 | 138513 | 104769 | 276650
Sum of UG FOOTAGE COMPLETED | Schedule Date | [5 empty] | MTX | 13034
Project | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | Grand Total | Power Connect | 4828
D-H0223C |  |  |  | 547 | 792 | 1339 | US Builders | 6718
D-H0223D |  |  |  |  | 823 | 823 | Power Connect
D-HDH04 |  |  |  | 23 | 24 | 47 | Grand Total | 71118
D-HDH31 |  |  | 1319 |  |  | 1319
D-HDH34 | 283 |  | 732 | 309 |  | 1324
D-HDH45 |  | 1240 | 1978 | 851 |  | 4069
D-HDH66
D-HDH73 |  |  | 1606 | 1334 |  | 2940
D-HDH76 |  | 300 | 696 | 227 | 333 | 1556
D-HWP415 |  |  |  |  | 21 | 21
D-HWP436 | 383 | 1017 | 242 | 424 | 19 | 2085
D-HWP713 |  | 1050 |  |  |  | 1050
D-H0222D |  |  |  | 1400 | 1462 | 2862
D-H0223A |  |  |  | 1806 | 345 | 2151
D-HWP102 |  |  |  | 47 | 1494 | 1541
D-HDH84
D-H0222B |  |  |  |  | 1095 | 1095
D-H0222C |  |  |  |  | 2989 | 2989
Grand Total | 666 | 3607 | 6573 | 6968 | 9397 | 27211
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | Grand Total
D-H0223C |  | 1277 | 1721 | 670 | 0 | 3668
D-H0223D |  |  |  | 1422 | 946 | 2368
D-HDH04 |  |  |  |  | 9 | 9
D-HDH31 |  |  |  |  | 0 | 0
D-HDH34 | 73 |  | 25 |  |  | 98
D-HDH45 |  |  |  |  | 54 | 54
D-HDH66 |  |  |  | 437 | 0 | 437
D-HDH73 |  |  | 992 | 513 | 0 | 1505
D-HDH76 |  | 800 | 208 | 529 | 327 | 1864
D-HWP415 |  |  |  |  | 3 | 3
D-HWP436 |  | 236 |  |  | 0 | 236
D-HWP713 |  |  |  |  | 0 | 0
FB-HDH02A |  | 74 | 671 |  | 0 | 745
D-H0222D |  |  |  |  | 886 | 886
D-H0223A |  |  | 400 |  | 384 | 784
D-HWP102 | 2087 |  |  |  | 0 | 2087
D-HDH84 |  |  |  |  | 0 | 0
D-H0222B |  | 860 | 1540 | 1360 | 0 | 3760
D-H0222C |  | 967 | 1708 |  | 229 | 2904
D-HDH71 | 555 |  |  | 577 | 239 | 1371
Golden Wings MDU |  |  |  |  | 0 | 0
D-HWP412 |  |  |  |  | 0 | 0
D-HWP425 |  |  |  |  | 0 | 0
D-HWP441 |  |  |  |  | 0 | 0
FB-HWP101 |  | 214 |  |  | 0 | 214
D-H0222A |  | 956 |  | 1168 | 0 | 2124
FB-HDH01 |  |  |  |  | 0 | 0
D-H0223E |  |  | 1090 | 840 | 530 | 2460
FB-HWP401- |  |  | 120 |  |  | 120
D-HDH68 |  |  | 399 | 335 | 1339 | 2073
D-HNP138 |  |  | 891 | 1213 | 1054 | 3158
FB-HWP401 |  |  |  |  | 0 | 0
Grand Total | 2715 | 5384 | 9765 | 9064 | 6000 | 32928
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | Grand Total
D-H0223C | 0 |  | 0 | 0 | 0 | 0
D-H0223D | 0 |  | 0 | 0 | 0 | 0
D-HDH04 | 0 | 0 | 0 | 0 | 0 | 0
D-HDH31 | 0 |  | 0 | 0 | 0 | 0
D-HDH34 | 0 | 414 | 367 | 245 | 0 | 1026
D-HDH45 | 0 |  | 0 | 0 | 0 | 0
D-HDH66 | 0 |  | 0 | 0 | 0 | 0
D-HDH73 | 0 |  | 0 | 0 | 201 | 201
D-HDH76 | 286 | 358 | 0 | 32 | 9 | 685
D-HWP415 | 0 |  | 0 | 0 | 0 | 0
D-HWP436 | 0 |  | 0 | 0 | 0 | 0
D-HWP713 | 0 |  | 0 | 0 | 0 | 0
FB-HDH02A | 363 | 171 | 0 | 397 | 88 | 1019
D-H0222D | 134 | 408 | 452 | 0 | 875 | 1869
D-H0223A |  | 840 | 0 | 0 | 0 | 840
D-HWP102 | 0 |  | 0 | 0 | 0 | 0
D-HDH84 | 0 |  | 0 | 0 | 0 | 0
D-H0222B | 1460 | 970 | 430 | 0 | 0 | 2860
D-H0222C | 182 |  | 0 | 0 | 0 | 182
D-HDH71 | 0 |  | 0 | 0 | 0 | 0
Golden Wings MDU | 0 |  | 0 |  | 0 | 0
D-HWP412 | 0 |  | 0 | 0 | 0 | 0
D-HWP425 | 0 |  | 0 | 35 | 0 | 35
D-HWP441 | 0 |  | 0 | 0 | 0 | 0
FB-HWP101 | 0 |  | 32 | 85 | 0 | 117
D-H0222A | 0 |  | 0 | 0 | 0 | 0
FB-HDH01 | 0 |  | 0 | 0 | 0 | 0
D-H0223E | 0 |  | 372 | 0 | 0 | 372
FB-HWP401- | 0 |  | 0 | 0 | 0 | 0
D-HDH68 | 1292 | 1022 | 1246 | 0 | 288 | 3848
D-HNP138 | 0 | 0 | 0 | 0 | 0 | 0
D-HNP137 | 0 | 1570 | 461 | 1109 | 980 | 4120
D-HWP105 | 1454 | 1360 | 1263 | 0 | 0 | 4077
D-HNP123 | 2215 | 0 | 0 | 0 | 0 | 2215
BHT-FWP-06-W |  | 285 |  |  |  | 285
BHT-FWP-06 |  |  | 617 | 286 | 0 | 903
D-HNP143 |  |  | 700 | 1590 | 1370 | 3660
FB-HWP701 |  |  | 200 | 489 | 0 | 689
D-HDH74 |  |  |  | 884 | 738 | 1622
D-HWP103 |  |  |  | 1357 | 0 | 1357
D-HDH46 |  |  |  | 874 | 1602 | 2476
FX4-FWP-08 |  |  |  |  | 20 | 20
D-HWP701 |  |  |  | 0 |  | 0
Grand Total | 7386 | 7398 | 6140 | 7383 | 6171 | 34478
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | Grand Total
D-H0223C | 0 | 0 | 0 |  |  | 0
D-H0223D | 0 | 0 | 0 |  |  | 0
D-HDH04 | 0 | 3 |  |  |  | 3
D-HDH31 | 0 | 0 |  |  |  | 0
D-HDH34 | 0 | 0 |  |  |  | 0
D-HDH45 | 0 | 0 | 0 | 0 |  | 0
D-HDH66 | 0 | 0 | 0 |  |  | 0
D-HDH73 | 0 | 0 | 0 | 0 |  | 0
D-HDH76 | 0 | 12 | 9 |  |  | 21
D-HWP415 | 0 | 0 | 0 |  |  | 0
D-HWP436 | 0 | 0 | 0 |  |  | 0
D-HWP713 | 0 | 0 | 0 | 0 |  | 0
FB-HDH02A | 0 | 0 | 0 |  |  | 0
D-H0222D | 0 | 199 | 0 | 0 |  | 199
D-H0223A | 0 | 0 | 0 | 0 |  | 0
D-HWP102 | 0 | 0 | 0 | 0 |  | 0
D-HDH84 | 0 | 0 | 0 |  |  | 0
D-H0222B | 0 | 0 | 0 | 0 | 0 | 0
D-H0222C | 0 | 0 | 0 | 0 | 0 | 0
D-HDH71 | 0 | 0 | 0 | 0 | 0 | 0
Golden Wings MDU | 0 | 0 | 0 |  |  | 0
D-HWP412 | 0 | 0 | 0 |  |  | 0
D-HWP425 | 0 | 0 | 0 |  |  | 0
D-HWP441 | 0 | 0 | 0 |  |  | 0
FB-HWP101 | 0 | 0 | 0 |  |  | 0
D-H0222A | 0 | 0 | 201 | 1207 | 220 | 1628
FB-HDH01 | 0 | 106 | 0 | 0 | 0 | 106
D-H0223E | 649 | 528 | 489 | 534 |  | 2200
FB-HWP401- | 0 | 0 | 0 |  |  | 0
D-HDH68 | 0 | 0 | 0 | 0 | 0 | 0
D-HNP138 | 0 | 0 | 0 | 0 | 0 | 0
FB-HWP401 |  |  |  | 0 | 0 | 0
D-HNP137 | 0 | 0 | 0 | 0 | 0 | 0
D-HWP105 | 0 | 0 | 0 | 0 | 0 | 0
D-HNP123 | 0 | 0 | 0 | 0 | 0 | 0
BHT-FWP-06 | 0 | 491 | 291 | 571 | 0 | 1353
D-HNP143 | 0 | 0 | 0 | 1170 | 0 | 1170
FB-HWP701 | 921 | 614 | 1004 | 0 |  | 2539
D-HDH74 | 0 | 0 | 961 | 914 | 1903 | 3778
D-HWP103 | 1288 | 685 | 0 | 0 | 0 | 1973
D-HDH46 | 834 | 1081 | 688 | 0 | 0 | 2603
FX4-FWP-08 | 0 | 0 | 0 | 0 | 0 | 0
D-HWP705 |  | 1710 | 1700 | 0 | 0 | 3410
FB-H0222A |  | 304 | 205 | 451 | 0 | 960
FB-H02223A |  | 1617 | 0 | 101 | 0 | 1718
D-HNP141 |  | 228 | 0 | 0 | 0 | 228
D-HDH78 |  | 1257 | 2121 | 2742 | 75 | 6195
D-HDH67 |  |  | 984 | 1078 | 2048 | 4110
FB-HDH275 |  |  | 2760 | 945 | 1073 | 4778
D-HDH70 |  |  | 1246 | 664 | 834 | 2744
D-HWP701 |  |  | 1353 | 1123 | 0 | 2476
D-HDH03 |  |  |  | 338 | 0 | 338
Grand Total | 3692 | 8835 | 14012 | 11838 | 6153 | 44530
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | Grand Total
D-H0223D
D-HDH04
D-HDH34
D-HDH45
D-HDH73
D-HDH76
FB-HDH02A
D-H0222D
D-HWP102
D-HDH84
FB-HWP101
D-H0222A | 195 |  | 187 | 340 | 270 | 992
FB-HDH01
D-HNP138 |  |  | 1409 | 1016 |  | 2425
FB-HWP401
D-HNP137 |  | 1342 |  |  |  | 1342
D-HWP105
D-HNP123
BHT-FWP-06 | 436 |  |  | 6275 |  | 6711
D-HNP143 |  | 315 |  |  |  | 315
FB-HWP701 |  | 1230 | 200 |  |  | 1430
D-HWP103
D-HDH46 | 15 |  |  |  |  | 15
FX4-FWP-08
D-HWP705
FB-H0222A
FB-H02223A
D-HNP141 |  |  | 1460 | 0 | 420 | 1880
D-HDH67 | 919 |  |  | 1672 | 0 | 2591
FB-HDH275 | 2387 | 841 | 18 | 0 |  | 3246
D-HDH70 | 1095 | 65 |  |  |  | 1160
D-HWP701 | 1105 |  |  |  |  | 1105
D-HDH03 |  |  |  |  | 360 | 360
BHUD-FWP-08-E | 920 |  |  |  |  | 920
D-H0221D | 656 |  | 728 | 1400 | 709 | 3493
D-H0221B |  | 977 | 953 | 2472 | 399 | 4801
FB-H0221A |  | 803 | 551 | 0 |  | 1354
D-HDH04-J Garcia
D-HDH75 |  |  | 1373 | 3928 | 1528 | 6829
D-HNP138- |  |  |  | 1016 |  | 1016
FB-HNP138 |  |  |  | 706 |  | 706
FB-HDH02A D-HDH75 Tie In |  |  |  |  | 583 | 583
Grand Total | 7728 | 5573 | 6879 | 18825 | 4269 | 43274
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | Grand Total
D-H0223C
D-HDH34
D-HDH76
FB-HDH02A | 762 | 0 | 0 | 76 |  | 838
D-H0222D
D-H0223A
D-H0222A | 58 | 574 | 704 | 1009 | 200 | 2545
BHT-FWP-06 |  | 380 | 300 | 150 |  | 830
D-HDH74
D-HDH46 |  | 0 | 0 | 137 |  | 137
FB-H0222A |  |  |  | 310 |  | 310
D-HNP141 | 982 | 749 | 713 |  |  | 2444
FB-HDH275 |  | 0 | 0 | 0 |  | 0
D-H0221D | 905 | 630 | 894 |  |  | 2429
D-HDH04
D-H0220C | 691 |  |  |  |  | 691
D-H0221A | 1430 | 1383 | 1334 | 1548 |  | 5695
D-H0221F | 1460 | 1350 | 1507 |  | 2287 | 6604
D-H0223F
D-HDH34
FB-H0220A |  | 575 |  |  |  | 575
D-H0221C |  | 1065 | 825 | 705 |  | 2595
FB-H0223A
D-H0220B |  | 442 | 854 | 290 | 673 | 2259
FB-HOE117 |  | 1740 | 2934 |  | 161 | 4835
D-HOE215 |  | 483 | 1799 |  | 0 | 2282
D-HOE102 |  | 1333 | 1701 |  | 546 | 3580
D-HDH69 |  |  | 1972 | 178 | 266 | 2416
34th St Crossing |  |  |  | 0 |  | 0
BHT-FWP-07 |  |  |  | 195 |  | 195
D-H0220A |  |  |  |  | 0 | 0
302B FDH
Grand Total | 6288 | 10704 | 15537 | 4598 | 4133 | 41260
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | Grand Total
FB-HDH02A | 644 |  |  |  |  | 644
D-H0223A | 0 |  |  |  |  | 0
D-H0222B | 745 |  |  |  |  | 745
D-H0222A | 265 | 0 | 0 |  | 635 | 900
BHT-FWP-06
D-HDH74 |  |  | 0 |  |  | 0
D-HDH67 | 0 |  |  |  |  | 0
D-HDH03
D-H0221D
D-H0221B |  |  | 0 |  |  | 0
FB-H0221A |  |  |  | 192 |  | 192
D-H0220C |  |  |  | 3867 | 594 | 4461
D-H0221F | 695 |  |  |  |  | 695
FB-HOE117 | 418 | 0 | 0 |  |  | 418
D-HOE215 | 499 | 0 | 0 |  |  | 499
D-HDH69 | 1089 | 0 | 0 |  |  | 1089
BHT-FWP-07 | 453 | 166 | 166 | 302 |  | 1087
D-H0220A | 1880 | 0 | 0 |  |  | 1880
D-HNP114 | 349 | 952 | 952 | 1328 | 397 | 3978
D-HWP706 | 1413 | 0 | 1394 |  |  | 2807
FB-HOE201 | 1355 |  | 0 |  |  | 1355
BHZD-FOE-03-W | 2227 |  |  |  |  | 2227
D-HDH32 |  | 0 | 0 | 344 |  | 344
BHUD-FOE-02-W |  | 1149 | 1149 |  |  | 2298
D-HNP151 |  |  |  | 313 |  | 313
D-HDH82 |  |  |  | 1265 |  | 1265
D-HWP707 |  |  |  | 1334 |  | 1334
D-HWP702 |  |  |  | 1970 |  | 1970
D-HOE206
D-HDH80 |  |  |  |  | 2144 | 2144
Grand Total | 12032 | 2267 | 3661 | 10915 | 3770 | 32645
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | Grand Total
FB-HDH02A | 550 |  |  | 426 |  | 976
BHT-FWP-06 |  | 45 |  |  |  | 45
FB-HWP701 |  | 150 | 295 | 504 |  | 949
D-HNP141
FB-HDH275
D-H0221D | 132 |  |  |  |  | 132
D-H0220C | 367 |  |  |  |  | 367
D-H0220B |  |  |  |  | 314 | 314
FB-HOE117
BHT-FWP-07 | 43 |  |  |  |  | 43
FB-HOE201
D-HDH32
BHUD-FOE-02-W
D-HDH82
D-HWP707 | 618 | 700 |  |  |  | 1318
D-HWP702
D-HOE206
D-HDH80 | 990 | 1871 | 1307 |  |  | 4168
D-HNP113 | 590 | 343 |  |  |  | 933
BHU-FDH-01-W | 198 |  |  |  |  | 198
D-HWP703 | 1840 | 1520 | 2060 | 1330 |  | 6750
D-HDH47 |  |  | 1376 | 875 | 1301 | 3552
D-HDH43 |  |  | 617 | 627 | 431 | 1675
D-HDH60 |  |  |  | 711 | 695 | 1406
Grand Total | 5328 | 4629 | 5655 | 4473 | 2741 | 22826
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | Grand Total
D-HDH04
D-HDH73
FB-HDH02A |  | 561 | 260 | 40 | 408 | 1269
BHT-FWP-06 |  | 37 | 115 |  |  | 152
D-HNP141
D-HDH67
D-HDH70
D-HDH75 |  |  | 173 |  |  | 173
D-H0220C
D-H0223F |  |  |  | 96 |  | 96
D-HDH69 |  |  |  | 433 |  | 433
BHT-FWP-07
D-HDH47 |  | 1018 |  | 569 |  | 1587
D-HDH43 | 276 | 779 | 868 | 338 | 26 | 2287
D-HDH60 | 796 | 1929 | 876 | 651 |  | 4252
D-HDH49 | 1335 | 1133 | 1624 |  | 350 | 4442
D-HDH58 |  | 1526 | 1503 | 1590 | 370 | 4989
D-HDH62 | 547 | 845 | 400 | 906 | 198 | 2896
D-HWP1306 | 259 | 243 |  | 193 |  | 695
D-HDH41 |  | 1538 | 2713 | 862 | 1507 | 6620
D-HWP1309 |  |  |  | 647 |  | 647
D-HDH48 |  |  |  |  | 706 | 706
FX4-FWP-13
Grand Total | 3213 | 9609 | 8532 | 6325 | 3565 | 31244
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | Grand Total
FB-HDH02A |  | 205 | 190 | 48 | 150 | 593
D-H0222B
BHT-FWP-06
D-HNP141
D-HDH67
D-HDH03 |  |  | 113 |  |  | 113
D-HDH75
FB-H0223A
D-HDH43
D-HDH60
D-HDH49 | 1050 |  |  |  |  | 1050
D-HDH58
D-HDH62 |  |  |  | 64 | 21 | 85
D-HWP1306 |  | 510 | 275 |  |  | 785
D-HWP1309 |  | 932 | 1190 | 909 |  | 3031
D-HDH48 |  | 1701 | 314 | 662 | 728 | 3405
FX4-FWP-13 |  | 23 |  |  |  | 23
D-HDH42 |  |  | 2348 | 1378 | 726 | 4452
D-HDH55 | 621 | 464 |  |  |  | 1085
D-HDH56 | 1285 | 951 | 1598 | 1671 |  | 5505
D-HDH57 |  | 1864 | 1514 | 1095 |  | 4473
D-HDH52 |  |  |  | 988 |  | 988
D-HDH54 |  |  |  | 588 | 431 | 1019
D-HDH50 |  |  |  |  | 1108 | 1108
D-HDH53 |  |  |  |  | 385 | 385
Grand Total | 2956 | 6650 | 7542 | 7403 | 3549 | 28100
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | Grand Total
FB-HDH02A | 423 |  |  |  |  | 423
BHT-FWP-06
D-HNP151 |  |  |  |  | 1367 | 1367
D-HDH47
D-HDH62
D-HWP1306 |  | 242 | 310 | 302 |  | 854
D-HWP1309 |  | 470 |  |  |  | 470
D-HDH48 | 961 | 370 |  |  |  | 1331
D-HDH42 | 1602 |  |  |  |  | 1602
D-HDH57 |  |  | 594 |  |  | 594
D-HDH52 |  | 608 | 609 | 614 |  | 1831
D-HDH54 | 1936 | 2103 | 1498 | 229 |  | 5766
D-HDH50 |  | 440 | 1175 | 822 | 1020 | 3457
D-HDH53 | 813 | 1597 | 1632 | 692 |  | 4734
D-HWP-1304 | 1216 |  |  |  |  | 1216
D-HWP1304 |  | 1520 | 1216 | 1098 |  | 3834
D-HWP903 |  | 1190 | 1033 | 1031 |  | 3254
Grand Total | 6951 | 8540 | 8067 | 4788 | 2387 | 30733
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | Grand Total
FB-HDH02A |  | 320 |  |  |  | 320
D-H0222A |  |  | 131 |  |  | 131
FB-H0221A
D-HNP151 |  | 424 |  |  |  | 424
D-HNP113 |  |  |  | 468 | 940 | 1408
D-HDH47
D-HDH49
D-HWP1306 | 610 | 451 | 802 | 75 |  | 1938
D-HWP1309
D-HDH42
D-HDH52 | 404 | 158 | 353 | 40 | 153 | 1108
D-HDH54
D-HWP903 | 1053 | 812 |  |  |  | 1865
D-HNP144 | 640 | 490 | 127 |  |  | 1257
FB-HNP111
D-HWP904 | 575 | 1847 | 1052 | 1846 |  | 5320
D-HWP902 |  | 565 | 1935 | 1483 |  | 3983
D-HNP106 |  |  | 592 | 592 | 730 | 1914
D-HNP117 |  |  | 645 | 853 |  | 1498
D-HNP104 |  |  |  | 616 | 900 | 1516
FB-HNP144 |  |  |  | 225 |  | 225
Grand Total | 3282 | 5067 | 5637 | 6198 | 2723 | 22907
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | Grand Total
FB-HDH02A
(blank)
D-H0222A |  | 55 |  |  |  | 55
FB-HWP701 |  |  | 1190 |  |  | 1190
D-H0223F |  | 30 |  |  |  | 30
D-H0221C |  |  |  |  | 887 | 887
FB-HOE201 |  | 385 | 678 | 381 |  | 1444
D-HWP1306 |  | 251 | 424 | 497 |  | 1172
D-HDH55 |  |  |  | 1342 | 1484 | 2826
D-HDH57 |  |  |  | 85 |  | 85
D-HWP902 |  | 933 |  |  |  | 933
D-HNP117
D-HNP104 |  | 212 |  | 1316 | 1232 | 2760
FB-HNP133 |  |  | 153 |  |  | 153
D-H0222A / D-H0233F
HGP16 / HGP38
D-HNP135 |  |  |  | 201 | 30 | 231
BHT-FWP-10 |  |  |  | 1580 |  | 1580
D-HDH02 |  |  |  |  | 151 | 151
Grand Total |  | 1866 | 2445 | 5402 | 3784 | 13497
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | Grand Total
D-H0222B | 301 | 191 |  |  |  | 492
D-H0222A |  |  |  |  | 175 | 175
D-HNP123 | 54 | 101 |  |  |  | 155
FB-HWP701 |  |  | 678 |  |  | 678
D-H0221C |  |  |  |  | 236 | 236
D-H0220B |  |  | 999 |  | 719 | 1718
FB-HOE201 | 605 |  | 600 | 772 |  | 1977
D-HWP1306 | 286 | 226 |  |  |  | 512
D-HDH55 | 1280 | 1029 |  |  |  | 2309
D-HDH57 |  |  | 181 |  |  | 181
D-HDH53
D-HNP104 | 1156 | 947 |  |  |  | 2103
BHT-FWP-10 | 270 |  |  | 948 |  | 1218
FB-HWP801 | 644 | 1430 | 970 |  |  | 3044
D-HOE116 |  |  |  |  | 285 | 285
D-DHD52 |  |  |  | 260 | 129 | 389
D-DHD55
Grand Total | 4596 | 3924 | 3428 | 1980 | 1544 | 15472
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | Grand Total
FB-HDH02A | 100 |  |  |  | 100
D-H0221C | 224 | 200 |  |  | 424
FB-HOE201 | 757 | 610 | 959 | 493 | 2819
D-HNP151 |  |  |  | 218 | 218
D-HWP1306
BHT-FWP-10 | 954 | 2783 | 2248 |  | 5985
FB-HWP801 | 948 |  | 736 |  | 1684
BHZD-FWP-13-E
D-HDH50 \ D-HDH52
D-HDH57 \ D-HDH58
D-HDH50-52
D-HDH57-60
FB-HWP-701
Grand Total | 2983 | 3593 | 3943 | 711 | 11230
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | Grand Total
FB-HWP701
D-HWP701
D-H0220B |  | 1483 | 83 |  |  | 1566
FB-HOE201 | 720 | 948 |  | 1101 | 437 | 3206
D-HNP113 |  |  |  | 341 |  | 341
D-HDH02
FB-HWP801 | 1957 |  |  |  |  | 1957
BHZD-FWP-13-E | 275 | 280 | 310 |  |  | 865
BHT-FWP-09 | 800 | 631 | 1401 |  |  | 2832
D-HDH18 | 6 |  |  |  |  | 6
D-HDH50\52
D-HNP110
D-HWP905 |  |  | 610 | 2523 |  | 3133
D-HDH52/49/58
Grand Total | 3758 | 3342 | 2404 | 3965 | 437 | 13906
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | Grand Total
FB-HWP701
FB-HOE201 | 730 | 583 |  |  |  | 1313
FX4-FWP-13 | 115 |  |  |  |  | 115
BHT-FWP-10 |  |  | 370 |  |  | 370
BHZD-FWP-13-E | 263 | 270 |  | 395 |  | 928
BHT-FWP-09 | 1100 |  | 1975 | 1395 |  | 4470
D-HWP905 |  | 1293 |  |  |  | 1293
225 Granada St | 155 |  |  |  |  | 155
BHUD-FWP-06
Grand Total | 2363 | 2146 | 2345 | 1790 |  | 8644
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | Grand Total
D-H0222B
D-HDH69
D-H0220A | 1394 | 1756 | 846 |  |  | 3996
FB-HOE201 | 465 | 218 | 729 | 464 |  | 1876
BHUD-FOE-02-W |  |  |  | 977 |  | 977
D-HNP135 |  |  | 81 |  | 114 | 195
BHT-FWP-10
FB-HWP801
BHZD-FWP-13-E | 280 | 70 | 594 |  | 52 | 996
BHT-FWP-09 | 450 | 1246 |  |  |  | 1696
BHT-FWP-08 |  | 1465 | 1380 |  |  | 2845
Grand Total | 2589 | 4755 | 3630 | 1441 | 166 | 12581
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | Grand Total
D-H0220B
D-H0220A |  | 1946 |  |  |  | 1946
FB-HOE201 |  |  |  | 112 |  | 112
BHUD-FOE-02-W |  |  |  | 676 | 430 | 1106
D-HNP113 |  |  | 649 |  |  | 649
D-HNP135 | 237 | 322 | 245 | 1091 | 303 | 2198
BHZD-FWP-13-E | 68 | 50 |  |  |  | 118
BHT-FWP-08 | 1269 | 1141 | 1308 | 1296 |  | 5014
FB-HDH01A-2A | 65 |  |  |  |  | 65
FB-HWP175 | 924 |  |  |  |  | 924
D-HWP801 |  | 1044 | 1100 | 1050 |  | 3194
FB-HWP1376 |  |  | 335 | 200 |  | 535
Grand Total | 2563 | 4503 | 3637 | 4425 | 733 | 15861
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | Grand Total
(blank) |  |  |  |  | 0 | 0
FB-HOE201 |  | 282 |  |  |  | 282
BHUD-FOE-02-W | 885 | 478 | 490 | 372 |  | 2225
D-HNP144
D-HNP135 | 360 |  |  |  |  | 360
FB-HWP801
BHT-FWP-08
FB-HWP175 | 120 |  |  |  |  | 120
FB-HWP1376 |  | 120 | 71 |  |  | 191
D-HWP821 |  |  | 355 |  |  | 355
Grand Total | 1365 | 880 | 916 | 372 | 0 | 3533
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | Grand Total
BHZD-FOE-03-W |  |  |  |  | 198 | 198
BHUD-FOE-02-W
D-HOE206
D-HNP117 |  |  |  | 400 |  | 400
D-HWP821 | 846 | 827 |  |  |  | 1673
FB-HWP902 |  | 465 | 321 |  |  | 786
BHUD-FWP-13-W | 1644 | 60 |  |  |  | 1704
Grand Total | 2490 | 1352 | 321 | 400 | 198 | 4761
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | Grand Total
D-HOE215 |  | 403 | 39 |  |  | 442
BHZD-FOE-03-W | 862 |  |  |  |  | 862
D-HNP117 |  | 203 | 170 | 106 |  | 479
BHZD-FWP-13-E |  |  | 280 | 1972 |  | 2252
FB-HWP902
D-HWP822 |  | 1210 | 397 |  |  | 1607
FB-HWP1302 |  |  | 90 |  |  | 90
D-HWP814 |  |  | 426 | 583 |  | 1009
FX4-FML-05 |  |  |  |  | 47 | 47
Grand Total | 862 | 1816 | 1402 | 2661 | 47 | 6788
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | Grand Total
D-HOE215 |  | 318 |  |  |  | 318
BHZD-FOE-03-W |  |  | 461 | 880 | 585 | 1926
D-HOE206 |  |  |  | 868 |  | 868
D-HNP117 |  |  | 272 | 79 |  | 351
BHZD-FWP-13-E | 936 | 1723 | 130 | 420 |  | 3209
BHT-FWP-09 |  |  | 853 | 1279 |  | 2132
D-HWP821
BHUD-FWP-13-W |  |  | 579 | 619 |  | 1198
D-HWP822
D-HWP814 | 1843 | 1714 | 678 |  |  | 4235
D-HWP812 | 1070 | 1224 | 235 |  |  | 2529
BHUD-FOE-03-W |  | 605 |  |  |  | 605
D-HWP815 |  |  | 363 | 1077 |  | 1440
FB-HWP804
Grand Total | 3849 | 5584 | 3571 | 5222 | 585 | 18811
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | Grand Total
D-H0223C |  |  |  |  | 318 | 318
D-H0223A |  |  |  |  | 183 | 183
BHZD-FOE-03-W | 345 |  |  |  |  | 345
BHZD-FWP-13-E | 420 |  |  |  |  | 420
BHT-FWP-09 | 817 |  | 1385 |  |  | 2202
BHUD-FWP-13-W | 1181 | 1933 | 2853 | 1587 |  | 7554
D-HWP814
D-HWP815 | 1430 | 1004 |  |  |  | 2434
FB-HWP804 |  | 581 |  |  |  | 581
BHT-FOE-03 |  |  | 314 |  |  | 314
FB-HOE301 |  |  |  | 2390 | 1377 | 3767
Grand Total | 4193 | 3518 | 4552 | 3977 | 1878 | 18118
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | Grand Total
D-HNP117
BHUD-FWP-13-W
BHT-FOE-03
FB-HOE301 |  | 190 | 840 | 531 | 718 | 2279
FB-HWP482 | 918 |  |  |  |  | 918
BHZD-FWP-11-W |  | 2675 | 1964 | 377 |  | 5016
FB-HWP775 |  |  |  | 674 |  | 674
Grand Total | 918 | 2865 | 2804 | 1582 | 718 | 8887
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | Grand Total
D-HOE215 |  | 319 |  |  |  | 319
D-HNP117 | 376 | 35 | 48 | 144 | 64 | 667
FB-HOE301 | 571 | 1293 | 540 | 554 | 89 | 3047
FB-HWP482 | 1175 | 1154 | 428 |  |  | 2757
FB-HWP775 |  | 111 | 12 |  |  | 123
FB-HWP802 | 288 | 380 | 229 | 163 |  | 1060
12 Oaks MHP |  | 406 | 1031 |  |  | 1437
Skyview MHP
FB-HLR201 |  |  |  |  | 391 | 391
Grand Total | 2410 | 3698 | 2288 | 861 | 544 | 9801
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | Grand Total
D-HOE206 |  |  | 499 | 231 | 316 | 1046
D-HNP113
D-HNP117 | 141 |  | 181 | 82 | 96 | 500
FB-HWP1376 | 343 | 416 | 216 |  |  | 975
BHT-FOE-03 |  | 430 |  |  |  | 430
FB-HOE301 | 377 | 408 | 607 | 1022 |  | 2414
FB-HWP482
FB-HWP775
FB-HLR201 | 396 |  |  |  |  | 396
FB-HWP776 | 1109 |  |  |  |  | 1109
D-HNP111 |  | 205 |  |  |  | 205
Skyview |  | 1456 | 1420 | 1170 | 1081 | 5127
D-HWP803 |  | 1460 | 1428 | 1654 |  | 4542
D-HNP108 |  |  |  |  | 878 | 878
Grand Total | 2366 | 4375 | 4351 | 4159 | 2371 | 17622
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | Grand Total
D-HOE215 |  |  | 358 |  |  | 358
BHZD-FOE-03-W |  |  | 1241 |  |  | 1241
D-HOE206 | 503 | 295 |  |  | 6 | 804
D-HNP113 |  | 1009 |  |  |  | 1009
D-HNP117 | 20 |  |  | 250 | 177 | 447
FB-HOE301 | 639 |  |  |  |  | 639
FB-HLR201 |  |  | 400 | 320 |  | 720
Skyview | 809 | 533 |  |  |  | 1342
D-HNP108 | 715 |  |  |  | 1131 | 1846
FB-HWP375 |  |  | 130 |  |  | 130
D-HWP805 | 735 |  |  | 1453 |  | 2188
FB-HWP1375 |  | 260 |  | 315 |  | 575
FB-HWP1310 |  | 390 |  |  |  | 390
D-HWP826 |  | 558 | 1248 | 1260 |  | 3066
D-HWP824 |  | 1224 | 967 |  |  | 2191
D-HWP825 |  |  | 1017 |  |  | 1017
D-HWP1310
Grand Total | 3421 | 4269 | 5361 | 3598 | 1314 | 17963
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | Grand Total
(blank)
D-HOE215 |  |  |  | 99 |  | 99
BHZD-FOE-03-W
D-HDH82
D-HOE206 |  | 15 | 65 | 6 |  | 86
D-HNP117
D-HNP135 |  |  |  |  | 125 | 125
D-HWP812 |  |  | 130 |  |  | 130
D-HWP803 |  |  |  |  | 128 | 128
D-HWP805 |  |  | 2472 |  |  | 2472
D-HWP826 |  | 977 |  |  |  | 977
D-HWP825 |  |  | 2819 |  |  | 2819
D-HWP1310 |  |  | 1491 | 1549 |  | 3040
HGP-03
D-HWP802 |  |  |  | 903 |  | 903
FB-HOE375 |  |  |  |  | 285 | 285
Grand Total |  | 992 | 6977 | 2557 | 538 | 11064
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | Grand Total
D-HNP113 |  |  |  | 279 |  | 279
D-HNP135 |  |  | 299 | 302 | 209 | 810
Skyview | 2498 | 1192 | 1925 |  |  | 5615
D-HNP108 |  |  |  | 443 |  | 443
D-HWP1310 | 918 |  |  |  |  | 918
D-HWP802 | 254 | 1686 | 611 |  |  | 2551
FB-HOE375 |  |  |  | 82 |  | 82
FB-HWP975 |  | 329 | 333 |  |  | 662
D-HWP827 |  |  | 740 |  |  | 740
FB-HWP1075 |  |  |  | 267 |  | 267
BHT-FLX-01 |  |  | 307 | 920 | 610 | 1837
Grand Total | 3670 | 3207 | 4215 | 2293 | 819 | 14204
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | Grand Total
D-HOE215
BHZD-FOE-03-W |  |  | 139 |  |  | 139
D-HOE206
FB-HNP133 |  |  |  | 97 |  | 97
D-HNP135 | 42 | 219 |  |  | 70 | 331
Skyview
D-HWP802 |  |  | 250 |  |  | 250
D-HWP827 | 1238 | 1531 | 1250 | 361 |  | 4380
FB-HWP1075 | 711 |  |  |  |  | 711
D-HGP22 (Repair) |  |  | 75 |  |  | 75
D-HWP809 |  | 1808 |  | 1204 |  | 3012
D-HOE302 |  | 251 | 253 | 1076 |  | 1580
BHT-FLX-01 | 829 |  | 863 | 499 | 475 | 2666
D-HWP823 |  |  |  | 754 |  | 754
D-HWP811 |  |  |  | 562 |  | 562
Grand Total | 2820 | 3809 | 2830 | 4553 | 545 | 14557
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | Grand Total
D-HOE215
BHZD-FOE-03-W | 60 |  |  |  |  | 60
FB-HNP111 |  |  |  | 175 |  | 175
D-HNP135 |  | 224 |  |  |  | 224
BHT-FOE-03 |  |  | 406 |  |  | 406
FB-HLR201 |  |  | 362 | 399 |  | 761
D-HWP827
D-HWP809
D-HOE302 |  | 120 | 190 |  |  | 310
BHT-FLX-01 | 839 |  | 616 | 969 | 552 | 2976
D-HWP823 | 1285 |  |  |  |  | 1285
D-HWP811 | 978 | 675 | 170 |  |  | 1823
FB-HNP104 | 153 |  | 260 |  |  | 413
OakHill MHP | 329 | 427 | 537 | 646 | 793 | 2732
FB-HWP480 | 335 |  |  |  |  | 335
BHU-FAL-01-E | 415 | 291 |  |  | 755 | 1461
D-HWP816 |  | 1231 | 1538 | 1377 |  | 4146
D-HWP818 |  |  | 1205 | 1000 |  | 2205
BHU-FWP-08-E |  |  | 240 | 504 |  | 744
Mas Verde |  |  |  |  | 4135 | 4135
D-HOE306 |  |  |  |  | 551 | 551
Skyview Estates
Grand Total | 4394 | 2968 | 5524 | 5070 | 6786 | 24742
Sum of UG FOOTAGE COMPLETED | Schedule Date
Project | 2025-09-29 | Grand Total
(blank)
Grand Total

## Daily Production_RAW DATA
Project | CONTRACTOR | Schedule Date | UG FOOTAGE COMPLETED | Fiber Footage | COMMENTS | Production Month
D-HDH31 | Reycamp | 2025-02-10 | 2677 |  |  | February
D-HDH34 | Lightspeed | 2025-02-10 |  |  | 4 Toby Boxes | February
D-HDH04 | J Garcia Construction | 2025-02-11 | 202 |  |  | February
D-HDH34 | Lightspeed | 2025-02-11 | 241 |  |  | February
FB-HDH02A | Multiple | 2025-02-11 | 1990 |  |  | February
D-HWP436 | HH/LS | 2025-02-11 | 534 |  |  | February
D-HDH34 | Lightspeed | 2025-02-12 | 366 |  |  | February
FB-HDH02A | HH/LS | 2025-02-12 | 1045 |  |  | February
D-HWP436 | HH/LS | 2025-02-12 | 460 |  |  | February
D-H0223D | Brothers | 2025-02-12 | 1426 |  |  | February
D-HDH34 | Lightspeed | 2025-02-13 | 202 |  |  | February
D-HWP415 | Lightspeed | 2025-02-13 | 106 |  |  | February
D-HWP436 | HH/LS | 2025-02-13 | 886 |  |  | February
D-H0223D | Brothers | 2025-02-13 | 1190 |  |  | February
D-HDH34 | Lightspeed | 2025-02-14 | 120 |  |  | February
D-HWP436 | HH/LS | 2025-02-14 | 202 |  |  | February
D-H0223D | Brothers | 2025-02-14 | 23 |  |  | February
D-H0223C | Longo Underground | 2025-02-14 | 1049 |  |  | February
D-HDH34 | Lightspeed | 2025-02-17 | 283 |  |  | February
D-HWP436 | HH/LS | 2025-02-17 | 383 |  |  | February
D-HDH66 | Bartlett Fiber | 2025-02-18 |  |  | 30-Toby Boxes | February
D-HWP436 | HH/LS | 2025-02-18 | 1017 |  |  | February
D-HDH76 | J Garcia Construction | 2025-02-18 | 300 |  |  | February
D-HDH45 | Reycamp | 2025-02-18 | 1240 |  |  | February
D-HWP713 | Brothers | 2025-02-18 | 1050 |  | 12 Toby Boxes/FDH | February
D-HDH04 | J Garcia Construction | 2025-02-19 |  |  | 7 Toby Boxes | February
D-HDH31 | Reycamp | 2025-02-19 | 1319 |  |  | February
D-HDH34 | Lightspeed | 2025-02-19 | 732 |  |  | February
D-HWP436 | HH/LS | 2025-02-19 | 242 |  |  | February
D-HDH76 | J Garcia Construction | 2025-02-19 | 696 |  |  | February
D-HDH45 | Reycamp | 2025-02-19 | 1978 |  | 10 Toby Boxes | February
D-HDH73 | Power Connect | 2025-02-19 | 1606 |  |  | February
D-HDH04 | J Garcia Construction | 2025-02-20 | 23 |  | 9 Toby Boxes | February
D-HDH34 | Lightspeed | 2025-02-20 | 309 |  | 2 Toby Boxes | February
D-HWP436 | HH/LS | 2025-02-20 | 424 |  |  | February
D-H0223C | Longo Underground | 2025-02-20 | 547 |  | 6 Toby Boxes | February
D-HDH76 | J Garcia Construction | 2025-02-20 | 227 |  |  | February
D-HDH45 | Reycamp | 2025-02-20 | 851 |  | 20 Toby Boxes | February
D-HDH73 | Power Connect | 2025-02-20 | 1334 |  |  | February
D-H0222D | Bartlett Fiber | 2025-02-20 | 1400 |  |  | February
D-H0223A | Bartlett Fiber | 2025-02-20 | 1806 |  |  | February
D-HWP102 | Power Connect | 2025-02-20 | 47 |  |  | February
D-HDH04 | J Garcia Construction | 2025-02-21 | 24 |  | 5 Toby Boxes | February
D-HDH84 | Reycamp | 2025-02-21 |  |  | Sponge Testing | February
D-HWP415 | Lightspeed | 2025-02-21 | 21 |  | 6 Toby Boxes | February
D-HWP436 | HH/LS | 2025-02-21 | 19 |  | 8 Toby Boxes | February
D-H0223D | Brothers | 2025-02-21 | 823 |  | 6 Toby Boxes | February
D-H0223C | Longo Underground | 2025-02-21 | 792 |  | 6 Toby Boxes | February
D-HDH76 | J Garcia Construction | 2025-02-21 | 333 |  |  | February
D-H0223A | Bartlett Fiber | 2025-02-21 | 345 |  |  | February
D-HWP102 | Power Connect | 2025-02-21 | 1494 |  |  | February
D-H0222B | Brothers | 2025-02-21 | 1095 |  | 6 Toby Boxes | February
D-H0222D | Bartlett Fiber | 2025-02-21 | 1462 |  | 4 Toby Boxes | February
D-H0222C | Power Connect | 2025-02-21 | 2989 |  |  | February
D-HDH34 | Lightspeed | 2025-02-24 | 73 |  |  | February
D-HWP102 | Power Connect | 2025-02-24 | 2087 |  | 29 Toby Boxes | February
D-HDH71 | HDD Underground | 2025-02-24 | 555 |  |  | February
D-HDH04 | J Garcia Construction | 2025-02-25 |  |  | 1 Toby Boxes | February
D-HDH31 | Reycamp | 2025-02-25 |  |  |  | February
D-HDH66 | Bartlett Fiber | 2025-02-25 |  |  |  | February
D-HDH84 | Reycamp | 2025-02-25 |  |  |  | February
FB-HDH02A | Lightspeed | 2025-02-25 | 74 |  |  | February
Golden Wings MDU | SB Martinez | 2025-02-25 |  |  |  | February
D-HWP412 | SB Martinez | 2025-02-25 |  |  |  | February
D-HWP415 | Lightspeed | 2025-02-25 |  |  |  | February
D-HWP425 | Brothers | 2025-02-25 |  |  |  | February
D-HWP436 | HH Underground-Lightspeed | 2025-02-25 | 236 |  | 11 Toby Boxes | February
D-HWP441 | Brothers | 2025-02-25 |  |  |  | February
FB-HWP101 | Power Connect | 2025-02-25 | 214 |  |  | February
D-H0223D | Brothers | 2025-02-25 |  |  |  | February
D-H0223C | Longo Underground | 2025-02-25 | 1277 |  | 12 Toby Boxes | February
D-HDH76 | J Garcia Construction | 2025-02-25 | 800 |  | 2 Toby Boxes | February
D-HDH45 | Reycamp | 2025-02-25 |  |  |  | February
D-HWP713 | Brothers | 2025-02-25 |  |  |  | February
D-HDH73 | Power Connect | 2025-02-25 |  |  |  | February
D-H0222D | Bartlett Fiber | 2025-02-25 |  |  |  | February
D-H0223A | Bartlett Fiber | 2025-02-25 |  |  |  | February
D-H0222B | Brothers | 2025-02-25 | 860 |  |  | February
D-H0222C | Power Connect | 2025-02-25 | 967 |  |  | February
D-H0222A | Key Underground | 2025-02-25 | 956 |  |  | February
FB-HDH01 | J Garcia Construction | 2025-02-25 |  |  | 2 splice locations | February
D-HDH04 | J Garcia Construction | 2025-02-26 |  |  |  | February
D-HDH31 | Reycamp | 2025-02-26 |  |  |  | February
D-HDH34 | Lightspeed | 2025-02-26 | 25 |  |  | February
D-HDH66 | Bartlett Fiber | 2025-02-26 |  |  |  | February
D-HDH84 | Reycamp | 2025-02-26 |  |  |  | February
FB-HDH02A | Lightspeed | 2025-02-26 | 671 |  |  | February
Golden Wings MDU | SB Martinez | 2025-02-26 |  |  |  | February
D-HWP412 | SB Martinez | 2025-02-26 |  |  |  | February
D-HWP415 | Lightspeed | 2025-02-26 |  |  |  | February
D-HWP425 | Brothers | 2025-02-26 |  |  |  | February
D-HWP436 | HH Underground-Lightspeed | 2025-02-26 |  |  | 1 Toby Box | February
D-HWP441 | Brothers | 2025-02-26 |  |  | 1 Toby Box | February
FB-HWP101 | Power Connect | 2025-02-26 |  |  |  | February
D-H0223D | Brothers | 2025-02-26 |  |  |  | February
D-H0223C | Longo Underground | 2025-02-26 | 1721 |  | 13 Toby Boxes | February
D-HDH76 | J Garcia Construction | 2025-02-26 | 208 |  |  | February
D-HDH45 | Reycamp | 2025-02-26 |  |  |  | February
D-HWP713 | Brothers | 2025-02-26 |  |  |  | February
D-HDH73 | Power Connect | 2025-02-26 | 992 |  |  | February
D-H0222D | Bartlett Fiber | 2025-02-26 |  |  |  | February
D-H0223A | Bartlett Fiber | 2025-02-26 | 400 |  | 2 Toby Boxes | February
D-HWP102 | Power Connect | 2025-02-26 |  |  |  | February
D-H0222B | Brothers | 2025-02-26 | 1540 |  | 6 Toby Boxes | February
D-H0222C | Power Connect | 2025-02-26 | 1708 |  |  | February
D-HDH71 | HDD Underground | 2025-02-26 |  |  |  | February
D-H0222A | Key Underground | 2025-02-26 |  |  |  | February
FB-HDH01 | J Garcia Construction | 2025-02-26 |  |  |  | February
D-H0223E | Key Underground | 2025-02-26 | 1090 |  |  | February
FB-HWP401- | HH Underground-Lightspeed | 2025-02-26 | 120 |  | 1 Toby Box | February
D-HDH68 | US Builders | 2025-02-26 | 399 |  |  | February
D-HNP138 | FCA Fiber | 2025-02-26 | 891 |  | 6 Toby Boxes | February
D-HDH04 | J Garcia Construction | 2025-02-27 |  |  |  | February
D-HDH31 | Reycamp | 2025-02-27 |  |  |  | February
D-HDH34 | Lightspeed | 2025-02-27 |  |  | Sponge Testing / Proofing Conduits | February
D-HDH66 | Bartlett Fiber | 2025-02-27 | 437 |  | 4 Toby Boxes / 8 Splices | February
D-HDH84 | Reycamp | 2025-02-27 |  |  |  | February
FB-HDH02A | Lightspeed | 2025-02-27 |  |  |  | February
Golden Wings MDU | SB Martinez | 2025-02-27 |  |  |  | February
D-HWP412 | SB Martinez | 2025-02-27 |  |  |  | February
D-HWP415 | Lightspeed | 2025-02-27 |  |  | Proofing Conduits | February
D-HWP425 | Brothers | 2025-02-27 |  |  |  | February
D-HWP436 | HH Underground-Lightspeed | 2025-02-27 |  |  | Proofing Conduits | February
D-HWP441 | Brothers | 2025-02-27 |  |  | Proofing Conduits | February
FB-HWP101 | Power Connect | 2025-02-27 |  |  |  | February
D-H0223D | Brothers | 2025-02-27 | 1422 |  | 11 Toby Boxes | February
D-H0223C | Longo Underground | 2025-02-27 | 670 |  | 4 Toby Boxes | February
D-HDH76 | J Garcia Construction | 2025-02-27 | 529 |  |  | February
D-HDH45 | Reycamp | 2025-02-27 |  |  |  | February
D-HWP713 | Brothers | 2025-02-27 |  |  |  | February
D-HDH73 | Power Connect | 2025-02-27 | 513 |  | 4 Toby Boxes | February
D-H0222D | Bartlett Fiber | 2025-02-27 |  |  |  | February
D-H0223A | Bartlett Fiber | 2025-02-27 |  |  |  | February
D-HWP102 | Power Connect | 2025-02-27 |  |  |  | February
D-H0222B | Brothers | 2025-02-27 | 1360 |  | 6 Toby Boxes | February
D-H0222C | Power Connect | 2025-02-27 |  |  |  | February
D-HDH71 | HDD Underground | 2025-02-27 | 577 |  | 4 Toby Boxes | February
D-H0222A | Key Underground | 2025-02-27 | 1168 |  | 1-HH, 1 Swing Arm | February
FB-HDH01 | J Garcia Construction | 2025-02-27 |  |  |  | February
D-H0223E | Key Underground | 2025-02-27 | 840 |  |  | February
FB-HWP401- | HH Underground-Lightspeed | 2025-02-27 |  |  |  | February
D-HDH68 | US Builders | 2025-02-27 | 335 |  | 2 Toby Boxes | February
D-HNP138 | FCA Fiber | 2025-02-27 | 1213 |  | 6 Toby Boxes | February
D-HDH04 | J Garcia Construction | 2025-02-28 | 9 |  | 6 Toby Boxes | February
D-HDH31 | Reycamp | 2025-02-28 |  |  |  | February
D-HDH34 | Lightspeed | 2025-02-28 |  |  | Sponge Testing / Proofing Conduits | February
D-HDH66 | Bartlett Fiber | 2025-02-28 |  |  |  | February
D-HDH84 | Reycamp | 2025-02-28 |  |  |  | February
FB-HDH02A | Lightspeed | 2025-02-28 |  |  |  | February
Golden Wings MDU | SB Martinez | 2025-02-28 |  |  |  | February
D-HWP412 | SB Martinez | 2025-02-28 |  |  |  | February
D-HWP415 | Lightspeed | 2025-02-28 | 3 |  | 2 Toby Boxes / Proffing Conduits | February
D-HWP425 | Brothers | 2025-02-28 |  |  |  | February
D-HWP436 | HH Underground-Lightspeed | 2025-02-28 |  |  |  | February
D-HWP441 | Brothers | 2025-02-28 |  |  |  | February
FB-HWP101 | Power Connect | 2025-02-28 |  |  |  | February
D-H0223D | Brothers | 2025-02-28 | 946 |  | 6 Toby Boxes | February
D-H0223C | Longo Underground | 2025-02-28 |  |  |  | February
D-HDH76 | J Garcia Construction | 2025-02-28 | 327 |  |  | February
D-HDH45 | Reycamp | 2025-02-28 | 54 |  | Sponging / Proofing Conduits | February
D-HWP713 | Brothers | 2025-02-28 |  |  |  | February
D-HDH73 | Power Connect | 2025-02-28 |  |  |  | February
D-H0222D | Bartlett Fiber | 2025-02-28 | 886 |  | 8 Toby Boxes | February
D-H0223A | Bartlett Fiber | 2025-02-28 | 384 |  | 5 Toby Boxes | February
D-HWP102 | Power Connect | 2025-02-28 |  |  |  | February
D-H0222B | Brothers | 2025-02-28 |  |  |  | February
D-H0222C | Power Connect | 2025-02-28 | 229 |  |  | February
D-HDH71 | HDD Underground | 2025-02-28 | 239 |  | 8 Toby Boxes | February
D-H0222A | Key Underground | 2025-02-28 |  |  |  | February
FB-HDH01 | J Garcia Construction | 2025-02-28 |  |  |  | February
D-H0223E | Key Underground | 2025-02-28 | 530 |  |  | February
FB-HWP401 | HH Underground-Lightspeed | 2025-02-28 |  |  |  | February
D-HDH68 | US Builders | 2025-02-28 | 1339 |  | 15 Toby Boxes | February
D-HNP138 | FCA Fiber | 2025-02-28 | 1054 |  |  | February
D-HDH04 | J Garcia Construction | 2025-03-03 |  |  |  | March
D-HDH31 | Reycamp | 2025-03-03 |  |  |  | March
D-HDH34 | Lightspeed | 2025-03-03 |  |  |  | March
D-HDH66 | Bartlett Fiber | 2025-03-03 |  |  |  | March
D-HDH84 | Reycamp | 2025-03-03 |  |  |  | March
FB-HDH02A | Lightspeed | 2025-03-03 | 363 |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-03 |  |  |  | March
D-HWP412 | SB Martinez | 2025-03-03 |  |  |  | March
D-HWP415 | Lightspeed | 2025-03-03 |  |  |  | March
D-HWP425 | Brothers | 2025-03-03 |  |  |  | March
D-HWP436 | HH Underground-Lightspeed | 2025-03-03 |  |  |  | March
D-HWP441 | Brothers | 2025-03-03 |  |  |  | March
FB-HWP101 | Power Connect | 2025-03-03 |  |  |  | March
D-H0223D | Brothers | 2025-03-03 |  |  |  | March
D-H0223C | Longo Underground | 2025-03-03 |  |  |  | March
D-HDH76 | J Garcia Construction | 2025-03-03 | 286 |  |  | March
D-HDH45 | Reycamp | 2025-03-03 |  |  |  | March
D-HWP713 | Brothers | 2025-03-03 |  |  |  | March
D-HDH73 | Power Connect | 2025-03-03 |  |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-03 | 134 |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-03 |  |  | 12 Toby Boxes | March
D-HWP102 | Power Connect | 2025-03-03 |  |  |  | March
D-H0222B | Brothers | 2025-03-03 | 1460 |  | 9 Toby Boxes | March
D-H0222C | Power Connect | 2025-03-03 | 182 |  |  | March
D-HDH71 | HDD Underground | 2025-03-03 |  |  |  | March
D-H0222A | Key Underground | 2025-03-03 |  |  |  | March
FB-HDH01 | J Garcia Construction | 2025-03-03 |  |  |  | March
D-H0223E | Key Underground | 2025-03-03 |  |  |  | March
FB-HWP401- | HH Underground-Lightspeed | 2025-03-03 |  |  |  | March
D-HDH68 | US Builders | 2025-03-03 | 1292 |  | 8 Toby Boxes | March
D-HNP138 | FCA Fiber | 2025-03-03 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-03 |  |  |  | March
D-HWP105 | Brothers | 2025-03-03 | 1454 |  | 8 Toby Boxes / 1 Flower Pot | March
D-HNP123 | HDD Underground | 2025-03-03 | 2215 |  | 19 Toby Boxes | March
D-HDH04 | J Garcia Construction | 2025-03-04 |  |  |  | March
D-HDH34 | Lightspeed | 2025-03-04 | 414 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-04 | 171 |  |  | March
D-HWP436 | HH Underground-Lightspeed | 2025-03-04 |  |  | 27 Toby Boxes / Proofing Conduits | March
D-H0223C | Longo Underground | 2025-03-04 |  |  | Vault / Swing Arm / Groundrod | March
D-HDH76 | J Garcia Construction | 2025-03-04 | 358 |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-04 | 408 |  | 1 Toby Box | March
D-H0223A | Bartlett Fiber | 2025-03-04 | 840 |  | 28 Toby Boxes / 46 Splices | March
D-H0222B | Brothers | 2025-03-04 | 970 |  | 6 Toby Boxes | March
D-HDH68 | US Builders | 2025-03-04 | 1022 |  | 8 Toby Boxes | March
D-HNP138 | FCA Fiber | 2025-03-04 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-04 | 1570 |  | 9 Toby Boxes | March
D-HWP105 | Brothers | 2025-03-04 | 1360 |  | 6 Toby Boxes / 1 Flower Pot | March
D-HNP123 | HDD Underground | 2025-03-04 |  |  |  | March
BHT-FWP-06-W | Lightspeed | 2025-03-04 | 285 |  |  | March
D-HDH04 | J Garcia Construction | 2025-03-05 | 0 |  |  | March
D-HDH31 | Reycamp | 2025-03-05 | 0 |  |  | March
D-HDH34 | Lightspeed | 2025-03-05 | 367 |  |  | March
D-HDH66 | Bartlett Fiber | 2025-03-05 | 0 |  |  | March
D-HDH84 | Reycamp | 2025-03-05 | 0 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-05 | 0 |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-05 | 0 |  |  | March
D-HWP412 | SB Martinez | 2025-03-05 | 0 |  |  | March
D-HWP415 | Lightspeed | 2025-03-05 | 0 |  | Re-Built FDH | March
D-HWP425 | Brothers | 2025-03-05 | 0 |  |  | March
D-HWP436 | HH Underground-Lightspeed | 2025-03-05 | 0 |  |  | March
D-HWP441 | Brothers | 2025-03-05 | 0 |  |  | March
FB-HWP101 | Power Connect | 2025-03-05 | 32 |  |  | March
D-H0223D | Brothers | 2025-03-05 | 0 |  |  | March
D-H0223C | Longo Underground | 2025-03-05 | 0 |  |  | March
D-HDH76 | J Garcia Construction | 2025-03-05 | 0 |  |  | March
D-HDH45 | Reycamp | 2025-03-05 | 0 |  |  | March
D-HWP713 | Brothers | 2025-03-05 | 0 |  |  | March
D-HDH73 | Power Connect | 2025-03-05 | 0 |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-05 | 452 |  | 6 Toby Boxes 20 Splices | March
D-H0223A | Bartlett Fiber | 2025-03-05 | 0 |  |  | March
D-HWP102 | Power Connect | 2025-03-05 | 0 |  |  | March
D-H0222B | Brothers | 2025-03-05 | 430 |  | 2 Toby Boxes / 1 HH | March
D-H0222C | Power Connect | 2025-03-05 | 0 |  |  | March
D-HDH71 | HDD Underground | 2025-03-05 | 0 |  |  | March
D-H0222A | Key Underground | 2025-03-05 | 0 |  |  | March
FB-HDH01 | J Garcia Construction | 2025-03-05 | 0 |  |  | March
D-H0223E | Key Underground | 2025-03-05 | 372 |  | 1 Toby Box / 3 Splices | March
FB-HWP401- | HH Underground-Lightspeed | 2025-03-05 | 0 |  |  | March
D-HDH68 | US Builders | 2025-03-05 | 1246 |  | 10 Toby Boxes / Vault / Swing Arm / Groundrod | March
D-HNP138 | FCA Fiber | 2025-03-05 | 0 |  |  | March
D-HNP137 | FCA Fiber | 2025-03-05 | 461 |  | 3 Toby Boxes | March
D-HWP105 | Brothers | 2025-03-05 | 1263 |  | 9 Toby Boxes / 1 Flower Pot / 1 HH / 1 Swing Arm / 1 FDH | March
D-HNP123 | HDD Underground | 2025-03-05 | 0 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-05 | 617 |  |  | March
D-HNP143 | Brothers | 2025-03-05 | 700 |  | 6 Toby Boxes | March
FB-HWP701 | Lightspeed | 2025-03-05 | 200 |  |  | March
D-HDH04 | J Garcia Construction | 2025-03-06 | 0 |  |  | March
D-HDH31 | Reycamp | 2025-03-06 | 0 |  |  | March
D-HDH34 | Lightspeed | 2025-03-06 | 245 |  | 11 Toby Boxes | March
D-HDH66 | Bartlett Fiber | 2025-03-06 | 0 |  |  | March
D-HDH84 | Reycamp | 2025-03-06 | 0 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-06 | 397 |  | 8 Splices | March
D-HWP701 | SB Martinez | 2025-03-06 | 0 |  |  | March
D-HWP412 | SB Martinez | 2025-03-06 | 0 |  |  | March
D-HWP415 | Lightspeed | 2025-03-06 | 0 |  |  | March
D-HWP425 | Brothers | 2025-03-06 | 35 |  |  | March
D-HWP436 | HH Underground-Lightspeed | 2025-03-06 | 0 |  |  | March
D-HWP441 | Brothers | 2025-03-06 | 0 |  |  | March
FB-HWP101 | Power Connect | 2025-03-06 | 85 |  |  | March
D-H0223D | Brothers | 2025-03-06 | 0 |  |  | March
D-H0223C | Longo Underground | 2025-03-06 | 0 |  |  | March
D-HDH76 | J Garcia Construction | 2025-03-06 | 32 |  | 12 Toby Boxes | March
D-HDH45 | Reycamp | 2025-03-06 | 0 |  |  | March
D-HWP713 | Brothers | 2025-03-06 | 0 |  |  | March
D-HDH73 | Power Connect | 2025-03-06 | 0 |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-06 | 0 |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-06 | 0 |  |  | March
D-HWP102 | Power Connect | 2025-03-06 | 0 |  |  | March
D-H0222B | Brothers | 2025-03-06 | 0 |  |  | March
D-H0222C | Power Connect | 2025-03-06 | 0 |  |  | March
D-HDH71 | HDD Underground | 2025-03-06 | 0 |  |  | March
D-H0222A | Key Underground | 2025-03-06 | 0 |  |  | March
FB-HDH01 | J Garcia Construction | 2025-03-06 | 0 |  |  | March
D-H0223E | Key Underground | 2025-03-06 | 0 |  |  | March
FB-HWP401- | HH Underground-Lightspeed | 2025-03-06 | 0 |  |  | March
D-HDH68 | US Builders | 2025-03-06 | 0 |  |  | March
D-HNP138 | FCA Fiber | 2025-03-06 | 0 |  |  | March
D-HNP137 | FCA Fiber | 2025-03-06 | 1109 |  | 16 Toby Boxes | March
D-HWP105 | Brothers | 2025-03-06 | 0 |  |  | March
D-HNP123 | HDD Underground | 2025-03-06 | 0 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-06 | 286 |  |  | March
D-HNP143 | Brothers | 2025-03-06 | 1590 |  | 10 Toby Boxes | March
FB-HWP701 | Lightspeed | 2025-03-06 | 489 |  | 1 HH / 3 Toby Boxes | March
D-HDH74 | Bartlett Fiber | 2025-03-06 | 884 |  | 9 Toby Boxes / 25 Splices | March
D-HWP103 | Brothers | 2025-03-06 | 1357 |  | 13 Toby Boxes | March
D-HDH46 | FCA Fiber | 2025-03-06 | 874 |  |  | March
D-HDH04 | J Garcia Construction | 2025-03-07 | 0 |  |  | March
D-HDH31 | Reycamp | 2025-03-07 | 0 |  |  | March
D-HDH34 | Lightspeed | 2025-03-07 | 0 |  | Sponging | March
D-HDH66 | Bartlett Fiber | 2025-03-07 | 0 |  |  | March
D-HDH84 | Reycamp | 2025-03-07 | 0 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-07 | 88 |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-07 | 0 |  |  | March
D-HWP412 | SB Martinez | 2025-03-07 | 0 |  |  | March
D-HWP415 | Lightspeed | 2025-03-07 | 0 |  |  | March
D-HWP425 | Brothers | 2025-03-07 | 0 |  |  | March
D-HWP436 | HH Underground-Lightspeed | 2025-03-07 | 0 |  |  | March
D-HWP441 | Brothers | 2025-03-07 | 0 |  |  | March
FB-HWP101 | Power Connect | 2025-03-07 | 0 |  |  | March
D-H0223D | Brothers | 2025-03-07 | 0 |  |  | March
D-H0223C | Longo Underground | 2025-03-07 | 0 |  |  | March
D-HDH76 | J Garcia Construction | 2025-03-07 | 9 |  | 6 Toby Boxes | March
D-HDH45 | Reycamp | 2025-03-07 | 0 |  |  | March
D-HWP713 | Brothers | 2025-03-07 | 0 |  |  | March
D-HDH73 | Power Connect | 2025-03-07 | 201 |  | 25 Toby Boxes | March
D-H0222D | Bartlett Fiber | 2025-03-07 | 875 |  | 13 Toby Boxes / 10 Splices | March
D-H0223A | Bartlett Fiber | 2025-03-07 | 0 |  |  | March
D-HWP102 | Power Connect | 2025-03-07 | 0 |  |  | March
D-H0222B | Brothers | 2025-03-07 | 0 |  | 1 Hand Hole / 1 Swing Arm | March
D-H0222C | Power Connect | 2025-03-07 | 0 |  |  | March
D-HDH71 | HDD Underground | 2025-03-07 | 0 |  |  | March
D-H0222A | Key Underground | 2025-03-07 | 0 |  |  | March
FB-HDH01 | J Garcia Construction | 2025-03-07 | 0 |  |  | March
D-H0223E | Key Underground | 2025-03-07 | 0 |  |  | March
FB-HWP401- | HH Underground-Lightspeed | 2025-03-07 | 0 |  |  | March
D-HDH68 | US Builders | 2025-03-07 | 288 |  | 1 Toby Box / 5 Splices | March
D-HNP138 | FCA Fiber | 2025-03-07 | 0 |  |  | March
D-HNP137 | FCA Fiber | 2025-03-07 | 980 |  | 9 Toby Boxes | March
D-HWP105 | Brothers | 2025-03-07 | 0 |  |  | March
D-HNP123 | HDD Underground | 2025-03-07 | 0 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-07 | 0 |  | 1 HH | March
D-HNP143 | Brothers | 2025-03-07 | 1370 |  | 8 Toby Boxes | March
FB-HWP701 | Lightspeed | 2025-03-07 | 0 |  |  | March
D-HDH74 | Bartlett Fiber | 2025-03-07 | 738 |  | 6 Toby Boxes / 12 Splices | March
D-HWP103 | Brothers | 2025-03-07 | 0 |  |  | March
D-HDH46 | FCA Fiber | 2025-03-07 | 1602 |  | 6 Toby Boxes | March
FX4-FWP-08 | Lightspeed | 2025-03-07 | 20 |  |  | March
D-HDH04 | J Garcia Construction | 2025-03-10 | 0 |  |  | March
D-HDH31 | Reycamp | 2025-03-10 | 0 |  |  | March
D-HDH34 | Lightspeed | 2025-03-10 | 0 |  | FDH / Restoration | March
D-HDH66 | Bartlett Fiber | 2025-03-10 | 0 |  |  | March
D-HDH84 | Reycamp | 2025-03-10 | 0 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-10 | 0 |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-10 | 0 |  |  | March
D-HWP412 | SB Martinez | 2025-03-10 | 0 |  |  | March
D-HWP415 | Lightspeed | 2025-03-10 | 0 |  |  | March
D-HWP425 | Brothers | 2025-03-10 | 0 |  |  | March
D-HWP436 | HH Underground-Lightspeed | 2025-03-10 | 0 |  |  | March
D-HWP441 | Brothers | 2025-03-10 | 0 |  |  | March
FB-HWP101 | Power Connect | 2025-03-10 | 0 |  |  | March
D-H0223D | Brothers | 2025-03-10 | 0 |  |  | March
D-H0223C | Longo Underground | 2025-03-10 | 0 |  |  | March
D-HDH76 | J Garcia Construction | 2025-03-10 | 0 |  | FDH / 1 Swing Arm | March
D-HDH45 | Reycamp | 2025-03-10 | 0 |  |  | March
D-HWP713 | Brothers | 2025-03-10 | 0 |  |  | March
D-HDH73 | Power Connect | 2025-03-10 | 0 |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-10 | 0 |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-10 | 0 |  |  | March
D-HWP102 | Power Connect | 2025-03-10 | 0 |  |  | March
D-H0222B | Brothers | 2025-03-10 | 0 |  |  | March
D-H0222C | Power Connect | 2025-03-10 | 0 |  |  | March
D-HDH71 | HDD Underground | 2025-03-10 | 0 |  |  | March
D-H0222A | Key Underground | 2025-03-10 | 0 |  |  | March
FB-HDH01 | J Garcia Construction | 2025-03-10 | 0 |  |  | March
D-H0223E | Key Underground | 2025-03-10 | 649 |  | 9 Toby Boxes | March
FB-HWP401- | HH Underground-Lightspeed | 2025-03-10 | 0 |  |  | March
D-HDH68 | US Builders | 2025-03-10 | 0 |  |  | March
D-HNP138 | FCA Fiber | 2025-03-10 | 0 |  |  | March
D-HNP137 | FCA Fiber | 2025-03-10 | 0 |  |  | March
D-HWP105 | Brothers | 2025-03-10 | 0 |  |  | March
D-HNP123 | HDD Underground | 2025-03-10 | 0 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-10 | 0 |  |  | March
D-HNP143 | Brothers | 2025-03-10 | 0 |  |  | March
FB-HWP701 | Lightspeed | 2025-03-10 | 921 |  |  | March
D-HDH74 | Bartlett Fiber | 2025-03-10 | 0 |  |  | March
D-HWP103 | Brothers | 2025-03-10 | 1288 |  | 3 Toby Boxes | March
D-HDH46 | FCA Fiber | 2025-03-10 | 834 |  |  | March
FX4-FWP-08 | Lightspeed | 2025-03-10 | 0 |  |  | March
D-HDH04 | J Garcia Construction | 2025-03-11 | 3 |  | 1 Toby Box | March
D-HDH31 | Reycamp | 2025-03-11 | 0 |  |  | March
D-HDH34 | Lightspeed | 2025-03-11 | 0 |  | Proofing Conduits | March
D-HDH66 | Bartlett Fiber | 2025-03-11 | 0 |  |  | March
D-HDH84 | Reycamp | 2025-03-11 | 0 |  |  | March
FB-HDH02A | Lightspeed | 2025-03-11 | 0 |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-11 | 0 |  |  | March
D-HWP412 | SB Martinez | 2025-03-11 | 0 |  |  | March
D-HWP415 | Lightspeed | 2025-03-11 | 0 |  |  | March
D-HWP425 | Brothers | 2025-03-11 | 0 |  |  | March
D-HWP436 | HH Underground-Lightspeed | 2025-03-11 | 0 |  |  | March
D-HWP441 | Brothers | 2025-03-11 | 0 |  |  | March
FB-HWP101 | Power Connect | 2025-03-11 | 0 |  |  | March
D-H0223D | Brothers | 2025-03-11 | 0 |  |  | March
D-H0223C | Longo Underground | 2025-03-11 | 0 |  |  | March
D-HDH76 | J Garcia Construction | 2025-03-11 | 12 |  | 6 Toby Boxes | March
D-HDH45 | Reycamp | 2025-03-11 | 0 |  |  | March
D-HWP713 | Brothers | 2025-03-11 | 0 |  |  | March
D-HDH73 | Power Connect | 2025-03-11 | 0 |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-11 | 199 |  | 2 Toby Boxes | March
D-H0223A | Bartlett Fiber | 2025-03-11 | 0 |  |  | March
D-HWP102 | Power Connect | 2025-03-11 | 0 |  |  | March
D-H0222B | Brothers | 2025-03-11 | 0 |  |  | March
D-H0222C | Power Connect | 2025-03-11 | 0 |  |  | March
D-HDH71 | HDD Underground | 2025-03-11 | 0 |  |  | March
D-H0222A | Key Underground | 2025-03-11 | 0 |  |  | March
FB-HDH01 | J Garcia Construction | 2025-03-11 | 106 |  | 2 Toby Boxes | March
D-H0223E | Key Underground | 2025-03-11 | 528 |  | 5 Toby Boxes / 2 Splices | March
FB-HWP401- | HH Underground-Lightspeed | 2025-03-11 | 0 |  |  | March
D-HDH68 | US Builders | 2025-03-11 | 0 |  |  | March
D-HNP138 | FCA Fiber | 2025-03-11 | 0 |  |  | March
D-HNP137 | FCA Fiber | 2025-03-11 | 0 |  |  | March
D-HWP105 | Brothers | 2025-03-11 | 0 |  |  | March
D-HNP123 | HDD Underground | 2025-03-11 | 0 |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-11 | 491 |  |  | March
D-HNP143 | Brothers | 2025-03-11 | 0 |  |  | March
FB-HWP701 | Lightspeed | 2025-03-11 | 614 |  |  | March
D-HDH74 | Bartlett Fiber | 2025-03-11 | 0 |  |  | March
D-HWP103 | Brothers | 2025-03-11 | 685 |  | 5 Toby Boxes/1 HH/1 Swing Arm/1 Groundrod | March
D-HDH46 | FCA Fiber | 2025-03-11 | 1081 |  |  | March
FX4-FWP-08 | Lightspeed | 2025-03-11 | 0 |  |  | March
D-HWP705 | Brothers | 2025-03-11 | 1710 |  | 13 Toby Boxes | March
FB-H0222A | Bartlett Fiber | 2025-03-11 | 304 |  |  | March
FB-H02223A | Power Connect | 2025-03-11 | 1617 |  |  | March
D-HNP141 | Power Connect | 2025-03-11 | 228 |  |  | March
D-HDH78 | FCA Fiber | 2025-03-11 | 1257 |  |  | March
D-HDH04 | J Garcia Construction | 2025-03-12 |  |  | QC / Restoration | March
D-HDH31 | Reycamp | 2025-03-12 |  |  |  | March
D-HDH34 | Lightspeed | 2025-03-12 |  |  | QC / Restoration | March
D-HDH66 | Bartlett Fiber | 2025-03-12 |  |  |  | March
D-HDH84 | Reycamp | 2025-03-12 |  |  |  | March
FB-HDH02A | Lightspeed | 2025-03-12 |  |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-12 | COMPLETED |  |  | March
D-HWP412 | SB Martinez | 2025-03-12 | COMPLETED |  |  | March
D-HWP415 | Lightspeed | 2025-03-12 |  |  |  | March
D-HWP425 | Brothers | 2025-03-12 | COMPLETED |  |  | March
D-HWP436 | HH Underground-Lightspeed | 2025-03-12 |  |  |  | March
D-HWP441 | Brothers | 2025-03-12 | COMPLETED |  |  | March
FB-HWP101 | Power Connect | 2025-03-12 |  |  |  | March
D-H0223D | Brothers | 2025-03-12 |  |  |  | March
D-H0223C | Longo Underground | 2025-03-12 |  |  |  | March
D-HDH76 | J Garcia Construction | 2025-03-12 | 9 |  | 7 Toby Boxes | March
D-HDH45 | Reycamp | 2025-03-12 |  |  |  | March
D-HWP713 | Brothers | 2025-03-12 |  |  |  | March
D-HDH73 | Power Connect | 2025-03-12 |  |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-12 |  |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-12 |  |  |  | March
D-HWP102 | Power Connect | 2025-03-12 |  |  |  | March
D-H0222B | Brothers | 2025-03-12 |  |  |  | March
D-H0222C | Power Connect | 2025-03-12 |  |  |  | March
D-HDH71 | HDD Underground | 2025-03-12 |  |  |  | March
D-H0222A | Key Underground | 2025-03-12 | 201 |  |  | March
FB-HDH01 | J Garcia Construction | 2025-03-12 |  |  |  | March
D-H0223E | Key Underground | 2025-03-12 | 489 |  | 5 Toby Boxes | March
FB-HWP401- | HH Underground-Lightspeed | 2025-03-12 |  |  |  | March
D-HDH68 | US Builders | 2025-03-12 |  |  |  | March
D-HNP138 | FCA Fiber | 2025-03-12 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-12 |  |  |  | March
D-HWP105 | Brothers | 2025-03-12 |  |  |  | March
D-HNP123 | HDD Underground | 2025-03-12 |  |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-12 | 291 |  |  | March
D-HNP143 | Brothers | 2025-03-12 |  |  |  | March
FB-HWP701 | Lightspeed | 2025-03-12 | 1004 |  | 1 HH | March
D-HDH74 | Bartlett Fiber | 2025-03-12 | 961 |  |  | March
D-HWP103 | Brothers | 2025-03-12 |  |  |  | March
D-HDH46 | FCA Fiber | 2025-03-12 | 688 |  |  | March
FX4-FWP-08 | Lightspeed | 2025-03-12 |  |  |  | March
D-HWP705 | Brothers | 2025-03-12 | 1700 |  | 15 Toby Boxes / 1 HH | March
FB-H0222A | Bartlett Fiber | 2025-03-12 | 205 |  |  | March
FB-H02223A | Power Connect | 2025-03-12 |  |  |  | March
D-HNP141 | Power Connect | 2025-03-12 |  |  |  | March
D-HDH78 | FCA Fiber | 2025-03-12 | 2121 |  |  | March
D-HDH67 | Power Connect | 2025-03-12 | 984 |  | 4 Toby Boxes | March
FB-HDH275 | HDD Underground | 2025-03-12 | 2760 |  | 5 Toby Boxes | March
D-HDH70 | Longo Underground | 2025-03-12 | 1246 |  | 10 Toby Boxes / 20 Splices | March
D-HWP701 | Brothers | 2025-03-12 | 1353 |  | 9 Toby Boxes | March
D-HDH04 | J Garcia Construction | 2025-03-13 |  |  | QC / Restoration | March
D-HDH31 | Reycamp | 2025-03-13 |  |  |  | March
D-HDH34 | Lightspeed | 2025-03-13 |  |  | QC / Restoration | March
D-HDH66 | Bartlett Fiber | 2025-03-13 |  |  |  | March
D-HDH84 | Reycamp | 2025-03-13 |  |  |  | March
FB-HDH02A | Lightspeed | 2025-03-13 |  |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-13 |  |  |  | March
D-HWP412 | SB Martinez | 2025-03-13 |  |  |  | March
D-HWP415 | Lightspeed | 2025-03-13 |  |  |  | March
D-HWP425 | Brothers | 2025-03-13 |  |  |  | March
D-HWP436 | HH Underground-Lightspeed | 2025-03-13 |  |  |  | March
D-HWP441 | Brothers | 2025-03-13 |  |  |  | March
FB-HWP101 | Power Connect | 2025-03-13 |  |  |  | March
D-H0223D | Brothers | 2025-03-13 |  |  |  | March
D-H0223C | Longo Underground | 2025-03-13 |  |  |  | March
D-HDH76 | J Garcia Construction | 2025-03-13 |  |  | QC / Restoration | March
D-HDH45 | Reycamp | 2025-03-13 |  |  |  | March
D-HWP713 | Brothers | 2025-03-13 |  |  |  | March
D-HDH73 | Power Connect | 2025-03-13 |  |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-13 |  |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-13 |  |  |  | March
D-HWP102 | Power Connect | 2025-03-13 |  |  |  | March
D-H0222B | Brothers | 2025-03-13 |  |  |  | March
D-H0222C | Power Connect | 2025-03-13 |  |  |  | March
D-HDH71 | HDD Underground | 2025-03-13 |  |  |  | March
D-H0222A | Key Underground | 2025-03-13 | 1207 |  | 9 Toby Boxes / 16 Splices / 2 Pits | March
FB-HDH01 | J Garcia Construction | 2025-03-13 |  |  |  | March
D-H0223E | Key Underground | 2025-03-13 | 534 |  | 7 Toby Boxes / 5 Splices | March
FB-HWP401 | HH Underground-Lightspeed | 2025-03-13 |  |  |  | March
D-HDH68 | US Builders | 2025-03-13 |  |  |  | March
D-HNP138 | FCA Fiber | 2025-03-13 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-13 |  |  |  | March
D-HWP105 | Brothers | 2025-03-13 |  |  |  | March
D-HNP123 | HDD Underground | 2025-03-13 |  |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-13 | 571 |  | 2 HH | March
D-HNP143 | Brothers | 2025-03-13 | 1170 |  | 11 Toby Boxes | March
FB-HWP701 | Lightspeed | 2025-03-13 |  |  |  | March
D-HDH74 | Bartlett Fiber | 2025-03-13 | 914 |  | 12 Toby Boxes / 4 Splices | March
D-HWP103 | Brothers | 2025-03-13 |  |  |  | March
D-HDH46 | FCA Fiber | 2025-03-13 |  |  |  | March
FX4-FWP-08 | Lightspeed | 2025-03-13 |  |  |  | March
D-HWP705 | Brothers | 2025-03-13 |  |  |  | March
FB-H0222A | Bartlett Fiber | 2025-03-13 | 451 |  |  | March
FB-H02223A | Power Connect | 2025-03-13 | 101 |  |  | March
D-HNP141 | Power Connect | 2025-03-13 |  |  |  | March
D-HDH78 | FCA Fiber | 2025-03-13 | 2742 |  |  | March
D-HDH67 | Power Connect | 2025-03-13 | 1078 |  | 6 Toby Boxes / 10 Splices | March
FB-HDH275 | HDD Underground | 2025-03-13 | 945 |  |  | March
D-HDH70 | Longo Underground | 2025-03-13 | 664 |  | 4 Toby Boxes / 8 Splices | March
D-HWP701 | Brothers | 2025-03-13 | 1123 |  | 4 Toby Boxes / 2 Flowerpots | March
D-HDH03 | Power Connect | 2025-03-13 | 338 |  | 2 Toby Boxes / 6 Splices | March
D-HDH04 | J Garcia Construction | 2025-03-14 |  |  | QC / Restoration | March
D-HDH31 | Reycamp | 2025-03-14 |  |  |  | March
D-HDH34 | Lightspeed | 2025-03-14 |  |  | QC / Restoration | March
D-HDH66 | Bartlett Fiber | 2025-03-14 |  |  |  | March
D-HDH84 | Reycamp | 2025-03-14 |  |  |  | March
FB-HDH02A | Lightspeed | 2025-03-14 |  |  |  | March
Golden Wings MDU | SB Martinez | 2025-03-14 |  |  |  | March
D-HWP412 | SB Martinez | 2025-03-14 |  |  | Restoration | March
D-HWP415 | Lightspeed | 2025-03-14 |  |  |  | March
D-HWP425 | Brothers | 2025-03-14 |  |  |  | March
D-HWP436 | HH Underground-Lightspeed | 2025-03-14 |  |  | Restoration | March
D-HWP441 | Brothers | 2025-03-14 |  |  |  | March
FB-HWP101 | Power Connect | 2025-03-14 |  |  | Restoration | March
D-H0223D | Brothers | 2025-03-14 |  |  |  | March
D-H0223C | Longo Underground | 2025-03-14 |  |  |  | March
D-HDH76 | J Garcia Construction | 2025-03-14 |  |  | QC / Restoration | March
D-HDH45 | Reycamp | 2025-03-14 |  |  |  | March
D-HWP713 | Brothers | 2025-03-14 |  |  |  | March
D-HDH73 | Power Connect | 2025-03-14 |  |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-14 |  |  |  | March
D-H0223A | Bartlett Fiber | 2025-03-14 |  |  |  | March
D-HWP102 | Power Connect | 2025-03-14 |  |  | Restoration | March
D-H0222B | Brothers | 2025-03-14 |  |  |  | March
D-H0222C | Power Connect | 2025-03-14 |  |  |  | March
D-HDH71 | HDD Underground | 2025-03-14 |  |  |  | March
D-H0222A | Key Underground | 2025-03-14 | 220 |  | 1 Toby Box / 2 Splices | March
FB-HDH01 | J Garcia Construction | 2025-03-14 |  |  |  | March
D-H0223E | Key Underground | 2025-03-14 |  |  | 2 Toby Boxes / 1 HH / 1 Swing Arm | March
FB-HWP401 | HH Underground-Lightspeed | 2025-03-14 |  |  |  | March
D-HDH68 | US Builders | 2025-03-14 |  |  |  | March
D-HNP138 | FCA Fiber | 2025-03-14 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-14 |  |  |  | March
D-HWP105 | Brothers | 2025-03-14 |  |  |  | March
D-HNP123 | HDD Underground | 2025-03-14 |  |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-14 |  |  |  | March
D-HNP143 | Brothers | 2025-03-14 |  |  |  | March
FB-HWP701 | Lightspeed | 2025-03-14 |  |  | Dug Up Conduit | March
D-HDH74 | Bartlett Fiber | 2025-03-14 | 1903 |  | 20 Toby Boxes / 9 Splices | March
D-HWP103 | Brothers | 2025-03-14 |  |  |  | March
D-HDH46 | FCA Fiber | 2025-03-14 |  |  |  | March
FX4-FWP-08 | Lightspeed | 2025-03-14 |  |  |  | March
D-HWP705 | Brothers | 2025-03-14 |  |  |  | March
FB-H0222A | Bartlett Fiber | 2025-03-14 |  |  |  | March
FB-H02223A | Power Connect | 2025-03-14 |  |  |  | March
D-HNP141 | Power Connect | 2025-03-14 |  |  |  | March
D-HDH78 | FCA Fiber | 2025-03-14 | 75 |  | 41 Toby Boxes / 1 HH / FDH / 1 Ground Rod | March
D-HDH67 | Power Connect | 2025-03-14 | 2048 |  | 14 Toby Boxes / 21 Pits | March
FB-HDH275 | HDD Underground | 2025-03-14 | 1073 |  |  | March
D-HDH70 | Longo Underground | 2025-03-14 | 834 |  | 6 Toby Boxes / 11 Splices | March
D-HWP701 | Brothers | 2025-03-14 |  |  |  | March
D-HDH03 | Power Connect | 2025-03-14 |  |  |  | March
D-HDH04 | J Garcia Construction | 2025-03-17 |  |  | QC / Restoration | March
D-HDH34 | Lightspeed | 2025-03-17 |  |  | QC / Restoration | March
D-HDH84 | Reycamp | 2025-03-17 |  |  |  | March
FB-HDH02A | Lightspeed | 2025-03-17 |  |  |  | March
FB-HWP101 | Power Connect | 2025-03-17 |  |  |  | March
D-H0223D | Brothers | 2025-03-17 |  |  |  | March
D-HDH76 | J Garcia Construction | 2025-03-17 |  |  | QC / Restoration | March
D-HDH45 | Reycamp | 2025-03-17 |  |  |  | March
D-HDH73 | Power Connect | 2025-03-17 |  |  |  | March
D-H0222D | Bartlett Fiber | 2025-03-17 |  |  |  | March
D-HWP102 | Power Connect | 2025-03-17 |  |  |  | March
D-H0222A | Key Underground | 2025-03-17 | 195 |  | 2 Toby Boxes / 4 Splices | March
FB-HDH01 | J Garcia Construction | 2025-03-17 |  |  |  | March
FB-HWP401 | HH Underground-Lightspeed | 2025-03-17 |  |  |  | March
D-HNP138 | FCA Fiber | 2025-03-17 |  |  |  | March
D-HNP137 | FCA Fiber | 2025-03-17 |  |  |  | March
D-HWP105 | Brothers | 2025-03-17 |  |  |  | March
D-HNP123 | HDD Underground | 2025-03-17 |  |  |  | March
BHT-FWP-06 | Lightspeed | 2025-03-17 | 436 |  |  | March
D-HNP143 | Brothers | 2025-03-17 |  |  |  | March
FB-HWP701 | Lightspeed | 2025-03-17 |  |  |  | March
D-HWP103 | Brothers | 2025-03-17 |  |  |  | March
D-HDH46 | FCA Fiber | 2025-03-17 | 15 |  | 9 Toby Boxes | March
FX4-FWP-08 | Lightspeed | 2025-03-17 |  |  |  | March
D-HWP705 | Brothers | 2025-03-17 |  |  |  | March
FB-H0222A | Bartlett Fiber | 2025-03-17 |  |  |  | March
FB-H02223A | Power Connect | 2025-03-17 |  |  |  | March
D-HNP141 | Power Connect | 2025-03-17 |  |  |  | March
D-HDH67 | Power Connect | 2025-03-17 | 919 |  | 5 Toby oxes / 5 Pits | March
FB-HDH275 | HDD Underground | 2025-03-17 | 2387 |  |  | March
D-HDH70 | Longo Underground | 2025-03-17 | 1095 |  | 7 Toby Boxes / 15 Splices / 1 HH / 1 Swing Arm / 1 Ground Rod | March
D-HWP701 | Brothers | 2025-03-17 | 1105 |  | 9 Toby Boxes / 1 FDH / 1 Ground Rod | March
D-HDH03 | Power Connect | 2025-03-17 |  |  |  | March
BHUD-FWP-08-E | Brothers | 2025-03-17 | 920 |  | 3 Vaults / 882 Fiber Cable | March
D-H0221D | Bartlett Fiber | 2025-03-17 | 656 |  |  | March
D-HDH04 | J Garcia Construction | 2025-03-18 |  |  | QC / Restoration | March
D-HDH34 | Lightspeed | 2025-03-18 |  |  | QC / Restoration | March
D-HDH45 | Reycamp | 2025-03-18 |  |  | QC / Restoration | March
D-HNP137 | FCA Fiber | 2025-03-18 | 1342 |  | 13 Toby Boxes | March
D-HWP105 | Brothers | 2025-03-18 |  |  | 1 FDH / 1 HH / 1 Ground Rod | March
D-HNP143 | Brothers | 2025-03-18 | 315 |  |  | March
FB-HWP701 | Lightspeed | 2025-03-18 | 1230 |  | 12 Toby Boxes / 1 HH / 1 FDH / 1 Swing Arm | March
FB-HDH275 | HDD Underground | 2025-03-18 | 841 |  | 6 Toby Boxes / 9 Splices | March
D-HDH70 | Longo Underground | 2025-03-18 | 65 |  | 3 HH | March
D-H0221B | Bartlett Fiber | 2025-03-18 | 977 |  | 10 Toby Boxes / 6 Splices | March
FB-H0221A | HAS Global | 2025-03-18 | 803 |  | 8 Toby Boxes / 7 Splices | March
D-HDH04-J Garcia | J Garcia Construction | 2025-03-19 |  |  | QC / Restoration | March
D-HDH34 | Lightspeed | 2025-03-19 |  |  | QC / Restoration | March
D-HDH76 | J Garcia Construction | 2025-03-19 |  |  | QC / Restoration | March
D-H0222A | Key Underground | 2025-03-19 | 187 |  |  | March
D-HNP138 | FCA Fiber | 2025-03-19 | 1409 |  | 14 Toby Boxes | March
FB-HWP701 | Power Connect | 2025-03-19 | 200 |  | 1 HH / 594 Pulling Fiber Cable | March
D-HNP141 | Power Connect | 2025-03-19 | 1460 |  | 11 Toby Boxes / 12 Splices | March
FB-HDH275 | HDD Underground | 2025-03-19 | 18 |  | 4 HH / 11 Pits | March
D-H0221D | Bartlett Fiber | 2025-03-19 | 728 |  | 2 Toby Box / 3 Splice | March
D-H0221B | Bartlett Fiber | 2025-03-19 | 953 |  | 1 Toby Box / 1 Splice | March
FB-H0221A | HAS Global | 2025-03-19 | 551 |  |  | March
D-HDH75 | Longo Underground | 2025-03-19 | 1373 |  | 12 Toby Box / 24 Splice | March
D-HNP138- | FCA Fiber | 2025-03-20 | 1016 |  | 11 Toby Boxes | March
FB-HNP138 |  | 2025-03-20 | 353 |  |  | March
FB-HDH275 | HDD Underground | 2025-03-20 |  |  |  | March
D-H0221D | Bartlett Fiber | 2025-03-20 | 700 |  | 9 Toby Box / 4 Splice | March
D-H0221B | Bartlett Fiber | 2025-03-20 | 1236 |  | 17 Toby Box / 13 Splice | March
FB-H0221A | HAS Global | 2025-03-20 |  |  |  | March
D-HDH75 | Longo Underground | 2025-03-20 | 1964 |  | 15 Toby Box / 30 Splice | March
D-HNP141 | Power Connect | 2025-03-20 | No Locates |  |  | March
D-H0222A | Lightspeed | 2025-03-20 | 170 |  | 1 Toby Box / 2 Splices | March
D-HDH67 |  | 2025-03-20 | 836 |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod / 5 Toby Boxes / 4 Pits | March
BHT-FWP-06 | Lightspeed | 2025-03-20 | 6275 |  | Restoration | March
D-HNP138 | FCA Fiber | 2025-03-20 | 1016 |  | 11 Toby Boxes | March
FB-HNP138 |  | 2025-03-20 | 353 |  |  | March
FB-HDH275 | HDD Underground | 2025-03-20 |  |  |  | March
D-H0221D | Bartlett Fiber | 2025-03-20 | 700 |  | 9 Toby Box / 4 Splice | March
D-H0221B | Bartlett Fiber | 2025-03-20 | 1236 |  | 17 Toby Box / 13 Splice | March
FB-H0221A | HAS Global | 2025-03-20 |  |  |  | March
D-HDH75 | Longo Underground | 2025-03-20 | 1964 |  | 15 Toby Box / 30 Splice | March
D-HNP141 | Power Connect | 2025-03-20 |  |  | No Locates | March
D-H0222A | Lightspeed | 2025-03-20 | 170 |  | 1 Toby Box / 2 Splices | March
D-HDH67 |  | 2025-03-20 | 836 |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod / 5 Toby Boxes / 4 Pits | March
BHT-FWP-06 | Lightspeed | 2025-03-20 |  |  | Restoration | March
D-HNP138 | FCA Fiber | 2025-03-21 |  |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | March
FB-HDH275 | HDD Underground | 2025-03-21 |  |  | Soft Dig Requested | March
D-H0221D | Bartlett Fiber | 2025-03-21 | 709 |  | 2 Toby Box / 1 Splices | March
D-H0221B | Bartlett Fiber | 2025-03-21 | 399 |  | 5 Toby Box / 1 Splices | March
D-HDH75 | Longo Underground | 2025-03-21 | 1528 |  | 15 Toby Box / 30 Splice / 1 HH / 1 Swing Arm / 1 Ground Rod | March
D-HNP141 | Power Connect | 2025-03-21 | 420 |  | 4 Toby Box / 5 Pits | March
D-H0222A | Lightspeed | 2025-03-21 | 270 |  | 1 Toby Box / 2 Splices | March
D-HDH67 | Power Connect | 2025-03-21 |  |  |  | March
FB-HDH02A D-HDH75 Tie In | Longo Underground | 2025-03-21 | 583 |  | 3 Dap Locations | March
D-HDH46 | FCA Fiber | 2025-03-21 |  |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | March
D-HDH03 | Power Connect | 2025-03-21 | 360 |  | 4 Pits | March
FB-HDH02A | Longo Underground | 2025-03-24 | 762 | 12 Splices |  | March
D-HDH76 | J Garcia Construction | 2025-03-24 |  |  | Schedule Final Walkout | March
D-HNP141 | Power Connect | 2025-03-24 | 982 | 10 Splices | 10 Toby Boxes | March
D-H0220C | Power Connect | 2025-03-24 | 691 |  | 4 Toby Boxes / 6 Pits | March
D-H0221A | Brothers | 2025-03-24 | 1430 | 9 Toby Boxes | 7 Splices | March
D-H0221F | Brothers | 2025-03-24 | 1460 |  | 10 Toby Boxes | March
FB-HDH02A | FCA Fiber | 2025-03-24 |  |  | Pending Soft Dig | March
D-H0221D | Bartlett Fiber | 2025-03-24 | 905 | 5 Splices | 7 Toby Boxes | March
D-H0223F | Lightspeed | 2025-03-24 |  |  | Moved Drill-Locates Not Clear | March
D-H0222D | Bartlett Fiber | 2025-03-24 |  |  | Sponging | March
D-HDH04 | Bartlett Fiber | 2025-03-24 |  |  | Schedule Final Walkout | March
D-HDH34 | Lightspeed | 2025-03-24 |  |  | Schedule Final Walkout | March
D-H0222A | Lightspeed | 2025-03-24 | 58 | 2 Splices | 1 toby box | March
FB-H0220A | Longo Underground | 2025-03-25 | 575 |  |  | March
D-HDH04 | Bartlett Fiber | 2025-03-25 |  |  | Schedule Final Walkout | March
D-HNP141 | Power Connect | 2025-03-25 | 749 |  | 7 Toby Box / 11 Pits | March
D-H0222A | Power Connect | 2025-03-25 | 574 |  | 2 Toby Box / 5 Pits | March
D-H0221A | Brothers | 2025-03-25 | 1383 | 7 Splice | 9 Toby Box | March
D-H0221F | Brothers | 2025-03-25 | 1350 | 8 Splice | 10 Toby Box | March
D-HDH46 | FCA Fiber | 2025-03-25 |  |  |  | March
FB-HDH02A | FCA Fiber | 2025-03-25 |  |  |  | March
D-H0221D | Bartlett Fiber | 2025-03-25 | 630 | 2 Splice | 10 Toby Box | March
FB-HDH275 | HDD Underground | 2025-03-25 |  |  |  | March
D-H0223C | Lightspeed | 2025-03-25 |  | 4 Splices |  | March
D-H0223A | Bartlett Fiber | 2025-03-25 |  |  | Sponging | March
D-H0221C | Bartlett Fiber | 2025-03-25 | 1065 | 5 Splices | 5 Toby Box | March
D-H0222A | US Builders | 2025-03-25 |  |  | Didn't Show On Site | March
D-HDH74 | Bartlett Fiber | 2025-03-25 |  |  | Sponging | March
FB-H0223A | Lightspeed | 2025-03-25 |  | 8 Splices | 4 pits | March
D-HDH76 | J Garcia Construction | 2025-03-25 |  |  | Schedule Final Walkout | March
D-HDH34 | Lightspeed | 2025-03-25 |  |  | Schedule Final Walkout | March
D-H0220B | US Builders | 2025-03-25 | 442 |  |  | March
BHT-FWP-06 | In-House | 2025-03-25 | 380 |  |  | March
FB-HOE117 | Brothers | 2025-03-25 | 1740 |  |  | March
D-HOE215 | HAS Global | 2025-03-25 | 483 | 1 splice | 1 toby box | March
D-HOE102 | MTX | 2025-03-25 | 1333 |  |  | March
D-HDH69 | Longo Underground | 2025-03-26 | 1972 | 30 Splices | 15 Toby Boxes | March
D-HDH04 | J Garcia Construction | 2025-03-26 |  |  | Schedule Final Walkout | March
D-HNP141 | Power Connect | 2025-03-26 | 713 |  | 5 Toby Boxes / 8 Pits | March
D-H0222A | Power Connect | 2025-03-26 | 545 |  | 11 Pits | March
D-H0221A | Brothers | 2025-03-26 | 1334 | 8 Splices | 9 Toby Boxes | March
D-H0221F | Brothers | 2025-03-26 | 1507 | 8 Splices | 9 Toby Boxes | March
D-HDH46 | FCA Fiber | 2025-03-26 |  |  |  | March
FB-HDH02A | FCA Fiber | 2025-03-26 |  |  |  | March
D-H0221D | Bartlett Fiber | 2025-03-26 | 894 | 4 Splices | 5 Toby Boxes | March
FB-HDH275 | HDD Underground | 2025-03-26 |  |  |  | March
34th St Crossing | Lightspeed | 2025-03-26 |  |  | Moved To Tomorrow | March
D-H0221C | Bartlett Fiber | 2025-03-26 | 825 | 3 Splices | 8 Toby Boxes | March
D-H0222A | US Builders | 2025-03-26 | 159 | 4 Splices | 3 Toby Boxes | March
D-HDH74 | Bartlett Fiber | 2025-03-26 |  |  | Sponging | March
D-H0220B | US Builders | 2025-03-26 | 854 |  |  | March
BHT-FWP-06 | In-House | 2025-03-26 | 300 |  |  | March
FB-HOE117 | Brothers | 2025-03-26 | 2934 |  | 8 HH / 20 Pits | March
D-HOE215 | HAS Global | 2025-03-26 | 1799 |  | 17 Pits | March
D-HOE102 | MTX | 2025-03-26 | 1701 | 10 Splices | 13 Toby Boxes/ 24 Pits | March
D-HDH69 | Lightspeed | 2025-03-27 | 178 | 10 Splices | 2 Toby Boxes | March
D-H0220B | US Builders | 2025-03-27 | 290 |  |  | March
D-HNP141 | Power Connect | 2025-03-27 |  |  | Crews Dispatched To D-H0222A | March
D-H0222A | Power Connect | 2025-03-27 | 593 |  | 3 Toby Boxes / 10 Pits | March
D-H0221A | Brothers | 2025-03-27 | 1548 | 11 Splices | 10 Toby Boxes | March
D-HDH46 | FCA Fiber | 2025-03-27 | 137 | 40 Splices | 20 Toby Boxes / 1 FDH / 1 HH / 1 Ground Rod | March
FB-HDH02A | FCA Fiber | 2025-03-27 |  |  |  | March
FB-H0222A | Bartlett Fiber | 2025-03-27 | 310 |  |  | March
FB-HDH275 | HDD Underground | 2025-03-27 |  |  |  | March
34th St Crossing | Lightspeed | 2025-03-27 |  |  |  | March
D-H0221C | Bartlett Fiber | 2025-03-27 | 705 | 5 Splices |  | March
D-H0222A | US Builders | 2025-03-27 | 416 | 6 Splices | 3 Toby Boxes / 10 Pits | March
D-HDH74 | Bartlett Fiber | 2025-03-27 |  |  | Moved FDH | March
D-H0221F | Brothers | 2025-03-27 |  |  | Drill Breakdown | March
FB-HDH02A | AMT | 2025-03-27 | 76 |  | 2 Pits | March
BHT-FWP-06 | Lightspeed | 2025-03-27 | 150 |  |  | March
BHT-FWP-07 | Lightspeed | 2025-03-27 | 195 |  |  | March
D-HDH69 | EHL | 2025-03-28 | 266 |  | 2 Pits | March
D-H0220B | US Builders | 2025-03-28 | 673 |  |  | March
D-H0220A | Power Connect | 2025-03-28 |  |  |  | March
D-H0222A | Power Connect | 2025-03-28 |  |  |  | March
D-H0221F | Brothers | 2025-03-28 | 1530 | 11 Toby Boxes | 10 Splices | March
D-H0221F | Brothers | 2025-03-28 | 757 | 7 Splices | 7 Toby Boxes | March
D-HDH46 | FCA Fiber | 2025-03-28 |  |  | Drill Still Broken Down | March
FB-HDH02A | FCA Fiber | 2025-03-28 |  |  |  | March
FB-HDH275 | HDD Underground | 2025-03-28 |  |  | Restoration | March
34th St Crossing | Lightspeed | 2025-03-28 |  |  | Drill Breakdown | March
D-H0222A | US Builders | 2025-03-28 | 200 |  | 1 Pit | March
BHT-FWP-06 | Lightspeed | 2025-03-28 |  |  | 1 Vault | March
302B FDH | Lightspeed | 2025-03-28 |  |  |  | March
FB-HOE117 | Brothers | 2025-03-28 |  |  | Drill Breakdown | March
D-HOE215 | HAS Global | 2025-03-28 |  |  |  | March
FB-HOE117 | MTX | 2025-03-28 | 161 | 8 Splices | 5 Pits | March
D-HOE102 | MTX | 2025-03-28 | 546 | 98 Splices | 15 Toby Boxes / 10 Pits /1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | March
D-HDH69 | EHL | 2025-03-31 | 715 | 10 Splices | 18 Toby Boxes | March
D-H0223A | Bartlett Fiber | 2025-03-31 | 0 |  | Sponging | March
D-H0220A | Power Connect | 2025-03-31 | 1880 | 12 Splices | 4 Toby Boxes | March
D-H0222A | Power Connect | 2025-03-31 | 265 |  | 10 Pits | March
D-H0221F | Brothers | 2025-03-31 | 695 | 4 Splices | 4 Toby Boxes | March
FB-HDH02A | FCA Fiber | 2025-03-31 | 644 |  | 3 Daps | March
D-HNP114 | FCA Fiber | 2025-03-31 | 349 |  | 1 Toby Boxes / 1 Dap | March
D-HDH69 | Lightspeed | 2025-03-31 | 374 | 8 Splices | 4 Toby Boxes | March
D-H0222A | US Builders | 2025-03-31 | 0 |  | Pulled From Project | March
D-HDH67 | Bartlett Fiber | 2025-03-31 | 0 |  | Verifying Pipe | March
D-H0222B | Power Connect | 2025-03-31 | 745 |  | 6 Pits | March
BHT-FWP-07 | In-House | 2025-03-31 | 453 |  |  | March
D-HWP706 | In-House | 2025-03-31 | 1413 |  | 11 Toby Boxes | March
FB-HOE117 | Brothers | 2025-03-31 | 418 |  |  | March
D-HOE215 | HAS Global | 2025-03-31 | 499 |  | 3 Toby Boxes / 5 Pits | March
FB-HOE117 | MTX | 2025-03-31 | 0 |  | Proofing Conduits | March
FB-HOE201 | Brothers | 2025-03-31 | 1355 |  |  | March
BHZD-FOE-03-W | MTX | 2025-03-31 | 2227 |  |  | March
D-HDH69 | EHL | 2025-04-01 |  |  |  | April
D-H0221B | Bartlett Fiber | 2025-04-01 |  |  | Sponging | April
D-H0220A | Power Connect | 2025-04-01 |  |  |  | April
D-H0222A | Power Connect | 2025-04-01 |  |  |  | April
D-HNP114 | FCA Fiber | 2025-04-01 | 952 |  | 6 Toby Boxes | April
D-HDH69 | Lightspeed | 2025-04-01 |  |  |  | April
D-HDH74 | Bartlett Fiber | 2025-04-01 |  |  | Restoration | April
D-HDH32 | MTX | 2025-04-01 |  |  |  | April
BHT-FWP-07 | In-House | 2025-04-01 | 166 |  |  | April
D-HWP706 | Brothers | 2025-04-01 | 1,394 / 10 Toby Boxes |  |  | April
FB-HOE201 | Brothers | 2025-04-01 |  |  | Hit Sewer Main | April
D-HOE215 | HAS Global | 2025-04-01 |  |  |  | April
FB-HOE117 | In-House | 2025-04-01 |  |  |  | April
BHUD-FOE-02-W | MC Logistics | 2025-04-01 | 1149 |  | 3 Pits | April
D-HDH69 | EHL | 2025-04-02 |  |  |  | April
D-H0221B | Bartlett Fiber | 2025-04-02 | 0 |  | Sponging | April
D-H0220A | Power Connect | 2025-04-02 |  |  |  | April
D-H0222A | Power Connect | 2025-04-02 |  |  |  | April
D-HNP114 | FCA Fiber | 2025-04-02 | 952 |  | 6 Toby Boxes | April
D-HDH69 | Lightspeed | 2025-04-02 |  |  |  | April
D-HDH74 | Bartlett Fiber | 2025-04-02 | 0 |  | Restoration | April
D-HDH32 | MTX | 2025-04-02 |  |  |  | April
BHT-FWP-07 | In-House | 2025-04-02 | 166 |  |  | April
D-HWP706 | Brothers | 2025-04-02 | 1394 |  | 10 Toby Boxes | April
FB-HOE201 | Brothers | 2025-04-02 | 0 |  | Hit Sewer Main | April
D-HOE215 | HAS Global | 2025-04-02 |  |  |  | April
FB-HOE117 | In-House | 2025-04-02 |  |  |  | April
BHUD-FOE-02-W | MC Logistics | 2025-04-02 | 1149 |  | 3 Pits | April
D-HDH69 | Lightspeed | 2025-04-03 |  |  | Tie Ins | April
FB-H0221A | Bartlett Fiber | 2025-04-03 | 192 |  |  | April
D-H0220C | Power Connect | 2025-04-03 | 3867 |  | 17 Toby Boxes / 43 Pits / 51 Splices | April
D-HNP114 | FCA Fiber | 2025-04-03 | 1328 |  | 13 Toby Boxes / 31 Splices | April
D-HNP151 | Longo Underground | 2025-04-03 | 313 |  | 3 Toby Boxes / 18 Splices | April
D-HDH32 | MTX | 2025-04-03 | 344 |  | 1 Toby Boxes / 2 Pits / 24 Splices | April
D-HDH82 | MTX | 2025-04-03 | 1265 |  | 10 Toby Boxes / 20 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | April
BHT-FWP-07 | Lightspeed | 2025-04-03 | 302 |  | 1 Pit | April
D-HWP707 | Brothers | 2025-04-03 | 1334 |  | 8 Toby Boxes / 12 Pits / 14 Dap Splices | April
D-HWP702 | Brothers | 2025-04-03 | 1970 |  | 16 Toby Boxes / 1HH | April
FB-HOE201 | Brothers | 2025-04-03 |  |  | On Hold | April
D-HOE206 | HAS Global | 2025-04-03 |  |  | On Hold | April
FB-HOE117 | Lightspeed | 2025-04-03 |  |  | On Hold | April
BHUD-FOE-02-W | MC Logistics | 2025-04-03 |  |  | On Hold | April
D-H0222A | Longo Underground | 2025-04-04 | 635 |  | 5 Toby Boxes / 10 Splices | April
D-H0221D | Bartlett Fiber | 2025-04-04 |  |  | 3 Splices | April
D-H0220C | Power Connect | 2025-04-04 | 594 |  | 5 Toby Boxes / 7 Pits / 9 Splices | April
D-H0222A | Power Connect | 2025-04-04 |  |  | Job Re-Assigned To Longo Underground | April
D-HDH03 | Power Connect | 2025-04-04 |  |  | Drill Breakdown | April
D-HNP114 | FCA Fiber | 2025-04-04 | 397 |  | 3 Toby Boxes / 20 Splices | April
D-HDH80 | MTX | 2025-04-04 | 2144 |  | 19 Toby Boxes / 19 Pits / 47 Splices | April
BHT-FWP-06 | Lightspeed | 2025-04-04 |  |  | 1 HH | April
BHT-FWP-07 | Lightspeed | 2025-04-04 |  |  | 1 HH | April
FB-HOE201 | Brothers | 2025-04-04 |  |  | On Hold | April
D-HOE206 | HAS Global | 2025-04-04 |  |  | On Hold | April
FB-HOE117 | Lightspeed | 2025-04-04 |  |  | On Hold | April
BHUD-FOE-02-W | MC Logistics | 2025-04-04 |  |  | On Hold | April
D-HWP702 | Brothers | 2025-04-07 |  |  | 1 HH / 1 Swing Arm / 1 FDH / 1 Ground Rod | April
D-HDH80 | MTX | 2025-04-07 | 990 |  | 6 Pits | April
D-H0220C | Power Connect | 2025-04-07 | 367 |  | 5 Toby Boxes / 5 Pits / 30 Splices | April
D-H0221D | Bartlett Fiber | 2025-04-07 | 132 |  |  | April
FB-HDH02A | Bartlett Fiber | 2025-04-07 | 370 |  |  | April
D-HNP113 | HDD Underground | 2025-04-07 | 590 |  |  | April
BHU-FDH-01-W | Lightspeed | 2025-04-07 | 198 | 198 | 2 HH | April
FB-HDH02A | Lightspeed | 2025-04-07 | 180 |  | 3 HH | April
FB-HDH275 | HDD Underground | 2025-04-07 |  | 5575 | 7,497 Tracer Wire / 1 HH | April
BHT-FWP-07 | Lightspeed | 2025-04-07 | 43 |  |  | April
D-HWP707 | Brothers | 2025-04-07 | 618 |  | 3 Toby Boxes / 2 Pits / 3 Splices / 1 HH | April
D-HWP703 | Brothers | 2025-04-07 | 1840 |  | 14 Toby Boxes | April
D-HDH80 | MTX | 2025-04-08 | 1871 |  | 9 Toby Boxes / 20 Pits / 7 Splices | April
D-HNP113 | HDD Underground | 2025-04-08 | 343 |  |  | April
FB-HDH275 | FCA Fiber | 2025-04-08 |  | 2372 |  | April
BHT-FWP-06 | Lightspeed | 2025-04-08 | 45 |  |  | April
D-HWP707 | Brothers | 2025-04-08 | 700 |  | 5 Toby Boxes | April
D-HWP703 | Brothers | 2025-04-08 | 1520 |  | 14 Toby Boxes | April
FB-HWP701 | Brothers | 2025-04-08 | 150 |  |  | April
FB-HOE201 | Brothers | 2025-04-08 |  |  | On Hold | April
D-HOE206 | HAS Global | 2025-04-08 |  |  | On Hold | April
FB-HOE117 | Lightspeed | 2025-04-08 |  |  | On Hold | April
BHUD-FOE-02-W | MC Logistics | 2025-04-08 |  |  | On Hold | April
D-HDH80 | MTX | 2025-04-09 | 1307 |  | 14 Toby Boxes / 9 Pits / 73 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | April
D-H0220C | Power Connect | 2025-04-09 |  |  | 4 Toby Boxes / 1 Pits / 135 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | April
D-HDH47 | Bartlett Fiber | 2025-04-09 | 1376 |  | 9 Toby Boxes / 9 Splices | April
D-HDH43 | US Builders | 2025-04-09 | 617 |  |  | April
BHT-FWP-06 | Lightspeed | 2025-04-09 |  |  | 1 HH | April
D-HWP703 | Brothers | 2025-04-09 | 2060 |  | 14 Toby Boxes | April
FB-HWP701 | In-House | 2025-04-09 | 295 |  |  | April
FB-HOE201 | Brothers | 2025-04-09 |  |  | On Hold | April
D-HOE206 | HAS Global | 2025-04-09 |  |  | On Hold | April
FB-HOE117 | In-House | 2025-04-09 |  |  | On Hold | April
BHUD-FOE-02-W | MC Logistics | 2025-04-09 |  |  | On Hold | April
D-HDH80 | MTX | 2025-04-10 |  |  | Restoration | April
D-HDH82 | MTX | 2025-04-10 |  |  | Restoration | April
D-HDH47 | Bartlett Fiber | 2025-04-10 | 875 |  | 8 Toby Boxes / 25 Splices | April
D-HDH60 | US Builders | 2025-04-10 | 711 |  | 2 Toby Boxes / 3 Splices | April
D-HDH43 | Longo Underground | 2025-04-10 | 627 |  |  | April
FB-HDH02A | Lightspeed | 2025-04-10 | 426 | 360 | 360 Tracer Wire | April
FB-HWP701 | Lightspeed | 2025-04-10 | 504 |  |  | April
D-HWP703 | Brothers | 2025-04-10 | 1330 |  | 7 Toby Boxes / 10 Pits / 52 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | April
D-HDH43 | US Builders | 2025-04-11 | 431 |  |  | April
D-HDH47 | Bartlett Fiber | 2025-04-11 | 1301 |  | 9 Toby Boxes / 18 Splices | April
D-HDH60 | Longo Underground | 2025-04-11 | 695 |  | 7 Toby Boxes / 10 Splices | April
D-HDH80 | MTX | 2025-04-11 |  |  | Restoration | April
D-HDH32 | MTX | 2025-04-11 |  |  | Restoration | April
D-H0220C | Power Connect | 2025-04-11 |  |  | 5 Toby Boxes / 1 FDH | April
D-HNP141 | Power Connect | 2025-04-11 |  |  | 4 Toby Boxes / 1 FDH | April
D-H0220B | Bartlett Fiber | 2025-04-11 | 314 |  |  | April
BHT-FWP-07 | Lightspeed | 2025-04-11 |  | 1275 | 1.275 Tracer Wire | April
D-HWP703 | Lightspeed | 2025-04-11 |  |  | Sponging / Restortion | April
FB-HWP701 | Brothers | 2025-04-11 |  | 899 | 899 Tracer Wire | April
D-HDH43 | US Builders | 2025-04-14 | 276 |  |  | April
D-HDH47 | Bartlett Fiber | 2025-04-14 |  |  | Drill Breakdown--No Production | April
D-HDH49 | Brothers | 2025-04-14 | 1335 |  | 10 Toby Boxes | April
D-HDH58 | Brothers | 2025-04-14 |  |  |  | April
D-HDH60 | Longo Underground | 2025-04-14 | 796 |  | 9 Toby Boxes / 24 Splices | April
D-HDH62 | US Builders | 2025-04-14 | 547 |  |  | April
D-H0220C | Power Connect | 2025-04-14 |  |  |  | April
D-HNP141 | Power Connect | 2025-04-14 |  |  |  | April
BHT-FWP-06 | Lightspeed | 2025-04-14 |  |  | No Production | April
D-HWP1306 | Lightspeed | 2025-04-14 | 259 |  |  | April
D-HDH43 | US Builders | 2025-04-15 | 779 |  | 4 Toby Boxes / 8 Splices | April
D-HDH47 | Bartlett Fiber | 2025-04-15 | 1018 |  | 8 Toby Boxes / 34 Splices | April
D-HDH49 | Brothers | 2025-04-15 | 1133 |  | 8 Toby Boxes / 48 Splices | April
D-HDH58 | Brothers | 2025-04-15 | 1526 |  | 9 Toby Boxes / 30 Splices | April
D-HDH60 | Longo Underground | 2025-04-15 | 1929 |  | 15 Toby Boxes / 60 Splices | April
D-HDH62 | US Builders | 2025-04-15 | 845 |  |  | April
FB-HDH02A | Lightspeed | 2025-04-15 | 561 |  |  | April
D-H0220C | Power Connect | 2025-04-15 |  |  | Toby Boxes / Restoration | April
D-HNP141 | Power Connect | 2025-04-15 |  |  | Toby Boxes / Restoration | April
D-HDH73 | Power Connect | 2025-04-15 |  |  | Restoration | April
BHT-FWP-06 | Lightspeed | 2025-04-15 | 37 |  |  | April
D-HWP1306 | Lightspeed | 2025-04-15 | 243 |  | 2 Pits | April
D-HDH41 | MTX | 2025-04-15 | 1538 |  | 13 Toby Boxes / 7 Pits / 30 Splices | April
D-HDH04 | Bartlett Fiber | 2025-04-16 |  |  | Toby Box Relocation | April
D-HDH41 | MTX | 2025-04-16 | 2713 |  | 20 Toby Boxes / 16 Pits / 62 Splices | April
D-HDH43 | US Builders | 2025-04-16 | 868 |  | 7 Toby Boxes / 13 Splices | April
D-HDH49 | Brothers | 2025-04-16 | 1624 |  | 11 Toby Boxes / 42 Splices | April
D-HDH58 | Brothers | 2025-04-16 | 1503 |  | 10 Toby Boxes / 46 Splices | April
D-HDH60 | Longo Underground | 2025-04-16 | 876 |  | 4 Toby Boxes / 7 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH62 | US Builders | 2025-04-16 | 400 |  |  | April
FB-HDH02A | Lightspeed | 2025-04-16 | 260 |  | 2 Pits / 10 Splices | April
D-HDH75 | Longo Underground | 2025-04-16 | 173 |  |  | April
D-HDH67 | Power Connect | 2025-04-16 |  |  | Restoration | April
D-HDH73 | Power Connect | 2025-04-16 |  |  | Restoration | April
D-HDH70 | Longo Underground | 2025-04-16 |  |  | Restoration | April
BHT-FWP-06 | Lightspeed | 2025-04-16 | 115 |  | 3 HH | April
D-HWP1306 | Lightspeed | 2025-04-16 |  |  | Drill Breakdown | April
D-HDH41 | MTX | 2025-04-17 | 862 |  | 6 Toby Boxes / 3 Pits / 6 Splices | April
D-HDH43 | US Builders | 2025-04-17 | 338 |  | 6 Toby Boxes / 2 Splices | April
D-HDH47 | Bartlett Fiber | 2025-04-17 | 569 |  | 5 Toby Boxes / 6 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH49 | Brothers | 2025-04-17 |  |  | Crew Re-Located To Lakeland | April
D-HDH58 | Brothers | 2025-04-17 | 1590 |  | 11 Toby Boxes | April
D-HDH60 | Longo Underground | 2025-04-17 | 651 |  | 6 Toby Boxes / 8 Splices | April
D-HDH62 | US Builders | 2025-04-17 | 906 |  |  | April
FB-HDH02A | Lightspeed | 2025-04-17 | 40 |  |  | April
D-H0223F | Lightspeed | 2025-04-17 | 96 |  | 3 Pits / 24 Splices--Frontier Damage Completed. | April
D-HDH69 | Longo Underground | 2025-04-17 | 433 |  | 4 Toby Boxes / 8 Splices | April
D-HWP1309 | Brothers | 2025-04-17 | 647 |  | 6 Toby Boxes | April
D-HWP1306 | Lightspeed | 2025-04-17 | 193 |  | 2 Toby Boxes | April
D-HDH41 | MTX | 2025-04-18 | 1507 |  | 9 Toby Boxes / 2 Pits / 35 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH43 | US Builders | 2025-04-18 | 26 |  | 12 Toby Boxes / 26 Splices | April
D-HDH47 | Bartlett Fiber | 2025-04-18 |  |  | Crew Re-Located To Another Project | April
D-HDH49 | Brothers | 2025-04-18 | 350 |  | 2 Toby Boxes | April
D-HDH58 | Brothers | 2025-04-18 | 370 |  | 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | April
D-HDH48 | Bartlett Fiber | 2025-04-18 | 706 |  | 3 Toby Boxes | April
D-HDH62 | US Builders | 2025-04-18 | 198 |  | 4 Toby Boxes / 17 Splices | April
FB-HDH02A | Lightspeed | 2025-04-18 |  | 6350 | 6,350 Tracer Wire | April
FB-HDH02A | Lightspeed | 2025-04-18 | 408 |  | 4 Pits / 4 Splices | April
D-H0220C | Power Connect | 2025-04-18 |  |  | Restoration | April
D-HDH73 | Power Connect | 2025-04-18 |  |  | Restoration-QC Walk | April
FX4-FWP-13 | Brothers | 2025-04-18 |  |  | Concrete | April
BHT-FWP-07 | Lightspeed | 2025-04-18 |  |  | Restoration | April
D-HDH42 | FCA | 2025-04-21 |  |  | No Production--Issue With Locates | April
D-HDH43 | US Builders | 2025-04-21 |  |  | Toby boxes | April
D-HDH48 | BFI | 2025-04-21 |  |  | No Production--Issue With Locates | April
D-HDH49 | Brothers | 2025-04-21 | 1050 |  | 9 Toby Boxes / 22 Splices | April
D-HDH55 | HAS Global | 2025-04-21 | 621 |  |  | April
D-HDH56 | Longo Underground | 2025-04-21 | 1285 |  | 9 Toby Boxes / 36 Splices | April
D-HDH58 | Brothers | 2025-04-21 |  |  | Restoration-In-House QC Walk | April
D-HDH60 | Longo Underground | 2025-04-21 |  |  | Proofing | April
D-HDH62 | US Builders | 2025-04-21 |  |  | No Production | April
D-HDH67 | Power Connect | 2025-04-21 |  |  | Restoration | April
D-HNP141 | Power Connect | 2025-04-21 |  |  | Restoration | April
D-HWP1306 | Lightspeed | 2025-04-21 |  |  | No Production | April
D-HDH42 | FCA | 2025-04-22 |  |  |  | April
D-HDH43 | US Builders | 2025-04-22 |  |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH48 | BFI | 2025-04-22 | 1701 |  | 12 Toby Boxes / 49 Splices | April
D-HDH55 | HAS Global | 2025-04-22 | 464 |  | 6 Toby Boxes / 3 Pits / 22 Splices | April
D-HDH56 | Longo Underground | 2025-04-22 | 951 |  | 11 Toby Boxes / 20 Splices | April
D-HDH57 | MTX | 2025-04-22 | 1864 |  | 13 Toby Boxes / 13 Splices | April
D-HDH62 | US Builders | 2025-04-22 |  |  | No Production | April
D-HDH75 | Longo Underground | 2025-04-22 |  |  | Sponging | April
FB-HDH02A | Lightspeed | 2025-04-22 | 205 |  | 2 Pits / 4 Splices | April
D-HNP141 | Power Connect | 2025-04-22 |  |  | ABF Testing / Restoration | April
D-HWP1306 | Lightspeed | 2025-04-22 | 510 |  | 5 Toby Boxes / 4 Pits / 14 Splices | April
D-HWP1309 | Brothers | 2025-04-22 | 932 |  | 6 Toby Boxes | April
FX4-FWP-13 | Brothers | 2025-04-22 | 23 |  | 1 Vault / 1 Cabinet / 6 Ground Rods | April
D-HDH03 | Lightspeed | 2025-04-23 | 113 |  | 4 Pits / 48 Splices | April
D-HDH42 | FCA | 2025-04-23 | 2348 |  | 21 Toby Boxes / 15 Pits / 43 Splices | April
D-HDH43 | US Builders | 2025-04-23 |  |  | Sponging | April
D-HDH48 | BFI | 2025-04-23 | 314 |  | 4 Toby Boxes | April
D-HDH52 | MTX | 2025-04-23 |  |  | Crew Will Be Starting Tomorrow | April
D-HDH55 | HAS Global | 2025-04-23 |  |  | No Report | April
D-HDH56 | Longo Underground | 2025-04-23 | 1598 |  |  | April
D-HDH57 | MTX | 2025-04-23 | 1514 |  | 7 Toby Boxes / 8 Pits / 31 Splices | April
FB-HDH02A | Lightspeed | 2025-04-23 | 190 |  | 2 Pits / 2 Splices | April
D-H0222B | Power Connect | 2025-04-23 |  |  | Toby Boxes / Restoration
D-HNP141 | Power Connect | 2025-04-23 |  |  | ABF Testing / Restoration
D-HWP1306 | Lightspeed | 2025-04-23 | 275 |  | 2 Toby Boxes | April
D-HWP1309 | Brothers | 2025-04-23 | 1190 |  | 6 Toby Boxes / 1 HH | April
D-HDH42 | FCA | 2025-04-24 | 1378 |  | 14 Toby Boxes / 7 Pits / 20 Splices | April
D-HDH48 | BFI | 2025-04-24 | 662 |  | 8 Toby Boxes / 4 Splices | April
D-HDH52 | MTX | 2025-04-24 | 988 |  | 6 Toby Boxes / 6 Pits / 15 Splices | April
D-HDH54 | HAS Global | 2025-04-24 | 588 |  | 3 Toby Boxes / 20 Splices | April
D-HDH55 | HAS Global | 2025-04-24 |  |  | Project Shutdown | April
D-HDH56 | Longo Underground | 2025-04-24 | 1671 |  | 15 Toby Boxes / 36 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH57 | MTX | 2025-04-24 | 1095 |  | 10 Toby Boxes / 8 Pits / 39 Splices | April
D-HDH62 | US Builders | 2025-04-24 | 64 |  | 20 Toby Boxes / 53 Splices | April
FB-HDH02A | Lightspeed | 2025-04-24 | 48 |  | 2 Pits / 2 Splices | April
D-H0222B | Power Connect | 2025-04-24 |  |  | 3 Toby Boxes / 6 Splices | April
FB-H0223A | Power Connect | 2025-04-24 |  |  | Crew Did Not Work On This Project Today | April
BHT-FWP-06 | Lightspeed | 2025-04-24 |  | 2815 | 2,815 Tracer Wire | April
D-HWP1309 | Brothers | 2025-04-24 | 909 |  | 8 Toby Boxes | April
D-HDH42 | FCA | 2025-04-25 | 726 |  | 6 Toby Boxes / 6 Pits / 6 Splices | April
D-HDH48 | BFI | 2025-04-25 | 728 |  | 5 Toby Boxes / 13 Splices | April
D-HDH50 | FCA | 2025-04-25 | 1108 |  | 12 Toby Boxes / 7 Pits / 8 Splices | April
D-HDH52 | MTX | 2025-04-25 |  |  | Crew Shutdown By Tillman | April
D-HDH54 | HAS Global | 2025-04-25 | 431 |  | 5 Toby Boxes / 11 Splices | April
D-HDH53 | Longo Underground | 2025-04-25 | 385 |  | 4 Toby Boxes / 8 Splices | April
D-HDH57 | MTX | 2025-04-25 |  |  | Crew Shutdown By Tillman | April
D-HDH60 | Longo UG | 2025-04-25 |  |  | Restoration | April
D-HDH62 | US Builders | 2025-04-25 | 21 |  | 11 Toby Boxes / 34 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
FB-HDH02A | Lightspeed | 2025-04-25 | 150 |  |  | April
BHT-FWP-06 | Lightspeed | 2025-04-25 |  |  | Restoration | April
FX4-FWP-13 | Brothers | 2025-04-25 |  |  | Bollards | April
D-HDH42 | FCA | 2025-04-28 | 1602 |  | 12 Toby Boxes / 8 Pits / 30 Splices | April
D-HDH48 | BFI | 2025-04-28 | 961 |  | 9 Toby Boxes / 28 Splices | April
D-HDH50 | FCA | 2025-04-28 |  |  | Crew Will Be Starting Tomorrow | April
D-HDH52 | Lightspeed | 2025-04-28 |  |  |  | April
D-HDH53 | Longo Underground | 2025-04-28 | 813 |  | 7 Toby Boxes / 6 Splices | April
D-HDH54 | HAS Global | 2025-04-28 | 1936 |  | 14 Toby Boxes / 62 Splices | April
FB-HDH02A | Lightspeed | 2025-04-28 | 423 |  | 4 Pits / 6 Splices | April
BHT-FWP-06 | Lightspeed | 2025-04-28 |  |  | Restoration | April
D-HWP-1304 | Brothers | 2025-04-28 | 1216 |  | 11 Toby Boxes | April
D-HDH42 | FCA | 2025-04-29 |  |  | FDH / ABF Testing | April
D-HDH48 | BFI | 2025-04-29 | 370 |  | 4 Toby Boxes / 4 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | April
D-HDH50 | FCA | 2025-04-29 | 440 |  | 2 Toby Boxes / 3 Pits / 23 Splices | April
D-HDH52 | Lightspeed | 2025-04-29 | 608 |  | 3 Toby Boxes / 5 Splices | April
D-HDH53 | Longo Underground | 2025-04-29 | 1597 |  | 13 Toby Boxes / 46 Splices | April
D-HDH54 | HAS Global | 2025-04-29 | 2103 |  | 13 Toby Boxes / 39 Splices | April
D-HWP1306 | Lightspeed | 2025-04-29 | 242 |  |  | April
D-HWP1304 | Brothers | 2025-04-29 | 1520 |  | 10 Toby Boxes | April
D-HWP1309 | Brothers | 2025-04-29 | 470 |  | 4 Toby Boxes | April
D-HWP903 | Brothers | 2025-04-29 | 1190 |  | 10 Toby Boxes | April
D-HDH62 | US Builders | 2025-04-30 |  |  | Restoration | April
D-HDH50 | FCA | 2025-04-30 | 1175 |  | 9 Toby Boxes / 7 Pits / 30 Splices | April
D-HDH52 | Lightspeed | 2025-04-30 | 609 |  | 4 Toby Boxes / 31 Splices | April
D-HDH53 | Longo Underground | 2025-04-30 | 1632 |  | 11 Toby Boxes / 28 Splices | April
D-HDH54 | HAS Global | 2025-04-30 | 1498 |  | 9 Toby Boxes / 34 Splices | April
D-HDH57 | Bartlett Fiber | 2025-04-30 | 594 |  | 7 Toby Boxes / 24 Splices | April
FB-HDH02A | FCA | 2025-04-30 |  |  | Crew Did Not Work This Location Today | April
D-HWP1306 | Lightspeed | 2025-04-30 | 310 |  |  | April
D-HWP1304 | Brothers | 2025-04-30 | 1216 |  | 13 Toby Boxes | April
D-HWP903 | Brothers | 2025-04-30 | 1033 |  | 8 Toby Boxes / 10 Pits / 26 Splices / 1 Flower Pot | April
D-HDH62 | US Builders | 2025-05-01 |  |  | Restoration | May
D-HDH42 | FCA | 2025-05-01 |  |  | Crew Did Not Work This Location Today
D-HDH50 | FCA | 2025-05-01 | 822 |  | 7 Toby Boxes / 3 Pits / 7 Splices | May
D-HDH52 | Lightspeed | 2025-05-01 | 614 |  | 4 Toby Boxes / 7 Splices | May
D-HDH53 | Longo Underground | 2025-05-01 | 692 |  | 7 Toby Boxes / 22 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
D-HDH54 | HAS Global | 2025-05-01 | 229 |  | 1 Toby Boxes / 2 Splices | May
D-HDH57 | FCA | 2025-05-01 |  |  | Crew Did Not Work This Location Today | May
FB-HDH02A | FCA | 2025-05-01 |  |  | Crew Did Not Work This Location Today | May
D-HWP1306 | Lightspeed | 2025-05-01 | 302 |  |  | May
D-HWP1304 | Brothers | 2025-05-01 | 1098 |  | 9 Toby Boxes / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
D-HWP903 | Brothers | 2025-05-01 | 1031 |  | 9 Toby Boxes / 6 Pits / 4 Splices | May
D-HDH50 | FCA | 2025-05-02 | 1020 |  | 10 Toby Boxes / 2 Pits / 46 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
D-HDH52 | Lightspeed | 2025-05-02 |  |  | Crew Did Not Work This Location Today | May
FB-HDH02A | FCA | 2025-05-02 |  |  | Crew Did Not Work This Location Today | May
D-HNP151 | Longo Underground | 2025-05-02 | 1367 |  | 10 Toby Boxes / 31 Splices | May
D-HDH47 | BFI | 2025-05-02 |  |  | Restoration | May
D-HDH54 | HAS Global | 2025-05-02 |  |  | Proofing / Sponging | May
BHT-FWP-06 | Lightspeed | 2025-05-02 |  |  | Restoration | May
D-HDH52 | Lightspeed | 2025-05-05 | 404 |  | 4 Toby Boxes | May
D-HNP144 | FCA | 2025-05-05 | 640 |  | 5 Toby Boxes / 4 Pits / 22 Splices | May
FB-HNP111 | FCA | 2025-05-05 |  |  | Crew Did Not Start This Location | May
FB-H0221A | Lightspeed | 2025-05-05 |  | 636 | 636 48Ct Fiber Cable | May
D-HDH47 | Bartlett Fiber | 2025-05-05 |  |  | Restoration / QC | May
D-HDH54 | HAS Global | 2025-05-05 |  |  | ABF Proofing | May
D-HWP1306 | Lightspeed | 2025-05-05 | 610 |  | 4 Toby Boxes | May
D-HWP903 | Brothers | 2025-05-05 | 1053 |  | 10 Toby Boxes / 4 Pits / 7 Splices | May
D-HWP904 | Brothers | 2025-05-05 | 575 |  | 8 Toby Boxes / 4 Pits / 9 Splices | May
D-HWP1309 | Brothers | 2025-05-05 |  |  | FDH | May
D-HDH52 | Lightspeed | 2025-05-06 | 158 |  | 1 Toby Box / 2 Splices | May
FB-HDH02A | Lightspeed | 2025-05-06 | 155 |  | 4 Splices | May
FB-HDH02A | FCA | 2025-05-06 | 165
D-HNP144 | FCA | 2025-05-06 | 490 |  | 4 Toby Boxes / 2 Pits / 6 Splices | May
FB-HNP111 | FCA | 2025-05-06 |  |  | Crew Did Not Start This Location Today | May
D-HNP151 | Longo Underground | 2025-05-06 | 424 |  | 4 Toby Boxes / 9 Splices | May
D-HDH54 | HAS Global | 2025-05-06 |  |  | ABF Proofing / FDH Placing | May
D-HWP1306 | Lightspeed | 2025-05-06 | 451 |  |  | May
D-HWP903 | Brothers | 2025-05-06 | 812 |  | 10 Toby Boxes / 8 Pits / 32 Splices | May
D-HWP904 | Brothers | 2025-05-06 | 1847 |  | 12 Toby Boxes / 7 Pits / 36 Splices | May
D-HWP902 | Brothers | 2025-05-06 | 565 |  | 5 Toby Boxes | May
D-HDH52 | Lightspeed | 2025-05-07 | 353 |  | 4 Toby Boxes | May
D-H0222A | Lightspeed | 2025-05-07 | 131 |  | 1 Toby Box
D-HNP106 | Power Connect | 2025-05-07 | 592 |  | 6 Toby Boxes / 6 Pits | May
D-HNP144 | FCA | 2025-05-07 | 127 |  | 1 Toby Box / 1 Pit / 2 Splices | May
D-HNP117 | FCA | 2025-05-07 | 645 |  | 2 Toby Boxes / 2 Pits | May
D-HDH54 | HAS Global | 2025-05-07 |  |  | ABF Proofing / FDH Placing | May
D-HDH49 | Lightspeed | 2025-05-07 |  |  | Restoration
D-HWP1306 | Lightspeed | 2025-05-07 | 802 |  | 3 Toby Boxes | May
D-HWP904 | Brothers | 2025-05-07 | 1052 |  | 11 Toby Boxes / 7 Pits / 16 Splices | May
D-HWP902 | Brothers | 2025-05-07 | 1935 |  | 16 Toby Boxes / 15 Pits / 49 Splices | May
D-HDH52 | Lightspeed | 2025-05-08 | 40 |  | 1 Toby Box | May
D-HNP104 | Longo | 2025-05-08 | 616 |  | 3 Toby Boxes / 8 Splices | May
D-HNP106 | Power Connect | 2025-05-08 | 592 |  | 6 Toby Boxes | May
D-HNP113 | BFI | 2025-05-08 | 468 |  |  | May
D-HNP117 | FCA | 2025-05-08 | 853 |  | 7 Toby Boxes / 2 Pits / 18 Splices | May
FB-HNP144 | Lightspeed | 2025-05-08 | 225 |  |  | May
D-HDH49 | Lightspeed | 2025-05-08 |  |  | Restoration | May
D-HDH54 | HAS Global | 2025-05-08 |  |  | ABF Proofing / FDH Placing | May
D-HWP1306 | Lightspeed | 2025-05-08 | 75 |  | 6 Toby Boxes | May
D-HWP902 | Brothers | 2025-05-08 | 1483 |  | 8 Toby Boxes / 8 Pits / 16 Splices | May
D-HWP904 | Brothers | 2025-05-08 | 1846 |  | 16 Toby Boxes / 10 Pits / 74 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
D-HDH42 | FCA | 2025-05-09 |  |  | 1 FDH / 1 Swing Arm / 1 HH 1 Ground Rod / ABF Testing | May
D-HDH52 | Lightspeed | 2025-05-09 | 153 |  | 4 Splices | May
D-HNP104 | Longo | 2025-05-09 | 900 |  | 7 Toby Boxes / 22 Splices | May
D-HNP106 | Power Connect | 2025-05-09 | 730 |  | 6 Toby Boxes / 10 Pits | May
D-HNP113 | BFI | 2025-05-09 | 940 |  |  | May
D-HNP117 | FCA | 2025-05-09 |  |  | Locate Issue--Crew Could Not Work On This Project Today | May
D-HWP1306 | Lightspeed | 2025-05-09 |  |  | Restoration | May
D-HWP903 | Brothers | 2025-05-09 |  |  | 1 FDH / 1 Swing Arm / 1 HH 1 Ground Rod | May
|  | 2025-05-12 |  |  |  | May
D-HNP104 | Longo Underground | 2025-05-13 | 212 |  |  | May
D-HNP117 | FCA | 2025-05-13 |  |  | Locate Issue Crew Did Not Work This Location Today | May
D-H0222A | Lightspeed | 2025-05-13 | 55 |  | 1 Toby Box / 4 Splices | May
FB-HDH02A | Lightspeed | 2025-05-13 |  |  | Conduit Splicing | May
FB-HDH02A | Lightspeed | 2025-05-13 |  |  | Conduit Splicing | May
D-H0223F | Lightspeed | 2025-05-13 | 30 |  | 7 Splices--Maintenance Project | May
D-HWP1306 | Lightspeed | 2025-05-13 | 251 |  | 3 Toby Boxes | May
D-HWP902 | Brothers | 2025-05-13 | 933 |  | 5 Toby Boxes / 5 Pits / 8 Splices | May
FB-HOE201 | Power Connect | 2025-05-13 | 385 |  |  | May
FB-HNP133 | Lightspeed | 2025-05-14 | 153 |  |  | May
D-H0221C | BFI | 2025-05-14 |  |  | Vac Breakdown--No Production | May
D-H0222A / D-H0233F | Lightspeed | 2025-05-14 |  |  | Proofing | May
HGP16 / HGP38 | Lightspeed | 2025-05-14 |  |  | Repair Work | May
D-HWP1306 | Lightspeed | 2025-05-14 | 424 |  | 3 Toby Boxes | May
FB-HWP701 | Brothers | 2025-05-14 | 1190 |  | 1 HH | May
FB-HOE201 | Power Connect | 2025-05-14 | 678 |  |  | May
D-H0221C | BFI | 2025-05-15 |  |  | Crew Did Not Work This Location Today | May
D-HNP104 | Longo Underground | 2025-05-15 | 1316 |  | 12 Toby Boxes / 43 Splices | May
D-HNP135 | Lightspeed | 2025-05-15 | 201 |  |  | May
D-HDH57 | Lightspeed | 2025-05-15 | 85 |  | 2 Toby Boxes / 3 Splices | May
D-HDH55 | Has Global | 2025-05-15 | 1342 |  | 8 Toby Boxes / 29 Splices | May
D-HWP1306 | Lightspeed | 2025-05-15 | 497 |  | 4 Toby Boxes | May
BHT-FWP-10 | Brothers | 2025-05-15 | 1580 |  | 1 HH | May
FB-HOE201 | Power Connect | 2025-05-15 | 381 |  |  | May
D-H0221C | BFI | 2025-05-16 | 887 |  | 8 Toby Boxes / 34 Splices | May
D-HNP104 | Longo Underground | 2025-05-16 | 1232 |  | 10 Toby Boxes / 37 Splices | May
D-HNP135 | Lightspeed | 2025-05-16 | 30 |  |  | May
D-HDH55 | HAS Global | 2025-05-16 | 1484 |  | 8 Toby Boxes / 32 Splices | May
D-HDH02 | Lightspeed | 2025-05-16 | 151 |  | 48 Splices | May
D-HWP1306 | Lightspeed | 2025-05-16 |  |  | FDH/Restoration | May
FB-HOE201 | Power Connect | 2025-05-16 |  |  | No Crews Working Today In Market 3 | May
D-H0222B | Lightspeed | 2025-05-19 | 301 |  | 48 Splices | May
D-HDH53 | Longo Underground | 2025-05-19 |  |  | ABF proofing | May
D-HDH55 | HAS Global | 2025-05-19 | 1280 |  | 7 Toby Boxes / 30 Splices | May
D-HNP104 | Longo Underground | 2025-05-19 | 1156 |  | 7 Toby Boxes / 15 Splices / 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
D-HNP123 | Lightspeed | 2025-05-19 | 54 |  | 1 Toby Box / 14 Splices | May
D-HWP1306 | Lightspeed | 2025-05-19 | 286 |  | 3 Toby Boxes | May
BHT-FWP-10 | Brothers | 2025-05-19 | 270 |  | 2 HH | May
FB-HWP801 | Brothers | 2025-05-19 | 644 |  |  | May
FB-HOE201 | Power Connect | 2025-05-19 | 605 |  |  | May
D-HDH55 | HAS Global | 2025-05-20 | 1029 |  | 11 Toby Boxes / 22 Splices | May
D-HNP104 | Longo Underground | 2025-05-20 | 947 |  | 7 Toby Boxes / 22 Splices | May
D-HNP123 | Lightspeed | 2025-05-20 | 101 |  |  | May
D-H0220B | Longo UG | 2025-05-20 |  |  | No Report | May
D-H0222B | Lightspeed | 2025-05-20 | 191 |  | 4 Splices | May
D-H0221C | Lightspeed | 2025-05-20 |  |  | Crew Completed Cross Trenching | May
D-HWP1306 | Lightspeed | 2025-05-20 | 226 |  | 5 Toby Boxes | May
FB-HWP801 | Brothers | 2025-05-20 | 1430 |  | 3 HH | May
D-H0220B | Longo Underground | 2025-05-21 | 999 |  | 8 Toby Boxes / 66 Splices | May
D-HDH57 | Lightspeed | 2025-05-21 | 181 |  |  | May
D-H0221C | Lightspeed | 2025-05-21 |  |  | Crew Did Not Work On This Location Today | May
D-H0222A | Lightspeed | 2025-05-21 |  |  | Did Not Receive A Report | May
D-HWP1306 | Lightspeed | 2025-05-21 |  |  | 1 FDH / 1 Swing Arm / 1 HH / 1 Ground Rod | May
FB-HWP701 | Brothers | 2025-05-21 | 678 | 2850 | 2 HH / 2 Ground Rods / 2,850' 48Ct Fiber Cable / 1,796 Tracer Wire / 1,796 Mule Tape | May
FB-HWP801 | Brothers | 2025-05-21 | 970 |  | 1 HH | May
FB-HOE201 | Power Connect | 2025-05-21 | 600 |  |  | May
D-HOE116 | Power Connect | 2025-05-21 |  |  | Spliced Conduits For Continuity | May
D-DHD52 | Lightspeed | 2025-05-22 | 260 |  |  | May
D-DHD55 | HAS Global | 2025-05-22 |  |  | ABF Proofing / Restoration | May
D-HWP1306 | Lightspeed | 2025-05-22 |  |  | Sponge/Restoration | May
BHT-FWP-10 | Brothers | 2025-05-22 | 948 |  | 1 HH | May
FB-HOE201 | Power Connect | 2025-05-22 | 772 |  |  | May
D-DHD52 | Lightspeed | 2025-05-23 | 129 |  | 1 Toby Box / 13 Splices | May
D-H0220B | Longo Underground | 2025-05-23 | 719 |  | 7 Toby Boxes / 1 Splice | May
D-H0221C | Lightspeed | 2025-05-23 | 236 |  | 3 Toby Boxes | May
D-H0222A | Lightspeed | 2025-05-23 | 175 |  | 72 Splices | May
D-HWP1306 | Lightspeed | 2025-05-23 |  |  | Sponge/Restoration | May
FB-HOE201 | Power Connect | 2025-05-23 |  |  | Crew Did Not Work This Location Today | May
D-HOE116 | Power Connect | 2025-05-23 | 285 |  | 18 Splices | May
D-H0221C | Lightspeed | 2025-05-27 | 224 |  | 1 Toby Box | May
FB-HDH02A | Lightspeed | 2025-05-27 | 100 |  |  | May
D-HWP1306 | Lightspeed | 2025-05-27 |  |  | Sponge/Restoration | May
FB-HWP801 | Brothers | 2025-05-27 | 948 |  | 3 HH / 3 Ground Rod | May
BHT-FWP-10 | Brothers | 2025-05-27 | 954 |  | 1 HH / 1 Ground Rod | May
BHZD-FWP-13-E | Lightspeed | 2025-05-27 |  |  | Drill Breakdown | May
FB-HOE201 | Power Connect | 2025-05-27 | 757 |  |  | May
D-H0221C | Lightspeed | 2025-05-28 | 200 |  | 1 Toby Box / 48 Splices | May
D-HWP1306 | Lightspeed | 2025-05-28 |  |  | Sponge/Restoration | May
BHT-FWP-10 | Brothers | 2025-05-28 | 2783 |  | 9 HH / 9 Ground Rods | May
FB-HOE201 | Power Connect | 2025-05-28 | 610 |  |  | May
D-H0221C | Lightspeed | 2025-05-29 |  |  | Hand Dig / Repair / Proofing / Supervising | May
D-HDH50 \ D-HDH52 | Lightspeed | 2025-05-29 |  |  | Hand Dig / Repair / Proofing / Supervising | May
D-HDH57 \ D-HDH58 | Lightspeed | 2025-05-29 |  |  | Hand Dig / Repair / Proofing / Supervising | May
D-HWP1306 | Lightspeed | 2025-05-29 |  |  | Restoration | May
BHT-FWP-10 | Brothers | 2025-05-29 | 2248 |  | 5 HH / 5 Ground Rods | May
FB-HWP801 | Brothers | 2025-05-29 | 736 |  | 2 HH / 2 Ground Rods | May
FB-HOE201 | Power Connect | 2025-05-29 | 959 |  |  | May
D-HDH50-52 | Lightspeed | 2025-05-30 |  |  | Stingray | May
D-HDH57-60 | Lightspeed | 2025-05-30 |  |  | Stingray | May
D-HNP151 | Longo Underground | 2025-05-30 | 218 |  | 1 Toby Box | May
FB-HWP-701 | Lightspeed | 2025-05-30 |  |  | Restoration | May
FB-HOE201 | Power Connect | 2025-05-30 | 493 |  |  | May
BHT-FWP-09 | Brothers | 2025-06-02 | 800 |  |  | June
BHZD-FWP-13-E | Lightspeed | 2025-06-02 | 275 |  |  | June
FB-HWP801 | Brothers | 2025-06-02 | 1957 |  | 7 HH / 7 Ground Rods | June
FB-HOE201 | Power Connect | 2025-06-02 | 720 |  |  | June
D-HDH18 | Lightspeed | 2025-06-02 | 6 |  | 48 Splices | June
D-HDH02 | Lightspeed | 2025-06-03 |  |  | Repair / ABF Proofing | June
D-HDH50\52 | Lightspeed | 2025-06-03 |  |  | Restoration | June
D-H0220B | Longo Underground | 2025-06-03 | 1483 |  | 12 Toby Boxes / 40 Splices | June
D-HNP110 | Power Connect | 2025-06-03 |  |  | No Production Vehicle Breakdown | June
BHT-FWP-09 | Brothers | 2025-06-03 | 631 |  | 2 HH / 2 Ground Rods | June
BHZD-FWP-13-E | Lightspeed | 2025-06-03 | 280 |  |  | June
FB-HWP701 | Power Connect | 2025-06-03 |  |  | Restoration | June
FB-HOE201 | Power Connect | 2025-06-03 | 948 |  |  | June
D-H0220B | Longo Underground | 2025-06-04 | 83 |  |  | June
D-HNP113 | Longo Underground | 2025-06-04 |  |  | Crew Did Not Work This Location Today Due To Rain | June
BHT-FWP-09 | Brothers | 2025-06-04 | 1401 |  |  | June
BHZD-FWP-13-E | Lightspeed | 2025-06-04 | 310 |  |  | June
D-HWP905 | Brothers | 2025-06-04 | 610 |  | 5 Toby Boxes / 5 Pits / 4 Splices | June
FB-HWP801 | Brothers | 2025-06-04 |  | 8415 | 6,328' Tracer Wire / 12,656' Mule Tape / 3 HH / 6 Ground Rods | June
FB-HOE201 | Power Connect | 2025-06-04 |  |  | Crew Did Not Work This Location Today Due To Rain | June
D-HNP113 | Longo Underground | 2025-06-05 | 341 |  | 4 Toby Boxes / 15 Splices | June
D-HDH52/49/58 | Lightspeed | 2025-06-05 |  |  | Restoration | June
BHZD-FWP-13-E | Lightspeed | 2025-06-05 |  |  | No Production | June
D-HWP905 | Brothers | 2025-06-05 | 2523 |  | 15 Toby Boxes / 19 Pits / 46 Splices | June
D-HWP701 | Lightspeed | 2025-06-05 |  |  | No Report--Will Be Sent In The Morning | June
FB-HOE201 | Power Connect | 2025-06-05 | 1101 |  | 2 HH | June
FB-HOE201 | Power Connect | 2025-06-06 | 437 |  | 1 HH | June
BHT-FWP-09 | Brothers | 2025-06-09 | 1100 |  |  | June
FX4-FWP-13 | Brothers | 2025-06-09 | 115 |  |  | June
225 Granada St | Lightspeed | 2025-06-09 | 155 |  |  | June
BHZD-FWP-13-E | Lightspeed | 2025-06-09 | 263 |  |  | June
FB-HOE201 | Power Connect | 2025-06-09 | 730 |  |  | June
D-HWP905 | Brothers | 2025-06-10 | 1293 |  | 12 Toby Boxes / 7 Pits / 35 Splices / 1 FDH | June
BHZD-FWP-13-E | Lightspeed | 2025-06-10 | 270 |  |  | June
FB-HOE201 | Power Connect | 2025-06-10 | 583 |  |  | June
BHT-FWP-09 | Brothers | 2025-06-11 | 1975 |  | 2 HH / 2 Ground Rods | June
BHT-FWP-10 | Brothers | 2025-06-11 | 370 |  | 2 HH / 2 Ground Rods | June
BHZD-FWP-13-E | Lightspeed | 2025-06-11 |  |  | Crew Did Not Work This Location Today | June
BHT-FWP-09 | Brothers | 2025-06-12 | 1395 |  | 2 HH / 2 Ground Rods | June
FB-HWP701 | Brothers | 2025-06-12 |  |  | Restoration | June
BHZD-FWP-13-E | Lightspeed | 2025-06-12 | 395 |  |  | June
FB-HWP701 | Brothers | 2025-06-13 |  |  | Restoration | June
BHUD-FWP-06 | Lightspeed | 2025-06-13 |  |  | Ground Rods | June
BHZD-FWP-13-E | Lightspeed | 2025-06-13 |  |  | Vaults/ Tie Ins | June
FB-HOE201 | Power Connect | 2025-06-13 |  | 7408 | 6,128 Tracer Wire | June
D-H0220A | Longo Underground | 2025-06-16 | 1394 |  | 9 Toby Boxes | June
BHT-FWP-09 | Brothers | 2025-06-16 | 450 |  | 4 HH | June
BHZD-FWP-13-E | Lightspeed | 2025-06-16 | 280 |  |  | June
BHT-FWP-10 | Brothers | 2025-06-16 |  | 4976 | Pulling Fiber Cable / 4,976 Tracer Wire | June
FB-HOE201 | Power Connect | 2025-06-16 | 465 |  | 1 HH | June
D-H0220A | Longo Underground | 2025-06-17 | 1756 |  | 6 Toby Boxes | June
BHT-FWP-09 | Brothers | 2025-06-17 | 1246 |  | 5 HH / 5 Ground Rods | June
BHZD-FWP-13-E | Lightspeed | 2025-06-17 | 70 |  |  | June
BHT-FWP-08 | Brothers | 2025-06-17 | 1465 |  | 4 HH / 4 Ground Rods | June
BHT-FWP-10 | Brothers | 2025-06-17 |  | 4177 | 4,177 Tracer Wire | June
FB-HOE201 | Power Connect | 2025-06-17 | 218 |  | 1 HH | June
D-H0220A | Longo Underground | 2025-06-18 | 846 |  | 4 Toby Boxes | June
D-HNP135 | Lightspeed | 2025-06-18 | 81 |  |  | June
D-HDH69 | Lightspeed | 2025-06-18 |  |  | Restoration | June
D-H0222B | Lightspeed | 2025-06-18 |  |  | Restoration | June
BHT-FWP-08 | Brothers | 2025-06-18 | 1380 |  | 4 HH / 4 Ground Rods | June
BHZD-FWP-13-E | Lightspeed | 2025-06-18 | 594 |  |  | June
FB-HOE201 | Power Connect | 2025-06-18 | 729 |  |  | June
FB-HOE201 | Power Connect | 2025-06-19 | 464 |  |  | June
BHUD-FOE-02-W | Power Connect | 2025-06-19 | 977 |  | 2 HH | June
D-HNP135 | Lightspeed | 2025-06-20 | 114 |  |  | June
BHZD-FWP-13-E | Lightspeed | 2025-06-20 | 52 |  | 1 HH | June
FB-HWP801 | Brothers | 2025-06-20 |  |  | Restoration | June
FB-HOE201 | Power Connect | 2025-06-20 |  | 1086 | 755 Tracer Wire | June
D-HNP135 | Lightspeed | 2025-06-23 | 237 |  | 4 Toby Boxes / 7 Splices | June
FB-HDH01A-2A | Lightspeed | 2025-06-23 | 65 |  |  | June
FB-HWP175 | Brothers | 2025-06-23 | 924 |  | 1 HH | June
BHZD-FWP-13-E | Lightspeed | 2025-06-23 | 68 |  | 1 HH / 1 Ground Rod | June
BHT-FWP-08 | Brothers | 2025-06-23 | 1269 |  | 1 HH / 1 Ground Rod | June
D-HNP135 | Lightspeed | 2025-06-24 | 322 |  |  | June
D-H0220A | Longo Underground | 2025-06-24 | 1946 |  | 10 Toby Boxes / 1 HH / 1 FDH / 1 Swing Arm / 1 Ground Rod | June
D-HWP801 | Brothers | 2025-06-24 | 1044 |  | 10 Toby Boxes / 9 Daps | June
BHZD-FWP-13-E | Lightspeed | 2025-06-24 | 50 |  | 3 HH / 3 Ground Rods | June
BHT-FWP-08 | Brothers | 2025-06-24 | 1141 |  | 5 HH / 5 Ground Rods | June
FB-HOE201 | Power Connect | 2025-06-24 |  | 883 | 683 Tracer Wire | June
D-HNP135 | Lightspeed | 2025-06-25 | 245 |  | 2 Toby Boxes | June
D-HNP113 | Longo Underground | 2025-06-25 | 649 |  | 10 Toby Boxes / 35 Splices | June
D-HWP801 | Brothers | 2025-06-25 | 1100 |  | 12 Toby Boxes / 6 Daps | June
FB-HWP1376 | Lightspeed | 2025-06-25 | 335 |  |  | June
BHT-FWP-08 | Brothers | 2025-06-25 | 1308 |  | 3 HH / 3 Ground Rods | June
D-HNP135 | Lightspeed | 2025-06-26 | 1091 |  |  | June
D-H0220A | Longo Underground | 2025-06-26 |  |  | ABF Testing | June
D-H0220B | Longo Underground | 2025-06-26 |  |  | ABF Testing | June
D-HWP801 | Brothers | 2025-06-26 | 1050 |  | 6 Toby Boxes / 6 Daps / 2 Vaults / 1 HH / 1 Flower Pot | June
FB-HWP1376 | Lightspeed | 2025-06-26 | 200 |  |  | June
BHT-FWP-08 | Brothers | 2025-06-26 | 1296 |  | 4 HH / 4 Ground Rods | June
FB-HWP175 | Brothers | 2025-06-26 |  |  | Issue With Conduit Placement | June
FB-HOE201 | Power Connect | 2025-06-26 | 112 |  | 1 HH | June
BHUD-FOE-02-W | Power Connect | 2025-06-26 | 676 |  | 1 HH / 1 Ground Rod | June
FB-HOE201 | Raven | 2025-06-26 |  | 6183 | 5,376 Tracer Wire
D-HNP135 | Lightspeed | 2025-06-27 | 303 |  | 2 Toby Boxes | June
D-H0220B | Longo Underground | 2025-06-27 |  |  | ABF Testing | June
FB-HWP175 | Brothers | 2025-06-27 |  | 1605 | 1,605 Tracer Wire | June
BHUD-FOE-02-W | Power Connect | 2025-06-27 | 430 |  |  | June
D-HNP135 | Lightspeed | 2025-06-30 | 360 |  | 6 Toby Boxes / 22 Splices | June
FB-HWP175 | Lightspeed | 2025-06-30 | 120 | 120 | 1,725 Tracer Wire | June
BHUD-FOE-02-W | Power Connect | 2025-06-30 | 885 |  | 2 HH | June
FB-HWP1376 | Lightspeed | 2025-07-01 | 120 |  |  | July
FB-HWP801 | Brothers | 2025-07-01 |  | 53 | 53 Tracer Wire / 106 Mule Tape | July
BHT-FWP-08 | Brothers | 2025-07-01 |  | 10059 | 7,859 Tracer Wire / 15,718 Mule Tape
BHUD-FOE-02-W | Power Connect | 2025-07-01 | 478 |  |  | July
FB-HOE201 | Power Connect | 2025-07-01 | 282 |  |  | July
D-HNP144 | Lightspeed | 2025-07-02 |  |  | No Clear Location To Drill On--Already Completed By FCA | July
FB-HWP1376 | Lightspeed | 2025-07-02 | 71 |  | 1 HH | July
D-HWP821 | Brothers | 2025-07-02 | 355 |  | 6 Toby Boxes | July
BHT-FWP-08 | Brothers | 2025-07-02 |  |  | Restoration | July
BHUD-FOE-02-W | Power Connect | 2025-07-02 | 490 |  | 1 HH | July
FB-HWP1376 | Lightspeed | 2025-07-03 |  |  | Restoration | July
BHUD-FOE-02-W | Power Connect | 2025-07-03 | 372 |  | 1 HH | July
BHUD-FOE-02-W | Raven | 2025-07-03 |  | 5776 | 5,276 Tracer Wire
|  | 2025-07-04 | 0 |  |  | July
FB-HWP902 | Lightspeed | 2025-07-07 |  |  | Pot Holing | July
D-HWP821 | Brothers | 2025-07-07 | 846 |  |  | July
BHUD-FWP-13-W | Brothers | 2025-07-07 | 1644 |  |  | July
BHUD-FOE-02-W | Raven | 2025-07-07 |  |  | Pulling Tracer Wire | July
FB-HWP902 | Lightspeed | 2025-07-08 | 465 |  |  | July
D-HWP821 | Brothers | 2025-07-08 | 827 |  | 18 Toby Boxes / 1 FDH / 1 Flower Pot | July
BHUD-FWP-13-W | Brothers | 2025-07-08 | 60 |  | 1 HH / 1 Ground Rod | July
FB-HWP902 | Lightspeed | 2025-07-09 | 321 |  |  | July
D-HOE206 | Power Connect | 2025-07-09 |  |  |  | July
D-HNP117 | Lightspeed | 2025-07-10 | 400 |  |  | July
FB-HWP902 | Lightspeed | 2025-07-10 |  |  | 2 HH/ 2 Ground Rod / Restoration | July
FB-HWP902 | Lightspeed | 2025-07-11 |  | 786 |  | July
BHZD-FOE-03-W | Raven | 2025-07-11 | 198 |  |  | July
FB-HWP902 | Lightspeed | 2025-07-14 |  |  | Restoration | July
BHZD-FOE-03-W | Raven | 2025-07-14 | 862 |  |  | July
D-HNP117 | Lightspeed | 2025-07-15 | 203 |  |  | July
BHZD-FWP-13-E | Lightspeed | 2025-07-15 |  |  | No Production--Issues In The Field | July
D-HWP822 | Brothers | 2025-07-15 | 1210 |  | 10 Toby Boxes / 4 Flower Pots | July
D-HOE215 | Raven | 2025-07-15 | 403 |  |  | July
D-HNP117 | Lightspeed | 2025-07-16 | 170 |  |  | July
BHZD-FWP-13-E | Lightspeed | 2025-07-16 | 280 |  |  | July
D-HWP822 | Brothers | 2025-07-16 | 397 |  | 3 Toby Boxes / 1 Flower Pot | July
FB-HWP1302 | Lightspeed | 2025-07-16 | 90 |  |  | July
D-HWP814 | Brothers | 2025-07-16 | 426 |  | 2 Toby Boxes | July
D-HOE215 | Raven | 2025-07-16 | 39 |  |  | July
BHZD-FWP-13-E | Lightspeed | 2025-07-17 | 1972 |  |  | July
D-HWP814 | Brothers | 2025-07-17 | 583 |  | 5 Toby Boxes | July
D-HNP117 | Lightspeed | 2025-07-17 | 106 |  |  | July
FX4-FML-05 | Lightspeed | 2025-07-18 | 47 |  |  | July
BHZD-FWP-13-E | Lightspeed | 2025-07-18 |  |  | Restoration / 1 HH | July
D-HNP117 | Lightspeed | 2025-07-21 |  |  | No Production--Water Line Hit | July
BHZD-FWP-13-E | Lightspeed | 2025-07-21 | 551 |  |  | July
BHZD-FWP-13-E | Longo Underground | 2025-07-21 | 385 |  |  | July
D-HWP812 | Brothers | 2025-07-21 | 1070 |  | 9 Toby Boxes | July
D-HWP814 | Brothers | 2025-07-21 | 1843 |  | 13 Toby Boxes / 1 Flower Pot | July
D-HOE215 | Raven | 2025-07-21 |  |  | Drill Breakdown--No Production | July
D-HNP117 | Lightspeed | 2025-07-22 |  |  | No Production--Drill Breakdown | July
D-HWP812 | Brothers | 2025-07-22 | 1224 |  | 12 Toby Boxes / 4 Flower Pots | July
D-HWP814 | Brothers | 2025-07-22 | 1714 |  | 12 Toby Boxes | July
BHZD-FWP-13-E | Longo Underground | 2025-07-22 | 300 |  |  | July
BHZD-FWP-13-E | HAS Global | 2025-07-22 | 1107 |  |  | July
BHZD-FWP-13-E | Lightspeed | 2025-07-22 | 316 |  |  | July
D-HOE215 | Raven | 2025-07-22 | 318 |  |  | July
BHUD-FOE-03-W | Raven | 2025-07-22 | 605 |  |  | July
D-HNP117 | Lightspeed | 2025-07-23 | 272 |  | 3 Toby Boxes / 1 Dap | July
BHZD-FWP-13-E | Lightspeed | 2025-07-23 | 130 |  | 2 HH | July
D-HWP812 | Brothers | 2025-07-23 | 235 |  | 5 Toby Boxes / 4 Daps | July
D-HWP814 | Brothers | 2025-07-23 | 678 |  | 8 Toby Boxes / 11 Daps / 41 Splices | July
BHUD-FWP-13-W | Longo Underground | 2025-07-23 | 579 |  |  | July
D-HWP815 | Brothers | 2025-07-23 | 363 |  | 4 Toby Boxes / 2 Daps | July
BHT-FWP-09 | Brothers | 2025-07-23 | 853 |  | 1 HH | July
BHZD-FOE-03-W | Raven | 2025-07-23 | 461 |  |  | July
D-HNP117 | Lightspeed | 2025-07-24 | 79 |  | 1 Dap / 4 Splices | July
BHZD-FWP-13-E | Lightspeed | 2025-07-24 | 420 |  |  | July
FB-HWP804 | Telecom | 2025-07-24 |  |  | Potholed Locations | July
D-HWP815 | Brothers | 2025-07-24 | 1077 |  | 7 Toby Boes / 1 HH / 3 Daps / 1 Ground Rod | July
BHUD-FWP-13-W | Longo Underground | 2025-07-24 | 619 |  | 6 HH / 6 Ground Rods | July
BHZD-FWP-13-E | HAS Global | 2025-07-24 |  |  | 5 HH | July
BHT-FWP-09 | Brothers | 2025-07-24 | 1279 |  | 1 HH | July
BHZD-FOE-03-W | Raven | 2025-07-24 | 880 |  |  | July
D-HOE206 | Power Connect | 2025-07-24 | 868 |  | 7 Toby Boxes / 3 Daps | July
D-HNP117 | Lightspeed | 2025-07-25 |  |  | Restoration | July
BHZD-FWP-13-E | Lightspeed | 2025-07-25 |  |  | HHs / Tie ins | July
D-HWP814 | Brothers | 2025-07-25 |  |  | FDH / Sponging | July
D-HWP812 | Brothers | 2025-07-25 |  |  | FDH / Sponging | July
D-HWP822 | Brothers | 2025-07-25 |  |  | FDH / Sponging | July
D-HWP821 | Lightspeed | 2025-07-25 |  |  | Blowing Stingray | July
BHZD-FOE-03-W | Raven | 2025-07-25 | 585 |  | 2 HH | July
BHZD-FWP-13-E | Lightspeed | 2025-07-28 | 420 |  | 1 HH | July
BHT-FWP-09 | Brothers | 2025-07-28 | 817 |  |  | July
D-HWP815 | Brothers | 2025-07-28 | 1430 |  | 9 Toby Boxes / 2 Flower Pots / 8 Daps / 59 Splices | July
FB-HWP804 | Lightspeed | 2025-07-28 |  |  | Drill Breakdown--No Production | July
BHUD-FWP-13-W | Longo Underground | 2025-07-28 | 1181 |  |  | July
BHZD-FOE-03-W | Raven | 2025-07-28 | 345 |  |  | July
BHUD-FWP-13-W | Longo Underground | 2025-07-29 | 1933 |  |  | July
BHT-FWP-09 | Brothers | 2025-07-29 |  | 5590 | 5,590 Tracer Wire | July
D-HWP815 | Brothers | 2025-07-29 | 1004 |  | 9 Toby Boxes / 2 Flower Pots / 9 Daps / 130 Splices / 1 HH / 1 FDH / 1 Ground Rod | July
FB-HWP804 | Lightspeed | 2025-07-29 | 581 | 1200 | 1,200 Tracer Wire | July
BHUD-FWP-13-W | Longo Underground | 2025-07-30 | 1951 |  |  | July
BHUD-FWP-13-W | Brothers | 2025-07-30 | 902 |  |  | July
BHT-FWP-09 | Brothers | 2025-07-30 | 1385 |  | 1 HH | July
D-HWP814 | Lightspeed | 2025-07-30 |  | 847 | 847 Tracer Wire / 1,694 Mule Tape | July
BHZD-FWP-13-E | Kettle 1 | 2025-07-30 |  | 6067 |  | July
BHT-FOE-03 | Raven | 2025-07-30 | 314 |  |  | July
D-H0223C | Lightspeed | 2025-07-31 |  |  | Drill Breakdown | July
BHUD-FWP-13-W | Longo Underground | 2025-07-31 | 725 |  |  | July
BHUD-FWP-13-W | Brothers | 2025-07-31 | 862 |  |  | July
BHZD-FWP-13-E | Kettle 1 | 2025-07-31 |  | 2691 |  | July
FB-HOE301 | Raven | 2025-07-31 | 2390 |  |  | July
D-H0223C | Ligthspeed | 2025-08-01 | 318 |  | Repair--1 Toby Box / 2 Splices | August
D-H0223A | Ligthspeed | 2025-08-01 | 183 |  | Repair--3 Toby Boxes / 7 Splices | August
BHUD-FWP-13-W | Kettle 1 | 2025-08-01 |  |  | 14 Hand Holes / 14 Ground Rods | August
FB-HOE301 | Raven | 2025-08-01 | 1377 |  |  | August
BHUD-FWP-13-W | Kettle 1 | 2025-08-04 |  | 13125 |  | August
FB-HWP482 | Brothers | 2025-08-04 | 918 |  |  | August
BHZD-FWP-11-W | Brothers | 2025-08-05 | 2675 |  |  | August
FB-HOE301 | Raven | 2025-08-05 | 190 |  | 1 HH | August
D-HNP117 | Lightspeed | 2025-08-06 |  |  | 1 HH | August
BHZD-FWP-11-W | Brothers | 2025-08-06 | 1964 |  |  | August
FB-HOE301 | Raven | 2025-08-06 | 840 |  |  | August
BHT-FOE-03 | Raven | 2025-08-06 |  |  | No Production--Crew Did Not Work This Location Today | August
BHZD-FWP-11-W | Brothers | 2025-08-07 | 377 |  | 9 HH / 9 Ground Rods | August
BHZD-FWP-11-W | Kattle One | 2025-08-07 |  | 5289 | 5,289 Tracer Wire | August
FB-HWP775 | Brothers | 2025-08-07 | 674 |  |  | August
FB-HOE301 | Raven | 2025-08-07 | 531 |  |  | August
D-HNP117 | Lightspeed | 2025-08-08 |  |  | No Production--Water Line Hit | August
BHZD-FWP-11-W | Brothers | 2025-08-08 |  |  | Restoration | August
FB-HOE301 | Raven | 2025-08-08 | 718 |  |  | August
D-HNP117 | Lightspeed | 2025-08-11 | 376 |  | 1 Toby Box | August
FB-HWP482 | Brothers | 2025-08-11 | 1175 |  |  | August
FB-HWP802 | Lightspeed | 2025-08-11 | 288 |  |  | August
FB-HOE301 | Raven | 2025-08-11 | 571 |  |  | August
D-HNP117 | Lightspeed | 2025-08-12 | 35 |  |  | August
FB-HWP482 | Brothers | 2025-08-12 | 1154 |  |  | August
FB-HWP802 | Lightspeed | 2025-08-12 | 380 |  |  | August
FB-HWP775 | Brothers | 2025-08-12 | 111 |  | 3 HH / 3 Ground Rods | August
D-HOE215 | Raven | 2025-08-12 | 319 |  |  | August
FB-HOE301 | Raven | 2025-08-12 | 1293 |  |  | August
12 Oaks MHP | Brothers | 2025-08-12 | 406 |  |  | August
D-HNP117 | Lightspeed | 2025-08-13 | 48 |  | 1 Dap / 4 Splices | August
FB-HWP482 | Brothers | 2025-08-13 | 428 |  | 2 HH | August
FB-HWP802 | Lightspeed | 2025-08-13 | 229 |  | 1 HH | August
12 Oaks MHP | Brothers | 2025-08-13 | 1031 |  | 14 Toby Boxes / 1 HH / 1 Ground Rod | August
FB-HWP775 | Brothers | 2025-08-13 | 12 |  | 1 HH / 1 Ground Rod | August
FB-HOE301 | Raven | 2025-08-13 | 540 |  |  | August
D-HNP117 | Lightspeed | 2025-08-14 | 144 |  |  | August
Skyview MHP | Brothers | 2025-08-14 |  |  | Crew Did Not Work This Location Today | August
FB-HWP802 | Lightspeed | 2025-08-14 | 163 |  |  | August
FB-HOE301 | Raven | 2025-08-14 | 554 |  |  | August
FB-HLR201 | Lightspeed | 2025-08-14 |  |  | No Production | August
D-HNP117 | Lightspeed | 2025-08-15 | 64 |  |  | August
FB-HWP482 | Kattle One | 2025-08-15 |  | 1243 | 993 Tracer Wire / 1,986 Mule Tape / 4 HH / 4 Ground Rods | August
FB-HWP802 | Lightspeed | 2025-08-15 |  | 1060 | 1,060 Tracer Wire / 2 HH / 2 Ground Rods | August
FB-HWP775 | Kattle One | 2025-08-15 |  | 1297 | 797 Tracer Wire / 1,594 Mule Tape | August
FB-HOE301 | Raven | 2025-08-15 | 89 |  |  | August
FB-HLR201 | Lightspeed | 2025-08-15 | 391 |  |  | August
D-HNP117 | Lightspeed | 2025-08-18 | 141 |  |  | August
FB-HWP482 | Kattle One | 2025-08-18 |  | 2679 | 2,379 Tracer Wire / 4,658 Mule Tape | August
FB-HWP1376 | Lightspeed | 2025-08-18 | 343 |  |  | August
FB-HWP775 | Kattle One | 2025-08-18 |  | 2145 | 1,757 Tracer Wire | August
FB-HWP776 | Brothers | 2025-08-18 | 1109 |  | 6 HH / Ground Rods | August
FB-HOE301 | Raven | 2025-08-18 | 377 |  |  | August
FB-HLR201 | Lightspeed | 2025-08-18 | 396 |  |  | August
D-HNP111 | Lightspeed | 2025-08-19 | 205 |  |  | August
Skyview | Brothers | 2025-08-19 | 1456 |  |  | August
FB-HWP1376 | Lightspeed | 2025-08-19 | 416 |  |  | August
D-HWP803 | Brothers | 2025-08-19 | 1460 |  | 6 Daps | August
FB-HOE301 | Raven | 2025-08-19 | 408 |  |  | August
D-HOE206 | Lightspeed | 2025-08-19 |  |  | No Production--Crew Potholed | August
BHT-FOE-03 | Raven | 2025-08-19 | 430 |  |  | August
D-HNP117 | Lightspeed | 2025-08-20 | 181 |  |  | August
D-HNP113 | Longo Underground | 2025-08-20 |  |  | No Production--Water Line Hit | August
Skyview | Brothers | 2025-08-20 | 1420 |  |  | August
FB-HWP1376 | Lightspeed | 2025-08-20 | 216 |  |  | August
D-HWP803 | Brothers | 2025-08-20 | 1428 |  | 1 HH / 1 Ground Rod | August
FB-HOE301 | Raven | 2025-08-20 | 607 |  | 11 HH | August
D-HOE206 | Lightspeed | 2025-08-20 | 499 |  |  | August
D-HNP117 | Lightspeed | 2025-08-21 | 82 |  |  | August
D-HNP113 | Longo Underground | 2025-08-21 |  |  | No Production | August
Skyview | Brothers | 2025-08-21 | 1170 |  |  | August
FB-HWP1376 | Lightspeed | 2025-08-21 |  |  | No Production | August
D-HWP803 | Brothers | 2025-08-21 | 1654 |  |  | August
FB-HWP776 | Kattle One | 2025-08-21 |  | 1109 | 1,109 Tracer Wire | August
FB-HOE301 | Raven | 2025-08-21 | 1022 |  |  | August
D-HOE206 | Lightspeed | 2025-08-21 | 231 |  |  | August
D-HNP117 | Lightspeed | 2025-08-22 | 96 |  |  | August
D-HNP108 | Longo Underground | 2025-08-22 | 878 |  | 2 Toby Boxes / 16 Splices | August
Skyview | Brothers | 2025-08-22 | 1081 |  |  | August
FB-HWP1376 | Lightspeed | 2025-08-22 |  | 2001 | 1,701 Tracer Wire | August
FB-HOE301 | Raven | 2025-08-22 |  | 6090 | 8,871 Tracer Wire | August
D-HOE206 | Lightspeed | 2025-08-22 | 316 |  |  | August
D-HNP117 | Lightspeed | 2025-08-25 | 20 |  |  | August
D-HNP108 | Longo Underground | 2025-08-25 | 715 |  |  | August
Skyview | Brothers | 2025-08-25 | 809 |  |  | August
FB-HWP1375 | Lightspeed | 2025-08-25 |  |  | No Production Due To Rain | August
D-HWP805 | Brothers | 2025-08-25 | 735 |  | 7 Toby Boxes / 1 Dap | August
FB-HOE301 | Raven | 2025-08-25 | 639 |  |  | August
D-HOE206 | Lightspeed | 2025-08-25 | 503 |  |  | August
D-HNP117 | Lightspeed | 2025-08-26 |  |  | No Production | August
D-HNP113 | Longo Underground | 2025-08-26 | 1009 |  | 8 Toby Boxes / 2 Daps | August
Skyview | Brothers | 2025-08-26 | 533 |  |  | August
FB-HWP1375 | Lightspeed | 2025-08-26 | 260 |  |  | August
FB-HWP1310 | Lightspeed | 2025-08-26 | 390 |  |  | August
D-HWP826 | Brothers | 2025-08-26 | 558 |  | 7 Toby Boxes | August
D-HWP824 | Brothers | 2025-08-26 | 1224 |  | 15 Toby Boxes / 11 Daps | August
D-HOE206 | Lightspeed | 2025-08-26 | 295 |  |  | August
BHZD-FOE-03-W | Raven | 2025-08-26 |  |  | Drill Breakdown | August
D-HWP825 | Longo Underground | 2025-08-27 | 1017 |  | 5 Toby Boxes / 8 Daps | August
FB-HWP1375 | Lightspeed | 2025-08-27 |  |  | No Production | August
FB-HWP375 | Lightspeed | 2025-08-27 | 130 | 130 | 130 Tracer Wire / 1 HH / 1 Ground Rod | August
D-HWP826 | Brothers | 2025-08-27 | 1248 |  | 10 Toby Boxes / 8 Daps | August
D-HWP824 | Brothers | 2025-08-27 | 967 |  | 8 Toby Boxes / 8 Daps / 1 Flower Pot | August
FB-HLR201 | Lightspeed | 2025-08-27 | 400 |  |  | August
D-HOE215 | Raven | 2025-08-27 | 358 |  | 2 Toby Boxes / 2 Daps | August
BHZD-FOE-03-W | Raven | 2025-08-27 | 1241 |  |  | August
D-HNP117 | Lightspeed | 2025-08-28 | 250 |  |  | August
FB-HWP1375 | Lightspeed | 2025-08-28 | 315 | 575 | 575 Tracer Wire | August
D-HWP805 | Brothers | 2025-08-28 | 1453 |  | 14 Toby Boxes / 11 Daps | August
D-HWP826 | Brothers | 2025-08-28 | 1260 |  | 7 Toby Box / 6 Daps | August
FB-HOE301 | Raven | 2025-08-28 |  |  | 2 HH | August
FB-HLR201 | Lightspeed | 2025-08-28 | 320 |  |  | August
D-HOE215 | Raven | 2025-08-28 |  |  | No Production | August
BHZD-FOE-03-W | Raven | 2025-08-28 |  |  | No Production | August
D-HNP117 | Lightspeed | 2025-08-29 | 177 |  | 1 Toby Box / 1 Dap | August
D-HNP108 | Longo Underground | 2025-08-29 | 1131 |  |  | August
BHZD-FOE-03-W | Raven | 2025-08-29 |  |  | 1 HH | August
D-HOE206 | Lightspeed | 2025-08-29 | 6 |  | 3 Toby Boxes / 2 Daps / 20 Splices | August
FB-HOE301 | Raven | 2025-08-29 |  | 8378 | 3,086 Tracer Wire | August
D-HWP1310 | Lightspeed | 2025-08-29 |  | 390 | 390 Tracer Wire | Septemeber
|  | 2025-09-01 |  |  |  | Septemeber
D-HNP117 | Lightspeed | 2025-09-02 |  |  | Swing Arm / Ground Rod | Septemeber
D-HWP826 | Brothers | 2025-09-02 | 977 |  | 8 Toby Boxes / 6 Daps | Septemeber
D-HOE206 | Lightspeed | 2025-09-02 | 15 |  | 3 Toby Boxes / 3 Daps / 19 Splices | Septemeber
BHZD-FOE-03-W | Raven | 2025-09-02 |  | 7962 | 6,880 Tracer Wire | Septemeber
D-HNP117 | Lightspeed | 2025-09-03 |  |  | Restoration | Septemeber
D-HDH82 | Lightspeed | 2025-09-03 |  |  | FDH Move | Septemeber
D-HWP1310 | Brothers | 2025-09-03 | 1491 |  | 11 Toby Boxes / 9 Daps | Septemeber
D-HWP805 | Brothers | 2025-09-03 | 2472 | 730 | 27 Toby Boxes / 20 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP825 | Longo Underground | 2025-09-03 | 2819 |  | 25 Toby Boxes / 15 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP812 | Lightspeed | 2025-09-03 | 130 |  | 1 Dap | Septemeber
D-HOE206 | Lightspeed | 2025-09-03 | 65 |  | 1 Toby Box / 1 Dap / 2 Splices | Septemeber
BHZD-FOE-03-W | Raven | 2025-09-03 |  |  | Pulling Tracer Wire | Septemeber
D-HNP117 | Lightspeed | 2025-09-04 |  |  | Proofing | Septemeber
HGP-03 | Lightspeed | 2025-09-04 |  |  | Damage Repair | Septemeber
D-HWP1310 | Brothers | 2025-09-04 | 1549 |  | 12 Toby Boxes / 10 Daps | Septemeber
D-HWP802 | Brothers | 2025-09-04 | 903 |  | 6 Toby Boxes / 4 Daps | Septemeber
D-HWP812 | Lightspeed | 2025-09-04 |  | 800 |  | Septemeber
D-HOE215 | Lightspeed | 2025-09-04 | 99 |  | 2 Toby Boxes / 1 Dap / 3 Splices | Septemeber
D-HOE206 | Lightspeed | 2025-09-04 | 6 |  | 1 Dap / 12 Splices | Septemeber
D-HNP135 | Lightspeed | 2025-09-05 | 125 |  |  | Septemeber
FB-HOE375 | Lightspeed | 2025-09-05 | 285 |  |  | Septemeber
D-HWP803 | Brothers | 2025-09-05 | 128 | 2000 | 34 Toby Boxes / 15 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP825 | Lightspeed | 2025-09-05 |  | 2062 |  | Septemeber
D-HWP802 | Longo Underground | 2025-09-08 | 254 |  | 4 Toby Boxes / 3 Daps | Septemeber
Skyview | Brothers | 2025-09-08 | 2498 |  |  | Septemeber
D-HWP1310 | Brothers | 2025-09-08 | 918 |  | 11 Toby Boxes / 4 Daps | Septemeber
D-HWP802 | Longo Underground | 2025-09-09 | 1686 |  | 7 Toby Boxes / 4 Daps | Septemeber
Skyview | Brothers | 2025-09-09 | 1192 |  | 120 Toby Boxes / 103 Daps | Septemeber
FB-HWP975 | Brothers | 2025-09-09 | 329 |  |  | Septemeber
D-HNP135 | Lightspeed | 2025-09-10 | 299 |  |  | Septemeber
D-HWP802 | Longo Underground | 2025-09-10 | 611 |  | 9 Toby Boxes / 5 Daps | Septemeber
Skyview | Brothers | 2025-09-10 | 1925 |  |  | Septemeber
FB-HWP975 | Lightspeed | 2025-09-10 | 333 |  |  | Septemeber
D-HWP827 | Brothers | 2025-09-10 | 740 |  | 4 Toby Boxes / 1 Dap | Septemeber
BHT-FLX-01 | Baseline | 2025-09-10 | 307 |  |  | Septemeber
FB-HOE375 | Lightspeed | 2025-09-10 |  |  | No Production | Septemeber
D-HNP135 | Lightspeed | 2025-09-11 | 302 |  |  | Septemeber
D-HNP113 | Longo Underground | 2025-09-11 | 279 |  | 5 Toby Boxes / 5 Splices | Septemeber
D-HNP108 | Longo Underground | 2025-09-11 | 443 |  | 3 Toby Boxes / 4 Splices | Septemeber
FB-HWP975 | Lightspeed | 2025-09-11 |  | 662 | 3 HH | Septemeber
FB-HWP1075 | Lightspeed | 2025-09-11 | 267 |  |  | Septemeber
BHT-FLX-01 | Baseline | 2025-09-11 | 920 |  |  | Septemeber
FB-HOE375 | Lightspeed | 2025-09-11 | 82 |  | 2 HH / 2 Ground Rods | Septemeber
D-HNP135 | Lightspeed | 2025-09-12 | 209 |  | 1 Toby Box | Septemeber
FB-HWP975 | Lightspeed | 2025-09-12 |  |  | Restoration | Septemeber
BHT-FLX-01 | Baseline | 2025-09-12 | 610 |  |  | Septemeber
FB-HOE375 | Lightspeed | 2025-09-12 |  |  | Restoration | Septemeber
D-HNP135 | Lightspeed | 2025-09-15 | 42 |  |  | Septemeber
D-HWP827 | Brothers | 2025-09-15 | 1238 |  |  | Septemeber
FB-HWP1075 | Lightspeed | 2025-09-15 | 711 |  |  | Septemeber
BHT-FLX-01 | Baseline | 2025-09-15 | 829 |  | 1 HH / 1 Ground Rod | Septemeber
D-HOE206 | Lightspeed | 2025-09-15 |  |  | ABF Testing | Septemeber
D-HNP135 | Lightspeed | 2025-09-16 | 219 |  | 1 Toby Box / 2 Daps / 6 Splices | Septemeber
D-HWP827 | Brothers | 2025-09-16 | 1531 |  |  | Septemeber
FB-HWP1075 | Lightspeed | 2025-09-16 |  |  | 2 HH / 2 Ground Rods | Septemeber
D-HWP809 | Brothers | 2025-09-16 | 1808 |  |  | Septemeber
BHT-FLX-01 | Baseline | 2025-09-16 |  |  | 1 HH | Septemeber
D-HOE215 | Lightspeed | 2025-09-16 |  |  | 1 FDH / 1 Swing Arm | Septemeber
D-HOE206 | Lightspeed | 2025-09-16 |  |  | 1 FDH / 1 Swing Arm | Septemeber
D-HOE302 | North Path | 2025-09-16 | 251 |  |  | Septemeber
D-HGP22 (Repair) | Lightspeed | 2025-09-17 | 75 |  |  | Septemeber
D-HWP827 | Brothers | 2025-09-17 | 1250 |  | 11 Toby Boxes / 5 Daps | Septemeber
D-HWP802 | Longo Underground | 2025-09-17 | 250 |  | 3 Toby Boxes / 2 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP809 | Brothers | 2025-09-17 |  |  | 18 Toby Boxes / 13 Daps / 2 Flower Pots | Septemeber
BHT-FLX-01 | Baseline | 2025-09-17 | 863 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-17 | 253 |  |  | Septemeber
D-HOE215 | Lightspeed | 2025-09-17 |  |  | ABF Testing | Septemeber
BHZD-FOE-03-W | Lightspeed | 2025-09-17 | 139 |  |  | Septemeber
FB-HNP133 | Lightspeed | 2025-09-18 | 97 |  | 1 Dap / 2 Splices | Septemeber
D-HNP135 | Lightspeed | 2025-09-18 |  |  | 1 HH / 1 Swing Arm | Septemeber
D-HWP827 | Brothers | 2025-09-18 | 361 |  | 1 Toby Box / 3 Daps / 1 Flower Pot | Septemeber
D-HWP809 | Brothers | 2025-09-18 | 1204 |  | 15 Toby Boxes / 11 Daps / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP811 | Brothers | 2025-09-18 | 562 |  |  | Septemeber
D-HWP823 | Brothers | 2025-09-18 | 754 |  | 6 Toby Boxes / 1 Flower Pot / 6 Daps / 41 Splices | Septemeber
BHT-FLX-01 | Baseline | 2025-09-18 | 499 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-18 | 1076 |  |  | Septemeber
D-HOE215 | Lightspeed | 2025-09-18 |  |  | ABF Testing | Septemeber
D-HNP135 | Lightspeed | 2025-09-19 | 70 |  |  | Septemeber
FB-HWP1075 | Lightspeed | 2025-09-19 |  | 1210 | 1,010 Tracer Wire | Septemeber
BHT-FLX-01 | Baseline | 2025-09-19 | 475 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-19 |  |  | No Production | Septemeber
Skyview | Brothers | 2025-09-19 |  |  | 3 FDH / 3 HH / 3 Swing Arms / 3 Ground Rods | Septemeber
FB-HNP104 | Lightspeed | 2025-09-22 | 153 |  |  | Septemeber
OakHill MHP | H&H Underground | 2025-09-22 | 329 |  |  | Septemeber
D-HWP811 | Brothers | 2025-09-22 | 978 |  | 9 Toby Boxes / 6 Daps | Septemeber
D-HWP823 | Brothers | 2025-09-22 | 1285 |  | 13 Toby Boxes / 2 Flower Pots / 8 Daps / 79 Splices / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
FB-HWP480 | Lightspeed | 2025-09-22 | 335 |  | 1 HH / 1 Ground Rod | Septemeber
BHT-FLX-01 | Baseline | 2025-09-22 | 839 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-22 |  |  | No Production--Locate Issue | Septemeber
BHZD-FOE-03-W | Lightspeed In-House | 2025-09-22 | 60 | 1005 | 805 Tracer Wire / 1 HH / 1 Ground Rod | Septemeber
BHU-FAL-01-E | HAS GLOBAL | 2025-09-22 | 415 |  |  | Septemeber
D-HNP135 | Lightspeed | 2025-09-23 | 224 |  | 1 Toby Box / 1 Dap | Septemeber
OakHill MHP | H&H Underground | 2025-09-23 | 427 |  |  | Septemeber
D-HWP811 | Brothers | 2025-09-23 | 675 |  |  | Septemeber
D-HWP816 | Brothers | 2025-09-23 | 1231 |  | 8 Toby Boxes / 3 Daps / 51 Splices | Septemeber
FB-HWP480 | Lightspeed | 2025-09-23 |  | 335 | 335 Tracer Wire / 1 HH | Septemeber
BHT-FLX-01 | Baseline | 2025-09-23 |  |  | No Production--Drill Issue | Septemeber
D-HOE302 | North Path | 2025-09-23 | 120 |  |  | Septemeber
D-HOE215 | Lightspeed In-House | 2025-09-23 |  |  | ABF Testing | Septemeber
BHU-FAL-01-E | HAS Global | 2025-09-23 | 291 |  |  | Septemeber
FB-HNP104 | Lightspeed | 2025-09-24 | 260 |  |  | Septemeber
OakHill MHP | H&H Underground | 2025-09-24 | 537 |  |  | Septemeber
D-HWP818 | Brothers | 2025-09-24 | 1205 |  | 11 Toby Boxes / 1 Flower Pot / 7 Daps | Septemeber
D-HWP816 | Brothers | 2025-09-24 | 1538 |  | 13 Toby Boxes / 10 Daps / 67 Splices | Septemeber
BHU-FWP-08-E | Lightspeed | 2025-09-24 | 240 |  |  | Septemeber
D-HWP827 | Brothers | 2025-09-24 |  |  | 3 Toby Boxes / 1 Flower Pot / 4 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
D-HWP811 | Brothers | 2025-09-24 | 170 |  | 18 Toby Boxes / 1 Flower Pot / 15 Daps / 1 FDH / 1 HH / 1 Swing Arm / 1 Ground Rod | Septemeber
BHT-FLX-01 | Baseline | 2025-09-24 | 616 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-24 | 190 |  |  | Septemeber
FB-HLR201 | Lightspeed | 2025-09-24 | 362 |  |  | Septemeber
BHU-FAL-01-E | HAS Global | 2025-09-24 |  |  | Crew Did Not Show Up Today | Septemeber
BHT-FOE-03 | North Path | 2025-09-24 | 406 |  |  | Septemeber
D-HWP827 | Lightspeed | 2025-09-24 |  | 1837 | 12 CT Stingray | Septemeber
D-HWP809 | Lightspeed | 2025-09-24 |  | 731 | 12 CT Stingray | Septemeber
D-HWP811 | Lightspeed | 2025-09-24 |  | 178 | 12 CT Stingray | Septemeber
Skyview Estates | Lightspeed | 2025-09-24 |  | 2600 | 12 CT Stingray | Septemeber
FB-HNP111 | Lightspeed | 2025-09-25 | 175 |  |  | Septemeber
OakHill MHP | H&H Underground | 2025-09-25 | 646 |  | 18 Toby Boxes | Septemeber
D-HWP818 | Brothers | 2025-09-25 | 1000 |  |  | Septemeber
D-HWP816 | Brothers | 2025-09-25 | 1377 |  | 11 Toby Boxes / 8 Daps / 61 Splices | Septemeber
BHU-FWP-08-E | Lightspeed | 2025-09-25 | 504 |  |  | Septemeber
Mas Verde | Juan Garcia Underground | 2025-09-25 |  |  | No Production--Equipment Issues | Septemeber
BHT-FLX-01 | Baseline | 2025-09-25 | 969 |  |  | Septemeber
D-HOE302 | North Path | 2025-09-25 |  |  | Restoration | Septemeber
FB-HLR201 | Lightspeed | 2025-09-25 | 399 |  |  | Septemeber
BHU-FAL-01-E | HAS Global | 2025-09-25 |  |  | No Production--Truck Breakdown | Septemeber
OakHill MHP | H&H Underground | 2025-09-26 | 793 |  | 6 Toby Boxes | Septemeber
Mas Verde | Juan Garcia UnderGround | 2025-09-26 | 3471 |  |  | Septemeber
Mas Verde | Baseline | 2025-09-26 | 300 |  |  | Septemeber
Mas Verde | Patriot Underground | 2025-09-26 | 364 |  |  | Septemeber
BHT-FLX-01 | Baseline | 2025-09-26 | 552 |  |  | Septemeber
D-HOE306 | North Path | 2025-09-26 | 551 |  |  | Septemeber
FB-HLR201 | Lightspeed | 2025-09-26 |  |  | No Crews Worked On This Location Today | Septemeber
BHU-FAL-01-E | Lightspeed | 2025-09-26 | 755 |  |  | Septemeber
|  | 2025-09-29 |  |  |  | Septemeber
Septemeber

## UG Condensed
NTP Number | AREA | SOW TSD Date | Penguin ID |  | HHP | On Track or In Jeopardy | NTP Received | SOW Received | Permit Status | Door Tag Date | Constuction Status | Locate Date | UG Conduit Status | Proofing Conduits-ABF Tested | Pulling Fiber | Stingrays | Fiber Spliced | Restoration | Tillman QC Status | COP Package To Biz-Ops Date | Invoice | #REF!
BHT-FOE-03 | Bradenton | 2025-11-30 | MAN97574 |  | 0 |  | Yes | Yes | Received | 2025-07-14 | In Process | 2025-07-14 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
BHUD-FOE-02-W | Bradenton | 2025-03-26 | MAN92070 |  | 0 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-05 | Completed | Completed | Completed | Not Required | Completed | Completed | Pending |  | Pending | #REF!
BHUD-FOE-06-E | Bradenton | 2025-03-26 | MAN92243 |  | 0 |  | Yes | Yes | Received | 2025-02-28 | In Process | 2025-03-05 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending |  | Pending | #REF!
BHZD-FOE-03-W | Bradenton | 2025-11-30 | PPM89496 |  | 0 |  | Yes | Yes | Received | 2025-05-16 | In Process | 2025-05-16 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending |  | Pending
D-HOE102 | Bradenton | 2025-03-31 | MAN89819 |  | 56 |  | Yes | Yes | Received | 2025-02-13 | Completed | 2025-03-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HOE111 | Bradenton | 2025-03-26 | PPM92353 |  | 60 |  | Yes | Yes | Received | 2025-02-28 | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HOE116 | Bradenton | 2025-03-26 | PPM90592 |  | 84 |  | Yes | Yes | Received | 2025-02-28 | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HOE117 | Bradenton | 2025-03-26 | MAN90788 |  | 79 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HOE120 | Bradenton | 2025-03-26 | MAN90778 |  | 83 |  | Yes | Yes | Received | 2025-02-28 | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HOE206 | Bradenton | 2025-11-30 | PPM92353 | 31 | 31 |  | Yes | Yes | Received | 2025-02-28 | In Process | 2025-02-28 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending
D-HOE215 | Bradenton | 2025-04-25 | PPM92353 |  | 31 |  | Yes | Yes | Received | 2025-02-28 | In Process | 2025-02-28 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending |  | Pending | #REF!
FB-HLR201 | Bradenton | 2025-10-30 | MAN98152 |  | 0 |  | Yes | Yes | Received | 2025-07-29 | In Process | 2025-07-29 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
D-HOE302 | Bradenton | 2025-11-30 | MAN98158 |  | 57 |  | Yes | Yes | Received | 2025-07-25 | In Process | 2025-07-25 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
FB-HOE117 | Bradenton | 2025-02-23 | MAN89824 |  | 0 |  | Yes | Yes | Received | 2025-02-13 | Completed | 2025-03-02 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-07-18 | Submitted | #REF!
FB-HOE201 | Bradenton | 2025-03-26 | MAN91981 |  | 0 |  | Yes | Yes | Received | 2/29/2025 | Completed | 2/29/2025 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending |  | Pending | #REF!
FB-HOE301 | Bradenton | 2025-11-30 | MAN98180 |  | 0 |  | Yes | Yes | Received | 2025-07-25 | Completed | 2025-07-25 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending
FB-HOE375 | Bradenton | 2025-11-30 | MAN99383 |  | 0 |  | Yes | Yes | Received | 2025-08-12 | Completed | 2025-08-12 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending
12 Oaks MHP | Lakeland | 2025-08-30 |  |  | 50 |  | Yes | Yes | Not Required | 2025-08-04 | Completed | 2025-08-04 | Completed | Completed | Completed | Not Required | Completed | Completed | Pending
BHT-FWP-06 | Lakeland | 2025-03-26 | PLK89457 |  | 0 |  | Yes | Yes | Received | 2025-02-20 | Completed | 2025-02-21 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-03 | Submitted | #REF!
BHT-FWP-07 | Lakeland | 2025-04-25 | PLK91807 |  | 0 |  | Yes | Yes | Received | 2025-02-20 | Completed | 2025-03-21 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-05-02 | Submitted | #REF!
BHT-FWP-08 | Lakeland | 2025-07-30 | PLK96231 |  | 0 |  | Yes | Yes | Received | Not Required | Completed | 2025-06-06 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-07-10 | Submitted
BHT-FWP-09 | Lakeland | 2025-06-30 | PLK95075 |  | 0 |  | Yes | Yes | Received | 2025-05-09 | Completed | 2025-05-12 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed
BHT-FWP-10 | Lakeland | 2025-05-30 | PLK94470 |  | 0 |  | Yes | Yes | Received | 2025-05-01 | Completed | 2025-05-05 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-18 | Submitted
BHUD-FWP-08-E | Lakeland | 2025-05-10 | PLK91306 |  | 0 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-02-28 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-05-16 | Submitted | #REF!
BHUD-FWP-13-W | Lakeland | 2025-07-30 | PLK95092 |  | 0 |  | Yes | Yes | Received | Not Required | Completed | 2025-07-02 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed
BHZD-FWP-11-W | Lakeland | 2025-07-30 | PLK97102 |  | 0 |  | Yes | Yes | Received | Not Required | Completed | 2025-07-15 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed
BHZD-FWP-13-E | Lakeland | 2025-07-30 | PLK95389 |  | 0 |  | Yes | Yes | Received | 2025-05-16 | Completed | 2025-05-16 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed
D-HWP102 | Lakeland | 2025-02-23 | MAN91697 |  | 54 |  | Yes | Yes | Received | 2025-01-02 | Completed | 2025-02-04 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP103 | Lakeland | 2025-02-23 | PLK88967 |  | 49 |  | Yes | Yes | Received | 2025-02-25 | Completed | 2025-02-04 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP105 | Lakeland | 2025-02-28 | PLK90239 |  | 56 |  | Yes | Yes | Received | 2025-02-19 | Completed | 2025-02-19 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-02 | Submitted | #REF!
D-HWP1304 | Lakeland | 2025-04-25 | PLK93497 |  | 82 |  | Yes | Yes | Received | 2025-04-09 | Completed | 2025-04-09 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-15 | Submitted
D-HWP1306 | Lakeland | 2025-04-25 | PLK92368 |  | 79 |  | Yes | Yes | Received | 2025-04-02 | Completed | 2025-04-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-04 | Submitted | #REF!
D-HWP1309 | Lakeland | 2025-04-25 | PLK92363 |  | 59 |  | Yes | Yes | Received | 2025-04-03 | Completed | 2025-04-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-20 | Submitted
D-HWP412 | Lakeland | 2025-01-31 | PLK87663 |  | 23 |  | Yes | Yes | Received | 2025-01-02 | Completed | 2025-01-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP415 | Lakeland | 2025-01-31 | PLK88133 |  | 70 |  | Yes | Yes | Received | 2025-01-02 | Completed | 2025-01-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-16 | Submitted | #REF!
D-HWP425 | Lakeland | 2025-01-31 | PLK88584 |  | 75 |  | Yes | Yes | Received | Completed | Completed | 2025-01-15 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP436 | Lakeland | 2025-01-31 | PLK88375 |  | 65 |  | Yes | Yes | Received | 2025-01-16 | Completed | 2025-01-16 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP441 | Lakeland | 2025-01-31 | PLK88853 |  | 81 |  | Yes | Yes | Received | Completed | Completed | 2025-01-15 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP701 | Lakeland | 2025-03-26 | PLK89401 |  | 50 |  | Yes | Yes | Received | 2025-02-17 | Completed | 2025-02-27 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP702 | Lakeland | 2025-03-26 | PLK92108 |  | 52 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-13 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP703 | Lakeland | 2025-04-25 | PLK92329 |  | 86 |  | Yes | Yes | Received | 2025-03-21 | Completed | 2025-03-21 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP705 | Lakeland | 2025-02-28 | PLK91019 |  | 51 |  | Yes | Yes | Received | Completed | Completed | 2025-03-10 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-09 | Submitted | #REF!
D-HWP707 | Lakeland | 2025-04-25 | PLK91963 |  | 35 |  | Yes | Yes | Received | 2025-03-20 | Completed | 2025-03-25 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP713 | Lakeland | 2025-02-23 | PLK89267 |  | 22 |  | Yes | Yes | Received | Completed | Completed | 2025-02-07 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HWP801 | Lakeland | 2025-07-30 | PLK95087 |  | 90 |  | Yes | Yes | Received | 2025-05-20 | Completed | 2025-06-02 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-07-09 | Submitted
D-HWP803 | Lakeland | 2025-08-30 | PLK97105 |  | 62 |  | Yes | Yes | Received | 2025-08-11 | Completed | 2025-08-11 | Completed | Completed | Completed | Not Required | Completed | Completed | Pending
D-HWP805 | Lakeland | 2025-09-30 | PLK97109 |  | 85 |  | Yes | Yes | Received | 2025-08-13 | Completed | 2025-08-13 | Completed | Completed | Completed | Completed | Completed | Completed | Pending
D-HWP812 | Lakeland | 2025-08-30 | PLK97117 |  | 77 |  | Yes | Yes | Received | 2025-07-02 | Completed | 2025-07-02 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-08 | Submitted
D-HWP814 | Lakeland | 2025-08-30 | PLK97122 |  | 81 |  | Yes | Yes | Received | 2025-07-09 | Completed | 2025-07-09 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-26 | Submitted
D-HWP815 | Lakeland | 2025-08-30 | PLK97093 |  | 86 |  | Yes | Yes | Received | 2025-07-02 | Completed | 2025-07-02 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-08 | Submitted
D-HWP821 | Lakeland | 2025-07-30 | PLK96634 |  | 66 |  | Yes | Yes | Received | 2025-06-25 | Completed | 2025-06-25 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2025-07-10 | Submitted
D-HWP822 | Lakeland | 2025-07-30 | PLK97098 |  | 43 |  | Yes | Yes | Received | 2025-07-02 | Completed | 2025-07-02 | Completed | Not Required | Completed | Completed | Completed | Completed | Completed | 2025-09-16 | Submitted
D-HWP824 | Lakeland | 2025-08-30 |  |  | 73 |  | Yes | Yes | Received | 2025-08-18 | Completed | 2025-08-18 | Completed | Completed | Completed | Completed | Completed | Completed | Pending
D-HWP825 | Lakeland | 2025-08-30 |  |  | 70 |  | Yes | Yes | Received | 2025-08-18 | Completed | 2025-08-18 | Completed | Completed | Completed | Completed | Completed | Completed | Pending
D-HWP826 | Lakeland | 2025-08-30 |  |  | 84 |  | Yes | Yes | Received | 2025-08-18 | Completed | 2025-08-18 | Completed | Completed | Completed | Completed | Completed | Completed | Pending
D-HWP902 | Lakeland | 2025-07-24 | PLK93385 |  | 62 |  | Yes | Yes | Received | 2025-04-15 | Completed | 2025-05-06 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-05 | Submitted
D-HWP903 | Lakeland | 2025-07-24 | PLK93393 |  | 89 |  | Yes | Yes | Received | 2025-04-15 | Completed | 2025-04-29 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-19 | Submitted
D-HWP904 | Lakeland | 2025-07-24 | PLK93379 |  | 87 |  | Yes | Yes | Received | 2025-04-15 | Completed | 5/52025 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-19 | Submitted
D-HWP905 | Lakeland | 2025-07-30 | PLK94794 |  | 60 |  | Yes | Yes | Received | 2025-05-13 | Completed | 2025-06-04 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-16 | Submitted
FB-HWP101 | Lakeland | 2025-01-31 | PLK88377 |  | 0 |  | Yes | Yes | Received | Completed | Completed | 2025-01-16 | Completed | Completed | In Process | Not Required | Completed | Completed | Completed | 2025-04-11 | Submitted | #REF!
FB-HWP1302 | Lakeland | 2025-07-30 | PLK97344 |  | 0 |  | Yes | Yes | Received | 2025-07-10 | Completed | 2025-07-10 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-07 | Submitted
FB-HWP1310 | Lakeland | 2025-09-30 |  |  | 0 |  | Yes | Yes | Received | 2025-08-15 | Completed | 2025-08-13 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending
FB-HWP1375 | Lakeland | 2025-08-30 | PLK97346 |  | 0 |  | Yes | Yes | Received | 2025-08-15 | Completed | 2025-08-15 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-09-08
FB-HWP1376 | Lakeland | 2025-07-30 | PLK96627 |  | 0 |  | Yes | Yes | Received | 2025-06-16 | Completed | 2025-06-16 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending |  | Pending
FB-HWP175 | Lakeland | 2025-06-30 | PLK96355 |  | 0 |  | Yes | Yes | Received | 2025-06-10 | Completed | 2025-06-09 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-07 | Submitted
FB-HWP375 | Lakeland | 2025-08-30 |  |  | 0 |  | Yes | Yes | Received | 2025-08-07 | Completed | 2025-08-07 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending | 2025-09-05
FB-HWP401 | Lakeland | 2025-02-28 |  |  | 0 |  | No | No | Received | Completed | Completed | Completed | Completed | Completed | Completed | Not Required | Completed | Completed | Completed |  | Pending | #REF!
FB-HWP482 | Lakeland | 2025-08-30 | PLK97720 |  | 0 |  | Yes | Yes | Received | 2025-08-01 | Completed | 2025-08-01 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending
FB-HWP701 | Lakeland | 2025-02-28 | PLK89265 |  | 0 |  | Yes | Yes | Received | 2025-02-17 | Completed | 2025-02-17 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed |  | Submitted | #REF!
FB-HWP775 | Lakeland | 2025-08-30 | PLK98767 |  | 0 |  | Yes | Yes | Received | 2025-08-01 | Completed | 2025-08-01 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending
FB-HWP776 | Lakeland | 2025-08-30 |  |  | 0 |  | Yes | Yes | Received | 2025-08-13 | Completed | 2025-08-13 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-09-08
FB-HWP801 | Lakeland | 2025-06-30 | PLK94839 |  | 0 |  | Yes | Yes | Received | 2025-05-13 | Completed | 2025-05-13 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-13 | Pending
FB-HWP802 | Lakeland | 2025-08-30 | PLK98828 |  | 0 |  | Yes | Yes | Received | 2025-07-30 | Completed | 2025-08-02 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending | 2025-09-09
FB-HWP804 | Lakeland | 2025-07-30 | PLK97717 |  | 0 |  | Yes | Yes | Received | 2025-07-15 | Completed | 2025-07-15 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-09-05 | Submitted
FB-HWP902 | Lakeland | 2025-07-30 | PLK97335 |  | 0 |  | Yes | Yes | Received | 2025-06-30 | Completed | 2025-06-30 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-26 | Submitted
FB-HWP975 | Lakeland | 2025-09-30 |  |  | 0 |  | Yes | Yes | Received | 2025-09-02 | Completed | 2025-09-02 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending | 2025-09-23
FB-HWP1075 | Lakeland | 2025-09-30 |  |  | 0 |  | Yes | Yes | Received | 2025-09-02 | Completed | 2025-09-02 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending | 2025-09-25
FX4-FWP-08 | Lakeland | 2025-05-15 | PLK89273 |  | 0 |  | Yes | Yes | Received | Completed | Completed | Completed | Completed | Not Required | Not Required | Not Required | Completed | Completed | Completed | 2025-06-12 | Submitted | #REF!
FX4-FWP-13 | Lakeland | 2025-05-10 | PLK93160 |  | 0 |  | Yes | Yes | Received | TBD | Completed | TBD | Completed | Not Required | Not Required | Not Required | Completed | Completed | Completed | 2025-07-10 | Pending
Golden Wings MHP | Lakeland | 2025-01-31 | PLK88370 |  | 48 |  | Yes | Yes | Not Required | Completed | Completed | 2025-01-21 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
Skyview Estates MHP | Lakeland | 2025-08-30 |  |  | 208 |  | Yes | Yes | Not Required | 2025-08-05 | Completed | 2025-08-05 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed
BHU-FDH-01-W | St Petersburg | 2025-02-28 | PPM89496 |  | 0 |  | Yes | Yes | Received | 2025-02-17 | Completed | 2025-02-18 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-10 | Pending | #REF!
D-H0220A | St Petersburg | 2025-03-26 | PPM95827 |  | 57 |  | Yes | Yes | Received | 2025-03-12 | Completed | 2025-03-12 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-08-06 | Submitted | #REF!
D-H0220B | St Petersburg | 2025-03-26 | PPM91680 |  | 60 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-08-05 | Submitted | #REF!
D-H0220C | St Petersburg | 2025-03-26 | PPM91630 |  | 80 |  | Yes | Yes | Received | 2025-03-12 | Completed | 2025-03-12 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-16 | Submitted | #REF!
D-H0220D | St Petersburg | 2025-03-26 | PPM90335 |  | 68 |  | Yes | Yes | Received | 2025-02-28 | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-H0221A | St Petersburg | 2025-03-26 | PPM91357 |  | 80 |  | Yes | Yes | Received | 2025-03-12 | Completed | 2025-03-12 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-04-10 | Pending | #REF!
D-H0221B | St Petersburg | 2025-03-26 | PPM91351 |  | 56 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-06 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-06-17 | Pending | #REF!
D-H0221C | St Petersburg | 2025-03-26 | PPM91690 |  | 71 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-11 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-06-20 | Pending | #REF!
D-H0221D | St Petersburg | 2025-03-26 | PPM91321 |  | 81 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-07 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-23 | Submitted | #REF!
D-H0221E | St Petersburg | 2025-03-26 | PPM90342 |  | 38 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-H0221F | St Petersburg | 2025-04-25 | PPM91656 |  | 83 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-11 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-H0222A | St Petersburg | 2025-02-23 | PPM89513 |  | 86 |  | Yes | Yes | Received | 2025-02-26 | Completed | 2025-02-05 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending |  | Pending | #REF!
D-H0222B | St Petersburg | 2025-02-23 | PPM89528 |  | 76 |  | Yes | Yes | Received | 2025-02-04 | Completed | 2025-02-06 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-06 | Submitted | #REF!
D-H0222C | St Petersburg | 2025-02-23 | PPM89539 |  | 89 |  | Yes | Yes | Received | 2025-02-07 | Completed | 2025-02-06 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending |  | Pending | #REF!
D-H0222D | St Petersburg | 2025-02-23 | PPM89539 |  | 86 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-01-31 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-16 | Submitted | #REF!
D-H0223A | St Petersburg | 2025-02-23 | PPM89575 |  | 77 |  | Yes | Yes | Received | 2025-01-29 | Completed | 2025-02-04 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-07-02 | Pending | #REF!
D-H0223C | St Petersburg | 2025-02-23 | PPM89447 |  | 81 |  | Yes | Yes | Received | 2025-02-12 | Completed | 2025-02-04 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-06 | Submitted | #REF!
D-H0223D | St Petersburg | 2025-02-23 | PPM89579 |  | 81 |  | Yes | Yes | Received | 2025-02-11 | Completed | 2025-02-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Pending | #REF!
D-H0223E | St Petersburg | 2025-02-23 | PPM89581 |  | 84 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-07 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-06-02 | Pending | #REF!
D-HDH03 | St Petersburg | 2025-01-31 | PPM89589 |  | 90 |  | Yes | Yes | Received | Completed | Completed | 2025-02-11 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-27 | Submitted | #REF!
D-HDH04 | St Petersburg | 2025-01-31 | PPM88371 |  | 86 |  | Yes | Yes | Received | 2025-01-20 | Completed | 2025-01-18 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed |  | Pending | #REF!
D-HDH31 | St Petersburg | 2025-01-31 | PPM89043 |  | 86 |  | Yes | Yes | Received | Completed | Completed | 2025-01-18 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-12 | Submitted | #REF!
D-HDH32 | St Petersburg | 2025-01-31 | PPM89595 |  | 88 |  | Yes | Yes | Received | 2025-03-26 | Completed | 2025-03-27 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending |  | Pending | #REF!
D-HDH34 | St Petersburg | 2025-01-31 | PPM88372 |  | 88 |  | Yes | Yes | Received | 2025-02-18 | Completed | 2025-01-22 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending | 2025-06-12 | Pending | #REF!
D-HDH41 | St Petersburg | 2025-04-25 | PPM91655 |  | 85 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-04-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending
D-HDH42 | St Petersburg | 2025-04-25 | PPM92270 |  | 88 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-04-02 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-21 | Submitted
D-HDH43 | St Petersburg | 2025-04-25 | PPM92271 |  | 57 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Not Req | Completed | Completed | Priority | Pending | 2025-05-27 | Pending | #REF!
D-HDH45 | St Petersburg | 2025-02-23 | PPM89601 |  | 73 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-09-02 | Submitted | #REF!
D-HDH46 | St Petersburg | 2025-02-23 | PPM89610 |  | 65 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-20 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-13 | Submitted | #REF!
D-HDH47 | St Petersburg | 2025-04-25 | PPM92273 |  | 70 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-14 | Submitted | #REF!
D-HDH48 | St Petersburg | 2025-04-25 | PPM92278 |  | 84 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-04-08 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-14 | Submitted
D-HDH49 | St Petersburg | 2025-04-25 | PPM92276 |  | 75 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-31 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-21 | Submitted | #REF!
D-HDH50 | St Petersburg | 2025-04-25 | PPM93107 |  | 69 |  | Yes | Yes | Received | 2025-04-10 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-06 | Submitted
D-HDH52 | St Petersburg | 2025-04-25 | PPM93114 |  | 50 |  | Yes | Yes | Received | 2025-04-10 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-30 | Submitted
D-HDH53 | St Petersburg | 2025-04-25 | PPM93118 |  | 76 |  | Yes | Yes | Received | 2025-04-10 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-03 | Submitted
D-HDH54 | St Petersburg | 2025-04-25 | PPM93122 |  | 88 |  | Yes | Yes | Received | 2025-04-10 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-02 | Submitted
D-HDH55 | St Petersburg | 2025-04-25 | PPM93069 |  | 86 |  | Yes | Yes | Received | 2025-04-09 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-05 | Submitted
D-HDH56 | St Petersburg | 2025-04-25 | PPM92087 |  | 84 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-04-01 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-03 | Submitted
D-HDH57 | St Petersburg | 2025-04-25 | PPM92588 |  | 87 |  | Yes | Yes | Received | 2025-04-10 | Completed | 2025-04-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending | 2025-06-30 | Pending
D-HDH58 | St Petersburg | 2025-04-25 | PPM92280 |  | 81 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-31 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-12 | Submitted | #REF!
D-HDH60 | St Petersburg | 2025-04-25 | PPM92088 |  | 80 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-03 | Submitted | #REF!
D-HDH62 | St Petersburg | 2025-04-25 | PPM92283 |  | 63 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Not Req | Completed | Completed | Priority | Pending | 2025-06-24 | Pending | #REF!
D-HDH66 | St Petersburg | 2025-01-31 | PPM88373 |  | 90 |  | Yes | Yes | Received | Completed | Completed | 2025-01-22 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-06 | Submitted | #REF!
D-HDH67 | St Petersburg | 2025-04-25 | PPM91122 |  | 86 |  | Yes | Yes | Received | Completed | Completed | 2025-03-04 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-11 | Submitted | #REF!
D-HDH68 | St Petersburg | 2025-02-23 | PPM89616 |  | 90 |  | Yes | Yes | Received | 2025-02-12 | Completed | 2025-01-22 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-04 | Submitted | #REF!
D-HDH69 | St Petersburg | 2025-03-26 | PPM89618 |  | 82 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-06 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-08-14 | Submitted | #REF!
D-HDH70 | St Petersburg | 2025-04-25 | PPM91121 |  | 82 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-04 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-06 | Submitted | #REF!
D-HDH71 | St Petersburg | 2025-03-31 | PPM89623 |  | 64 |  | Yes | Yes | Received | 2025-02-13 | Completed | 2025-02-10 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-21 | Submitted | #REF!
D-HDH72 | St Petersburg | 2025-03-26 | PPM89624 |  | 82 |  | Yes | Yes | Received | Completed | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Completed |  | Pending | #REF!
D-HDH73 | St Petersburg | 2025-02-23 | PPM89626 |  | 59 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-12 | Submitted | #REF!
D-HDH73 | St Petersburg | 2025-03-26 | PPM90342 |  | 38 |  | Yes | Yes | Received | Completed | Completed | 2025-02-13 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-13 | Submitted | #REF!
D-HDH74 | St Petersburg | 2025-02-23 | PPM89643 |  | 85 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-21 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-06-17 | Pending | #REF!
D-HDH75 | St Petersburg | 2025-04-25 | PPM91431 |  | 88 |  | Yes | Yes | Received | Completed | Completed | 2025-03-04 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-11 | Submitted | #REF!
D-HDH76 | St Petersburg | 2025-02-23 | PPM89553 |  | 86 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-14 | Submitted | #REF!
D-HDH77 | St Petersburg | 2025-03-26 | PPM92290 |  | 84 |  | Yes | Yes | Received | 2025-02-27 | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HDH78 | St Petersburg | 2025-02-23 | PPM90248 |  | 85 |  | Yes | Yes | Received | 2025-02-19 | Completed | 2025-02-19 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-13 | Submitted | #REF!
D-HDH79 | St Petersburg | 2025-03-26 | PPM90331 |  | 87 |  | Yes | Yes | Received | Completed | Completed | Completed | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HDH80 | St Petersburg | 2025-04-25 | PPM92262 |  | 91 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-27 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-11 | Submitted | #REF!
D-HDH82 | St Petersburg | 2025-04-25 | PPM92198 |  | 20 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-27 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-03 | Submitted | #REF!
D-HDH83 | St Petersburg | 2025-03-26 | PPM90333 |  | 87 |  | Yes | Yes | Received | Completed | Completed | 2025-02-03 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HDH84 | St Petersburg | 2025-01-31 | PPM88311 |  | 79 |  | Yes | Yes | Received | Completed | Completed | 2025-01-18 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending |  | Pending | #REF!
D-HNP104 | St Petersburg | 2025-07-24 | PPM93993 |  | 78 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-04-02 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-19 | Submitted
D-HNP106 | St Petersburg | 2025-11-30 | PPM93922 |  | 69 |  | Yes | Yes | Received | 2025-03-25 | In Process | 2025-03-28 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
D-HNP107 | St Petersburg | 2025-11-30 | PPM90859 |  | 85 |  | Yes | Yes | Received | 2025-03-25 | Not Started | 2025-03-28 | Not Started | [7 empty] | Pending | #REF!
D-HNP111 | St Petersburg | 2025-11-30 | PPM92084 |  | 86 |  | Yes | Yes | Received | 2025-03-25 | In Process | 2025-04-02 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
D-HNP113 | St Petersburg | 2025-11-30 | PPM90871 |  | 70 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Completed | Not Required | Completed | Pending | Pending |  | Pending | #REF!
D-HNP114_H0103D | St Petersburg | 2025-11-30 | PLK88966 |  | 81 |  | Yes | Yes | Received | 2025-02-14 | In Process | 2025-02-08 | In Process | In Process | Not Req | In Process | In Process | Pending | Pending |  | Pending | #REF!
D-HNP117 | St Petersburg | 2025-11-30 | PPM93990 |  | 60 |  | Yes | Yes | Received | 2025-03-25 | Completed | 2025-03-28 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending |  | Pending
D-HNP123 | St Petersburg | 2025-11-30 | PPM89671 |  | 90 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-10 | Completed | Completed | Not Req | Completed | Completed | Pending | Pending | 2025-06-10 | Pending | #REF!
D-HNP135 | St Petersburg | 2025-11-30 | PPM94426 |  | 70 |  | Yes | Yes | Received | 2025-03-25 | In Process | 2025-03-25 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
D-HNP137 | St Petersburg | 2025-11-30 | PPM89749 |  | 78 |  | Yes | Yes | Received | 2025-02-20 | Completed | 2025-02-08 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-30 | Submitted | #REF!
D-HNP138 | St Petersburg | 2025-11-30 | PPM89683 |  | 87 |  | Yes | Yes | Received | 2025-02-20 | Completed | 2025-02-08 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-05-15 | Submitted | #REF!
D-HNP141 | St Petersburg | 2025-11-30 | PPM89690 |  | 60 |  | Yes | Yes | Received | 2025-02-10 | Completed | 2025-02-11 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-13 | Submitted | #REF!
D-HNP143 | St Petersburg | 2025-11-30 | PPM89772 |  | 87 |  | Yes | Yes | Received | 2025-02-11 | Completed | 2025-02-11 | Completed | Completed | Not Req | Completed | Completed | Completed | Pending | 2025-03-31 | Pending | #REF!
D-HNP144 | St Petersburg | 2025-11-30 | PPM90863 |  | 79 |  | Yes | Yes | Received | 2025-03-19 | In Process | 2025-03-21 | In Process | In Process | Not Req | In Process | In Process | Pending |  |  | Pending | #REF!
D-HNP151 | St Petersburg | 2025-11-30 | PPM90865 |  | 50 |  | Yes | Yes | Received | 2025-03-19 | Completed | 2025-03-20 | Completed | Completed | Not Req | Completed | Completed | Completed | Completed | 2025-06-09 | Submitted | #REF!
FB-H0205A | St Petersburg | 2025-03-26 | PPM90591 |  | 0 |  | Yes | Yes | Received | 2025-02-28 | Completed | Completed | Completed | Completed | Completed | Not Required | Completed | Completed | Pending |  | Pending | #REF!
FB-H0220A | St Petersburg | 2025-03-26 | PPM89778 |  | 0 |  | Yes | Yes | Received | 2025-02-24 | Completed | 2025-03-07 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-08-28 | Submitted | #REF!
FB-H0221A | St Petersburg | 2025-03-26 | PPM89791 |  | 0 |  | Yes | Yes | Received | 2025-02-28 | Completed | 2025-03-10 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-06 | Submitted | #REF!
FB-H0222A | St Petersburg | 2025-02-23 | PPM88374 |  | 0 |  | Yes | Yes | Received | 2025-02-07 | Completed | 2025-02-05 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-06-30 | Submitted | #REF!
FB-H0223A | St Petersburg | 2025-02-23 | PPM89789 |  | 0 |  | Yes | Yes | Received | 2025-01-29 | Completed | 2025-02-05 | Completed | Completed | Completed | Not Required | Completed | Completed | Pending |  | Pending | #REF!
FB-HDH01 | St Petersburg | 2025-01-31 |  |  | 0 |  |  |  | Received | Completed | Completed | Completed | Completed | Completed | Completed | Not Required | Completed | Completed | Completed |  | Pending | #REF!
FB-HDH01A-2A | St Petersburg | 2025-06-30 | PPM96333 |  | 0 |  | Yes | Yes | Received | Completed | Completed | 2025-06-10 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-07-16 | Submitted
FB-HDH02A | St Petersburg | 2025-02-28 | PPM87852 |  | 0 |  | Yes | Yes | Received | Completed | Completed | 2025-02-05 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed |  | Pending | #REF!
FB-HDH275 | St Petersburg | 2025-03-26 | PPM89801 |  | 0 |  | Yes | Yes | Received | 2025-02-26 | Completed | 2025-03-04 | Completed | Completed | Completed | Not Required | Completed | Completed | Completed | 2025-09-02 | Submitted | #REF!
FB-HNP104 | St Petersburg | 2025-03-26 | PPM90880 |  | 0 |  | Yes | Yes | Received | 2025-03-25 | Not Started | 2025-03-27 | Not Started |  |  | Not Required |  |  |  |  | Pending | #REF!
FB-HNP133 | St Petersburg | 2025-11-30 | PPM92370 |  | 0 |  | Yes | Yes | Received | 2025-03-26 | In Process | 2025-03-27 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending
FB-HNP138 | St Petersburg | 2025-04-30 | PPM89817 |  | 0 |  | Yes | Yes | Received | 2025-02-12 | In Process | 2025-02-08 | In Process | In Process | In Process | Not Required | In Process | Pending | Pending |  | Pending | #REF!
FB-HNP144 | St Petersburg | 2025-04-25 | PPM90914 |  | 0 |  | Yes | Yes | Received | 2025-03-25 | Not Started | 2025-03-27 | Not Started |  |  | Not Required |  |  |  |  | Pending | #REF!
FX4-FML-05 | St Petersburg | 2025-07-24 | PPM93377 |  | 0 |  | Yes | Yes | Received | TBD | Completed | TBD | Completed | Not Required | Not Required | Not Required | Completed | Pending | Pending
Note on A7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hand Dig Tie In For Tillman.
Note on A87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Splice Only Project.
Note on A133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A139: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.
Note on A159: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NTP Received Fiber Placement and Splice Only Project.

## Projects No Longer With LS
Constuction Status
[21 empty] | Local Team | Penguin Task | Penguin Task | Penguin Task | Penguin Task | PLC
NTP Number | AREA | SOW TSD Date | Vendor Assignment | Date Assigned | Assigned Supervisor | Penguin ID | HHP | On Track or In Jeopardy | Permit Status | Blockers/Risks | Door Tag Date | SOW Received | SOW Estimated Cost | NTP Received | Constuction Status | Locate Date | Footage UG | Completed Footage UG | Footage AE | % Complete | Materials | Construction Start Date | UG Percentage Complete | Aerial Percentage Complete | Splicing Percentage Complete | Construction Total Percent Complete | Notes
BHCD-FDF-01-E | Ft Myers | 2025-03-01 | Not To Build Per Tillman | 2025-02-19 | Betsy | PPM89279 | 0 |  | Received | Bond | 2025-02-21 | Yes | 15436.85 | Yes | Locates Called | 2025-02-25 | 1358 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | Door tagging tomorrow afternoon 2-21-25
BHCD-FEF-01-W | Ft Myers | 2025-03-01 | Not To Build Per Tillman | 2025-02-19 | Betsy | PPM89283 | 0 |  | Received | Bond | 2025-02-17 | Yes | 31717.7 | Yes | Locates Called | 2025-02-25 | 2434 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
BHC-FEF-01-E | Ft Myers | 2025-03-01 | Not To Build Per Tillman | 2025-02-19 | Betsy | PPM89298 | 0 |  | Received | Bond | 2025-02-17 | Yes | 122715.95 | Yes | Locates Called | 2025-02-25 | 9619 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
FB-HWP477 | Lakeland | 2025-09-30 | Lightspeed In-House |  | Anthony | PLK97348 | 0 |  | Pending | Permits |  | Yes | 12886.4 | Yes | Not Started |  | 884 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | Need city, App only. 8/1- Had Brothers call in locates for this and 12 Oaks MHP.
FX4-FGG-01 | Naples | 2025-04-01 | Not To Build Per Tillman | TBD | TBD | MAN93945 | 0 |  | Received | Permits |  | Yes | 1343.9 | Yes | Not Started |  | 74 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | Sch 8-5 County
D-HTB101 | North Port | 2025-03-25 | Not To Build Per Tillman | 2025-02-12 |  |  | 81 |  | Received |  |  | Yes | 84564.5 | Yes | Not Started |  | 7151 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | Lightspeed Not To Build North Port As Per Tillman.
D-HTB102 | North Port | 2025-03-25 | Not To Build Per Tillman | 2025-02-12 |  |  | 43 |  | Received |  |  | Yes | 42408 | Yes | Not Started |  | 3499 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
D-HTB103 | North Port | 2025-03-31 | Not To Build Per Tillman | 2025-02-12 |  |  | 39 |  | Received |  |  | Yes | 96198.5 | Yes | Not Started |  | 7385 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
D-HTB104 | North Port | 2025-03-25 | Not To Build Per Tillman | 2025-02-12 |  |  | 36 |  | Received |  |  | Yes | 71001 | Yes | Not Started |  | 7378 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | Lightspeed Not To Build North Port As Per Tillman.
D-HTB105 | North Port | 2025-03-25 | Not To Build Per Tillman | 2025-02-12 |  |  | 88 |  | Received |  |  | Yes | 84103 | Yes | Not Started |  | 7141 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | Lightspeed Not To Build North Port As Per Tillman.
D-HTB106 | North Port | 2025-03-31 | Not To Build Per Tillman | 2025-02-12 |  |  | 88 |  | Received |  |  | Yes | 90832 | Yes | Not Started |  | 7715 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
D-HTB107 | North Port | 2025-03-25 | Not To Build Per Tillman | 2025-02-12 |  |  | 88 |  | Received |  |  | Yes | 96242 | Yes | Not Started |  | 6455 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | Lightspeed Not To Build North Port As Per Tillman.
D-HTB108 | North Port | 2025-03-25 | Not To Build Per Tillman | 2025-02-12 |  |  | 73 |  | Received |  |  | Yes | 66271.5 | Yes | Not Started |  | 6542 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | Lightspeed Not To Build North Port As Per Tillman.
D-HTB159 | North Port | 2025-03-31 | Not To Build Per Tillman | 2025-02-12 |  |  | 57 |  | Received |  |  | Yes | 48577 | Yes | Not Started |  | 4443 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
FB-HTB101 | North Port | 2025-03-01 | Not To Build Per Tillman | 2025-02-12 |  | PLK88376 | 0 |  | Received |  |  | Yes | 2530 | Yes | Not Started |  | 0 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | Lightspeed Not To Build North Port As Per Tillman.
FB-HTB103 | North Port | 2025-03-31 | Not To Build Per Tillman | 2025-02-12 |  |  | 0 |  | Received |  |  | Yes | 7803.15 | Yes | Not Started |  | 451 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | CABINET SET 2-10/UG COM
FX4-FTB-01 | North Port | 2025-03-01 | Not To Build Per Tillman | 2025-02-12 |  |  | 0 |  | Received |  |  | Yes | 4254.7 | Yes | Not Started |  | 42 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | Lightspeed Not To Build North Port As Per Tillman.
Bayboro | St Petersburg | 2025-03-01 | Removed From Lightspeed | 2025-02-07 |  |  | 39 |  | Not Required |  |  | Yes | 12213.67 | Yes | Not Started |  | 1292 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
Charles Court | St Petersburg | 2025-03-01 | Removed From Lightspeed | 2025-02-07 |  |  | 19 |  | Not Required |  |  | Yes | 1618.84 | Yes | Not Started |  | 193 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
D-H0223F | St Petersburg | 2025-02-28 | Reassigned |  |  |  | 90 |  |  |  |  | Yes | 69076 | No | Not Started |  | 3936 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
D-HDH13 | St Petersburg | 2025-01-31 | Reassigned |  |  |  | 65 |  |  |  |  | Yes | 28762 | No | Not Started |  | 1881 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
D-HDH63 | St Petersburg | 2025-03-31 | Removed From Lightspeed | TBD | TBD |  | 61 |  | Pending |  | TBD | Yes | 31560 | No | Not Started |  | 2064 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | Any of the work that is left on HDH63 should be included in its Feeder B
D-HGP24 | St Petersburg | 2025-02-28 | Reassigned |  |  |  | 48 |  |  |  |  | Yes | 29812 | No | Not Started |  | 1592 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
D-HGP27 | St Petersburg | 2025-02-28 | Reassigned |  |  |  | 48 |  |  |  |  | Yes | 26964 | No | Not Started |  | 1838 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
Martin Luther King | St Petersburg | 2025-03-01 | Removed From Lightspeed | 2025-02-07 |  |  | 25 |  | Not Required |  |  | Yes | 7844.43 | Yes | Not Started |  | 171 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
Palm Villa | St Petersburg | 2025-03-01 | Removed From Lightspeed | 2025-02-07 |  |  | 52 |  | Not Required |  |  | Yes | 17100.2 | Yes | Not Started |  | 1246 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
The Morgan | St Petersburg | 2025-03-01 | Removed From Lightspeed | 2025-02-07 |  |  | 305 |  | Not Required |  |  | Yes | 91420.91 | Yes | Not Started |  | 8225 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
Velvet Cloake | St Petersburg | 2025-03-01 | Removed From Lightspeed | 2025-02-07 |  |  | 91 |  | Not Required |  |  | Yes | 29508.91 | Yes | Not Started |  | 2856 | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
Note on A7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-5-2025 As Per Tom Lightspeed To Invoice For GRP.
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not to Build North Port as Per Tillman.
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not to Build North Port as Per Tillman.
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not to Build North Port as Per Tillman.
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not to Build North Port as Per Tillman.
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not to Build North Port as Per Tillman.
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not to Build North Port as Per Tillman.
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not to Build North Port as Per Tillman.
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not to Build North Port as Per Tillman.
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not to Build North Port as Per Tillman.
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not to Build North Port as Per Tillman.
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not To Build North Port As Per Tillman.
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lightspeed Not To Build North Port As Per Tillman.

## Completed Jobs Summary
APRIL |  |  | CURRENT ASSIGNMENTS |  |  | MONTHLY ASSIGNED FOOTAGE
SOW TSD Date | (Multiple Items) |  | Sum of Footage UG |  |  | Vendor Assignment | (Multiple Items) |  |  |  | On Track or In Jeopardy | In Jeopardy
|  |  | Vendor Assignment | NTP Number | Total |  |  | Tillman forecasted Month | APRIL |  | Tillman forecasted Month | APRIL
Count of NTP Number |  |  | Brothers |  | 91902 | Sum of Footage UG | [8 empty] | Working Day | 22
On Track or In Jeopardy | NTP Number | Total | J Garcia |  | 6526 | NTP Number | Total | Count of Job No |  |  | Count of Job No |  |  |  | Day to Month | 13
Grand Total |  |  | Lightspeed In-House |  | 57130 | BHU-FDH-01-W | 153 | On Track or In Jeopardy | Job No | Total | Blockers | Job No | Total
|  |  | Longo Underground |  | 26128 | D-H0222A | 7980 | In Jeopardy | BHT-FWP-06 | 1 | Manpower |  | 1 |  |  | % Month | % to Goal
|  |  | Multiple |  | 22725 | D-H0222C | 7562 |  | BHT-FWP-07 | 1 | NTP Permit |  | 1 | Monthly Forecast Footage | 203521 | 59.09% | 31.45%
|  |  | Power Connect |  | 24514 | D-H0223A | 5005 |  | D-HDH40 | 1 | Tie-ends | D-HDH40 | 1 | Footage Complete | 64000
|  |  | Power Connect |  | 15789 | D-HDH04 | 6526 |  | D-HDH41 | 1 |  | D-HDH42 | 1
|  |  | Reycamp |  | 4975 | D-HDH32 | 2931 |  | D-HDH42 | 1 |  | D-HDH43 | 1
|  |  | Bartlett Fiber |  | 9984 | D-HDH34 | 5661 |  | D-HDH43 | 1 |  | D-HDH51 | 1
|  |  | Grand Total |  | 259673 | D-HDH72 | 0 |  | D-HDH44 | 1 |  | D-HDH62 | 1
[6 empty] | D-HDH84 | 4975 |  | D-HDH50 | 1 | Tie-ends Total |  | 5
[6 empty] | FB-H0223A | 1735 |  | D-HDH51 | 1 | (blank) |  | 12
[6 empty] | FB-HDH02A | 22725 |  | D-HDH52 | 1 | Grand Total |  | 19
[6 empty] | FB-HNP138 | 1534 |  | D-HDH53 | 1
[6 empty] | D-HOE116 | 285 |  | D-HDH54 | 1
[6 empty] | BHUD-FOE-02-W | 5151 |  | D-HDH55 | 1
[6 empty] | D-HNP107 | 6041 |  | D-HDH57 | 1
[6 empty] | FB-HNP104 | 1831 |  | D-HDH61 | 1
[6 empty] | FB-HNP144 | 2003 |  | D-HDH62 | 1
[6 empty] | D-H0221C | 4979 |  | D-HDH80 | 1
[6 empty] | D-HNP106/D-H0102C | 4822 |  | FB-HDH02A | 1
[6 empty] | D-HNP108/D-H0102E | 6182 |  | FB-HWP601 | 1
[6 empty] | D-HNP110/D-H0102G | 3796 | In Jeopardy Total |  | 19
[6 empty] | D-HNP111/D-H0103A | 7020 | Complete | D-HDH47 | 1
[6 empty] | D-HNP115/D-H0103E | 6387 |  | D-HDH48 | 1
[6 empty] | D-HNP135/D-H0106G | 6152 |  | D-HDH49 | 1
[6 empty] | FB-HNP111 | 1157 |  | D-HDH56 | 1
[6 empty] | FB-HNP118 | 831 |  | D-HDH58 | 1
[6 empty] | FB-HNP133 | 1697 |  | D-HDH59 | 1
[6 empty] | FX4-FAL-01 | 238 |  | D-HDH60 | 1
[6 empty] | FX4-FML-05 | 129 |  | D-HDH82 | 1
[6 empty] | FB-HWP801 | 5776 |  | D-HWP702 | 1
[6 empty] | BHZD-FWP-13-E | 8305 |  | D-HWP703 | 1
[6 empty] | BHT-FWP-09 | 13306 |  | D-HWP706 | 1
[6 empty] | D-HWP803 | 3787 |  | D-HWP707 | 1
[6 empty] | D-HWP805 | 4537 | Complete Total |  | 12
[6 empty] | D-HWP809 | 3012 | Grand Total |  | 31
[6 empty] | D-HWP811 | 2385
[6 empty] | BHUD-FWP-13-W | 11054
[6 empty] | BHZD-FWP-11-W | 5276
[6 empty] | D-HWP813 | 4774
[6 empty] | D-HWP816 | 4833
[6 empty] | FB-HLR201 | 12735
[6 empty] | FB-HOE375 | 321
[6 empty] | Skyview Estates MHP | 11700
[6 empty] | D-HWP818 | 3895
[6 empty] | D-HWP1310 | 4348
[6 empty] | D-HWP824 | 2649
[6 empty] | D-HWP826 | 4071
[6 empty] | D-HWP802 | 3566
[6 empty] | D-HWP823 | 2084
[6 empty] | D-HWP827 | 4048
[6 empty] | D-HWP908 | 4022
[6 empty] | Vault Move EMMA / N FLA | 3
[6 empty] | Vault Move FDH302B | 3
[6 empty] | D-HWP825 | 3836
[6 empty] | BHU-FAL-01-W-2 | 158
[6 empty] | D-HWP910 | 6691
[6 empty] | FB-HWP480 | 328
[6 empty] | FB-HWP1075 | 1010
[6 empty] | BHU-FWP-08-E | 865
[6 empty] | BHZD-FWP-08-W | 807
[6 empty] | Grand Total | 259673

## Vendors
Lakeland | Crew # | Lakeland | Crew #
Brothers | 3 | Brothers | 1
HH Underground | 3 | HDD Underground | 2
SB Martinez- | 2 | SB Martinez-
IH | 4 | IH | 1
St Pete |  | St Pete | Crew #
J Garcia | 3 | J Garcia | 2
Reycamp | 3 | Reycamp
FCA | 2 | FCA | 1
Power Connect | 4 | Power Connect | 2
Longo | 2 | Longo | 2
Bartlett | 5 | Bartlett | 3
Tampa |  | Tampa | Crew #
US Builders | 1 | US Builders | 1
Diathena | TBD | Diathena | TBD
HAS Global | TBD | HAS Global | TBD
Crystal Coast | TBD | Crystal Coast | TBD

## Project Summary
[7 empty] | D&E Update | [8 empty] | Constuction Status
[17 empty] | Prism | Local Team | Penguin Task | Penguin Task | Penguin Task | Penguin Task | PLC | Noes
Job No | AREA | TSD | HHP | Tillman forecasted Month | Days | On Track or In Jeopardy | Permit Status | Funding | Required Permits | Drafting | Submitted | Approved | Pending Permits | % Complete | Blockers | Constuction Status | Funding | Materials | Construction Start | UG Percentage Complete | Aerial Percentage Complete | Splicing Percentage Complete | Construction Total Percent Complete | Additional Information | Required Footage
FB-HNP104 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP107 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP106 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP110 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP109 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | NTP Permit | Hold | Missing | [7 empty] | #REF!
D-HNP108 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP104 | St Petersburg | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Not Started | Funded | [7 empty] | #REF!
FB-HNP111 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP114 | St Petersburg | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP111 | St Petersburg | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP113 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP117 | St Petersburg | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
D-HNP115 | St Petersburg | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Locates Called | Funded | [7 empty] | #REF!
FB-HDH02A | St Petersburg | #N/A |  | APRIL |  | In Jeopardy | [9 empty] | Locates Called | Funded | [7 empty] | #REF!
D-HDH80 | St Petersburg | 2025-05-30 |  | APRIL |  | In Jeopardy | [8 empty] | Manpower |  | Funded | [7 empty] | #REF!
D-HDH82 | St Petersburg | #N/A |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH47 | St Petersburg | #N/A |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH44 | #N/A | 2025-05-30 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [6 empty] | Need to follow-up if we need to place any additional underground conduit for the tie ins | #REF!
D-HDH48 | St Petersburg | #N/A |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH41 | St Petersburg | #N/A |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [6 empty] | blowing sting ray 5.1 | #REF!
D-HDH40 | #N/A | 2025-02-28 |  | APRIL |  | In Jeopardy | [8 empty] | Tie-ends | In Process | Funded | [6 empty] | blowing sting ray 5.1 | #REF!
D-HDH42 | St Petersburg | 2025-04-25 |  | APRIL |  | In Jeopardy | [8 empty] | Tie-ends | In Process | Funded | [7 empty] | #REF!
D-HDH43 | St Petersburg | 2025-04-25 |  | APRIL |  | In Jeopardy | [8 empty] | Tie-ends | In Process | Funded | [7 empty] | #REF!
D-HDH62 | St Petersburg | 2025-04-25 |  | APRIL |  | In Jeopardy | [8 empty] | Tie-ends | In Process | Funded | [7 empty] | #REF!
D-HDH51 |  |  |  | APRIL |  | In Jeopardy | [8 empty] | Tie-ends | In Process | Funded | [6 empty] | Need to follow-up if we need to place any additional underground conduit for the tie ins | #REF!
D-HDH61 | #N/A | #N/A |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [6 empty] | Need to follow-up if we need to place any additional underground conduit for the tie ins | #REF!
D-HDH56 | St Petersburg | 2025-04-25 |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH60 | St Petersburg | 2025-04-25 |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [6 empty] | Pending: confirm rock adder w/ Tillman Inspector to complete measurements | #REF!
D-HDH58 | St Petersburg | 2025-04-25 |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH53 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
D-HDH50 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
D-HDH52 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
D-HDH49 | St Petersburg | 2025-04-25 |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [7 empty] | #REF!
D-HDH54 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
D-HDH55 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
D-HDH59 | #N/A | #N/A |  | APRIL |  | Complete | [9 empty] | Complete | Funded | [6 empty] | Need to follow-up if we need to place any additional underground conduit for the tie ins | #REF!
D-HDH57 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded | [7 empty] | #REF!
FB-HNP144 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Not Started | Funded | [7 empty] | #REF!
FB-HNP138 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | In Process | Funded | [7 empty] | #REF!
FB-HNP133 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | Not Started | Funded | [7 empty] | #REF!
FB-HNP118 | St Petersburg | 2025-05-30 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Manpower | In Process | Funded | [7 empty] | #REF!
BHT-FWP-06 | St Petersburg | 2025-05-30 |  | APRIL |  | In Jeopardy | [9 empty] | Not Started | Funded | [7 empty] | #REF!
BHT-FWP-07 | St Petersburg | 2025-05-30 |  | APRIL |  | In Jeopardy | [9 empty] | Not Started | Funded | [7 empty] | #REF!
FB-HWP601 | St Petersburg | 2025-05-30 |  | APRIL |  | In Jeopardy | [8 empty] | NTP Permit | Not Started | Missing | [7 empty] | #REF!
D-HWP707 | St Petersburg | 2025-05-30 |  | APRIL |  | Complete | [8 empty] | QC | Complete | Funded | [7 empty] | #REF!
D-HWP703 | Lakeland | 2025-04-25 |  | APRIL |  | Complete | [8 empty] | QC | Complete | Funded | [7 empty] | #REF!
D-HWP702 | Lakeland | 2025-04-25 |  | APRIL |  | Complete | [8 empty] | QC | Complete | Funded | [7 empty] | #REF!
D-HWP706 | #N/A | #N/A |  | APRIL |  | Complete | [8 empty] | QC | Complete | Funded | [7 empty] | #REF!
D-HWP1306 | Lakeland | 2025-09-25 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | In Process | Funded | [7 empty] | #REF!
D-HWP1309 | Lakeland | 2025-09-25 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | In Process | Funded | [7 empty] | #REF!
D-HWP1304 | Lakeland | 2025-09-25 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | Locates | In Process | Funded | [7 empty] | #REF!
D-HWP905 | Lakeland | 2025-07-24 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | NTP Permit | Not Started | Missing | [7 empty] | #REF!
D-HWP603 |  | #N/A |  | APRIL, MAY |  | In Jeopardy | [8 empty] | SOW | Not Started | Missing | [7 empty] | #REF!
BHT-FWP-10 | Lakeland | 2025-05-10 |  | APRIL, MAY |  | In Jeopardy | [8 empty] | NTP Permit | Not Started | Missing | [7 empty] | #REF!
D-HWP1304 | St Petersburg | 2025-05-30 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded
D-HWP1306 | Lakeland | 2025-04-25 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded
D-HWP1309 | Lakeland | 2025-04-25 |  | APRIL |  | In Jeopardy | [9 empty] | In Process | Funded
| #N/A | #N/A
| Lakeland | 2025-09-25
| Lakeland | 2025-09-25
| Lakeland | 2025-09-25
| Lakeland | 2025-07-24
#N/A
Drafting | 0 | #DIV/0!
Submitted | 0 | #DIV/0!
Approved | 0 | #DIV/0!
Total | 0
Locates - St Pete
Locates - WOW
Locates
Locates - USIC
Permits

## Detail1
Details for Count of Job No - On Track or In Jeopardy: In Jeopardy, Tillman forecasted Month: APRIL
Job No | AREA | TSD | HHP | Tillman forecasted Month | Days | On Track or In Jeopardy | Permit Status | Funding | Required Permits | Drafting | Submitted | Approved | Pending Permits | % Complete | Blockers | Constuction Status | __PowerAppsId__
BHT-FWP-06 | Lakeland | 2025-04-25 |  | APRIL |  | In Jeopardy | [8 empty] | Tie Ins | In Process | 0b37d8b2-f997-4ac3-b152-273e636141f1
D-HDH42 | St Petersburg | 2025-04-25 |  | APRIL |  | In Jeopardy | [8 empty] | Locates | Locates Called | e754d815-ce99-46ab-ab19-9e8d6e5eee02
D-HDH49 | St Petersburg | 2025-04-25 |  | APRIL |  | In Jeopardy | [8 empty] | Locates | In Process | c366833a-8c7d-4039-a7e6-ce0a96ada5ef
D-HDH50 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [8 empty] | Locates | In Process | 21679d1c-9fc5-4b70-a186-a1e17edbfd23
D-HDH52 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [8 empty] | Locates | In Process | 5c4943f4-d2a0-4145-8a64-3c567cf228bb
D-HDH53 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [8 empty] | Locates St Pete | Not Started | 9eb98861-dc8d-4ee8-93cc-e970dcce56da
D-HDH54 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [8 empty] | Locates | In Process | a2014b87-ba1c-4c33-9034-fc5f6e70d217
D-HDH55 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [8 empty] | Locates | In Process | 3a4f7b4b-c045-4c30-81eb-bf35619cfb2a
D-HDH57 | St Petersburg | 2025-06-23 |  | APRIL |  | In Jeopardy | [8 empty] | Locates | Not Started | d6c0ba80-13ee-44b9-a16b-65d164970a42
D-HDH80 | St Petersburg | 2025-04-25 |  | APRIL |  | In Jeopardy | [8 empty] | Manpower |  | 4d2945ee-1369-4b51-b63a-976a99c72d8c
FB-HWP601 | #N/A | #N/A |  | APRIL |  | In Jeopardy | [8 empty] | NTP Permit | Not Started | 8a7991c0-220f-4ac3-a273-e4d7fddba7b3